{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":56,"n_cols":8,"rows_kept":56,"cut":false,"hidden":false,"merged":[[0,0,0,2],[2,0,7,0],[8,0,21,0],[22,0,38,0],[39,0,48,0],[16,1,21,1],[8,1,15,1],[2,1,3,1],[49,0,52,0],[53,0,55,0],[32,1,38,1],[22,1,31,1],[39,1,42,1],[43,1,45,1],[46,1,47,1]]}
["功能点",null,null,"round1","round2","round3","round4","round5"]
["系统框架","包括人员组织角色、总体架构",null,"2017-03-31"]
["首页","gis图展示","展示管廊延布",null,"2017-04-07"]
[null,null,"点击查看属性及统计数据",null,null,"2017-04-14"]
[null,"当日工作",null,null,null,"2017-04-14"]
[null,"当日告警",null,null,null,"2017-04-14"]
[null,"资产统计",null,null,null,"2017-04-14"]
[null,"工作统计",null,null,null,"2017-04-14"]
["资产管理","管廊资产","总览",null,"2017-04-07"]
[null,null,"新增",null,null,"2017-04-14"]
[null,null,"修改",null,null,"2017-04-14"]
[null,null,"删除",null,null,"2017-04-14"]
[null,null,"查看",null,null,"2017-04-14"]
[null,null,"导出报表",{"$nulls":4},"2017-04-28"]
[null,null,"结合图形选择设备位置",null,null,null,"2017-04-21"]
[null,null,"生成工单",null,null,null,"2017-04-21"]
[null,"管线资产","总览",null,"2017-04-07"]
[null,null,"新增",null,null,"2017-04-14"]
[null,null,"修改",null,null,"2017-04-14"]
[null,null,"删除",null,null,"2017-04-14"]
[null,null,"查看",null,null,"2017-04-14"]
[null,null,"导出报表",{"$nulls":4},"2017-04-28"]
["运维检修","巡视","总览",null,"2017-04-07"]
[null,null,"新增",null,null,"2017-04-14"]
[null,null,"修改",null,null,"2017-04-14"]
[null,null,"删除",null,null,"2017-04-14"]
[null,null,"查看",null,null,"2017-04-14"]
[null,null,"导出报表",{"$nulls":4},"2017-04-28"]
[null,null,"设置周期",null,null,null,"2017-04-21"]
[null,null,"查看巡视地理信息",null,null,null,"2017-04-21"]
[null,null,"生成工单",null,null,null,"2017-04-21"]
[null,null,"流程完善",null,null,null,"2017-04-21"]
[null,"检修","总览",null,"2017-04-07"]
[null,null,"新增",null,null,"2017-04-14"]
[null,null,"修改",null,null,"2017-04-14"]
[null,null,"删除",null,null,"2017-04-14"]
[null,null,"查看",null,null,"2017-04-14"]
[null,null,"导出报表",{"$nulls":4},"2017-04-28"]
[null,null,"流程完善",null,null,null,"2017-04-21"]
["综合监控","环境监控","环境监控",null,"2017-04-07"]
[null,null,"三维查看",null,null,null,"2017-04-21"]
[null,null,"设备控制（页面效果）",{"$nulls":4},"2017-04-28"]
[null,null,"真实数据接入",{"$nulls":4},"2017-04-28"]
[null,"状态监控","状态监控",null,"2017-04-07"]
[null,null,"生成巡视计划",null,null,null,"2017-04-21"]
[null,null,"生成工单",null,null,null,"2017-04-21"]
[null,"设备控制","设备控制（页面效果）",null,null,null,"2017-04-21"]
[null,null,"真实数据接入",{"$nulls":4},"2017-04-28"]
[null,"视频监控",{"$nulls":5},"2017-04-28"]
["图形浏览","gis浏览",null,null,"2017-04-07"]
[null,"bim图形浏览",null,null,null,"2017-04-14"]
[null,"资产数据接入bim模型",{"$nulls":5},"2017-04-28"]
[null,"监控数据接入",{"$nulls":5},"2017-04-28"]
["统计分析","统计",null,null,"2017-04-07"]
[]
[null,"分析",{"$nulls":4},"2017-04-21"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}