{"text_format":"2","workbook":"xlsx","n_sheets":9,"sheets":["计划","A.业主意见","B.首页","C.项目管理","D.初步设计审批","E.智能监管平台","F.经营人基础信息","G.许可证附证","H.码头"],"not_rendered":{"charts":0,"images":33,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"计划","index":0,"n_rows":38,"n_cols":9,"rows_kept":38,"cut":false,"hidden":false,"merged":[]}
["序号","模块","编号","问题描述","记录时间","开始时间","结束时间","状态","修改方案"]
[1,"A",1,"画面关闭重新打开时不缓存上次的内容","2016-08-12",null,null,"未开始","增加按钮，可初始化查询条件"]
[2,"A",2,"分页查询有bug，当前只有一条时仍会显示第二页，而且没数据","2016-08-12","2016-08-12","2016-08-12","已完成","增加分页判断逻辑，总页数小于当前页时显示最后一页"]
[3,"B",1,"人员图标与风格不搭，鼠标移动到人员名称（系统管理员）时显示超链接样式，点击打开修改密码窗口","2016-08-12",null,null,"未开始"]
[4,"B",2,"首页等图标鼠标移动后增加动态效果，修改密码去掉，注销改成“安全退出”，点击时弹出确认框后再退出系统","2016-08-12",null,null,"未开始"]
[5,"B",3,"登录人与港口名称位置交换","2016-08-12",null,null,"未开始"]
[6,"B",4,"1024*768下显示不正常，用户姓名消失了，要设置最小宽度，可以出滚动条","2016-08-12",null,null,"未开始"]
[7,"B",5,"当tab未满时不显示这个箭头","2016-08-12",null,null,"未开始"]
[8,"B",6,"此处隐藏意义不大，可以考虑左侧菜单全部隐藏，或者去掉此处按钮","2016-08-12",null,null,"未开始"]
[9,"B",7,"工作提醒中有未读消息要有红色喇叭标识，未读消息有“new”的标识","2016-08-12",null,null,"未开始"]
[10,"B",8,"按钮横排显示，双击“待办事务”双击进入待办列表，同样消息提醒双击也进入消息列表","2016-08-12",null,null,"未开始"]
[11,"B",9,"行政人员信息与经营人信息图标太像，行政人员可以设计个帽子什么的，区分大一点","2016-08-12",null,null,"未开始"]
[12,"B",10,"单船申报图标和证书信息图标不确切，需要重新设计","2016-08-12",null,null,"未开始"]
[13,"B",11,"右上角的待办任务图标提示字改为“待办事务”，与左下方一致","2016-08-12",null,null,"未开始"]
[14,"B",12,"下面三个菜单图标重新设计，不能反映出所标示的功能","2016-08-12",null,null,"未开始"]
[15,"C",1,"从项目信息中的“项目进度”功能进入建设进度管理功能后下方留白太大","2016-08-12",null,null,"未开始","修改代码"]
[16,"C",2,"查询条件仅保留一行，点击可下拉出更多查询条件","2016-08-12",null,null,"未开始","修改代码"]
[17,"C",3,"登录名称显示nul","2016-08-12","2016-08-12","2016-08-12","已完成","修改代码"]
[18,"C",4,"项目信息中字段填写类型校验","2016-08-12",null,null,"未开始"]
[19,"C",5,"项目投资类型增加“合资”，并在选择合资时显示政府投资额，并自动计算政府投资占比","2016-08-12",null,null,"未开始"]
[20,"C",6,"项目与码头关联、码头与泊位关联（信息更新问题？）泊位名称、吨级、长度","2016-08-12",null,null,"未开始"]
[21,"C",7,"增加项目编码、水域类型、泊位个数（自动统计）、建成时间","2016-08-12",null,null,"未开始"]
[22,"C",8,"通过码头可以查找本码头的所有项目（资源系统中点击码头时可以打开项目列表，进而查看项目具体信息和附件）","2016-08-12",null,null,"取消"]
[23,"C",9,"通过能力必填、泊位吨级去掉、码头增加结构形式。","2016-08-12",null,null,"未开始"]
[24,"C",10,"一览列表调整","2016-08-12",null,null,"未开始"]
[25,"C",11,"投资计划管理，提示信息有误","2016-08-12",null,null,"未开始"]
[26,"C",12,"无法录入数值：","2016-08-12",null,null,"未开始"]
[27,"C",13,"实施过程中流程节点是否有用？建设进度附件和实施过程对齐","2016-08-12",null,null,"未开始"]
[28,"C",14,"缺少列表导出excel功能","2016-08-12",null,null,"未开始"]
[29,"C",15,"“建设地点”改为“建设地址”，按规范","2016-08-12",null,null,"未开始"]
[30,"D",1,"审核意见默认“同意”","2016-08-12",null,null,"未开始"]
[31,"B",13,"泊位统计中加一个空格，冒号对齐","2016-08-12",null,null,"未开始"]
[32,"F",1,"列表查询条件显示一行，点击更多时显示更多条件","2016-08-12",null,null,"未开始"]
[33,"F",2,"经营许可证编号列放到经营人名称列后面","2016-08-12",null,null,"未开始"]
[34,"G",1,"附证有效期判断有误，5月份的附证在8月份看还是有效状态，这个列表按发证日期排列，最近发证的放最前面","2016-08-12",null,null,"未开始"]
[35,"G",2,"附证危险品名称没有显示","2016-08-12",null,null,"未开始"]
[36,"H",1,"是否危化品码头选择“是”，查询报错","2016-08-12",null,null,"未开始"]
[36,"H",2,"码头用途选择内容点击查询后恢复了默认","2016-08-12",null,null,"未开始"]

{"sheet":"A.业主意见","index":1,"n_rows":21,"n_cols":1,"rows_kept":21,"cut":false,"hidden":false,"merged":[]}
["2016-08-11"]
["1.画面关闭重新打开时不缓存上次的内容"]
{"$rows_empty":17}
["2016-08-11"]
["2.分页查询有bug，当前只有一条时仍会显示第二页，而且没数据"]

{"sheet":"B.首页","index":2,"n_rows":173,"n_cols":1,"rows_kept":173,"cut":false,"hidden":false,"merged":[]}
["1、人员图标与风格不搭，鼠标移动到人员名称（系统管理员）时显示超链接样式，点击打开修改密码窗口"]
[]
[]
[]
[]
[]
[]
["2、首页等图标鼠标移动后增加动态效果，修改密码去掉，注销改成“安全退出”，点击时弹出确认框后再退出系统"]
[]
[]
[]
[]
["3、登录人与港口名称位置交换"]
[]
[]
[]
[]
[]
["4、1024*768下显示不正常，用户姓名消失了，要设置最小宽度，可以出滚动条"]
{"$rows_empty":44}
["5、当tab未满时不显示这个箭头"]
{"$rows_empty":12}
["6、此处隐藏意义不大，可以考虑左侧菜单全部隐藏，或者去掉此处按钮"]
{"$rows_empty":39}
["7、工作提醒中有未读消息要有红色喇叭标识，未读消息有“new”的标识"]
{"$rows_empty":18}
["8、按钮横排显示，双击“待办事务”双击进入待办列表，同样消息提醒双击也进入消息列表"]
["9、行政人员信息与经营人信息图标太像，行政人员可以设计个帽子什么的，区分大一点"]
["10、单船申报图标和证书信息图标不确切，需要重新设计"]
{"$rows_empty":15}
["11、右上角的待办任务图标提示字改为“待办事务”，与左下方一致"]
[]
[]
[]
[]
[]
[]
["12、下面三个菜单图标重新设计，不能反映出所标示的功能"]
{"$rows_empty":11}
["13、泊位统计中加一个空格，冒号对齐"]

{"sheet":"C.项目管理","index":3,"n_rows":274,"n_cols":1,"rows_kept":274,"cut":false,"hidden":false,"merged":[]}
["2016-08-11"]
["从项目信息中的“项目进度”功能进入建设进度管理功能后下方留白太大"]
{"$rows_empty":42}
["2016-08-11"]
["查询条件仅保留一行，点击可下拉出更多查询条件"]
{"$rows_empty":23}
["2016-08-11"]
["登录名称显示nul"]
{"$rows_empty":9}
["2016-08-11"]
["项目信息中字段填写类型校验"]
{"$rows_empty":42}
["2016-08-11"]
["1、项目投资类型增加“合资”，并在选择合资时显示政府投资额，并自动计算政府投资占比"]
["2、项目与码头关联、码头与泊位关联（信息更新问题？）泊位名称、吨级、长度"]
["3、增加项目编码、水域类型、泊位个数（自动统计）、建成时间"]
["4、通过码头可以查找本码头的所有项目（资源系统中点击码头时可以打开项目列表，进而查看项目具体信息和附件）"]
["5、通过能力必填、泊位吨级去掉、码头增加结构形式。"]
[]
["2016-08-11"]
["一览列表调整"]
{"$rows_empty":45}
["2016-08-11"]
["投资计划管理，提示信息有误"]
{"$rows_empty":27}
["2016-08-11"]
["无法录入数值："]
{"$rows_empty":18}
["2016-08-11"]
["实施过程中流程节点是否有用？建设进度附件和实施过程对齐"]
{"$rows_empty":39}
["2016-08-11"]
["缺少列表导出excel功能"]
[]
[]
["2016-08-11"]
[" "]

{"sheet":"D.初步设计审批","index":4,"n_rows":2,"n_cols":1,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
["2016-08-11"]
["默认意见:同意"]

{"sheet":"E.智能监管平台","index":5,"n_rows":2,"n_cols":1,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
["2016-08-10"]
["左侧菜单添加隐藏、显示切换功能，gis综合平台的左侧树宽度可调整"]

{"sheet":"F.经营人基础信息","index":6,"n_rows":21,"n_cols":1,"rows_kept":21,"cut":false,"hidden":false,"merged":[]}
["1、列表查询条件显示一行，点击更多时显示更多条件"]
{"$rows_empty":19}
["2、经营许可证编号列放到经营人名称列后面"]

{"sheet":"G.许可证附证","index":7,"n_rows":37,"n_cols":1,"rows_kept":37,"cut":false,"hidden":false,"merged":[]}
["1、附证有效期判断有误，5月份的附证在8月份看还是有效状态，这个列表按发证日期排列，最近发证的放最前面"]
{"$rows_empty":35}
["2、附证危险品名称没有显示"]

{"sheet":"H.码头","index":8,"n_rows":25,"n_cols":1,"rows_kept":25,"cut":false,"hidden":false,"merged":[]}
["1、是否危化品码头选择“是”，查询报错"]
{"$rows_empty":23}
["2、码头用途选择内容点击查询后恢复了默认"]