{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["JTT_6公路项目工程形象进度统计","Sheet1"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"JTT_6公路项目工程形象进度统计","index":0,"n_rows":4969,"n_cols":98,"rows_kept":2250,"cut":true,"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1},"flags":["formulas_cached_only"]}
["RECID","RECVER","UNITID","DATATIME","FLOATORDER","TZ05010001001","TZ05010001002","TZ05010001003","TZ05010001004","TZ05010001005","TZ05010001006","TZ05010001007","TZ05010001008","TZ05010001009","TZ05010001010","TZ05010001011","TZ05010001012","TZ05010001013","TZ05010001014","TZ05010001015","TZ05010002001","TZ05010002002","TZ05010002003","TZ05010002004","TZ05010002005","TZ05010002006","TZ05010002007","TZ05010002008","TZ05010002009","TZ05010002010","TZ05010002011","TZ05010002012","TZ05010002013","TZ05010002014","TZ05010002015","TZ05010003001","TZ05010003002","TZ05010003003","TZ05010003004","TZ05010003005","TZ05010003006","TZ05010003007","TZ05010003008","TZ05010003009","TZ05010003010","TZ05010003011","TZ05010003012","TZ05010003013","TZ05010003014","TZ05010003015","TZ05010004001","TZ05010004002","TZ05010004003","TZ05010004004","TZ05010004005","TZ05010004006","TZ05010004007","TZ05010004008","TZ05010004009","TZ05010004010","TZ05010004011","TZ05010004012","TZ05010004013","TZ05010004014","TZ05010004015","TZ05010005001","TZ05010005002","TZ05010005003","TZ05010005004","TZ05010005005","TZ05010005006","TZ05010005007","TZ05010005008","TZ05010005009","TZ05010005010","TZ05010005011","TZ05010005012","TZ05010005013","TZ05010005014","TZ05010005015","TZ05010000000","TZXM","TZ05010001016","TZ05010001017","TZ05010002016","TZ05010002017","TZ05010003016","TZ05010003017","TZ05010004016","TZ05010004017","TZ05010005016","TZ05010005017","TZ05010005018","TZ05010005019","TZ05010005020","TZ05010005021","TZ05010005022","TZ05010005023"]
["29E626CD0A53C61863A8A0E8EA28909F",0,null,"2014Y0005",-1,0,220,0,0,0,0,0,0,0,0,68,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,233,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"路基土石方58万方；完成部分箱涵、涵管施工；完成征地拆迁费用支付940万","44F92AE9A0000001A6C4B4A0FE608B65"]
["29F0D81E7E9F767F821CB9CB8BBCC80D",0,null,"2014Y0009",-1,{"$nulls":75},"除拆迁影响段落，主线机动车道完工通车。","46EA9A9840000021E67762482E18105E"]
["2A57654703D20E59AB54478A22E0CB90",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"开展征地拆迁工作，准备开展项目招投标工作。","44F92AE7C000002175F300290A52D82C"]
["2A5C299E8D6B28466ADE49D6D7C4E0C3",0,null,"2014Y0004",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,617,10,965000,100000,2120000,6,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,13,0,5000,64900,114600,2,0,0,5,2,0,0,0,0,{"$nulls":15},"完成土石方开挖348万方（93.77%）,土石方填筑9万方（94.5%）;水稳碎石基层100万平方（97.98%)，12%灰土96.5万平方（95%)，沥青212万平方84.8%);桥梁29500万元（74.75%）；交安1400万元（50.7%）；绿化3800万元（71.4%）。","44F92AE840000101423CCFA36BCE2089"]
["2A5EFA98F02BB5B4D5CE60CFB4A9F700",0,null,"2014Y0006",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["2A7B91C0E6B133D3DA20CE8CB54E5219",0,null,"2014Y0010",-1,{"$nulls":75},"目前桥梁已建成。","458302B080000021E4D2CC5B2F4B6514"]
["2AA140D4CA751360EEBF71BA17F7C205",0,null,"2014Y0006",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,231375,189942,193985,0,68,87,0,82,0,0,0,25000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,189942,193985,0,33,42,0,0,0,0,0,25000,{"$nulls":15}," 一、形象进度：目前正在进行路面底基层、基层、面层、桥涵施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层189942平方米（80%）、面层193985平方米（45%）；桥涵完成投资2152万元（66%）；防护工程2.5万方（68%）；绿化工程完成309万元（22%）。二、存在问题：无。    ","44F92AE80000000125D8496C7290DDFC"]
["2AC34595EB7DA6FC6226FEEECF77E82F",0,null,"2014Y0008",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段正在进行路基施工。","45825CCB00000021AE879AE5EFB9B065"]
["2AC5E6A3F6FAB53DFB78379C9FE093BF",0,null,"2014Y0010",-1,{"$nulls":75},"开展下部结构施工。","494F86EDE00000215894D3EF8FBDFA9B"]
["2AFA8D59B4C4A67B3E7D446FAE8CF72F",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["2B4AC161262D5A9688A52599AB9B2EDF",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"银珠路至242省道段现在正在完善前期手续和征地工作；南段已进场施工，完成部分路基、桥涵。","46A3CDDB80000021BADA4BD8961B8D19"]
["2C6AA1A2F718DE299807D48A0327ADEC",0,null,"2014Y0010",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["2CA70E9D64C3592D029C82BF7FAE2917",0,null,"2014Y0010",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["2D96338B3EC1848D8FD231E936E16640",0,null,"2014Y0008",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["2D9B5BDB133D4C1358CE89694D77A689",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程、停车场工程已完成,附属设施完成99%，绿化工程完成100%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["2EE2C885227CD5DD2FC362453E8A22FF",0,null,"2014Y0006",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,0,180,0,0,0,0,0,50,95,9,72,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,null,180,{"$nulls":5},35,95,9,{"$nulls":4},4447,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["2F1FF3D41BDF6085065AF280516EB470",0,null,"2014Y0010",-1,5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":27},"道路主体工程基本完成，完成投资1600万。","4965922940000021CADEE47D6F615CD4"]
["2F36A3CF963B48C8C69E66A26C3CB0EA",0,null,"2014Y0005",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,136,null,162650,140830,null,null,50,100,null,43,{"$nulls":3},1680,null,70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,20,null,149650,127830,null,null,20,{"$nulls":6},1680,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["2FCE218CB6AED5A23221CF6C8CCC3C72",0,null,"2014Y0008",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["3063E4539D54DE956459387599D5AD5C",0,null,"2014Y0005",-1,{"$nulls":75},"目前，路面基层已完成。","4583097620000021C29C88DEA1D39A75"]
["30AC11EA17140FA02E8B9459996FA4AC",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"场站部分扫尾，铁路专用线、装卸设备购置等。","452C38D9200000A160383FB696401BD8"]
["316DA95208B32D3BA2B936587A3C9042",0,null,"2014Y0005",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,231375,132456,150877,0,55,65,0,82,0,0,0,21000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,132456,150877,0,20,20,0,0,0,0,0,21000,{"$nulls":15},"一、形象进度：目前正在进行路面底基层、基层、面层、桥梁和绿化施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层132456平方米（56%）、面层150877平方米（35%）；桥涵完成投资1840万元（56.4%）；防护工程2.1万方（57%）；绿化工程完成212万元（15.1%）。二、存在问题：无。         ","44F92AE80000000125D8496C7290DDFC"]
["3197C6A000E75FB35D27D768CDFBE8D0",0,null,"2014Y0006",-1,{"$nulls":75},"徐圩港区防波堤东斜坡堤进尺1220米，累计折合进尺4.22公里","452C38DA800000A19C9699F0088370B9"]
["31AB2DF446BEBAECCEFD68387DB0E282",0,null,"2014Y0009",-1,{"$nulls":75},"新海新区段已建成通车；马涧通道边坡治理已开工建设；云台互通段基本完成临建施工；徐圩新区段已累计完成11公里，路基完成10公里，桥涵全部完成，路面完成40%，下穿通道完成45%。","44F92AE7E000004126A44C796491035A"]
["31B186674CA5A703833A3D74A42D7F80",0,null,"2014Y0006",-1,{"$nulls":75},"完成农村公路建设47.2公里","45A643D5200000210231D09FB0198FE4"]
["31BB114BA8C9B496C16C9625C6A76E4F",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一期工程交易中心主楼等工程完工。","452C38D960000061A773E74DF5A30C52"]
["338998D00C3D94C329EC9D32AFA7DAA5",0,null,"2014Y0010",-1,1,null,1,3500,3500,3500,{"$nulls":69},"已完成设计招标工作，目前正在开展征地拆迁和施工准备。","49799B6500000001CDC755BA5B4F4D55"]
["341A9D4A939F7260C26D14BAACA4C435",0,null,"2014Y0009",-1,{"$nulls":75},"    55#、57#泊位水工建筑物工程于8月1日交工验收；道路堆场东区总量11.6万平米，完成10.5万平米","46D12277000000016E90CB741749DE83"]
["001F3D19B5FF1525138613D603CA6703",0,null,"2014Y0003",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["00CA62BBC3828F45C3EE1519C547D628",0,null,"2014Y0005",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["0184EA587BB58E3CCB4BEEB8F8D7A618",0,null,"2014Y0009",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,156,null,221620,202193,null,null,100,100,null,43,{"$nulls":3},1680,null,70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,40,null,208620,189193,null,null,70,{"$nulls":6},1680,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["01FB1215A39ACD2F166E1B2A8045E500",0,null,"2014Y0006",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["0255B433C93E36810E92E9422D5C4B16",0,null,"2014Y0008",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"正在进行路基、涵洞桥梁施工，（本月停工）","45A630DD40000021758080AC865FC45B"]
["02B3CC4B1A1EB172C8B785823C933891",0,null,"2014Y0004",-1,41,14,120,1436401,null,1305854,{"$nulls":3},12,{"$nulls":5},21,8,19,30258,null,114623,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,null,1305854,{"$nulls":3},12,{"$nulls":5},21,8,19,30258,null,114623,{"$nulls":3},0,{"$nulls":21},"459779F8800000211228699830C698E7"]
["0316E96B117006152949B26F7AF886B5",0,null,"2014Y0009",-1,{"$nulls":75},"目前，桥梁已建成。","47678A76C0000021CA6C39AAC7090030"]
["036090932237C81DB1C771BDFA218127",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成土方开挖100%，完成基础100%，完成墙身90%\n","44F92AE9000000A114EC34ECCE42A6E8"]
["0404A68FAF050CFD2D12CF67203B6645",0,null,"2014Y0004",-1,16,121,0,287625,280590,834000,0,0,0,7,91,0,0,0,0,0,104,0,236980,424550,464985,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,2,0,13830,148830,281000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本期完成水稳86495平方；AC-20沥青131145平方；绿化2000万元；交安工程1100万元。\n本期完成投资5200万元，本年累计完成投资7950万元，累计完成投资49950万元（其中征地拆迁18000万元，其他费用1000万元）。费用1000万元）。","44F92AE8800000016600EFB6FA6DB838"]
["050738F83BB99DD6FCEC57D2E61D6085",0,null,"2014Y0008",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,180,null,433000,320000,{"$nulls":5},62,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},180,null,433000,320000,{"$nulls":5},61,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["0535B053739BD4028E0AC642A3304D13",0,null,"2014Y0006",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,691690,648055,230000,0,0,0,10,118,0,0,0,22740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,201270,402845,230000,0,0,0,1,0,0,0,0,5053,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["05731A3F91D480BFE31B429DAC0A0892",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体完工，陆域施工基本完成。","44F92AE8800000C1B072D9F00825DD28"]
["05C759FAD9DA753744E3445EE79CA7CE",0,null,"2014Y0010",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段正在进行路基施工。","45825CCB00000021AE879AE5EFB9B065"]
["06DA71F8BF80FB41CB62FA05B4DE4B78",0,null,"2014Y0008",-1,{"$nulls":75},"正在开展征地拆迁，施工单位已进场。","48173F21C00000213849C18090E227D5"]
["06FB50EB258DD0B244751C9DE44E94DE",0,null,"2014Y0007",-1,{"$nulls":75},"沪宁高速昆山高新区互通连接线（中华园路）新建工程加快路基施工及桥梁工程施工","476C4BC84000002168C8EFB59D88315C"]
["07EC79C903787EC556BEEAD9E9B859F2",0,null,"2014Y0006",-1,{"$nulls":75},"码头基本完工，陆域设备采购。","45B26F0B8000002123F9B996453503FA"]
["08056A4A033507AA17C549F8FF6CF8E5",0,null,"2014Y0008",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28A8980000021D5A75D5DAF1B946B"]
["085061AC9F18500977FA26D61BD00F36",0,null,"2014Y0007",-1,{"$nulls":75},"目前，桥梁已建成。","47678A76C0000021CA6C39AAC7090030"]
["085B67DB1CB672104F1AA0918699DC1F",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地拆迁、场地平整、围墙砌筑工作。","44F92AE7C000008151CBB288EBA76DE4"]
["09093E580970C3A1CCA874382A90FE14",0,null,"2014Y0009",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["0920A59B903643530F408465D20DF83D",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一期工程交易中心主楼等工程完工。","452C38D960000061A773E74DF5A30C52"]
["0937763B5184FE08F762F4E84833DDB5",0,null,"2014Y0004",-1,{"$nulls":75},"目前，正在进行征地拆迁工作。","4583086800000021610D57307F655C40"]
["0982563AE91EECDC652F3CD9506BE081",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,153,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本月完成开挖42万方，填筑21万方","44F92AE9800000A15AC5660EDAD7D017"]
["09C239AC10D3774AE5B750298AFA04FF",0,null,"2014Y0008",-1,{"$nulls":75},"完成路基填筑65%、涵洞80%。","4756E0D780000021BD984AD195D60C8A"]
["0A11D64A83D2A56F75243E2F87881FF6",0,null,"2014Y0010",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"完成天元路至秣陵段沥青上面层摊铺施工，完成绿化施工95%。","45A64FE000000021EF20F17B8FB2A64B"]
["0B532032E46263E78D8B8DEC3B7FE632",0,null,"2014Y0005",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["0BE906F9DE0377E5363A77B6E6017B1C",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["0C3FF3105F1D7E333BF8688E21E75BCA",0,null,"2014Y0008",-1,152,null,152,{"$nulls":12},35,null,35,{"$nulls":12},152,null,152,{"$nulls":12},35,null,35,{"$nulls":27},"目前农村公路已完成约35公里，完成投资20500万元（本月停工）","45A62941800000214B6E50365A9AF0C1"]
["0C670694C3E459EC2F463431E5E7676D",0,null,"2014Y0010",-1,25,1,25,30410,53630,108850,{"$nulls":9},20,1,20,30410,48630,808850,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":9},20,1,20,30410,48630,808850,{"$nulls":25},"45977C86A000000145F95B717A76C135"]
["0CACF86810CB668B5003FB4FE1E60FB5",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE900000041A21B1C596C76FE54"]
["0CBD818EEE781F59F6A969E0EDD2DAB2",0,null,"2014Y0010",-1,{"$nulls":75},"左幅水稳完成50%，桥梁工程完成80%。","46EA9EFBA0000021C04603F2E53ED447"]
["0CCC15AD8FA1F78DE37EAC244BF29093",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["0DD8093F317EDACBC0CCDEE82C5F23EA",0,null,"2014Y0010",-1,{"$nulls":75},"目前，正在进行路基施工。","4583086800000021610D57307F655C40"]
["0E4CDF112324F4568825F82E6824B87D",0,null,"2014Y0008",-1,{"$nulls":75},"目前桥梁已建成。","458302B080000021E4D2CC5B2F4B6514"]
["0E93CE985406FB6707A60E0F3057940E",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["0FC6F8B542B1E21CE9C338D161521694",0,null,"2014Y0008",-1,{"$nulls":75},"完成半幅路封闭围挡开挖。","452C38DA40000161563DFD045D6A3673"]
["102C1480FAECB96C001C59E640F08B65",0,null,"2014Y0007",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28726E0000021457D777E03877DDB"]
["10452495310548184AFC97EC960A9CC7",0,null,"2014Y0004",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,160,440,22087,0,6,0,0,0,0,0,0,0,0,0,0,0,0,2425,{"$nulls":15},"存在问题：JTHD-1标\n1、CK0+000~CK0+125  有房屋影响\n2、观音院连接线（得月阁）山上果树影响\nJTHD-2标\n1、FK3+200-FK+700、FK4+780-FK5+040徐明刚苗木\n","4592B501E000002123E927A043947D89"]
["1091D86A1EEFCBA99920673BFBE7F707",0,null,"2014Y0007",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["10A2152E851BF33706A48C6574484580",0,null,"2014Y0004",-1,{"$nulls":75},"码头部分管线安装。","45B28A8980000021D5A75D5DAF1B946B"]
["11484299F5609F932E45E447388623C9",0,null,"2014Y0002",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,112680,0,0,0,40,50,0,82,0,0,0,6100,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,27765,0,0,0,5,5,0,0,0,0,0,6100,{"$nulls":15},"一、形象进度：目前正在进行路基、路面底基层、桥涵施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层112680平方米（48.7%）；桥涵完成投资1350万元（41.4%）；防护工程0.61万方（16.6%）。二、存在问题：无。","44F92AE80000000125D8496C7290DDFC"]
["11B1EC110AD42844834FD58C27271B66",0,null,"2014Y0009",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：目前江宁区政府启动了征地拆迁工作，已完成土地丈量、房屋拆迁调查工作，正在进行杆管线迁移调查。指挥部配合开展红线放样和路田分家工作，施工单位也开展了驻地建设和测量放样复核等施工前准备工作，待江宁区政府提供建设用地后随时开展施工工作。二、存在问题：地方政府征地拆迁工作进展缓慢，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["122FD8C74D082C4963A73A25DA3ABB45",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468904228000002136B9240D71855BA8"]
["13062D6518A5A7E9EF8682B236F33EA1",0,null,"2014Y0005",-1,42,358,42,1222845,1159075,2222151,1,100,100,22,187,0,0,0,58568,null,320,null,970000,920000,1300000,1,100,100,22,187,{"$nulls":3},38000,42,358,42,1222845,1159075,2222151,1,100,100,22,187,0,0,0,58568,null,320,null,970000,920000,1300000,1,100,100,22,187,{"$nulls":3},38000,{"$nulls":16},"464ADF4B400000012FF9943B4A23B34E"]
["1306E75849C114DCA98A932EBE93A099",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["1330C5832E695F3CFEDB377FA4D7D9EC",0,null,"2014Y0007",-1,44,417,44,1357190,2046965,2063198,4,100,100,6,189,0,0,0,19712,44,417,36,1357190,2046965,1939406,3,99,100,6,189,{"$nulls":3},15967,38,22,38,302615,810646,1819624,1,25,25,2,1,{"$nulls":3},10392,38,22,30,302615,810646,1695832,0,24,25,2,1,{"$nulls":3},6647,{"$nulls":15},"形象进度：G328以北段38.42km:宁通至大仪主体工程基本完成，正在完善交安设施、绿化等附属工程","464AE306E00000210AA87B4400911FFD"]
["13A8921D9475F77E47F5997BF9EDC84A",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成疏港航道和港池码头工程，正在进行北侧堆场建设前期准备工作。","44F92AE740000061422D7CBDB598F0A4"]
["13AC6B7BA9194685B4FF3F46989F6FFB",0,null,"2014Y0003",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,146,0,142150,109467,735812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,0,2925,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"形象进度：铁心桥规四路贾东地块后1.2公里辅道路基、挡墙施工；景观墙施工；路灯施工。累计土石方146万方，路面底基层14.2万平米，基层10.9万平米，面层73.6万平米。本月完成投资1300万元，本年累计完成2000万元，累计完成167090万元。","44F92AE8400000A1F8CD4F6E58802DB5"]
["14124998BEACCD58A28B4238EF4D0EDA",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["148BCDDE220CA6AA2ACA4F022F67F49C",0,null,"2014Y0008",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["148EEA96F5B4FABF523E64DDC5B28BC4",0,null,"2014Y0005",-1,1339141,1127463,18,605466,519452,9333283,2,50,50,6,49,0,{"$nulls":3},1339141,1127463,18,605466,519452,7466626,2,50,50,6,55,0,{"$nulls":3},0,0,0,0,0,0,0,0,0,6,0,0,{"$nulls":3},0,0,0,0,0,0,0,0,0,6,0,0,{"$nulls":19},"45A64CBEC0000021EA2875A94CD2711C"]
["14933A398C9E7392823B19AE8C87074C",0,null,"2014Y0010",-1,{"$nulls":75},"东直立堤工程年内折合进尺60米，占年计划的3%，累计进尺185米，占总长4377米的4%，配套的预制厂已建成投产。","452C38D9600000015B091B22A009EB3A"]
["14B7D8ED61D84CADE28B47F996E97EEB",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场、辅助设施建设及设备安装。","44F92AE8C00000C150E871A6EE092CCD"]
["14BEA50CCBBE9B7E6F586F4DCFACE54E",0,null,"2014Y0005",-1,652423,1019946,25,652423,590283,564435,2,50,50,11,79,{"$nulls":4},0,51962,{"$nulls":4},0,50,50,0,0,{"$nulls":4},0,300000,0,0,0,0,1,0,0,0,0,{"$nulls":4},0,51962,0,0,0,0,0,0,0,0,0,{"$nulls":20},"45A64AD8E000002115357ED0397AE2AC"]
["151C10BB334EC29A3425D4E2202570D6",0,null,"2014Y0010",-1,{"$nulls":75},"累计完成投资3.5亿元，占总投资4.2亿元的83%，其中年内完成投资2.5亿元，占年度计划3.2亿元的78%。年内折合进尺1700米，占年度计划2000米的85%，累计折合进尺2100米，占工程总长的84%。","46EBEFA560000021402F9981E1B1599D"]
["157BA74BE09757A7FC1CA66C6A620799",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"南段路基整平已完成，北段路基完成300米。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["15CAD8B364DC112D77D9F7ADAA1F3F6D",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["1602911EBB531CF259202282C7F7BA32",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已建成8万平方米集装箱堆场，场地及其附属设施施工。","452C38D9200000A160383FB696401BD8"]
["1666968A60267A9AFCF7060365F8D4A6",0,null,"2014Y0009",-1,{"$nulls":9},6,{"$nulls":14},0,{"$nulls":14},6,{"$nulls":14},0,{"$nulls":20},"完成招投标工作，进行施工准备工作","45A62A6EC00000210FD9D03217C261AE"]
["16E6E21D435306DEA39D9874AF84DE0D",0,null,"2014Y0006",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"成天元路至秣陵段路面施工，绿化施工。","45A64FE000000021EF20F17B8FB2A64B"]
["17068F940C8CE36C3582E6A2A2AB2111",0,null,"2014Y0007",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,837155,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,653170,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本期完成沥青摊铺9.5万平方；绿化植色带5万平方；交安工程完成路侧1.6KM单波护栏，路面标线7200平方及剩余附属设施。\n本期完成投资1700万元（其中其他费用300万元），本年累计完成投资14900万元，累计完成投资56900万元（其中征地拆迁18000万元，其他费用1650万元）。","44F92AE8800000016600EFB6FA6DB838"]
["182C7B51AA5338D3B79832E7A17A9D26",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"南段路基整平已完成，北段路基完成100米。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["1854338F784F7E75FB67183EE9A69E8B",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量70%,附属设施完成70%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["193CDE0E23045B4AE57F0A9E95B5BDB5",0,null,"2014Y0007",-1,101,65,101,692100,671900,651700,{"$nulls":10},39,10,61440,59520,57600,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":10},39,10,61440,59520,57600,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["19538030469F53C1D6D3682D06043091",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场及辅助设施建设。","44F92AE8C00000C150E871A6EE092CCD"]
["19B0E7B139CE1EF30A1CB84697C409E4",0,null,"2014Y0010",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,95,null,6200000,640000,2400000,null,52,75,18,52,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,35,null,200000,60000,null,null,32,35,10,20,{"$nulls":20},"4597C2C660000021C7BD96E4F6D02E66"]
["19F3C9066CE64BCB1ABC49000C5DE3ED",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地拆迁、场地平整、围墙砌筑工作。","44F92AE7C000008151CBB288EBA76DE4"]
["1A0FD583BEBC114318318DBAB9FE554B",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成项目前期审批手续,完成部分征地拆迁,完成土方开挖65%,完成基础55%","44F92AE9000000A114EC34ECCE42A6E8"]
["1AA4F41EF35C088C41274A31869A6B7F",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["1B3A5991DB6047940DC309738EE4FACB",0,null,"2014Y0007",-1,25,1,25,30410,53630,108850,{"$nulls":9},13,1,13,30410,38630,68749,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":9},13,1,13,30410,38630,68749,{"$nulls":25},"45977C86A000000145F95B717A76C135"]
["1B7A2B640637FE0584E18E5206DE8003",0,null,"2014Y0008",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["1BD644D4D85601003AE1F83E5169D8A9",0,null,"2014Y0005",-1,{"$nulls":75},"完成征地拆迁、场地平整、围墙砌筑。","44F92AE7C000008151CBB288EBA76DE4"]
["1BE0FE6E1BB99F266F78C47D4858865D",0,null,"2014Y0008",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,591,0,0,0,0,0,0,0,0,93,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,351,0,0,0,0,0,0,0,0,30,0,0,0,0,{"$nulls":15},"完成上峰至土桥段下面层沥青摊铺工作，完成土桥至湖熟段45%路基施工，完成桥梁工程施工65%。征地拆迁费用支付510万。","44F92AE9800000A15AC5660EDAD7D017"]
["1BED1BF3B5F609A16066155E503C038B",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场及辅助设施建设。","44F92AE8C00000C150E871A6EE092CCD"]
["1BFB003F8A0B004914A69AE38E02108E",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量60%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["1C5C7857E02CA4CE7E59923CD91AD6A5",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["1CB8E8ADD653B5F4724EBA132253EE7B",0,null,"2014Y0005",-1,152,null,152,{"$nulls":12},34,null,15,{"$nulls":12},152,null,152,{"$nulls":12},34,null,15,{"$nulls":27},"目前道路开工里程34公里，已完成15公里，完成投资14500万元","45A62941800000214B6E50365A9AF0C1"]
["1D2668EABE6035BE8AF7B6130832CFFE",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量75%,附属设施完成75%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["1DC77899FCCA7A27ECBE9CE0CD2411CD",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，工程已开工建设，目前正在进行卡口及口岸大楼施工。码头水工下部结构已开工建设，目前正在进行基坑开挖及后方回填。","44F92AE800000121D51AC7AB782D4663"]
["1E049CDAF711B456F70C2E73F6511B5E",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"场地及其附属实施施工。","452C38D9200000A160383FB696401BD8"]
["1E4B6EAA78AB6FA9BE54226B7098EF5F",0,null,"2014Y0005",-1,{"$nulls":75},"目前，完成主桥挂篮现浇梁、引桥梁板桥面的铺装、护栏等施工。","45830129E0000021F3EEA0D7E47483E6"]
["1E7026F8D1D4B1D29FC2FA7A57BCAFB4",0,null,"2014Y0009",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,0,180,0,0,0,0,0,60,100,9,73,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,null,180,{"$nulls":5},60,100,9,1,{"$nulls":3},4447,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["1E94E4F1A88CA12C2C98C01F31172385",0,null,"2014Y0006",-1,1339141,1127463,18,605466,519452,9333283,2,50,50,6,49,0,{"$nulls":3},1339141,1127463,18,605466,519452,9333283,2,50,50,6,55,0,{"$nulls":3},0,0,0,0,0,1866657,0,0,0,6,0,0,{"$nulls":3},0,0,0,0,0,1866657,0,0,0,6,0,0,{"$nulls":18},"已完工","45A64CBEC0000021EA2875A94CD2711C"]
["1EA62EBFAF96C00F61F22C3429145030",0,null,"2014Y0005",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,86,6,19,16,44,0,0,0,0,23,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段基本完成路基，完成涵洞34道，中型桥梁1座在进行桥面铺装；\n白马段10.2公里进行路基施工，桥梁施工单位进场；\n剩余洪蓝至明觉段18公里正在进行房屋丈量及附属物清点工作","44F92AE780000001F6AE7427CA69104E"]
["1ED6FF996FE57C0D0B805401256F6B75",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["1F6C7AE27431FD702433EF513178C47E",0,null,"2014Y0009",-1,101,65,101,692100,671900,651700,{"$nulls":10},55,10,125760,98460,57600,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":10},55,10,125760,98460,57600,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["1F6D6B30CBB1C75DFDBEC467DEAE047C",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头基本完工，正在进行管架和管道施工。","44F92AE9A0000061EA403DE4CD1A8397"]
["1F736FFC3A29AFA65D398D437E95E801",0,null,"2014Y0007",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["1FA87C9351A05824E67352B9EA0D4FF2",0,null,"2014Y0006",-1,{"$nulls":75},"目前，完成主桥挂篮现浇梁、引桥梁板桥面的铺装、护栏等施工。","45830129E0000021F3EEA0D7E47483E6"]
["1FB3DF6F5193DE6851440C4AB4458CB2",0,null,"2014Y0007",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["1FCFADA9C48559020616072840C1EAB4",0,null,"2014Y0009",-1,0,270,0,0,0,0,0,0,0,0,68,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成锦文路至江宁河段路基施工70%，完成桥梁施工75%","44F92AE9A0000001A6C4B4A0FE608B65"]
["1FE533D425C303B56B40CE4984516914",0,null,"2014Y0010",-1,{"$nulls":75},"基本完工。","46D12277000000016E90CB741749DE83"]
["20266361F73F400ECCF4AA93D9CF0961",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已完成灌注桩600根、平整场地9000平方、安装吊机4台","452C38DDE00000411468534B18F06C9C"]
["2100B782369F81442532670F0C59C2CD",0,null,"2014Y0009",-1,{"$nulls":75},"完成招标工作，施工单位已进场开展路基处理工作。","48B15A89C0000021CEB0D93D0A59616D"]
["212D465DE84AFD1E3167EE42CE92EDFB",0,null,"2014Y0010",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28726E0000021457D777E03877DDB"]
["2170A8465E2159E974F15C3967617A6E",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["2196A3358DC6A59F61C422AABAA4758D",0,null,"2014Y0010",-1,24,339,24,652423,590283,564435,2,50,50,11,79,0,0,0,0,0,14,0,0,0,0,0,50,50,0,0,{"$nulls":5},20,0,0,0,0,0,0,20,0,2,{"$nulls":5},14,0,0,0,0,0,0,0,0,0,{"$nulls":19},"一标：清表驻地建设完成；二标便道碎石土回填，河塘清淤，回填碎石土。","45A64AD8E000002115357ED0397AE2AC"]
["21D36E485A09DF13CE8706E648B35EB3",0,null,"2014Y0009",-1,{"$nulls":75},"目前，已建成通车。","458307CAE00000414A3628960FD10AB2"]
["21EB0C8E4F362FB9DC6C5307014857F9",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"I标段24万平方米软基处理完工，正在实施回填工程，办公楼内外装修。","452C38D960000061A773E74DF5A30C52"]
["226AD9E268F0A89A57078C7EECE86095",0,null,"2014Y0008",-1,{"$nulls":75},"完成征地拆迁，完成土方开挖68%。","48171CB940000001DAB3F475A2461DC6"]
["233D825EF10C895CFE567A851539C2A5",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,123,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本月完成路基土石方工程47万方","44F92AE9A0000001A6C4B4A0FE608B65"]
["237777188C2C03CF2C337803646FF9B0",0,null,"2014Y0004",-1,{"$nulls":9},8,{"$nulls":14},4,{"$nulls":14},8,{"$nulls":14},4,{"$nulls":21},"45A622C860000021C54A12ED93C79943"]
["243F48A5FD149A4ADB533411FE66F06E",0,null,"2014Y0010",-1,{"$nulls":75},"   车船直取工程完工；液化罐区pcc桩基施工总量约4200根，完成3700根，化工品罐区18个储罐，完成制作安装14个\n","46D12095E00000210EEE5BA374F2A089"]
["24C1A91A7F16E43437F8D748DD3243F4",0,null,"2014Y0010",-1,101,65,101,692100,671900,651700,{"$nulls":10},65,10,654190,470320,234640,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":10},65,10,654190,470320,234640,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["24DDA4B789A8AB6EDD336C8D3687627D",0,null,"2014Y0005",-1,{"$nulls":75},"路基：管桩完成88.56%，河塘清淤完成95%,土方填筑完成18.79%；桥涵：桩基完成83.19%，承台完成60.95%,系梁完成35.95%,立柱完成48.67%，盖梁完成30.9%,预制箱梁完成19.26%,小构完成50%","44F92AE7400000C18C5FA6F58B9A0813"]
["25FE1F6CD2D20A20C2F458A587152326",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成项目前期审批手续,完成部分征地拆迁","44F92AE9000000A114EC34ECCE42A6E8"]
["261FF7E512D0A7065A84F514C056199F",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["2623AC01F1C526C01D1907F8C49311AC",0,null,"2014Y0009",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":16},"464AE565800000215C9C09C8A0BE8932"]
["27984F8C4FD706CFC3D72B4BA8B137CB",0,null,"2014Y0010",-1,44,417,44,1357190,2046965,2063198,5,100,100,6,189,0,0,0,19712,44,417,44,1357190,2046965,2063198,5,100,100,6,189,{"$nulls":3},19712,38,22,38,302615,810646,1819624,2,25,25,2,1,{"$nulls":3},10392,38,22,38,302615,810646,1819624,2,25,25,2,1,{"$nulls":3},10392,{"$nulls":15},"形象进度：全线工程基本完成","464AE306E00000210AA87B4400911FFD"]
["27A9260089531C6B1650277A02F1EA9C",0,null,"2014Y0003",-1,22,239,22,622171,604198,1078980,0,0,0,0,88,0,0,0,63700,0,143,0,0,0,0,0,0,0,0,49,0,0,0,0,0,227,0,0,0,0,0,0,0,0,88,0,0,0,0,0,143,0,0,0,0,0,0,0,0,48,0,0,0,0,{"$nulls":16},"452C38D8400000219DE485E94FD07CED"]
["27D811F63E28DB60CF52DD40B31952C4",0,null,"2014Y0009",-1,{"$nulls":75},"完成路基土方开挖75%、路基填筑23%。","48173F21C00000213849C18090E227D5"]
["2854DAC68C50413730FE9E70C6ACD068",0,null,"2014Y0005",-1,{"$nulls":75},"施工结束。","45B28A8980000021D5A75D5DAF1B946B"]
["2857FD535B7E61C49DEA0CF4BBF82F21",0,null,"2014Y0006",-1,152,null,152,{"$nulls":12},35,null,35,{"$nulls":12},152,null,152,{"$nulls":12},35,null,35,{"$nulls":27},"目前农村公路已完成约35公里，完成投资18500万元","45A62941800000214B6E50365A9AF0C1"]
["28AFD5F33142A584F8DD987FB1A5E7BB",0,null,"2014Y0004",-1,{"$nulls":75},"码头水工完成，陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["29364DBD5817792F10589E6E3DC5B9C3",0,null,"2014Y0008",-1,4,null,4,{"$nulls":12},4,null,4,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":27},"已完工通车","46EB7FD2000000217E9FB8B298777A5F"]
["294226B37A1AD56391C172BA8788A090",0,null,"2014Y0007",-1,8,147,8,273695,273695,273695,{"$nulls":3},4,11,{"$nulls":3},6498,null,77,null,14230,0,0,{"$nulls":3},0,2,{"$nulls":3},0,null,122,null,273695,273695,189000,{"$nulls":3},4,11,{"$nulls":3},4000,null,52,null,14230,0,0,{"$nulls":3},0,2,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1-4标段已进场，正在开展污水管线、河塘清淤、软基处理、路基填筑、桥涵及水利大坝等施工","464AEA1FC0000021B52E367C631B2D38"]
["2968D12B16A01285780D23B7D8CBC18D",0,null,"2014Y0009",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,807813,751580,568078,0,0,0,10,118,0,0,0,30740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,317393,506370,568078,0,0,0,1,0,0,0,0,5853,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["297E949D6B125670FBA416B089C7022B",0,null,"2014Y0008",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,807813,751580,568078,0,0,0,10,118,0,0,0,22740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,317393,506370,568078,0,0,0,1,0,0,0,0,5053,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["29A7800361120FD486766ECF5430ECBD",0,null,"2014Y0008",-1,{"$nulls":75},"半幅板块处理完成30%，水稳完成25%，沥青下面层完成15%。","46EA9D51A0000021F1A72CD5283EA913"]
["3491C05527B7690B3DBDC3C62FF278B0",0,null,"2014Y0004",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,86,6,19,16,44,0,0,0,0,23,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"公里该项目晶桥段正在进行5.9路基施工，完成涵洞23道，中型桥梁1座；\n白马段10.2公里进行路基施工，桥梁施工单位进场；\n剩余洪蓝至明觉段18公里完成施工图审查","44F92AE780000001F6AE7427CA69104E"]
["34EBF6772ABCE7CB10725F10F28880C8",0,null,"2014Y0005",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,92322,84720,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},3120,2610,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["35192A37B57FF6EB1F375867D0D9021A",0,null,"2014Y0004",-1,{"$nulls":75},"完成农村公路建设23.6公里","45A643D5200000210231D09FB0198FE4"]
["35A7C45031377A961EB7A5603500A727",0,null,"2014Y0009",-1,41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},32,11,78,168380,384460,916110,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},32,11,78,168380,384460,916110,{"$nulls":3},0,{"$nulls":21},"459779F8800000211228699830C698E7"]
["35ED7CDADC79056CCB306E51A66E8EB3",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量98%,附属设施完成98%，绿化工程完成100%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["37389C9E5B31515541D042D58364E7AA",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体完工，陆域施工基本完成。","44F92AE8800000C1B072D9F00825DD28"]
["377648DD2DD4A06CBB2CB172C9F9B669",0,null,"2014Y0010",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,86,6,19,16,44,0,0,0,0,23,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段基本完成路面水稳摊铺；进行沥青试铺段200米\n白马段10.2公里进行路基施工，桥梁正在施工；\n剩余洪蓝至明觉段18公里正在进行清表工作","44F92AE780000001F6AE7427CA69104E"]
["378839D95A77FF479B27A70D19B97836",0,null,"2014Y0010",-1,{"$nulls":75},"快车道施工已完毕。","452C38DA40000161563DFD045D6A3673"]
["384FE24AE4C45134EAE8D30BA4AF7173",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["386BAB221824672C338F8C51040525DB",0,null,"2014Y0010",-1,41,358,41,1222845,1080650,2222151,2,100,100,17,187,0,0,0,58568,41,358,41,1222845,1080650,2222151,2,100,100,17,187,{"$nulls":3},58568,39,13,30,141150,197200,1555607,1,20,0,10,155,0,0,0,18566,39,13,30,141150,197200,1555607,1,20,0,10,155,{"$nulls":3},18566,{"$nulls":15},"形象进度;全线工程基本完成","464ADF4B400000012FF9943B4A23B34E"]
["38805264FA55772F22FCFC92F958F81F",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成项目前期审批手续,完成部分征地拆迁,完成部分土方开挖","44F92AE9000000A114EC34ECCE42A6E8"]
["389934BA9C3FE29B3B6A7AC4DEB1ED21",0,null,"2014Y0002",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["39737622DEC66B58E113ADAF9E61BB56",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，征地拆迁已基本结束，场地平整、 临设、水电已到位，工程已开工建设。","44F92AE800000121D51AC7AB782D4663"]
["398BEC1A0CD710ECE54ED0AEA77D7E72",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场、辅助设施建设及设备安装","44F92AE8C00000C150E871A6EE092CCD"]
["39C2CEDFA93779289D10353072FBB293",0,null,"2014Y0008",-1,44,417,44,1357190,2046965,2063198,4,100,100,6,189,0,0,0,19712,44,417,36,1357190,2046965,1939406,4,100,100,6,189,{"$nulls":3},18726,38,22,38,302615,810646,1819624,1,25,25,2,1,{"$nulls":3},10392,38,22,30,302615,810646,1695832,1,25,25,2,1,{"$nulls":3},9406,{"$nulls":15},"形象进度：G328以北段38.42km:宁通至大仪主体工程基本完成，正在完善交安设施、绿化等附属工程","464AE306E00000210AA87B4400911FFD"]
["3A338123C949C153A653FD09A3038906",0,null,"2014Y0007",-1,1,3,1,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程量100%。本项目于2014年6月份已经建成完工。","44F92AE9600000E1EE7939B9B1929372"]
["3ABDE2A3B320B8DD550674A1696B4E58",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["3ACD266E6751D301ABC6BE792EA73623",0,null,"2014Y0010",-1,{"$nulls":75},"水工主体基本完工","46D1249420000001088D6938CA880F4D"]
["3BCF012C4A7AFFC55550309AA4B31918",0,null,"2014Y0005",-1,25,190,25,0,0,0,8,null,null,10,73,0,0,0,22233,0,170,0,0,0,0,0,50,90,9,72,0,0,0,0,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,null,170,{"$nulls":7},9,{"$nulls":21},"458887AF00000021883DEACA51071D92"]
["3BE2528B0B43F173432C538DC6B0BBDF",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成路基土石方工程50万方，完成征地拆迁工作1800万","44F92AE9A0000001A6C4B4A0FE608B65"]
["3C0875274325E8AB9220D858EA6408E3",0,null,"2014Y0007",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,62,7,201700,326000,251500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,3,null,14000,23000,18000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["3C3FF3C206140A26B53218167F6540F3",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["3C446FD957B785E4D9BD09B94CA648C7",0,null,"2014Y0003",-1,0,2,0,4595,4137,0,0,0,0,0,0,0,0,0,0,0,1,0,3906,3516,0,0,0,85,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,1,0,3906,3516,0,0,0,85,0,0,0,0,0,0,{"$nulls":15},"截止2014年2月  土石方开挖了1.7万方，已完成总工程量的85%；底基层完成了3906平方米，已完成工程量的85%;基层完成了3516平方米，已完成工程量的85%","44F92AE9600000E1EE7939B9B1929372"]
["3DBC989514AFA3D29C41C28F050112E4",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场及辅助设施建设。","44F92AE8C00000C150E871A6EE092CCD"]
["3E5CA8B93FF965F37CC7DFA03610FA44",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["3EC78481A15A08D79159F8CC2924736F",0,null,"2014Y0010",-1,{"$nulls":75},"板块处理完成60%，水稳完成50%，沥青下面层完成30%，桥梁工程完成40%。","46EA9D51A0000021F1A72CD5283EA913"]
["3F20DF7D6AB8D4ECB22D9200F47B8112",0,null,"2014Y0008",-1,{"$nulls":75},"（1）特殊路基处理:基本完成湿喷桩及管桩的施工。\n（2）路基：土石方填筑193.814万方，占总量的67.24%。\n（3）小型结构物：累计完成小构65道，占总量的95.59%。\n（4）桥梁工程：钻孔灌注桩完成4964根，占总量的95.04%；桥梁上部预制砼完成2229片，安装了1863片，占总量的37.77%。","44F92AE7400000C18C5FA6F58B9A0813"]
["3F3D1E5A49088B8E97457824E2FD1E9C",0,null,"2014Y0009",-1,{"$nulls":75},"目前，正在进行路基施工。","4583086800000021610D57307F655C40"]
["3F55D106C05B9FC2FB19B9D072143352",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，工程已开工建设，目前正在进行口岸大楼、联检楼、保税仓库、件杂货仓库、集装箱拆装库等基础施工。码头水工下部结构已开工建设。目前正在进行基坑开挖及后方回填。","44F92AE800000121D51AC7AB782D4663"]
["3FC282E2EDEE01A23D1C049BA464F62F",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"铁路专用线施工、装卸设备购置等.","452C38D9200000A160383FB696401BD8"]
["3FF67FC947ECDE5EFDAA5051B5478FC9",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头工程和疏港航道完成100%；北侧港区排水工程、用电工程和调度楼等附属设施完成100%，码头前沿道路和堆场完成85%。","44F92AE740000061422D7CBDB598F0A4"]
["407E1B43FAD2E105BDCADA7F19665A9B",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已基本完成，征地拆迁已基本结束，施工单位已进场。","44F92AE800000121D51AC7AB782D4663"]
["40A816913F4E83FC5FD8E5446202DE3B",0,null,"2014Y0010",-1,{"$nulls":75},"项目完成前期报批工作，正式开工。","495AB173C0000021BD1078AE8F558A41"]
["40B0AA3C6685273FBBEA4ACDB93F6455",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"16个泊位港池码头、2.24公里疏港航道基本建成；已订购部分固定吊、龙门吊等设备，完成2万米水泥搅拌桩软基处理并完成一纵、一横道路，完成200亩场地平整。完成下水、污水、管道铺设、给排水工程，完成供电、照明管道铺设以及正式用电工程,完成前方调度楼主体工程、前沿道路堆场工程。","44F92AE740000061422D7CBDB598F0A4"]
["4117FC38E002F9C6422A31ADF5346851",0,null,"2014Y0009",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["418A837EC7FDEAAEA9200948C6C8B45B",0,null,"2014Y0006",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["41D194756BEFDC0422742A5A97BF1734",0,null,"2014Y0002",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,14220720,0,0,0,0,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,15070,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["41DBBAC9BFD8B69E3FF68930F589EC1A",0,null,"2014Y0004",-1,41,14,120,1436401,null,1305854,{"$nulls":3},12,{"$nulls":5},21,8,19,30258,null,114623,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,null,1305854,{"$nulls":3},12,{"$nulls":5},21,8,19,30258,null,114623,{"$nulls":3},0,{"$nulls":21},"45977B6F60000021EC6F56E8E1B46524"]
["42669696BC62E33E6B90D967D82D56F3",0,null,"2014Y0004",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：未开工。二、存在问题：地方政府征地拆迁工作没有实质性开展，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["42F24596E0FD4FA4B39AC1CF06BF7DF0",0,null,"2014Y0010",-1,{"$nulls":75},"完成路基处理95%、路面底基层90%、基层80%。","4756E0D780000021BD984AD195D60C8A"]
["43043282425C150285AF3FFEDEF459CE",0,null,"2014Y0009",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,180,null,453000,340000,{"$nulls":5},62,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},180,null,453000,340000,{"$nulls":5},61,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["43807875DD521162C259067306C812D6",0,null,"2014Y0010",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":16},"464AE565800000215C9C09C8A0BE8932"]
["43B3DCB4129A20C5E4CB3A28B4F4B13B",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["44780ED89C66C1DD600124684A5DAC4A",0,null,"2014Y0008",-1,0,270,0,0,0,0,0,0,0,0,68,0,0,0,0,0,233,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,233,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成江宁河至锦文路段路基施工50%，完成桥梁工程施工55%。","44F92AE9A0000001A6C4B4A0FE608B65"]
["44AA019C1E4B6AC8FEC534BC271894E1",0,null,"2014Y0006",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["44EFA5E22366DEF91C2952B106B3DCE4",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE7A000006159C90A7558BC3A9C"]
["45C747CD9561021B033F97307D1834CB",0,null,"2014Y0009",-1,{"$nulls":75},"剩余部分待建工程，其他已全部交工验收。","45B26F0B8000002123F9B996453503FA"]
["45D9075710E39D56832C1E2D1DF22C4F",0,null,"2014Y0005",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["45F14C7264F87D2C887051ABF1678BFA",0,null,"2014Y0009",-1,{"$nulls":75},"完成部分征地拆迁工作。","48A6EC29E000000142F6B2638633E8C1"]
["45F230D96EDC2BD6786D2BE18F53E611",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["4650DF8D5E9CE5E9009EC95CFB64A68A",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已基本完成，征地拆迁已基本结束，施工单位已进场。","452C38DDE00000411468534B18F06C9C"]
["466977D0391EF3996268A8C872A1EF2F",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["467BB89BD8A537F8B0C856E7CB872452",0,null,"2014Y0007",-1,{"$nulls":75},"目前，主体建成。","4583097620000021C29C88DEA1D39A75"]
["46A40EF3CF6639CE38CEFAD6392924F2",0,null,"2014Y0008",-1,101,65,101,692100,671900,651700,{"$nulls":10},39,10,61440,59520,57600,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":10},39,10,61440,59520,57600,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["46D565D6BECE45A861CFD2EDEBC6A8DF",0,null,"2014Y0004",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["478249804A1301D0A113C4C1F9A8AFE3",0,null,"2014Y0010",-1,{"$nulls":75},"目前，桥梁建成。","45830129E0000021F3EEA0D7E47483E6"]
["6FFF2F3AE05EB82AAEB328112F5F09F1",0,null,"2014Y0010",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：目前江宁区政府启动了征地拆迁工作，已完成土地丈量、房屋拆迁调查工作，正在进行杆管线迁移调查。指挥部配合开展红线放样和路田分家工作，施工单位也开展了驻地建设和测量放样复核等施工前准备工作，待江宁区政府提供建设用地后随时开展施工工作。二、存在问题：地方政府征地拆迁工作进展缓慢，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["7099D4FC4656686972D90161C3C33AE2",0,null,"2014Y0009",-1,{"$nulls":75},"目前，正在进行明远路至京杭运河大桥段路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["711A9D02394F8C1474B3C447EEA50D27",0,null,"2014Y0010",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["7131548367FEE9A21D005FA319BDE862",0,null,"2014Y0007",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,85,null,6000000,580000,2400000,null,45,65,17,46,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,25,{"$nulls":5},25,25,9,14,{"$nulls":20},"4597C2C660000021C7BD96E4F6D02E66"]
["7221DB4DAB7D8FBFDEBFE6F45B30CA09",0,null,"2014Y0008",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,86,6,19,16,44,0,0,0,0,23,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段完成路基涵洞施工，正在进行路面施工；\n白马段10.2公里进行路基施工，桥梁正在施工；\n剩余洪蓝至明觉段18公里正在进行征地拆迁工作,招投标工作（本月停工）","44F92AE780000001F6AE7427CA69104E"]
["7266E61298F0F3EE388071EE2CF2910F",0,null,"2014Y0009",-1,{"$nulls":75},"港池疏浚完工，水工主体开始施工。","46D123DB80000021DDAA88D0A2421B9E"]
["72958E9C93184BA33A069832A7A2C34D",0,null,"2014Y0008",-1,{"$nulls":75},"全幅板块处理完成，水稳完成95%，沥青下面层完成90%，沥青上面层完成50%","46EA9A9840000021E67762482E18105E"]
["7298F6A35CA16C1E16E2CBAFDC392900",0,null,"2014Y0004",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,62,7,201700,326000,251500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,3,null,14000,23000,18000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["72C6A0917FFFED0122FE9542089D7BDC",0,null,"2014Y0008",-1,{"$nulls":75},"目前，桥梁已建成。","47678A76C0000021CA6C39AAC7090030"]
["739CA284586732A44D4619A0CEB25E55",0,null,"2014Y0005",-1,{"$nulls":75},"徐圩港区防波堤东斜坡堤进尺1220米，累计折合进尺4.22公里","452C38DA800000A19C9699F0088370B9"]
["73B1BF63DD48019987558FC7AA87C884",0,null,"2014Y0009",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["7409AB012A3B1F24E141435F252CFA11",0,null,"2014Y0006",-1,{"$nulls":75},"目前，正在进行征地拆迁工作。","4583086800000021610D57307F655C40"]
["7463517E580D31A3CCE4F9BB50BEEA86",0,null,"2014Y0008",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,22,118,16,968353,460868,460868,20,88,93,26,19,1,0,465,14945,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,2,35,0,250000,18000,18000,19,72,90,1,2,1,0,150,1450,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["752D2442A401441724600B4B04DE241D",0,null,"2014Y0008",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["7543A01014F52DCCF6C758A67E5DFF7B",0,null,"2014Y0009",-1,{"$nulls":75},"目前，已建成先导段2公里，剩余段正在进行路基施工。","4582F984A00000210B371656660E7377"]
["75B0B086E99FB4BB303891D2781334F7",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"站场西侧剩余区域爆破拆迁、场地工程基本完成。","452C38D9200000A160383FB696401BD8"]
["75D25C6258B2E3388096AA5693F0F905",0,null,"2014Y0009",-1,{"$nulls":75},"完成码头水工部分，房建工程完成基础工程，完成场内道路路基处理，基本完成桥梁上部结构施工。","48169DD9600000213A760AD1A7936625"]
["762AA38E78F2334F38FA88C5549B488B",0,null,"2014Y0003",-1,8,51,8,211000,184000,176000,0,0,0,3,47,0,0,0,15413,0,18,0,0,0,0,0,0,0,1,17,0,0,0,0,0,51,0,0,0,0,0,0,0,3,47,0,0,0,0,0,18,0,0,0,0,0,0,0,1,17,0,0,0,0,{"$nulls":16},"452C38D6600000415991C5B8B7842E8C"]
["769029A2261F0BAD3263EBDDF7DC0EFE",0,null,"2014Y0010",-1,{"$nulls":75},"目前，已建成先导段2公里，剩余段路基施工已完成。","4582F984A00000210B371656660E7377"]
["76C20B16D04BC2FBC9F22235CD5269C8",0,null,"2014Y0010",-1,{"$nulls":75},"西防波堤工程年内进尺2500米，占年计划2200米的114%，累计进尺2500米，占总长9562米的26%。","46D12756A00000212A79E7CE74664FD9"]
["777226AB36DC47AB030B314598C23C52",0,null,"2014Y0010",-1,{"$nulls":9},6,{"$nulls":14},0,{"$nulls":14},6,{"$nulls":14},0,{"$nulls":20},"施工单位进场，进行下部结构施工","45A62A6EC00000210FD9D03217C261AE"]
["778DE1492C720718B75D9F5C1DA5F786",0,null,"2014Y0008",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"完成天元路至秣陵段上面层路面施工，80%绿化施工。","45A64FE000000021EF20F17B8FB2A64B"]
["77A03381F9BD602BC0FDAA9B0BF89FF8",0,null,"2014Y0009",-1,152,null,152,{"$nulls":12},35,null,35,{"$nulls":12},152,null,152,{"$nulls":12},35,null,35,{"$nulls":27},"目前农村公路已完成约35公里，完成投资21500万元","45A62941800000214B6E50365A9AF0C1"]
["77C396F7E254941FA2CE7FAE7F0C3A1D",0,null,"2014Y0007",-1,{"$nulls":75},"招投标已完成，施工单位已进场。","452C38DA40000161563DFD045D6A3673"]
["77E74575BACDB8352E4D2F5C3CB65BCA",0,null,"2014Y0009",-1,{"$nulls":75},"目前，桥梁及接线道路已建成。","4767883F000000016F0AF6F671358D27"]
["78101BF15AE187D46B412FA8359EE07E",0,null,"2014Y0005",-1,{"$nulls":9},8,{"$nulls":14},4,{"$nulls":14},8,{"$nulls":14},4,{"$nulls":21},"45A622C860000021C54A12ED93C79943"]
["78DADB04B518F652CBA917CD543AC802",0,null,"2014Y0004",-1,{"$nulls":75},"目前，完成主桥承台和挂篮现浇梁、部分立柱墩台盖梁、引桥梁板的预制和安装。","45830129E0000021F3EEA0D7E47483E6"]
["78F11E63ABF27E9EA84CDEBF88AB7251",0,null,"2014Y0007",-1,{"$nulls":75},"完成农村公路建设53.7公里","45A643D5200000210231D09FB0198FE4"]
["7A502D1866E726986FE316682A0D42C6",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["7A79C6DB2027C41497491B24E961731E",0,null,"2014Y0009",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,86,6,19,16,44,0,0,0,0,23,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段基本完成路面水稳摊铺；\n白马段10.2公里进行路基施工，桥梁正在施工；\n剩余洪蓝至明觉段18公里正在进行征地拆迁工作,完成招投标工作，施工单位准备进场","44F92AE780000001F6AE7427CA69104E"]
["7ADBFB61E33AC38B5CC65B1ACC467DE3",0,null,"2014Y0010",-1,{"$nulls":75},"完成招标工作，施工单位进场。","494F7BCEC000002123A1FDE2C282EA21"]
["7B2DE613D3D4601752B3CC1BCF0E2CE2",0,null,"2014Y0010",-1,{"$nulls":75},"目前，桥梁及接线道路已建成。","4767883F000000016F0AF6F671358D27"]
["7B3CE13A33E8CC44DD6387AEB3530821",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，工程已开工建设，目前正在进行口岸大楼、联检楼、保税仓库、件杂货仓库、集装箱拆装库等基础施工。码头水工下部结构已开工建设","44F92AE800000121D51AC7AB782D4663"]
["7B4351B08720B728DE15C31D89417053",0,null,"2014Y0005",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["7BCA8D8F6CDE04011CBBDA035436BFD6",0,null,"2014Y0007",-1,{"$nulls":75},"目前，征地拆迁工作和项目部建设已完成。","4583086800000021610D57307F655C40"]
["7C1CE9CFD42D00EF93F8D31AB753361B",0,null,"2014Y0010",-1,{"$nulls":75},"完成征地拆迁、场地平整、围墙砌筑。","44F92AE7C000008151CBB288EBA76DE4"]
["7C5EEADAEE801CC230CA4305F028A738",0,null,"2014Y0010",-1,{"$nulls":75},"工程暂停施工","46D11F4F40000021C374A969A3743C9A"]
["7C6D75A150CF5C49E8F5E9E8658297DF",0,null,"2014Y0009",-1,4,null,4,{"$nulls":12},4,null,4,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":27},"已完工通车","46EB7FD2000000217E9FB8B298777A5F"]
["7C82EF2A158410563AFE6E4131FDD8B6",0,null,"2014Y0002",-1,16,121,0,287625,280590,834000,0,0,0,7,91,0,0,0,0,0,104,0,225630,312030,257175,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,2,0,2480,36310,73190,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本期完成水稳4170平方、下面层沥青3.3万平方。\n本月完成投资额500万元，本年累计完成投资1500万元，累计完成投资43500万元（其中征地拆迁18000万元,其他费用1000万元）。","44F92AE8800000016600EFB6FA6DB838"]
["7C907A615E01F32267DD8540F9A8F77F",0,null,"2014Y0006",-1,8,147,8,273695,273694,273694,{"$nulls":3},4,11,{"$nulls":3},6498,null,77,null,14230,0,0,{"$nulls":3},0,2,{"$nulls":3},0,null,122,null,273695,273694,189000,{"$nulls":3},4,11,{"$nulls":3},4000,null,52,null,14230,0,0,{"$nulls":3},0,2,{"$nulls":20},"464AEA1FC0000021B52E367C631B2D38"]
["7D8153A18BE7276364087BFEC50B8A26",0,null,"2014Y0008",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["7DA1C082C024FB1ACD10C17EE5439B03",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已建成21公里，其余段正进行招投标工作。","452C38DA80000041BB1AF46EF3FAECC2"]
["7DE0D384B72BA7B697974A0FC7B8B635",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头基本完工，正在进行管架和管道施工。","44F92AE9C00000414B088C76E8FF94CE"]
["7E5C0DE1EB6344A9D486C6EB246B0165",0,null,"2014Y0010",-1,{"$nulls":75},"桥梁工程完成96%，接线路基完成81%。","494F759FA0000021B650A21A5A0C6724"]
["7E6FD50E126A8EF783BCCCADA3865DF0",0,null,"2014Y0004",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,92322,null,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},3120,{"$nulls":26},"452C38D940000021B2C6170F6C9D6CB6"]
["7E887A6C16491989241170AF7FEDB13E",0,null,"2014Y0008",-1,{"$nulls":75},"徐圩港区防波堤东斜坡堤进尺1220米，累计折合进尺4.22公里","452C38DA800000A19C9699F0088370B9"]
["7EB9F651AA342544BAF97AB3B51A5004",0,null,"2014Y0008",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,231375,189942,258646,0,75,100,3,82,0,0,0,29000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,189942,258646,0,40,55,0,0,0,0,0,29000,{"$nulls":15}," 一、形象进度：目前正在进行路面沥青面层、桥梁、绿化、交安、山体防护治理施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层189942平方米（80%）、面层258646平方米（60%）；桥涵完成投资2315万元（71%）；防护工程2.9万方（79%）；绿化工程完成769万元（54.8%）；交通安全设施完成82万元（13.5%）；山体防护治理工程完成66万元（15%）。二、存在问题：无。（备注：根据市政府《2014年南京青奥会环境保障临时管控方案》（宁政发[2014]104号）及南京市交通运输局、南京市公路处“青奥会期间停止工地施工作业”《告知书》要求，溧白路各标段于2014年8月1日起全面停工。 ） ","44F92AE80000000125D8496C7290DDFC"]
["7EBB64E3FC4EA606D972282D5F451A30",0,null,"2014Y0004",-1,{"$nulls":75},"码头上部管线安装。","45B28726E0000021457D777E03877DDB"]
["7EE16C40CEDAB7F5AC8AAFD9606B26BF",0,null,"2014Y0008",-1,43,395,43,1269900,998375,1031050,1,100,100,19,179,0,0,0,10000,43,395,29,1269900,998375,866082,1,100,100,19,179,{"$nulls":3},8750,21,10,14,332520,164353,240080,1,17,0,2,5,0,0,0,1795,21,10,0,332520,164353,75112,1,17,0,2,5,{"$nulls":3},545,{"$nulls":15},"形象进度：先导段11.5km已于12年11月建成通车；北澄子河大桥至车樊线段12km于13年10月建成通车；车樊线以南段5.2km基本建成，已完成交工验收质量检测；马横线以北段14.2km底基层及桥梁基本完成，基层完成75%，沥青下面层已完成试验段施工。","464AE174E0000021897F83B2DBD33160"]
["7F18036BAC6487DC2C833AB2857B3502",0,null,"2014Y0005",-1,{"$nulls":75},"目前，东西接线路基已完成。","458307CAE00000414A3628960FD10AB2"]
["7FAF63D7C57014CF778CB4EBC6641DC5",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已基本完成，征地拆迁已基本结束，施工单位已进场。","44F92AE800000121D51AC7AB782D4663"]
["7FB53D05F5F52FB80A435FF1B1D9270E",0,null,"2014Y0008",-1,{"$nulls":75},"目前，征地拆迁工作和项目部建设已完成。","4583086800000021610D57307F655C40"]
["7FC5263E91D45C45DEDDE18C5D015C36",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"I标段24万平方米停车场施工；办公楼内装基本完成。","452C38D960000061A773E74DF5A30C52"]
["7FE3E87EBCC4407B35007636E1AD035E",0,null,"2014Y0004",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,1522500,0,0,0,0,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,115500,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["8034F34A0FCA67E5F93C250E990536AC",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["806BF2686239ED82D19A44FBA4B67E20",0,null,"2014Y0003",-1,0,250,0,996540,1006283,438383,0,0,0,0,0,0,525,525,17699,0,169,0,638600,661696,419017,0,52,99,0,0,0,525,525,16084,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,75,0,212905,238758,176037,0,52,99,0,0,0,525,525,8167,{"$nulls":15},"形象进度：土方开挖82943立方，占总量的73.12%；路基填筑29210立方,占总量的59.72%,；路面底基层10%灰土6500立方，占总量的87.1%,；完成底基层46881平方米，占总量的65.96%；完成路面沥青摊铺12000平方米,占总量的23.85%","44F92AE9400000C1F580982CCF7AEF56"]
["80A83A0F4CC1D4E756C806E454984BEF",0,null,"2014Y0005",-1,{"$nulls":15},0,0,0,0,null,0,{"$nulls":55},"45977B6F60000021EC6F56E8E1B46524"]
["816116115FF60FBEC42EB2E4CE630B14",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["818542531ACCB109A8FBCDA5C0F4D8F4",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已建成21公里，其余段正进行招投标工作。","452C38DA80000041BB1AF46EF3FAECC2"]
["47F56569DB0A69050DA0A4447B3180DB",0,null,"2014Y0009",-1,14,330000,14,120000,120000,120000,0,0,0,0,6,0,0,0,null,14,150000,7,60000,60000,0,0,0,0,0,6,0,0,0,null,14,180000,14,120000,120000,120000,0,0,0,0,0,0,0,0,null,7,0,7,60000,60000,0,0,0,0,0,0,0,0,0,{"$nulls":17},"46B8AAA3A00000217140A795E7A1AE32"]
["4881AA0DE58AD771210C7B621C2F21B4",0,null,"2014Y0007",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["4A13C358E2F87BA703DF9D3414FB0E84",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"自开工累计完成单洞掘进4210米；二衬3358米；墟沟互通自开工累计完成粉喷桩254352米、灌注桩340根、PTC管桩44800米，完成现浇支架搭设及预压34联，完成路基填筑98393立方。","44F92AE720000041FD47DFFCE454F006"]
["4A5D6A5688022ED0986CCB6D1C14B79C",0,null,"2014Y0009",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["4AE54475B523068E4032F014BD687711",0,null,"2014Y0008",-1,{"$nulls":75},"目前，完成先导段及二期路基路面、结构物及附属设施工程。","4582F984A00000210B371656660E7377"]
["4B4354B20F61FE46BF1732B99E33354C",0,null,"2014Y0008",-1,{"$nulls":75},"新海新区段已建成通车；马涧通道边坡治理已开工建设；云台互通段基本完成临建施工；徐圩新区段已累计完成10公里，路基桥涵基本完成。","44F92AE7E000004126A44C796491035A"]
["4B63A1D1F69CE5BA6F91F98F71585D68",0,null,"2014Y0004",-1,{"$nulls":75},"码头基本完工。","45B26F0B8000002123F9B996453503FA"]
["4B7363B0697654966F3C8EF33A1B0717",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已建成21公里，其余段正进行招投标工作。","452C38DA80000041BB1AF46EF3FAECC2"]
["4C3C136561451235084AC9FF23523EB3",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已累计建成纵五路至南复堆河段及纵一路段22.8公里，剩余4.7公里因与连云港港口连接线工程线位较近，正在进行路线方案研究。","452C38DA80000041BB1AF46EF3FAECC2"]
["4C98C7D61DC9AC9EA3C836382D2A9432",0,null,"2014Y0008",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,139132,798812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,32590,63000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成一期工程（马群至双龙街）13.7公里主线改造、万家楼互通马群换乘中心匝道、钟学北路互通、石杨路互通、双麒路互通建设；二期工程（花神庙至刘村）7.1公里主线改造、凤翔山庄及风翔村景观墙建设、五百户村及双龙街声屏障建设、铁心桥至油坊桥段2.5公里青奥景观带建设、铁心桥规四路至贾东地块1.8公里辅道建设、友谊路桥及黄河路桥建设、黄河路互通建设，完成马群至天保桥段绿色通道建设，完成全线监控设施工程建设，完成绕城公路沿线（环陵路至江山大街）景观照明工程建设。累计土石方160.0万方，路面底基层16.5万平米，基层13.9万平米，面层79.9万平米。本月完成投资2000万元，本年累计完成13000万元，累计完成178090万元。              \n二、存在问题：1、目前工程建设基本是在国有储备土地上实施，征地拆迁工作除雨花区段外，其它段落尚未实质性进展。\n    ","44F92AE8400000A1F8CD4F6E58802DB5"]
["4CA6346725890DAF62C5A721818ED694",0,null,"2014Y0008",-1,{"$nulls":75},"目前，桥梁及接线道路已建成。","4767883F000000016F0AF6F671358D27"]
["4DBCA0641F4309FBB911830278972016",0,null,"2014Y0005",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：未开工。二、存在问题：地方政府征地拆迁工作没有实质性开展，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["4E1207AEC85F1BA506F2B7FFAE0E5EE0",0,null,"2014Y0006",-1,{"$nulls":75},"正进行招标工作，预计7月份全面开工建设。","452C38DA40000161563DFD045D6A3673"]
["4E33518B0D42A60FF455B249E582014E",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["4F29997528C83D0229A884C010263216",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已累计建成纵五路至南复堆河段及纵一路段22.8公里，剩余4.7公里因与连云港港口连接线工程线位较近，正在进行路线方案研究。","452C38DA80000041BB1AF46EF3FAECC2"]
["502C7633BF1850E632D38E270D7530BE",0,null,"2014Y0010",-1,{"$nulls":75},"（1）路基：软土地基处理已完成；土石方填筑244.91万方，占总量（288.33）的84.94%。\n（2）小型结构物：累计完成管涵65道,占总量（68）的95.59%。\n（3）桥梁工程：钻孔灌注桩完成5143根，占总量（5223）的98.47%；桥梁上部预制砼安装完成2732片，占总量（4932）的55.39%。","44F92AE7400000C18C5FA6F58B9A0813"]
["504344F27572543D3D9ECEBE52A95D33",0,null,"2014Y0008",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["5202749352D19FE9FCAB8D46073F5999",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["52380D06926F4ADF6C888F32D4108CA4",0,null,"2014Y0009",-1,{"$nulls":75},"目前，正在进行桩基施工。","45830701A00000018662A81FE3FB2B60"]
["5248F8FD16FC2444BF128A282F99386D",0,null,"2014Y0004",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["52CD18F92C1F33174CF97D1DC986F429",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一期工程交易中心主楼等工程完工。","452C38D960000061A773E74DF5A30C52"]
["53ACB592E125B73AEC305806BA260317",0,null,"2014Y0005",-1,0,3,0,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,0,2,0,4600,4137,8100,0,0,0,1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,2,0,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程俩100%。","44F92AE9600000E1EE7939B9B1929372"]
["53AE083FCCA5479DBAB70929E04E0103",0,null,"2014Y0004",-1,{"$nulls":75},"目前，完成先导段及二期路基路面、结构物及附属设施工程。","4582F984A00000210B371656660E7377"]
["53B145ECD508982F217E74A22EE217D9",0,null,"2014Y0004",-1,{"$nulls":9},9,{"$nulls":14},0,{"$nulls":14},9,{"$nulls":14},0,{"$nulls":20},"雪松桥在建，其余桥梁已完成项目工可报告批复，正在进行施工图设计及招投标工作","45A62A6EC00000210FD9D03217C261AE"]
["53F40DA80D40536664E21458C499AEA0",0,null,"2014Y0005",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":16},96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":31},"464AE565800000215C9C09C8A0BE8932"]
["5498B6FFFD93F060223F7C18ADB8CE26",0,null,"2014Y0007",-1,{"$nulls":75},"徐圩港区防波堤东斜坡堤进尺1220米，累计折合进尺4.22公里","452C38DA800000A19C9699F0088370B9"]
["54BDD3E5D3B525AAB6EB3851C69C76E1",0,null,"2014Y0009",-1,{"$nulls":75},"工程主体完工，铁路工程主体完工；接轨方案审查会于8月15日在上海路局召开。\n","46D11DA8E0000021390F8E6CD9239F6A"]
["54BE775BB8F8FB50C9CB147DB8923F61",0,null,"2014Y0009",-1,{"$nulls":75}," 北幅已完成开挖回填，完成底基层摊铺1.6公里、基层摊铺1.4公里、下面层300米、雨水管线1.3公里。","452C38DA40000161563DFD045D6A3673"]
["553FF6F67E9BC039461F1E8EBB38BF35",0,null,"2014Y0007",-1,{"$nulls":75},"目前，桥梁已建成，正在进行接线部分路基施工。","4767883F000000016F0AF6F671358D27"]
["56205980CF63305149CAB32FA2E928A3",0,null,"2014Y0008",-1,1339141,1127463,18,605466,519452,9333283,2,50,50,6,49,0,{"$nulls":3},1339141,1127463,18,605466,519452,9333283,2,50,50,6,55,0,{"$nulls":3},0,0,0,0,0,1866657,0,0,0,6,0,0,{"$nulls":3},0,0,0,0,0,1866657,0,0,0,6,0,0,{"$nulls":18},"已完工","45A64CBEC0000021EA2875A94CD2711C"]
["56721845EBEEF280738718A433096F86",0,null,"2014Y0009",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,97022,90420,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},7820,8310,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["56BE2D6247B426ECE91FC0AE08B5F649",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"自开工累计完成单洞掘进4210米；二衬3358米；墟沟互通自开工累计完成粉喷桩254352米、灌注桩340根、PTC管桩44800米，完成现浇支架搭设及预压34联，完成路基填筑98393立方。","44F92AE720000041FD47DFFCE454F006"]
["56D7518E6E0E257ADD9451B2687D3C89",0,null,"2014Y0009",-1,{"$nulls":75},"东直立堤工程年内折合进尺60米，占年计划的3%，累计进尺185米，占总长4377米的4%，配套的预制厂已建成投产。","452C38D9600000015B091B22A009EB3A"]
["5745826CAC9BD332BF3DFA30AF055E84",0,null,"2014Y0002",-1,0,250,0,996540,1006283,438383,0,0,0,0,0,0,525,525,17699,0,156,0,618050,581353,337549,0,52,99,0,0,0,525,525,15337,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,62,0,192355,158415,94569,0,52,99,0,0,0,525,525,7420,{"$nulls":15},"形象进度：土石方累计完成156万立方米，占总量：62%；路面底基层累计完成618050平方米，占总量62%，沥青面层累计完成337549平方米，占总量77%；基层累计完成581353平方米，占总量60%","44F92AE9400000C1F580982CCF7AEF56"]
["5804560D4DDA8B78E335D87803015338",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成16个泊位港池码头和2.24公里疏港航道，完成2万米水泥搅拌桩软基处理、一纵一横道路和200亩场地平整工作。已订购部分固定吊、龙门吊等设备，完成管道铺设、给排水工程、正式用电工程,实施轨道梁、后方堆场等工程。","44F92AE740000061422D7CBDB598F0A4"]
["58A0E52CA9C80C1663C85EF3A964A55F",0,null,"2014Y0007",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,160,440,22087,0,6,0,0,0,0,0,0,0,0,0,0,0,0,2425,{"$nulls":15},"形象进度：一标本期完成产值627.8万元，累计完成产值3.7亿元；二标本期完成产值506.02万元，累计完成产值2.29亿元；支线标本期完成 141万元，累计完成产值3167.72万元。存在问题：JTHD-1标\nAK5+000-AK5+200道路宽度不够。\nJTHD-2标\nFK4+780-FK5+040徐明刚苗木。\n\n","4592B501E000002123E927A043947D89"]
["58ADA1F3D357607ACA768EF312168CD4",0,null,"2014Y0006",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,160,440,22087,0,6,0,0,0,0,0,0,0,0,0,0,0,0,2425,{"$nulls":15},"形象进度：一标本期完成产值1508.86万元，累计完成产值3.65亿元；二标本期完成产值894.53万元，累计完成产值2.1454亿元；支线标本期完成 397.76万元，累计完成产值3026.72万元。存在问题：JTHD-1标\nAK5+000-AK5+200道路宽度不够。\nJTHD-2标\nFK4+780-FK5+040徐明刚苗木。\n\n","4592B501E000002123E927A043947D89"]
["58E710AFE5885F33ADEA06447465294B",0,null,"2014Y0009",-1,{"$nulls":75},"目前，桥梁建成。","45830129E0000021F3EEA0D7E47483E6"]
["5964C9D053047A690A54E99765B4784A",0,null,"2014Y0007",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,624,10,972000,1015500,2150300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,20,0,12000,980400,144900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"路基：完成土石方开挖354万方（95.4%）,土石方填筑272.8万方（95.9%）;路面：水稳碎石基层101.55万平方（89.7%)，12%灰土97.25万平方（85.9%)，沥青215万平方(89.9%);桥梁：305800万元（77.7%）；交安1500万元（51%）；绿化4100万元（77.2%）。","44F92AE840000101423CCFA36BCE2089"]
["598E4960CFFD935DAD86503D5B97DD0F",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，工程已开工建设，目前正在进行口岸大楼、联检楼、保税仓库、件杂货仓库、集装箱拆装库等基础施工。码头水工下部结构已开工建设","44F92AE800000121D51AC7AB782D4663"]
["59AB980D3BEAFA756B15D17D66AAB60F",0,null,"2014Y0008",-1,{"$nulls":75},"沪宁高速昆山高新区互通连接线（中华园路）新建工程加快路基施工及桥梁工程施工","476C4BC84000002168C8EFB59D88315C"]
["59CB5BD0228FEABA4C078C61628823D8",0,null,"2014Y0006",-1,{"$nulls":75},"（1）特殊路基处理：已全部完成湿喷桩，共计55.43万延米；完成PC管桩70万延米，占总量（74.35）的94%\n（2）路基：土石方填筑95.77万方，占总量（313.46）的30.55%。\n（3）小型结构物：累计完成管涵31道,占总量（47）的65.96%，累计完成通道11道,占总量（16）的68.75%，累计完成箱涵8道,占总量（10）的80%.\n（4）桥梁工程：钻孔灌注桩完成4588根，占总量（5223）的87.84%；桥梁上部预制砼完成1368片，占总量（4932）的30.29%。\n","44F92AE7400000C18C5FA6F58B9A0813"]
["59E8376153F94945DE0533479FF9B2EE",0,null,"2014Y0010",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["59F072D8A48FF2581B294A78A7D20E3E",0,null,"2014Y0006",-1,{"$nulls":75},"施工结束。","45B28726E0000021457D777E03877DDB"]
["5A11004F1C90696F1BEA221FED3AD4E5",0,null,"2014Y0010",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,176,null,277820,256403,null,null,100,100,null,43,{"$nulls":3},3240,null,70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,60,null,264820,243403,null,null,70,{"$nulls":6},3240,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["5A1B22786BAC8FFA56DCF60286F733F5",0,null,"2014Y0007",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["5AA0087CF1EFFE2D1ECE74C00E56B72F",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"银珠路至242省道段现在正在完善前期手续和征地工作；南段已进场施工，完成部分路基、桥涵。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["5ABC2BA33D72551D449C1CE15E3814C4",0,null,"2014Y0005",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段正在进行征地拆迁工作。","45825CCB00000021AE879AE5EFB9B065"]
["5AD11A905AB5321D20457EE561E15DED",0,null,"2014Y0006",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,5,null,0,12600,0,{"$nulls":3},0,37,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,5,null,0,12600,0,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["5B348CE9E4DEFADC26EDDDE1230DCE77",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["5B86C0FCF8BA95749B4A80888F2B7784",0,null,"2014Y0006",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["5C389E4A44D3A1553680AD60FFE5B409",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"I标段24万平方米软基处理完工，郑州实施回填工程，办公楼内外装修。","452C38D960000061A773E74DF5A30C52"]
["5DB7F466425E0C89C010A9D9B3A16324",0,null,"2014Y0008",-1,41,358,41,1222845,1080650,2222151,2,100,100,17,187,0,0,0,58568,41,358,11,1222845,1080650,1999936,2,100,100,17,187,{"$nulls":3},51539,39,13,30,141150,197200,1555607,1,20,0,10,155,0,0,0,18566,39,13,0,141150,197200,1333392,1,20,0,10,155,{"$nulls":3},11537,{"$nulls":15},"形象进度：临城试验段3.105km已于09年建成通车；二期工程7.88km（包括宝射河大桥）于12年8月完成交工验收；三期工程30.4km基层基本完成，沥青面层完成42%。                                                                                               ","464ADF4B400000012FF9943B4A23B34E"]
["5E19B0BA877EABC0DC14C697788E0C81",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"开展征地拆迁工作，准备开展项目招投标工作。","44F92AE7C000002175F300290A52D82C"]
["5EEA156122C93E7825B7A93BDE2772D8",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["5F3A45AD3DB2E77277A1C4CEBB46D9BC",0,null,"2014Y0003",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"公里该项目晶桥段正在进行5.9路基施工，完成涵洞23道，中型桥梁1座；\n白马段10.2公里进行路基清表工作；\n剩余洪蓝至明觉段18公里设计单位正在进行初步设计工作","44F92AE780000001F6AE7427CA69104E"]
["5FB4A62C1802D42F8937AEAA75A5A93D",0,null,"2014Y0005",-1,{"$nulls":75},"施工结束。","45B28726E0000021457D777E03877DDB"]
["5FFFF04D35F627497E8C68A8F9B47D4E",0,null,"2014Y0006",-1,41,358,41,1222845,1080650,2222151,2,100,100,17,187,0,0,0,58568,41,358,11,1222845,1080650,1721447,2,100,100,17,187,{"$nulls":3},45097,39,13,30,141150,197200,1555607,1,20,0,10,155,0,0,0,18566,39,13,0,141150,197200,1054903,1,20,0,10,155,{"$nulls":3},5095,{"$nulls":16},"464ADF4B400000012FF9943B4A23B34E"]
["60648F61C68B429FC7CFA54DA20998FA",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已完成灌注桩600根、平整场地8000平方、安装吊机2台","452C38DDE00000411468534B18F06C9C"]
["60D07830776833CF1E39C654E74FBE1B",0,null,"2014Y0009",-1,{"$nulls":75},"目前已建成。","4583097620000021C29C88DEA1D39A75"]
["610928D243658F02795B0CD9A0EE3B05",0,null,"2014Y0008",-1,25,1,25,30410,53630,108850,{"$nulls":9},13,1,13,30410,38630,68749,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":9},13,1,13,30410,38630,68749,{"$nulls":25},"45977C86A000000145F95B717A76C135"]
["613E7016B326C3757C7AF17597DB7A73",0,null,"2014Y0009",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["61BDC9280E6005A1C2255DF4F97527C7",0,null,"2014Y0007",-1,41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},32,11,78,168380,384460,913051,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},32,11,78,168380,384460,913051,{"$nulls":3},0,{"$nulls":21},"459779F8800000211228699830C698E7"]
["61E97DB9212C35438203D67AED683612",0,null,"2014Y0004",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,1,null,0,0,0,{"$nulls":3},0,0,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,1,null,0,0,0,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["61FE2687B8176C65BF6B88C1F8C8D374",0,null,"2014Y0010",-1,{"$nulls":75},"东斜坡堤工程年内折合进尺2100米，占年计划3000米的70%，累计进尺5300米，占总长7834米的68%。","452C38DA800000A19C9699F0088370B9"]
["62E4E3A208503597833C71DF8E61C532",0,null,"2014Y0004",-1,{"$nulls":75},"目前，路基施工已完成。","4583097620000021C29C88DEA1D39A75"]
["63EA6C5B89F1780E6EB2CF96514C6270",0,null,"2014Y0005",-1,43,374,43,253980,998375,1031050,1,100,100,19,179,0,0,0,12300,null,299,null,203000,798700,618630,1,100,100,19,179,{"$nulls":3},11000,43,374,43,253980,998375,1031050,1,100,100,19,179,0,0,0,12300,null,299,null,203000,798700,618630,1,100,100,19,179,{"$nulls":3},11000,{"$nulls":16},"464AE174E0000021897F83B2DBD33160"]
["64C17A7BA552E922A2FDF72A50298B2F",0,null,"2014Y0007",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,231375,189942,258646,0,75,100,3,82,0,0,0,29000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,189942,258646,0,40,55,0,0,0,0,0,29000,{"$nulls":15}," 一、形象进度：目前正在进行路面沥青面层、桥梁、绿化、交安、山体防护治理施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层189942平方米（80%）、面层258646平方米（60%）；桥涵完成投资2315万元（71%）；防护工程2.9万方（79%）；绿化工程完成769万元（54.8%）；交通安全设施完成82万元（13.5%）；山体防护治理工程完成66万元（15%）。二、存在问题：无。  ","44F92AE80000000125D8496C7290DDFC"]
["64CB813270844BD800218D8C3DCA3D13",0,null,"2014Y0009",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,80,240,26085,0,24,0,0,80000,0,0,0,0,0,1,0,80,200,23032,{"$nulls":15},"形象进度：一标本期完成产值1144.43万元，累计完成产值3.9408亿元；二标本期完成产值519.99万元，累计完成产值2.3651亿元；支线标本期完成11.62万元，累计完成产值3242.34万元。存在问题：拆迁遗留问题，特别是新增连接线的征地拆迁，正在与金庭镇加紧沟通。\n\n","4592B501E000002123E927A043947D89"]
["650CED37AD8354CF70ED92F7E3F8EB93",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"基本建成310国道至黄海大道的9.3公里，黄海大道至242省道段正在进行路基施工。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["65DAF976C40246B88517FF9AFF66BE28",0,null,"2014Y0010",-1,{"$nulls":75},"目前已建成。","4583097620000021C29C88DEA1D39A75"]
["660E40F90C3E2CD2824EEFAE30EB21BD",0,null,"2014Y0009",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段正在进行路基施工。","45825CCB00000021AE879AE5EFB9B065"]
["677CAE6BA0BFC983BB2F2F4E57722D4F",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"自开工累计完成单洞掘进4210米；二衬3358米；墟沟互通自开工累计完成粉喷桩244300米、灌注桩340根、PTC管桩44800米，完成现浇支架搭设及预压33联，完成路基填筑70746立方。","44F92AE720000041FD47DFFCE454F006"]
["6797268510B50A9B27036A81EE5FC809",0,null,"2014Y0007",-1,{"$nulls":75},"目前，项目部驻地、拌和站场地、预制场建设等已完成。正在进行接线底基层施工。","45830701A00000018662A81FE3FB2B60"]
["67972C329BC6344C705126917422B359",0,null,"2014Y0007",-1,{"$nulls":75},"目前桥梁已建成。","458302B080000021E4D2CC5B2F4B6514"]
["67D5333A08FC6933691B4E352FB69AAA",0,null,"2014Y0007",-1,{"$nulls":75},"新海新区段已建成通车；马涧通道边坡治理已开工建设；云台互通段基本完成临建施工；徐圩新区段已累计完成10公里，路基桥涵基本完成。","44F92AE7E000004126A44C796491035A"]
["68E4186AD5975482AC76171BD0F930E0",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"疏港航道大桥、烧香支河大桥全部完成。","44F92AE7E000004126A44C796491035A"]
["6984A71C79EA71235AAAA358F0ADE33F",0,null,"2014Y0005",-1,{"$nulls":75},"完成农村公路建设39.2公里","45A643D5200000210231D09FB0198FE4"]
["698DBF155E64A3E3240F04D25E0770B0",0,null,"2014Y0004",-1,0,250,0,996540,1006283,438383,0,0,0,0,0,0,525,525,17699,0,210,0,830115,827179,837980,0,95,99,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,116,0,404420,404241,595000,0,95,99,0,0,0,525,525,9782,{"$nulls":15},"形象进度：土方开挖1088679立方，占总量的83.36%；路基填筑1019087立方,占总量的77.76%,；路面底基层10%灰土181814立方，占总量80%,；完成底基层827479平方米，占总量的78.54%；完成路面沥青摊铺837980平方米,占总量的39.07%","44F92AE9400000C1F580982CCF7AEF56"]
["6A4F4B09C7BD9D077C7BDDC17B4EAEAE",0,null,"2014Y0005",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,1869000,2,0,0,5,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,462000,2,0,0,5,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["6A879F7690EACFF589C02E92255C6EB8",0,null,"2014Y0007",-1,{"$nulls":9},6,{"$nulls":14},0,{"$nulls":14},6,{"$nulls":14},0,{"$nulls":20},"完成招投标工作，进行施工准备工作","45A62A6EC00000210FD9D03217C261AE"]
["6AD736AF493AA4CC63DF6135AF876A8D",0,null,"2014Y0010",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,22,118,16,1038353,682868,682868,21,94,93,26,19,1,0,465,15995,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,2,35,0,320000,240000,240000,20,78,90,1,2,1,0,150,2500,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["6B7C62BF1DBEB3286C446FB742FE553C",0,null,"2014Y0005",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,622,10,969000,100950,2120000,6,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,18,0,9000,65850,114600,2,0,0,5,2,0,0,0,0,{"$nulls":15},"完成土石方开挖349.5万方（94.2%）,土石方填筑272.3万方（95.8%）;路面：水稳碎石基层100.95万平方（89.2%)，12%灰土96.9万平方（85.6%)，沥青214万平方(89.9%);桥梁：29980万元（76.4%）；交安1400万元（50.7%）；绿化3900万元（73.3%）。","44F92AE840000101423CCFA36BCE2089"]
["6BE3390A290A0B3CA9185F9D721E80E5",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["6CAAF13D84716B2DD3B71CCD274E8746",0,null,"2014Y0004",-1,152,null,152,{"$nulls":12},34,null,10,{"$nulls":12},152,null,152,{"$nulls":12},34,null,10,{"$nulls":27},"目前道路开工里程34公里，已完成10公里，完成投资10000万元，其余道路正在进行前期工作。","45A62941800000214B6E50365A9AF0C1"]
["6CB8D5C19F0A7C3DB0AF69FC49B8C748",0,null,"2014Y0007",-1,{"$nulls":75},"完成征地拆迁、场地平整、围墙砌筑。","44F92AE7C000008151CBB288EBA76DE4"]
["6D679BBAAD01C3EBD3CF1430B68D141A",0,null,"2014Y0007",-1,{"$nulls":75},"目前，完成先导段及二期路基路面、结构物及附属设施工程。","4582F984A00000210B371656660E7377"]
["6DA06E832913C9E39C9525CA2E9CB7A5",0,null,"2014Y0006",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：未开工。二、存在问题：地方政府征地拆迁工作没有实质性开展，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["6DD3D3562BB7812BADD7BB3A25B549A4",0,null,"2014Y0008",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：未开工。二、存在问题：地方政府征地拆迁工作没有实质性开展，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["6DE25ACD15FF4D9C4D427F15973B5F5B",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头基本完工，正在进行管架和管道施工。","46890577E0000001700A26FA278C5CAF"]
["6E25172FB77B9BDACFB03CEF2DB3FA45",0,null,"2014Y0004",-1,{"$nulls":75},"目前，正在进行征地拆工作，驻地建设、施工便道、拌和站场地建设、预制场建设、便桥搭设等工作已完成。接线路基工程已完成清表、挖填方、排水及管线预埋等。","45830701A00000018662A81FE3FB2B60"]
["6E3F38D6DBE6BAD88B279EE3159E033A",0,null,"2014Y0004",-1,0,2,0,4595,4137,0,0,0,0,0,0,0,0,0,0,0,1,0,3906,3516,0,0,0,85,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,1,0,3906,3516,0,0,0,85,0,0,0,0,0,0,{"$nulls":15},"截止2014年2月  土石方开挖了1.7万方，已完成总工程量的85%；底基层完成了3906平方米，已完成工程量的85%;基层完成了3516平方米，已完成工程量的85%","44F92AE9600000E1EE7939B9B1929372"]
["6E51EA232DEFD73B2D8EBCEDE586A9DE",0,null,"2014Y0006",-1,1,3,1,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程量100%。本项目于2014年6月份已经建成完工。","44F92AE9600000E1EE7939B9B1929372"]
["6EAAEA1CCFC0D93B52F2A92D7724E7D4",0,null,"2014Y0004",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["6ECE0F4B65AA22FC3554C3D550DD5931",0,null,"2014Y0009",-1,{"$nulls":75},"工程暂停施工","46D11F4F40000021C374A969A3743C9A"]
["6F28DBAEC01B8ABC97CFB7E42C68AA94",0,null,"2014Y0003",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,613,10,960000,990000,2100000,6,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,9,0,0,54900,94600,2,0,0,5,2,0,0,0,0,{"$nulls":15},"完成土石方开挖347万方（93.5%）,土石方填筑265.5万方（93.3%）;水稳碎石基层99万平方（97%)，12%灰土96万平方（94.9%)，沥青210万平方84%);桥梁29400万元（74.5%）；交安1350万元（48.9%）；绿化3725万元（70%）。","44F92AE840000101423CCFA36BCE2089"]
["6F9010E612CD1990BA2CB790FC53FE80",0,null,"2014Y0010",-1,{"$nulls":75},"目前，已建成通车。","458307CAE00000414A3628960FD10AB2"]
["6F9DF3D44AC8D782516B25EF61F72DF5",0,null,"2014Y0007",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":16},"464AE565800000215C9C09C8A0BE8932"]
["818C67CC259C26BA66AB0CC752A198B7",0,null,"2014Y0009",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["819FBCB63519C68B27658BAB1403BE2D",0,null,"2014Y0007",-1,{"$nulls":75},"加快路基路面施工","477AAD380000002159DCBA91BD5FA484"]
["8215EEC293921E74289C4DEBD9ABA064",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场、辅助设施建设及设备安装。","44F92AE8C00000C150E871A6EE092CCD"]
["82491943C7F37D3B7DAA3A818CD85183",0,null,"2014Y0005",-1,25,1,25,30410,53630,108850,0,0,0,0,0,0,0,0,0,11,1,11,30410,38630,58850,0,0,0,0,0,0,0,0,0,25,1,25,30410,53630,108850,0,0,0,0,0,0,0,0,0,11,1,11,30410,38630,58850,0,0,0,0,0,0,0,0,0,{"$nulls":15},"该项目按计划正常有序实施","45977C86A000000145F95B717A76C135"]
["83B247E1B66AE91C7A130903C2C4DBCE",0,null,"2014Y0007",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["83E21969BDE4DCF4CA4D2E48EFE189B9",0,null,"2014Y0010",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28A8980000021D5A75D5DAF1B946B"]
["8440A86D4BC2E24A1CB241F516FBC2AD",0,null,"2014Y0009",-1,{"$nulls":75},"累计完成投资3.5亿元，占总投资4.2亿元的83%，其中年内完成投资2.5亿元，占年度计划3.2亿元的78%。年内折合进尺1700米，占年度计划2000米的85%，累计折合进尺2100米，占工程总长的84%。","46EBEFA560000021402F9981E1B1599D"]
["851A582A5E4C8B6C9AF45650BFCAD129",0,null,"2014Y0009",-1,{"$nulls":75},"东斜坡堤工程年内折合进尺2100米，占年计划3000米的70%，累计进尺5300米，占总长7834米的68%。","452C38DA800000A19C9699F0088370B9"]
["853F9369F6A55FD62A37D9DBD4EABAA9",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一标大桥已完成，挡墙完成50%，二标全部完成。","44F92AE7E000004126A44C796491035A"]
["85A9CD5765DA7F00145272A4487317C8",0,null,"2014Y0008",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,160,440,22087,0,6,0,0,0,0,0,0,0,0,0,0,0,0,2425,{"$nulls":15},"形象进度：一标本期完成产值578.19万元，累计完成产值3.7559亿元；二标本期完成产值267.2万元，累计完成产值2.3132亿元；支线标本期完成 63万元，累计完成产值3230.72万元。存在问题：连续阴雨天造成工地施工进入瘫痪状态，等雨期结束，立刻组织恢复施工。\n\n","4592B501E000002123E927A043947D89"]
["863A6FF08E48530D9013856D538D1534",0,null,"2014Y0007",-1,{"$nulls":75},"（1）特殊路基处理:基本完成湿喷桩及管桩的施工。\n（2）路基：土石方填筑164.956万方，占总量的55.64%。\n（3）小型结构物：累计完成小构64道，占总量的94.85%。\n（4）桥梁工程：钻孔灌注桩完成4775根，占总量的91.42%；桥梁上部预制砼完成1855片，安装了1501片，占总量的30.43%。","44F92AE7400000C18C5FA6F58B9A0813"]
["864AE867325A93A000635C7CCA463194",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场、辅助设施建设及设备安装。","44F92AE8C00000C150E871A6EE092CCD"]
["868F891B184F5AF1C2FE6147C4B978AE",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成部分路基、桥涵工程。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["8698151C7699C3AA95FB42826CA45965",0,null,"2014Y0008",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,95,null,6200000,640000,2400000,null,45,65,17,46,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,35,null,200000,60000,null,null,25,25,9,14,{"$nulls":20},"4597C2C660000021C7BD96E4F6D02E66"]
["8752C018DA28D795DD8EC34AC9C3B442",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头工程和疏港航道完成100%；北侧港区排水工程、用电工程和调度楼等附属设施完成100%，码头前沿道路和堆场完成80%。","44F92AE740000061422D7CBDB598F0A4"]
["8758CF672A07C18B7A00CBECCCE3512A",0,null,"2014Y0005",-1,12,147,12,280000,274000,274000,{"$nulls":4},11,{"$nulls":3},155400,null,4,{"$nulls":14},147,null,280000,274000,274000,{"$nulls":4},11,{"$nulls":3},155400,null,4,{"$nulls":29},"464AEA1FC0000021B52E367C631B2D38"]
["87B1C5635686286ED3CAF472776153A0",0,null,"2014Y0010",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,80,240,26085,0,24,0,0,80000,0,0,0,0,0,1,0,80,200,23032,{"$nulls":15},"一标本月完成产值1079.09万元，累计完成产值4.0583亿元,二标本月完成产值1164.90万元，累计完成产值2.4817亿元,支线标本月完成43.97万元，累计完成产值3286.31万元.绿化标总计完成产值约2608.9478万元。存在问题：拆迁遗留问题，特别是新增连接线的征地拆迁，正在与金庭镇加紧沟通。\n\n","4592B501E000002123E927A043947D89"]
["87F1979729C0F29919A6B002A0883486",0,null,"2014Y0006",-1,25,140,17,1336352,836248,1317741,23,null,null,28,21,2,0,510,22684,21,105,16,957353,455868,455868,19,88,93,26,19,1,0,465,14945,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,1,3,0,0,0,0,18,0,8,0,2,1,0,150,1450,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["886127B50683733B11DB6122018F10F7",0,null,"2014Y0007",-1,{"$nulls":75},"剩余部分待建工程，其他已全部交工验收。","45B26F0B8000002123F9B996453503FA"]
["88B8E4581BE6A93508A81E61311E5B43",0,null,"2014Y0008",-1,{"$nulls":75},"目前，道路已建成。","458307CAE00000414A3628960FD10AB2"]
["8996A5578021185A50907C161B41C7A2",0,null,"2014Y0010",-1,4,null,4,{"$nulls":12},4,null,4,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":27},"已完工通车","46EB7FD2000000217E9FB8B298777A5F"]
["89B88474FE734D6F8C18A571D7F323F0",0,null,"2014Y0008",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,62,7,212700,326000,251500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,3,null,25000,23000,18000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["89FD1FE0BC58AEC7A8797278CD87BD3B",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行征地拆迁工作。","452C38DA40000161563DFD045D6A3673"]
["8A327D5857379F76DE6A4E8AEBC88B2A",0,null,"2014Y0007",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,807813,751580,568078,0,0,0,10,118,0,0,0,22740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,317393,506370,568078,0,0,0,1,0,0,0,0,5053,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["8A4284C498F755668E5A98DCCDA6BDB1",0,null,"2014Y0005",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["8A55FFBE50143DAD2FD51281761F6FCF",0,null,"2014Y0003",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,688690,648055,0,0,0,0,10,118,0,0,0,22740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,198270,402845,0,0,0,0,1,0,0,0,0,5053,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["8A61364525427C4FFFF6E7230F330739",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["8AC88E1C7B4ABB55C4E83624F668F352",0,null,"2014Y0006",-1,101,65,101,692100,671900,651700,{"$nulls":10},11,10,61440,59520,57600,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":10},11,10,61440,59520,57600,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["B4097CB4F72E1E915F7BED65ECEBE47F",0,null,"2014Y0005",-1,101,65,101,692100,671900,651700,{"$nulls":10},8,10,61440,59520,57600,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":10},8,10,61440,59520,57600,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["B43A826FEC8A13955F26FA3F0A8B6A00",0,null,"2014Y0006",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"正在进行路基、涵洞施工，桥梁施工进场","45A630DD40000021758080AC865FC45B"]
["B4679B19FBA2FBC2702601B96BA5CA64",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已完成灌注桩600根、平整场地9000平方、安装吊机3台","452C38DDE00000411468534B18F06C9C"]
["B489D2B097B7FE5CF5467FCC65807DC8",0,null,"2014Y0010",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["B51550566D108E40C40FD32D373D0729",0,null,"2014Y0005",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,160,440,22087,0,6,0,0,0,0,0,0,0,0,0,0,0,0,2425,{"$nulls":15},"形象进度：一标本期完成产值1083.68万元，累计完成产值3.54亿元；二标本期完成产值459万元，累计完成产值2.145亿元；支线标本期完成 393.21万元，累计完成产值2628.96万元。存在问题：JTHD-1标\n1、AK5+000-AK5+200道路宽度不够。\n2、DKO+390和DKO+920有房屋影响。\nJTHD-2标\n1、FK3+200-FK+700、FK4+780-FK5+040徐明刚苗木。\n连接线\n 1、CK0+340-CK1+160有电线杆32根，影响施工\n","4592B501E000002123E927A043947D89"]
["B543359608B5AB0CAC83479DB64A568F",0,null,"2014Y0009",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["B626B726A551DE82838BDCE830F28379",0,null,"2014Y0008",-1,{"$nulls":75},"目前，桥梁主体建成，正在进行桥面系施工。","45830129E0000021F3EEA0D7E47483E6"]
["B6558F654496B7A1C0A7ED701F3A05D1",0,null,"2014Y0004",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段正在进行征地拆迁工作。","45825CCB00000021AE879AE5EFB9B065"]
["B6C2661A5D1F9E88BB2607B606424D7B",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["B7CF95690B3083DD831EB81C3A97CF73",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成项目前期审批手续,完成部分征地拆迁,完成部分土方开挖","44F92AE9000000A114EC34ECCE42A6E8"]
["B7ECC7B430C67D1AD0D13B9CAA9AD864",0,null,"2014Y0006",-1,43,395,43,1269900,998375,1031050,1,100,100,19,179,0,0,0,10000,43,395,29,1269900,957465,790970,0,99,100,19,179,{"$nulls":3},8750,21,10,14,332520,164353,240080,1,17,0,2,5,0,0,0,1795,21,10,0,332520,123443,0,0,16,0,2,5,{"$nulls":3},545,{"$nulls":16},"464AE174E0000021897F83B2DBD33160"]
["B886E07BA84D0D4315048AB19EF84FBB",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["B8BEB7FFD1F0A7035484A99BA1FBADCB",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体完工，陆域施工基本完成。","46890574A0000061061A11320ED6C6EE"]
["B99C796BB94180345AB017D85216290A",0,null,"2014Y0007",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,591,0,0,0,0,0,0,0,0,93,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,351,0,0,0,0,0,0,0,0,30,0,0,0,0,{"$nulls":15},"完成上峰至土桥段下面层沥青摊铺工作，完成土桥至湖熟段45%路基施工，完成桥梁工程施工65%。征地拆迁费用支付510万。","44F92AE9800000A15AC5660EDAD7D017"]
["BA311D00912613C69A6B2A8AFBEB0E89",0,null,"2014Y0006",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,624,10,972000,1014500,2150000,6,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,20,0,12000,979400,144600,2,0,0,5,2,0,0,0,0,{"$nulls":15},"路基：完成土石方开挖352万方（94.8%）,土石方填筑272.6万方（95.9%）;路面：水稳碎石基层101.45万平方（89.7%)，12%灰土97.2万平方（85.9%)，沥青214万平方(89.9%);桥梁：304800万元（77.7%）；交安1500万元（51%）；绿化4000万元（75.2%）。","44F92AE840000101423CCFA36BCE2089"]
["BA9B1E9EC41EF78ADC4D10E5660B109C",0,null,"2014Y0007",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["BAC2FB74956E39C644261494E37BFCC6",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["BB4BDCC1B56A98D0D40453BF8818DB27",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成土方开挖890%，完成基础80%，完成墙身70%\n","44F92AE9000000A114EC34ECCE42A6E8"]
["BBB03B2D0DF0AB38C63671122AA744C6",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"隧道单洞累计掘进完成82%;墟沟互通累计完成97%主体工程。","44F92AE720000041FD47DFFCE454F006"]
["BC060FD47772341886ADC8350B70DD70",0,null,"2014Y0010",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["BC6D8EEE303A25FD711608BBB72850F9",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已累计建成纵五路至南复堆河段及纵一路段22.8公里，剩余4.7公里因与连云港港口连接线工程线位较近，正在进行路线方案研究。","452C38DA80000041BB1AF46EF3FAECC2"]
["BCA31A0B6F4CA357E2B59088ABE961F8",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["BCA7C7CF3E3EFBCC0F1A20C9C6464677",0,null,"2014Y0005",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,150,null,287000,140000,{"$nulls":5},50,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},150,null,287000,140000,{"$nulls":5},49,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["BCED53983AAC0BB3799CB4148FF1C0BA",0,null,"2014Y0009",-1,{"$nulls":75},"水工工程扫尾，K0以东挡墙及后方开山石回填完工。7-14#泊位后方道堆、变电所及其它附属设施完工，综合办公楼施工；装卸设备、电缆等购置。","46D11E59C00000215FEEE684519DC4AA"]
["BD23897D52C6F7ADD9412CC61E7A2E48",0,null,"2014Y0009",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,95,null,6200000,640000,2400000,null,45,65,17,50,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,35,null,200000,60000,null,null,25,25,9,18,{"$nulls":20},"4597C2C660000021C7BD96E4F6D02E66"]
["BE835571D9CD1FA627AC34DD0ACD3800",0,null,"2014Y0004",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,196669,83099,129323,0,50,60,0,82,0,0,0,18000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,111754,83099,129323,0,15,15,0,0,0,0,0,18000,{"$nulls":15},"一、形象进度：目前正在进行路面、桥涵施工。路基清表、挖方、填方工程已完成；路面底基层196669平方米（85%）；基层83099平方米（35%）；面层129323平方米（30%）；桥涵完成投资1522万元（46.7%）；防护工程1.8万方（49%）。二、存在问题：无。","44F92AE80000000125D8496C7290DDFC"]
["BE8C2F56452A83B741F2DF4DD06CC43D",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["C032FAF6BF9E22A8465E1CF6D3BD9E03",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成16个泊位港池码头和2.24公里疏港航道，完成北侧堆场2万米水泥搅拌桩软基处理；完成一纵、一横道路和场地平整；完成下水、污水、管道铺设、给排水工程；完成供电、照明管道铺设及正式用电工程。","44F92AE740000061422D7CBDB598F0A4"]
["C04F93C083257A1152432B4E46B84437",0,null,"2014Y0009",-1,{"$nulls":75},"西防波堤工程年内进尺2500米，占年计划2200米的114%，累计进尺2500米，占总长9562米的26%。","46D12756A00000212A79E7CE74664FD9"]
["C060FAD1B1BA2EAE24BCF00D29C518F4",0,null,"2014Y0010",-1,{"$nulls":75},"完成路基填筑35600m2，完成进度的100%；完成雨污水管430m，完成进度的100%；桥涵结构完成进度的100%，摊铺水稳30808m2，完成进度的12%。","476C4BC84000002168C8EFB59D88315C"]
["C0CA92FD2678FF7361094E8B7AF6A2A3",0,null,"2014Y0010",-1,{"$nulls":75},"完成码头水工部分，房建工程完成主体梁板柱砼浇筑，完成场内道路桥梁主体工程。","48169DD9600000213A760AD1A7936625"]
["C1CC09C4605B894AA2810FF292183138",0,null,"2014Y0006",-1,{"$nulls":75},"目前，下部结构已完成，箱梁安装已完成，正在进行桥面系施工。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n","458302B080000021E4D2CC5B2F4B6514"]
["C1EF7BF0924850A387E9F2B2260EA1E4",0,null,"2014Y0009",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"正在进行路基、涵洞桥梁施工，桥涵进行下部结构施工","45A630DD40000021758080AC865FC45B"]
["C235191620D270DEB2C369A7D16D6AE1",0,null,"2014Y0006",-1,{"$nulls":75},"目前，主体建成。","4583097620000021C29C88DEA1D39A75"]
["C286C41A243225C0BE736E89A7CDE1DF",0,null,"2014Y0007",-1,24,339,24,652423,590283,564435,2,null,null,11,79,0,0,0,0,0,8,0,0,0,0,0,50,50,0,0,{"$nulls":5},20,0,0,0,0,0,0,0,0,0,{"$nulls":5},8,0,0,0,0,0,0,0,0,0,{"$nulls":20},"45A64AD8E000002115357ED0397AE2AC"]
["C2B475459B4A9384980AA8E074966317",0,null,"2014Y0005",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,5,null,0,3000,0,{"$nulls":3},0,0,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,5,null,0,3000,0,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["C2CDC6C77B931809F7E830649C12F4A7",0,null,"2014Y0009",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,591,0,0,0,0,0,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,351,0,0,0,0,0,0,0,0,39,0,0,0,0,{"$nulls":15},"完成汤山至湖熟段路基施工70%，路面施工30%，完成秦淮河桥梁下部结构施工。征地拆迁费用支付2020万。","44F92AE9800000A15AC5660EDAD7D017"]
["C2E87BBE3DDEBF2ED3E66C51C8670248",0,null,"2014Y0009",-1,{"$nulls":75},"全线清淤完成，管桩完成90%，高压旋喷桩完成94%，路基填筑完成50%，全线钻孔桩完成85%，桥梁立柱完成35%，承台完成60%，墩身完成50%，箱涵完成60%，人通完成10%，圆管涵完成86%。","46EA9C3D40000021E09CDF7BE3DADF50"]
["C2ED8490D4A8C473CFF4D2975B097515",0,null,"2014Y0006",-1,44,417,44,1357190,2046965,2063198,4,100,100,6,189,0,0,0,19712,44,417,36,1357190,2046965,1939406,3,99,100,6,189,{"$nulls":3},15967,38,22,38,302615,810646,1819624,1,25,25,2,1,{"$nulls":3},10392,38,22,30,302615,810646,1695832,0,24,25,2,1,{"$nulls":3},6647,{"$nulls":16},"464AE306E00000210AA87B4400911FFD"]
["C311790F29C1AE46894858D680930CAC",0,null,"2014Y0009",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28726E0000021457D777E03877DDB"]
["C35A724615DC4BA9BCE89C8A7FEAC411",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已基本完成，征地拆迁已基本结束，场地平整、 临设、水电已到位。","44F92AE800000121D51AC7AB782D4663"]
["C369FE3C50BBCA69966F954AAE61A797",0,null,"2014Y0010",-1,41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},35,11,78,184354,384460,916110,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},35,11,78,184354,384460,916110,{"$nulls":3},0,{"$nulls":21},"459779F8800000211228699830C698E7"]
["C3AF93F61B1DE7B9309CB25E4C89007B",0,null,"2014Y0010",-1,{"$nulls":75},"完成承台80%、系梁75%。","494F5FA260000021C65146E6197A1225"]
["C4CF125A8020E33467C8EA744339749B",0,null,"2014Y0009",-1,43,395,43,1269900,998375,1031050,1,100,100,19,179,0,0,0,10000,43,395,43,1269900,998375,1031050,1,100,100,19,179,{"$nulls":3},10000,21,10,14,332520,164353,240080,1,17,0,2,5,0,0,0,1795,21,10,14,332520,164353,240080,1,17,0,2,5,{"$nulls":3},1795,{"$nulls":15},"形象进度：全线工程基本完成","464AE174E0000021897F83B2DBD33160"]
["C53A5DA1361792A0FB995199327D4DD5",0,null,"2014Y0007",-1,0,251,0,1002220,1053482,2741204,0,0,0,0,0,0,525,525,17699,0,251,0,1002220,1053482,2741204,0,99,100,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,157,0,576525,630544,2498224,0,99,100,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1305992立方，占总量的100%；路基填筑1204064立方，占总量的100%；路面底基层10%灰土200444立方，占总量的100%,；水稳底基层1053482平方米，占总量的100%；路面沥青摊铺2741204平方米，占总量的100%。目前龙华至雍庄段进入细节扫尾工作以及做好交工验收的准备。","44F92AE9400000C1F580982CCF7AEF56"]
["C5518676AAF78C7077843DA109FF1BF8",0,null,"2014Y0005",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"正在进行路基施工，桥梁施工进场","45A630DD40000021758080AC865FC45B"]
["C5DF0564FF39626A399C294E0216AF8A",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已基本完成,还余小部分扫尾工程。","44F92AE7800000C16F0E702CC0B514F4"]
["C630EDE3BE0C432B94C89676F644BA88",0,null,"2014Y0004",-1,{"$nulls":75},"目前，西接线路基已完成，12%石灰土底基层已完成，涵洞已完成。东接线路基已完成，12%石灰土底基层已完成，水稳基层、涵洞已完成。","458307CAE00000414A3628960FD10AB2"]
["C6429467C04A2AF2E55C0C9B691EB154",0,null,"2014Y0008",-1,{"$nulls":75},"正在开展征地拆迁，施工单位已进场。","481728FDC00000217487531E1BD8D8C8"]
["C76B3C71711DB3C912060410A9A2433D",0,null,"2014Y0008",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},38,null,180000,84470,45733,{"$nulls":3},2,24,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["C76D7F9042B34BEE100D99C1F23EE24B",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量68%,附属设施完成58%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["C77BD1C8EB538A02E1A28F7CAF00EE2C",0,null,"2014Y0009",-1,44,417,44,1357190,2046965,2063198,5,100,100,6,189,0,0,0,19712,44,417,44,1357190,2046965,2063198,5,100,100,6,189,{"$nulls":3},19712,38,22,38,302615,810646,1819624,2,25,25,2,1,{"$nulls":3},10392,38,22,38,302615,810646,1819624,2,25,25,2,1,{"$nulls":3},10392,{"$nulls":15},"形象进度：全线工程基本完成","464AE306E00000210AA87B4400911FFD"]
["C7B383630BFBE040DD30F555EA85AC8A",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"铁路专用线施工、装卸设备购置等。","452C38D9200000A160383FB696401BD8"]
["8B5254A9DB6D46B96B693DE9D33B4E38",0,null,"2014Y0005",-1,{"$nulls":75},"目前，正在进行征地拆工作，驻地建设、拌和站场地建设、预制场建设等工作已完成。接线路基工程已完成清表、挖填方、排水及管线预埋等工作。","45830701A00000018662A81FE3FB2B60"]
["8B95A19C30468EE2504867E4BA760DDF",0,null,"2014Y0007",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,180,null,363000,230000,{"$nulls":5},50,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},180,null,363000,230000,{"$nulls":5},49,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["8BDEED364D2641D5D9530AEB7466E82E",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头基本完工，正在进行管架和管道施工。","44F92AE9C00000414B088C76E8FF94CE"]
["8C4103F9011FC950AA651DE7667785F6",0,null,"2014Y0009",-1,1,3,1,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程量100%。本项目于2014年6月份已经建成完工。","44F92AE9600000E1EE7939B9B1929372"]
["8CA9FAA0B79CA5C3853080F772B19E3B",0,null,"2014Y0006",-1,{"$nulls":75},"目前，东西接线路基已完成。","458307CAE00000414A3628960FD10AB2"]
["8CE61C8345528C89D835287EF47A4BEF",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量62%,附属设施完成52%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["8D114A8475C1951BD5670574CABB6384",0,null,"2014Y0007",-1,152,null,152,{"$nulls":12},35,null,35,{"$nulls":12},152,null,152,{"$nulls":12},35,null,35,{"$nulls":27},"目前农村公路已完成约35公里，完成投资20500万元","45A62941800000214B6E50365A9AF0C1"]
["8D500066E7F4CC59A8983E14AD03AE3B",0,null,"2014Y0008",-1,{"$nulls":9},6,{"$nulls":14},0,{"$nulls":14},6,{"$nulls":14},0,{"$nulls":20},"完成招投标工作，进行施工准备工作","45A62A6EC00000210FD9D03217C261AE"]
["8DA73FB41C69CA0BF57DBC68FDC502E7",0,null,"2014Y0006",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["8E052C8EBD92DD1491A9BDB3C969B0FB",0,null,"2014Y0005",-1,{"$nulls":75},"码头基本完工，陆域设备采购。","45B26F0B8000002123F9B996453503FA"]
["8E08FA524604EB14CA6564FBF221EE29",0,null,"2014Y0007",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["8E78F0B0567AECCC1F7727061F526A11",0,null,"2014Y0005",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,31,null,35965,31470,34733,{"$nulls":3},2,20,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},31,null,35965,31470,34733,{"$nulls":3},2,20,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["8EC8693380D69B979EAC62B6C4BC4FF4",0,null,"2014Y0006",-1,{"$nulls":9},8,{"$nulls":14},4,{"$nulls":14},8,{"$nulls":14},4,{"$nulls":21},"45A622C860000021C54A12ED93C79943"]
["8EE29960A43BBA87B2EF9429452F8B5F",0,null,"2014Y0010",-1,{"$nulls":75},"目前，正在进行明远路至京杭运河大桥段路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["8F4EA8C4873807BC14491FAA492D027B",0,null,"2014Y0007",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["8FB8AC3682B125E5BFF903C1CF638535",0,null,"2014Y0006",-1,14,330000,14,120000,120000,120000,0,0,0,0,6,0,0,0,null,14,150000,7,60000,60000,0,0,0,0,0,6,0,0,0,null,14,180000,14,120000,120000,120000,0,0,0,0,0,0,0,0,null,7,0,7,60000,60000,0,0,0,0,0,0,0,0,0,{"$nulls":17},"46B8AAA3A00000217140A795E7A1AE32"]
["8FC4D3034ACC174D1EA1574D39C5E401",0,null,"2014Y0010",-1,8,147,8,273695,273695,273695,{"$nulls":3},4,11,{"$nulls":3},6498,null,77,null,19230,15187,1368,{"$nulls":3},0,4,{"$nulls":3},0,null,122,null,273695,273695,189000,{"$nulls":3},4,11,{"$nulls":3},4000,null,52,null,19230,15187,1368,{"$nulls":3},0,4,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1-4标段已进场，1-3标正在开展污水管线、河塘清淤、软基处理、路基填筑、桥涵及水利大坝等施工，4标正开展路面底基层和基层施工，5标已定标。","464AEA1FC0000021B52E367C631B2D38"]
["9025EB066B934CA15316A8D5DEA315D1",0,null,"2014Y0007",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,93852,87350,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},4650,5240,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["9073921FDF02C26B788CB932F53EDBCA",0,null,"2014Y0010",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"正在进行路基、涵洞桥梁施工，桥梁进行下部结构施工","45A630DD40000021758080AC865FC45B"]
["9153B745F30B49682B0BDDED7CD4811B",0,null,"2014Y0004",-1,0,220,0,0,0,0,0,0,0,0,68,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,175,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"路基土石方53万方；完成部分箱涵、涵管施工；完成征地拆迁费用支付670万","44F92AE9A0000001A6C4B4A0FE608B65"]
["923E5F2C4E667F0FCA0948618C21069D",0,null,"2014Y0008",-1,{"$nulls":75},"剩余部分待建工程，其他已全部交工验收。","45B26F0B8000002123F9B996453503FA"]
["92F528E0C87843B9182AB1DA6FE85973",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头基本完工，正在进行管架和管道施工。","44F92AE9A0000061EA403DE4CD1A8397"]
["937A009AE8CA4ACE938C5BA5A66FDEC3",0,null,"2014Y0009",-1,25,1,25,30410,53630,108850,{"$nulls":9},13,1,13,30410,38630,68749,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":9},13,1,13,30410,38630,68749,{"$nulls":25},"45977C86A000000145F95B717A76C135"]
["93F3A3B2D18032D21D6024024204E7AC",0,null,"2014Y0005",-1,25,140,17,1336352,836248,1317741,23,null,null,28,21,2,0,510,22684,21,105,16,957353,455868,455868,19,88,93,26,19,1,0,465,14945,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,1,3,0,0,0,0,18,0,8,0,2,1,0,150,1450,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["947EC1B4F705F520DF1C7D42DEC100B5",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成项目前期审批手续,完成部分征地拆迁,完成土方开挖60%,完成基础50%","44F92AE9000000A114EC34ECCE42A6E8"]
["95603E6D3EC2AF2F5365B0A9AFEE2727",0,null,"2014Y0007",-1,{"$nulls":75},"徐圩配套预制厂形成一条生产线，东直立堤进尺125米","452C38D9600000015B091B22A009EB3A"]
["95E6A7E4BBFF13B20B284065AD017849",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["969A38DD60A2D329245D09A13DEAD36B",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量75%,附属设施完成80%，绿化工程完成50%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["971CA82AD19B1613829EE79A34C3B0A8",0,null,"2014Y0006",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["97476EA74F0A3425CD676D53CDF3FB3D",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["97A918E8C78C1C584679EE8914A365A3",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["97B9365DB90446E35E4226180573241B",0,null,"2014Y0008",-1,{"$nulls":75},"完成码头水工部分，房建工程完成基础工程，完成场内道路路基处理，开展桥梁上部结构施工。","48169DD9600000213A760AD1A7936625"]
["98A996859E2DC2335943000A889DF070",0,null,"2014Y0010",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,180,null,472000,343000,{"$nulls":5},62,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},180,null,472000,343000,{"$nulls":5},61,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["990E63E4227FC0E3777DD5D767FB0E0B",0,null,"2014Y0004",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"正在进行路基清表及施工，桥梁施工进场","45A630DD40000021758080AC865FC45B"]
["993C6C9563D392A00ACFCCDCCC5E194B",0,null,"2014Y0007",-1,0,270,0,0,0,0,0,0,0,0,68,0,0,0,0,0,233,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,233,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成江宁河至锦文路段路基施工50%，完成桥梁工程施工55%。","44F92AE9A0000001A6C4B4A0FE608B65"]
["9993224F981F41E5E293FFF5EEBECA88",0,null,"2014Y0005",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"完成天元路至秣陵段下面层沥青摊铺，路缘石铺装，绿化工程正在施工","45A64FE000000021EF20F17B8FB2A64B"]
["9A473D19ED07E605C8254275B5F003BD",0,null,"2014Y0010",-1,0,270,0,0,0,0,0,0,0,0,68,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成锦文路至江宁河段路基施工80%，完成桥梁施工80%","44F92AE9A0000001A6C4B4A0FE608B65"]
["9A552E2BCCB92AB44C090AFFBDD2ABA8",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"452C38D8200000A1FB0176F8CD91ABCB"]
["9A8DA33AB40493D2001DF9DE8E70622A",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"开展征地拆迁工作，准备开展项目招投标工作。","44F92AE7C000002175F300290A52D82C"]
["9AFA8B1D9161F115D84584E33D64ACA1",0,null,"2014Y0009",-1,{"$nulls":75},"路基完成63%，路面78%,交安设施67%，总体进度完成70%。","477AAD380000002159DCBA91BD5FA484"]
["9BB86CA522B3610EDFAF9448B43DCC4F",0,null,"2014Y0008",-1,14,330000,14,120000,120000,120000,0,0,0,0,6,0,0,0,null,14,150000,7,60000,60000,0,0,0,0,0,6,0,0,0,null,14,180000,14,120000,120000,120000,0,0,0,0,0,0,0,0,null,7,0,7,60000,60000,0,0,0,0,0,0,0,0,0,{"$nulls":17},"46B8AAA3A00000217140A795E7A1AE32"]
["9C8E5A9807934F33B990707E56AC0800",0,null,"2014Y0010",-1,{"$nulls":75},"完成土方开挖80%、路基填筑32%。","48173F21C00000213849C18090E227D5"]
["9D08EC744E0FB8D5941A1AEC70145A89",0,null,"2014Y0004",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,136,null,100720,95230,null,null,50,100,null,43,{"$nulls":5},70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,20,null,87720,82230,null,null,20,{"$nulls":23},"44F92AE7000000A12EDFE72CF5A96603"]
["9D2C1E22C14E57B76C06EDF27456203E",0,null,"2014Y0003",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,14220720,0,0,0,0,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,15070,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["9E10CF5139CE9B18C6D734797406784C",0,null,"2014Y0009",-1,2,null,2,{"$nulls":12},2,null,0,{"$nulls":12},2,null,2,{"$nulls":12},2,null,0,{"$nulls":27},"半幅路面下面层完成，另外半幅完成至水稳基层和约700米下面层","46EB8D54A00000216D988BCF50081565"]
["9E85A9545C6410BDF096656D04736657",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"路面完成10公里，新海新区段水稳基层基本完成，其余段施工单位已进场。","44F92AE7E000004126A44C796491035A"]
["9EE146F98ADF014C8F5E0B25D827F48E",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成项目前期审批手续,完成部分征地拆迁,完成土方开挖50%,完成基础32%","44F92AE9000000A114EC34ECCE42A6E8"]
["A0DFCA235A5F7F061EF3CAEA70D2FDB7",0,null,"2014Y0010",-1,8,null,8,{"$nulls":12},8,null,4,{"$nulls":12},8,null,8,{"$nulls":12},8,null,4,{"$nulls":27},"路基工程全部完成，路面工程完成3.5公里，完成投资3000万元。","4978BBA1C0000021B8CD96E7C2ECBAA0"]
["A1A3F7A91B3DC82B9135A7F5652D284B",0,null,"2014Y0005",-1,{"$nulls":75},"正在进行征地拆迁。","452C38DA40000161563DFD045D6A3673"]
["A1CA01F689BB9806AC74E8BAE3B22C1E",0,null,"2014Y0005",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,122532,735812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,15990,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成万家楼互通上下绕城公路匝道建设；友谊路桥、黄河路桥建成通车；完成黄河路互通匝道主线拼宽；完成景观墙建设；完成黄河路互通绿化工程；铁心桥规四路贾东地块后1.2公里辅道正在进行路面、挡墙施工；钟学北路互通正在进行路面施工；丰祥路西延段正在进行绿化施工；马群至双龙街段正在对绿化进行提档升级。累计土石方160万方，路面底基层16.5万平米，基层12.3万平米，面层73.6万平米。本月完成投资2500万元，本年累计完成7000万元，累计完成172090万元。                                                    二、存在问题：1、 目前工程建设基本是在国有储备土地上实施，征地拆迁工作除雨花区段外，其他段落尚未实质性进展。2、工程建设资金严重短缺。","44F92AE8400000A1F8CD4F6E58802DB5"]
["A2C1B902B17E5EF56821D7DA7CECC1B0",0,null,"2014Y0006",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,86,6,19,16,44,0,0,0,0,23,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段完成路基涵洞施工，正在进行路面施工；\n白马段10.2公里进行路基施工，桥梁正在施工；\n剩余洪蓝至明觉段18公里正在进行征地拆迁工作","44F92AE780000001F6AE7427CA69104E"]
["A2E9EBEAE09238F2E6272CA030880368",0,null,"2014Y0009",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,837155,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,653170,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本项目已于2014年6月28日通过交工验收。","44F92AE8800000016600EFB6FA6DB838"]
["A39DD26E7FE2B15EC18FACDF351C7D5A",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["A3AD7B9A0E09F278EB2F97C4B9504816",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["A3C8A914E8EE119D5D4527545308BD82",0,null,"2014Y0002",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,141,0,142150,109467,735812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,1,0,2925,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"形象进度：铁心桥规四路贾东地块后1.2公里辅道路基施工。累计土石方141万方，路面底基层14.2万平米，基层10.9万平米，面层73.6万平米。本月完成投资500万元，本年累计完成700万元，累计完成165790万元。","44F92AE8400000A1F8CD4F6E58802DB5"]
["A3F763B9EBF385CCCCE7BF2ABB125C72",0,null,"2014Y0010",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["A3F83ED1339A2657178A43A6387CA0A5",0,null,"2014Y0010",-1,2,null,2,{"$nulls":12},2,null,0,{"$nulls":12},2,null,2,{"$nulls":12},2,null,0,{"$nulls":27},"完成主车道全幅路面主车道及辅道沥青下面层","46EB8D54A00000216D988BCF50081565"]
["A4382972A5122B0E4DAC72748227C52E",0,null,"2014Y0009",-1,{"$nulls":75},"完成农村公路建设62公里","45A643D5200000210231D09FB0198FE4"]
["A46F835CAC84FBC9F2404BF8A4FD43A8",0,null,"2014Y0006",-1,652423,1019946,25,652423,590283,564435,2,50,50,11,79,{"$nulls":4},67319,71185,{"$nulls":4},0,50,50,0,0,{"$nulls":4},0,300000,0,0,0,0,1,0,0,0,0,{"$nulls":4},67319,71185,0,0,0,0,0,0,0,0,0,{"$nulls":20},"45A64AD8E000002115357ED0397AE2AC"]
["A4C130D56F89940DC28B7C077280E2C1",0,null,"2014Y0007",-1,41,358,41,1222845,1080650,2222151,2,100,100,17,187,0,0,0,58568,41,358,11,1222845,1080650,1721447,2,100,100,17,187,{"$nulls":3},45097,39,13,30,141150,197200,1555607,1,20,0,10,155,0,0,0,18566,39,13,0,141150,197200,1054903,1,20,0,10,155,{"$nulls":3},5095,{"$nulls":15},"形象进度：临城试验段3.105km已于09年建成通车；二期工程7.88km（包括宝射河大桥）于12年8月完成交工验收；三期工程30.4km基层基本完成，沥青面层完成42%。                                                                                               ","464ADF4B400000012FF9943B4A23B34E"]
["A5093FB24500D46E68A23EDA0945DDA9",0,null,"2014Y0009",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"完成天元路至秣陵段路基施工，完成天元路至秣陵段沥青下面层施工，完成绿化施工90%。","45A64FE000000021EF20F17B8FB2A64B"]
["A55B593FC17616855E05376C5EB1954C",0,null,"2014Y0009",-1,{"$nulls":75},"目前桥梁已建成。","458302B080000021E4D2CC5B2F4B6514"]
["A58C8AE8B9264BE6020AEC7AAA3C65D3",0,null,"2014Y0005",-1,{"$nulls":75},"目前，下部结构已完成，箱梁安装已完成，正在进行桥面系施工。","458302B080000021E4D2CC5B2F4B6514"]
["A5C28417023950BA5A16059BEB2399C4",0,null,"2014Y0006",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":16},"464AE565800000215C9C09C8A0BE8932"]
["A6449DFCA172C28C577D723D694A717B",0,null,"2014Y0010",-1,152,null,152,{"$nulls":12},35,null,35,{"$nulls":12},152,null,152,{"$nulls":12},35,null,35,{"$nulls":27},"目前农村公路已完成约35公里，完成投资24500万元","45A62941800000214B6E50365A9AF0C1"]
["A6DF14A3DB990C45DA5BE9FE292A5251",0,null,"2014Y0005",-1,7,16,7,{"$nulls":7},3,{"$nulls":4},7,16,{"$nulls":8},3,{"$nulls":4},7,16,{"$nulls":8},3,{"$nulls":4},7,16,{"$nulls":8},3,{"$nulls":20},0]
["A6F1AEC52F722497B4D83200FCA6DDC6",0,null,"2014Y0010",-1,0,251,0,1002220,1053482,2741204,0,0,0,0,0,0,525,525,17699,0,251,0,1002220,1053482,2741204,0,99,100,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,157,0,576525,630544,2498224,0,99,100,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1305992立方，占总量的100%；路基填筑1204064立方，占总量的100%；路面底基层10%灰土200444立方，占总量的100%,；水稳底基层1053482平方米，占总量的100%；路面沥青摊铺2741204平方米，占总量的100%。目前龙华至雍庄段进入细节扫尾工作以及做好交工验收的准备。","44F92AE9400000C1F580982CCF7AEF56"]
["A73BEF205671D75F861CD7368ACD88D5",0,null,"2014Y0009",-1,41,358,41,1222845,1080650,2222151,2,100,100,17,187,0,0,0,58568,41,358,41,1222845,1080650,2222151,2,100,100,17,187,{"$nulls":3},58568,39,13,30,141150,197200,1555607,1,20,0,10,155,0,0,0,18566,39,13,30,141150,197200,1555607,1,20,0,10,155,{"$nulls":3},18566,{"$nulls":15},"形象进度;全线工程基本完成","464ADF4B400000012FF9943B4A23B34E"]
["A7471ECD39D8611ADCDFF815E12A0E53",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，征地拆迁已基本结束，场地平整、 临设、水电已到位，工程已开工建设。","44F92AE800000121D51AC7AB782D4663"]
["A7E21339ADD09A59770046BE86EC3ACE",0,null,"2014Y0007",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,0,180,0,0,0,0,0,50,95,9,73,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,null,180,{"$nulls":5},50,95,9,1,{"$nulls":3},4447,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["A8385A1472DADF357ECC63C3BFF325B6",0,null,"2014Y0007",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28A8980000021D5A75D5DAF1B946B"]
["A844857429F9DF3BA278D5525910A2D6",0,null,"2014Y0010",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,837155,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,653170,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本项目已于2014年6月28日通过交工验收。","44F92AE8800000016600EFB6FA6DB838"]
["A869B2077788B52B8D741CB8B5E372FC",0,null,"2014Y0009",-1,{"$nulls":75},"右幅完工通车，左幅板块处理完成，桥梁护栏完成50%。","46EA9EFBA0000021C04603F2E53ED447"]
["A86BF6849A5E3FC70EF9AE8AB1B766B2",0,null,"2014Y0003",-1,16,121,0,287625,280590,834000,0,0,0,7,91,0,0,0,0,0,104,0,236980,338055,333840,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,2,0,13830,62335,149855,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本期完成5%灰土填筑995方，12%底基层11350平方，水稳26025平方、下面层沥青7.7万平方、交安200万元、绿化250万元。\n\n本月完成投资额1250万元，本年累计完成投资2750万元，累计完成投资44750万元（其中征地拆迁18000万元,其他费用1000万元）。","44F92AE8800000016600EFB6FA6DB838"]
["A8BF80FF08A140B6A100BA42FC1B1439",0,null,"2014Y0007",-1,14,330000,14,120000,120000,120000,0,0,0,0,6,0,0,0,null,14,150000,7,60000,60000,0,0,0,0,0,6,0,0,0,null,14,180000,14,120000,120000,120000,0,0,0,0,0,0,0,0,null,7,0,7,60000,60000,0,0,0,0,0,0,0,0,0,{"$nulls":17},"46B8AAA3A00000217140A795E7A1AE32"]
["A8FC2012F214D458E52716267B169696",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"隧道单洞累计掘进完成78.5%;墟沟互通累计完成90%主体工程,完成大港路大件通道工程。","44F92AE720000041FD47DFFCE454F006"]
["A9335BBF4C625E4A5AF6C45B11EB53F0",0,null,"2014Y0010",-1,{"$nulls":75},"完成招标代理的招标工作。","494F9423E0000021971B8B67E472FD4B"]
["A93653F5C036B79E791C6F314AD8CA5A",0,null,"2014Y0005",-1,{"$nulls":75},"目前，完成先导段及二期路基路面、结构物及附属设施工程。","4582F984A00000210B371656660E7377"]
["A9AB9E096FFCBBAD2775CDB93554DCCE",0,null,"2014Y0007",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：未开工。二、存在问题：地方政府征地拆迁工作没有实质性开展，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["AA3CDA30989EB8414F204FBC1DF2A009",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量98%,附属设施完成95%，绿化工程完成100%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["AADC92DFAC10F65DC3ECA7C70798DE5B",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头基本完工，正在进行管架和管道施工。","46890577E0000061E6557DD7B74D841E"]
["AB03608222554B1F30D3DE41C2A430C7",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"I标段24万平方米停车场施工；办公楼内装基本完成。","452C38D960000061A773E74DF5A30C52"]
["AB19C3B2DCC94EB7DB2ED113238D5148",0,null,"2014Y0008",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["AB323FD9AA6F45BBD6F832F2DE501EDA",0,null,"2014Y0008",-1,{"$nulls":75},"加快路基路面施工","477AAD380000002159DCBA91BD5FA484"]
["ABF3F2153905656A7476628D12ABA5A3",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"自开工累计完成单洞掘进3686米；二衬2986米；墟沟互通自开工累计完成粉喷桩244173米、灌注桩334根、PTC管桩44595米，完成现浇支架搭设及预压30联。","44F92AE720000041FD47DFFCE454F006"]
["AC790893A86F944C7BFE0AA30511C0DD",0,null,"2014Y0009",-1,{"$nulls":75},"液化罐区pcc桩基施工总量约4200根、完成3330根；罐体基础环墙总量40个、完成24个；成品油罐体总量8个、完成制作安装；管廊总长约600米、完成430米；化工品灌区18个储罐，完成8个制作安装。\n","46D12095E00000210EEE5BA374F2A089"]
["AC7E2A498C02764657CD2BBC6ABAEB1A",0,null,"2014Y0005",-1,0,250,0,996540,1006283,438383,0,0,0,0,0,0,525,525,17699,0,226,0,954625,974212,1573189,0,95,99,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,132,0,528930,551274,1330209,0,95,99,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1102888立方，占总量的84.48%；路基填筑1238548立方，占总量的97.41%；路面底基层10%灰土190925立方，占总量的91.68%,；水稳底基层974212平方米，占总量的92.48%；路面沥青摊铺1573189平方米，占总量的73.35%。","44F92AE9400000C1F580982CCF7AEF56"]
["ACF26C9F4D3883299F93F5880E96B614",0,null,"2014Y0002",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,611,10,960000,981600,2089400,5,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,7,0,0,46500,84000,1,0,0,5,2,0,0,0,0,{"$nulls":15},"完成土石方开挖346万方（93.2%）,土石方填筑265.3万方（93.3%）;水稳碎石基层98.16万平方（96.1%)，12%灰土96万平方（94.9%)，沥青208.94万平方83.58%);桥梁：28050万元（71.5%）；交安1350万元（48.9%）；绿化3550万元（66.7%）。","44F92AE840000101423CCFA36BCE2089"]
["AD373DDCE724D58FE543C04C3370C27A",0,null,"2014Y0007",-1,{"$nulls":75},"目前，路面施工基本完成。","458307CAE00000414A3628960FD10AB2"]
["AD8D6B0692DC7301A897F15474FE8A36",0,null,"2014Y0010",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,807813,751580,692278,0,0,0,10,118,0,0,0,30740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,317393,506370,692278,0,0,0,1,0,0,0,0,5853,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["ADED6BAB746DA72B4D30F6224C35C4E0",0,null,"2014Y0008",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,837155,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,653170,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本期完成沥青摊铺9.5万平方；绿化植色带5万平方；交安工程完成路侧1.6KM单波护栏，路面标线7200平方及剩余附属设施。\n本期完成投资1700万元（其中其他费用300万元），本年累计完成投资14900万元，累计完成投资56900万元（其中征地拆迁18000万元，其他费用1650万元）。","44F92AE8800000016600EFB6FA6DB838"]
["AE879F645E3D7884AD1DB75395B725FD",0,null,"2014Y0010",-1,{"$nulls":75},"港池疏浚完工，水工主体开始施工。","46D123DB80000021DDAA88D0A2421B9E"]
["AEB50D5691E23BCF3CD88283B38D7783",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，工程已开工建设，目前正在进行口岸大楼、联检楼、保税仓库、件杂货仓库、集装箱拆装库等基础施工。码头水工下部结构已开工建设，目前正在进行桩基施工。","44F92AE800000121D51AC7AB782D4663"]
["AF9B49094F8962EBD75F77EF95C0E0D8",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"南段路基整平800米。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["AFAA0C8565DF233B4A70E39993AF98B7",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成完成土方开挖80%，完成基础70%，完成墙身50%\n","44F92AE9000000A114EC34ECCE42A6E8"]
["AFD5BE5C17B3A0851AD38D5FFE3AA911",0,null,"2014Y0002",-1,0,2,0,4595,4137,0,0,0,0,0,0,0,0,0,0,0,1,0,3217,2896,0,0,0,70,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,1,0,3217,2896,0,0,0,70,0,0,0,0,0,0,{"$nulls":15},"截止2014年2月  土石方开挖了1.4万方，已完成总工程量的70%；底基层完成了3217平方米，已完成工程量的70%;基层完成了2896平方米，已完成工程量的70%","44F92AE9600000E1EE7939B9B1929372"]
["B14DC2C320AC5811304D08A717E07AFC",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已建成8万平方米集装箱堆场，场地及其附属设施施工。","452C38D9200000A160383FB696401BD8"]
["B193FE7E3316E37B1F373291F921CC61",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"隧道单洞掘进完成70%，墟沟互通完成72%主体工程。","44F92AE720000041FD47DFFCE454F006"]
["B1E165310660292F1634F76746F95849",0,null,"2014Y0007",-1,1339141,1127463,18,605466,519452,9333283,2,50,50,6,49,0,{"$nulls":3},1339141,1127463,18,605466,519452,9333283,2,50,50,6,55,0,{"$nulls":3},0,0,0,0,0,1866657,0,0,0,6,0,0,{"$nulls":3},0,0,0,0,0,1866657,0,0,0,6,0,0,{"$nulls":18},"已完工","45A64CBEC0000021EA2875A94CD2711C"]
["B1E7C4370B0DED745B5CED18CFFD8FA0",0,null,"2014Y0010",-1,{"$nulls":75},"工程主体完工，铁路工程主体完工；接轨方案审查会于8月15日在上海路局召开。\n","46D11DA8E0000021390F8E6CD9239F6A"]
["B1EAF45F317AD0A5730183E81FB6AEDC",0,null,"2014Y0009",-1,{"$nulls":75},"完成路基填筑40%、涵洞10%。","48171CB940000001DAB3F475A2461DC6"]
["B24ABBFDA5F0E4B494C5B7D86D1D56EB",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地拆迁、场地平整、围墙砌筑工作。","44F92AE7C000008151CBB288EBA76DE4"]
["B2770F4989FD777D274723929369493E",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制工作。由于春节放假和雨雪天气的影响，目前工程进展不是很快。","44F92AE700000101C8E931F14C72B63C"]
["B2F097E90C7821D9056F4901AB13DBEF",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已完成灌注桩980根、平整场地3万平方、安装吊机6台、吊机平台2座，办公楼主体已封顶。","452C38DDE00000411468534B18F06C9C"]
["B33D21DEE6D269B080A0ED4E71106E3C",0,null,"2014Y0005",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,511,0,0,0,0,0,0,0,0,80,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,271,0,0,0,0,0,0,0,0,17,0,0,0,0,{"$nulls":15},"路基土石方56万方；完成部分箱涵、涵管施工，完成桥梁梁板预制4片；完成征地拆迁费用支付1730万","44F92AE9800000A15AC5660EDAD7D017"]
["B37639CB388F84BA46C8957E6C5D3110",0,null,"2014Y0008",-1,2,null,2,{"$nulls":12},2,null,0,{"$nulls":12},2,null,2,{"$nulls":12},2,null,0,{"$nulls":27},"半幅路面下面层完成，另外半幅完成至水稳基层和约700米下面层","46EB8D54A00000216D988BCF50081565"]
["B395CC7BD6CFE04495B28F810D0588D1",0,null,"2014Y0008",-1,41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},32,11,78,168380,384460,913051,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},32,11,78,168380,384460,913051,{"$nulls":3},0,{"$nulls":21},"459779F8800000211228699830C698E7"]
["B3E0C1ED25DFCC3EF1A37633BCCC4D33",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"路面完成10公里，新海新区段路基完成，其余段加快建设。","44F92AE7E000004126A44C796491035A"]
["C7C425DF2F41A74704890239C9B3944C",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["C7D1746694CFF8B86FB57EEABAA159AF",0,null,"2014Y0004",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,155,0,142150,109467,735812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,15,0,2925,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"形象进度：铁心桥规四路贾东地块后1.2公里辅道路基、挡墙施工；景观墙施工；路灯施工。累计土石方146万方，路面底基层14.2万平米，基层10.9万平米，面层73.6万平米。本月完成投资1300万元，本年累计完成2000万元，累计完成167090万元。","44F92AE8400000A1F8CD4F6E58802DB5"]
["C8EC6A3AF178B0CBC4CAF474CA114ED6",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["C95123E57EAFB47866C81C7879AACE48",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头工程和疏港航道完成100%；北侧港区排水工程、用电工程和调度楼等附属设施完成100%，码头前沿道路和堆场完成80%。","44F92AE740000061422D7CBDB598F0A4"]
["C960527EB1EF021481AA1CCF67974E5D",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["C979AA3166E463798343F0E866B74338",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"开展征地拆迁工作，准备开展项目招投标工作。","44F92AE7C000002175F300290A52D82C"]
["C98286BD1716A83AFD1ED0A8CB7A1DCA",0,null,"2014Y0009",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["CA3311550CF3BDAD47328BEAA1397ECE",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["CA5CB47B9908C1D9E8F31A1B2B43A0EA",0,null,"2014Y0008",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,0,180,0,0,0,0,0,50,100,9,73,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,null,180,{"$nulls":5},50,100,9,1,{"$nulls":3},4447,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["CA8ED310F070B13482252F1FE8D29178",0,null,"2014Y0007",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"完成天元路至秣陵段上面层路面施工，80%绿化施工。","45A64FE000000021EF20F17B8FB2A64B"]
["CAB8876B39883E594B885EAB5CEB19A3",0,null,"2014Y0004",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["CABBFA78EA141EE14C0B607A149C8B84",0,null,"2014Y0009",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["CC19B6A4EDF173D525D7F883E14B0C64",0,null,"2014Y0007",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段正在进行路基施工。","45825CCB00000021AE879AE5EFB9B065"]
["CC30A0A0ACB2468A1A354CD8BD8D61E1",0,null,"2014Y0010",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,64,7,212700,335000,253500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,5,null,25000,32000,20000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["CC8DB04DD477249E21CADC41754CD1EF",0,null,"2014Y0007",-1,2,null,2,{"$nulls":12},2,null,0,{"$nulls":12},2,null,2,{"$nulls":12},2,null,0,{"$nulls":27},"半幅路面下面层完成，另外半幅完成至水稳基层和约700米下面层","46EB8D54A00000216D988BCF50081565"]
["CCC649D348246810926A77EB0CF3B6B9",0,null,"2014Y0010",-1,{"$nulls":75},"全线清淤完成，管桩完成95%，高压旋喷桩完成，路基填筑完成58%，全线钻孔桩完成90%，桥梁立柱完成40%，承台完成70%，墩身完成55%，箱涵完成60%，人通完成22%，圆管涵完成86%。","46EA9C3D40000021E09CDF7BE3DADF50"]
["CCF44613E1FAFE9406DB5637B9F82D5D",0,null,"2014Y0006",-1,{"$nulls":75},"徐圩配套预制厂形成一条生产线，东直立堤进尺125米","452C38D9600000015B091B22A009EB3A"]
["CD58D94BD7FFDE5ED347EA5036643978",0,null,"2014Y0008",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":16},"464AE565800000215C9C09C8A0BE8932"]
["CD7D051B5F3B8B0757C6A9A51324A0B7",0,null,"2014Y0010",-1,{"$nulls":75},"剩余部分待建工程，其他已全部交工验收。","45B26F0B8000002123F9B996453503FA"]
["CD9268234346B0772ECE0AFC45EEC990",0,null,"2014Y0008",-1,{"$nulls":75},"徐圩配套预制厂形成一条生产线，东直立堤进尺125米","452C38D9600000015B091B22A009EB3A"]
["CDC9C71AD1278D8B36588F141027EAB2",0,null,"2014Y0009",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,62,7,212700,326000,251500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,3,null,25000,23000,18000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["CEFDA5D4D2CE72BF4E407F104154FB5D",0,null,"2014Y0006",-1,29,null,29,{"$nulls":73},"46DAE27460000021425E8E842E99A04C"]
["CF5DE0A26B5F36F025EDA869F520C136",0,null,"2014Y0004",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,689690,648055,0,0,0,0,10,118,0,0,0,22740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,199270,402845,0,0,0,0,1,0,0,0,0,5053,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["CFAF5C38F96E2E03289C831554C90EC8",0,null,"2014Y0006",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,139132,798812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,32590,63000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成万家楼互通上下绕城公路匝道建设；友谊路桥、黄河路桥建成通车；完成黄河路互通匝道主线拼宽；完成景观墙建设；完成黄河路互通绿化施工；完成铁心桥规四路贾东地块后1.2公里辅道施工；完成丰祥路西延段绿化施工，完成钟学北路互通建设，完成绕城全线绿化提档升级。累计土石方160.0万方，路面底基层16.5万平米，基层13.9万平米，面层79.9万平米。本月完成投资3000万元，本年累计完成10000万元，累计完成175090万元。               \n二、存在问题：1、目前工程建设基本是在国有储备土地上实施，征地拆迁工作除雨花区段外，其它段落尚未实质性进展。\n             2、工程建设资金严重短缺。","44F92AE8400000A1F8CD4F6E58802DB5"]
["D0C71CB25040C3656526B8AA6F82F92A",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["D1B732F9310D5FDACC5E5150BC00A5BE",0,null,"2014Y0010",-1,14,330000,14,120000,120000,120000,0,0,0,0,6,0,0,0,null,14,150000,7,60000,60000,0,0,0,0,0,6,0,0,0,null,14,180000,14,120000,120000,120000,0,0,0,0,0,0,0,0,null,7,0,7,60000,60000,0,0,0,0,0,0,0,0,0,{"$nulls":17},"46B8AAA3A00000217140A795E7A1AE32"]
["D2244AC5296713465CA92E2A3341932F",0,null,"2014Y0005",-1,{"$nulls":75},"徐圩配套预制厂形成一条生产线，东直立堤进尺125米","452C38D9600000015B091B22A009EB3A"]
["D31E07D484FD6240907212E747DC1B3A",0,null,"2014Y0009",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,231375,237427,344861,0,85,100,3,82,0,0,0,32000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,237427,344861,0,50,55,0,0,0,0,0,32000,{"$nulls":15}," 一、形象进度：目前正在进行路面沥青面层、桥梁、绿化、交安、山体防护治理施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层237427平方米（100%）、面层344861平方米（80%）；桥涵完成投资2608万元（80%）；防护工程3.2万方（87%）；绿化工程完成842万元（60%）；交通安全设施完成182万元（30%）；山体防护治理工程完成132万元（30%）。二、存在问题：无。","44F92AE80000000125D8496C7290DDFC"]
["D37CEBBF0BE20C082DEDF146159EBE6C",0,null,"2014Y0010",-1,{"$nulls":75},"办公用房内部装修已进入收尾阶段，综合楼建设工程进入墙体施工阶段，公共厕所建设已结构封顶；场地混凝土浇筑工作按计划推进，室外管网铺设同步推进。","4706D6D520000021D78B264A806E8D95"]
["D403D16E60FAC450964BE0B34EF26BAE",0,null,"2014Y0004",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,150,null,287000,140000,{"$nulls":5},50,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},150,null,287000,140000,{"$nulls":5},49,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["D42ECF2C145285C7854CB8565E759051",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场、辅助设施建设及设备安装","44F92AE8C00000C150E871A6EE092CCD"]
["D4731079B1BEBACD4B307042E07EA71A",0,null,"2014Y0006",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,62,7,201700,326000,251500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,3,null,14000,23000,18000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["D4BAA3AB0983AAF247D7CEAD28DD639D",0,null,"2014Y0010",-1,{"$nulls":75},"一标（已交地11km）：水稳全部完成，路缘石完成10公里，沥青封层完成8km，附属工程完成50%，下穿通道完成挡墙210米。二标已完成。","44F92AE7E000004126A44C796491035A"]
["D4D67441E8EBEE8FCFF8C25DE0E25F2D",0,null,"2014Y0008",-1,{"$nulls":75},"全线清淤完成，管桩完成85%，高压旋喷桩完成90%，路基填筑完成45%，全线钻孔桩完成80%，桥梁立柱完成30%，承台完成60%，墩身完成47%。箱涵完成55%，人通完成10%，圆管涵完成86% ","46EA9C3D40000021E09CDF7BE3DADF50"]
["D4F946D7B464604BFF4C0207CD8EED0E",0,null,"2014Y0010",-1,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":4},11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":4},11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":4},11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":19},"目前，该项目11.071公里路基、路面工程已全部完成，累计投资7700万元。正在开展下穿机场灯光路段（U槽）和边坡防护附属工程施工。","4979BFCD200000210A165452CAEAC270"]
["D5334AD0FE2086F894C21E46C0039B3D",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"银珠路至242省道段现在正在完善前期手续和征地工作；南段已进场施工，完成部分路基、桥涵。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["D60F3332532230135297AAB15046E62B",0,null,"2014Y0008",-1,{"$nulls":75},"完成征地拆迁、场地平整、围墙砌筑。","44F92AE7C000008151CBB288EBA76DE4"]
["D648A5BA87C1ACB323380EBC7BE1F998",0,null,"2014Y0007",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,12800,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"正在进行路基、涵洞桥梁施工，","45A630DD40000021758080AC865FC45B"]
["D675BBB43D7496F29CA2C1525D43A6A6",0,null,"2014Y0010",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,25,190,0,0,0,0,4,70,100,10,73,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,25,190,{"$nulls":4},4,70,100,10,1,{"$nulls":3},4447,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["D6B04E6C2BE9A01CD922DEFE644E6E4B",0,null,"2014Y0009",-1,24,339,24,652423,590283,564435,2,50,50,11,79,0,0,0,0,0,8,0,0,0,0,0,50,50,0,0,{"$nulls":5},20,0,0,0,0,0,0,20,0,2,{"$nulls":5},8,0,0,0,0,0,0,0,0,0,{"$nulls":19},"8月份因青奥会停工","45A64AD8E000002115357ED0397AE2AC"]
["D6EB7A510530D5B8AF31B4F36A944A20",0,null,"2014Y0010",-1,{"$nulls":75},"浦口区老山4A级风景区连接线一表段工程（岔虎路）段已于2014年10月完工，二表段工程正在进行前期准备工作。","4979D47E20000021B8A53946C0B2654B"]
["D70AD2902B8704C876B7E80285B7A5A3",0,null,"2014Y0010",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,99014,90670,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},9812,8560,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["D7AFC30A9332B19DCAA6EB0198B388EA",0,null,"2014Y0009",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,22,118,16,968353,460868,460868,20,88,93,26,19,1,0,465,14995,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,2,35,0,250000,18000,18000,19,72,90,1,2,1,0,150,1500,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["D7B7C0E40C0CEF0A136EA00D3779B475",0,null,"2014Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已完成灌注桩600根、平整场地9000平方、安装吊机4台","452C38DDE00000411468534B18F06C9C"]
["D7FEF44D2C6EB5633DB37EC8B6210DE8",0,null,"2014Y0004",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"完成天元路至禄口段下面层沥青摊铺，路缘石铺装","45A64FE000000021EF20F17B8FB2A64B"]
["D8769651CD24887DEF222BCA927A91DA",0,null,"2014Y0010",-1,{"$nulls":75},"目前，正在进行桩基施工。","45830701A00000018662A81FE3FB2B60"]
["D89CF4E35E3A29C14CB5BA2D3F1390DF",0,null,"2014Y0003",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,115680,0,0,0,45,55,0,82,0,0,0,11000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,30765,0,0,0,10,10,0,0,0,0,0,11000,{"$nulls":15},"一、形象进度：目前正在进行路面底基层、桥涵施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层115680平方米（50%）；桥涵完成投资1450万元（44.5%）；防护工程1.1万方（29.9%）。二、存在问题：无。","44F92AE80000000125D8496C7290DDFC"]
["D8A9C01E494E49D361914AA243CA032B",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["D8C20FA2331CC6D1A223BC677730D7B0",0,null,"2014Y0004",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,20,{"$nulls":7},1,20,{"$nulls":5},51,{"$nulls":7},3,47,{"$nulls":5},20,{"$nulls":7},1,20,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["D8C9D8DD4C14AD07DD33410BBD655DB0",0,null,"2014Y0008",-1,24,339,24,652423,590283,564435,2,50,50,11,79,0,0,0,0,0,8,0,0,0,0,0,50,50,0,0,{"$nulls":5},20,0,0,0,0,0,0,20,0,2,{"$nulls":5},8,0,0,0,0,0,0,0,0,0,{"$nulls":19},"8月份因青奥会停工","45A64AD8E000002115357ED0397AE2AC"]
["D9CE330ED37273FF8D8C6A0CFCBC0012",0,null,"2014Y0005",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,62,7,201700,326000,251500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,3,null,14000,23000,18000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["DA49E7916068E04C64A997CD9B3F1203",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"隧道单洞累计掘进完成80%;墟沟互通累计完成95%主体工程。","44F92AE720000041FD47DFFCE454F006"]
["DA4A6D645949C548248948D455CB64E1",0,null,"2014Y0008",-1,{"$nulls":75},"目前，正在进行明远路至京杭运河大桥段路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["FCB378F05165B3F638C8F699EB2DD4A4",0,null,"2014Y0007",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,86,6,19,16,44,0,0,0,0,23,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段完成路基涵洞施工，正在进行路面施工；\n白马段10.2公里进行路基施工，桥梁正在施工；\n剩余洪蓝至明觉段18公里正在进行征地拆迁工作,招投标工作","44F92AE780000001F6AE7427CA69104E"]
["FCC1C3C4A389DFD6C59B6200ABF8BF26",0,null,"2014Y0008",-1,{"$nulls":75},"目前，下部结构已完成，接线部分路基施工已完成。","47678C386000002118C05B3B7B3DACF5"]
["FCD39E9A78112BEBBF02AE33DEF36241",0,null,"2014Y0009",-1,{"$nulls":75},"完成路面底基层45%、小型构造物100%。","4756E0D780000021BD984AD195D60C8A"]
["FD175295798146E1A27DC8B5AAE54A84",0,null,"2014Y0006",-1,{"$nulls":3},6527,6527,6527,{"$nulls":69},"进度进行中","46708C7F2000002102B360E7E6CFE2FE"]
["FD3B0BBF3CF0BF0F290108E0DA32B254",0,null,"2014Y0008",-1,{"$nulls":75},"目前已建成。","4583097620000021C29C88DEA1D39A75"]
["FD6E037B1F22C355DF80603622C3D7C3",0,null,"2014Y0006",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,80,null,6000000,580000,2400000,null,30,60,16,44,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,20,{"$nulls":5},15,20,8,12,{"$nulls":20},"4597C2C660000021C7BD96E4F6D02E66"]
["FDF7C02ACC3C12CE3763E39A9126EC2A",0,null,"2014Y0009",-1,{"$nulls":75},"完成征地拆迁、场地平整、围墙砌筑。","44F92AE7C000008151CBB288EBA76DE4"]
["FE32691DACBBB811A6DB5F1795104054",0,null,"2014Y0006",-1,{"$nulls":9},6,{"$nulls":14},0,{"$nulls":14},6,{"$nulls":14},0,{"$nulls":20},"正在进行招投标工作，预计下月开工","45A62A6EC00000210FD9D03217C261AE"]
["FEA9C5BC2CE6B5148738FECA09204BB5",0,null,"2014Y0010",-1,{"$nulls":75},"桩基施工基本完成","46EA9FBB800000213459FE5A48F06D61"]
["FECE681DE8F611CE196F13FF0031DA4F",0,null,"2014Y0009",-1,{"$nulls":75},"目前，桥梁主体建成。","47678C386000002118C05B3B7B3DACF5"]
["FFFBA97FDDA182103A66FC494DD6C6BB",0,null,"2014Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE7A000006159C90A7558BC3A9C"]
["C549361521AE563E81AB0437FF835090",0,null,"2014Y0011",-1,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,{"$nulls":15},"目前，该项目11.071公里路基、路面工程已全部完成，累计投资7850万元。正在开展下穿机场灯光路段（U槽）和边坡防护附属工程施工，11月完成波形梁钢护栏2700米，标线7200平方米，标志80块，边坡防护8500米，泄水槽400座，排水沟60米，完成投资150万元。","4979BFCD200000210A165452CAEAC270"]
["F9432F5F016E7BD8B6F78FB0CCB0EEB9",0,null,"2014Y0007",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["91C98F3C0EA12BB6D5E9EBDA3B7208D1",0,null,"2014Y0008",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["49F44BB56A611C6B69AB2F93F5A78E96",0,null,"2014Y0009",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["B26B45E6D5ABD59E46A6D4D0978A0EFC",0,null,"2014Y0010",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["7AA5E5ABD74A853FFDF9D6EB9F99391B",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["8AC7F1AE953DE2B589647FA0709B7CB7",0,null,"2014Y0011",-1,0,251,0,1002220,1053482,2741204,0,0,0,0,0,0,525,525,17699,0,251,0,1002220,1053482,2741204,0,99,100,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,157,0,576525,630544,2498224,0,99,100,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1305992立方，占总量的100%；路基填筑1204064立方，占总量的100%；路面底基层10%灰土200444立方，占总量的100%,；水稳底基层1053482平方米，占总量的100%；路面沥青摊铺2741204平方米，占总量的100%。目前龙华至雍庄段进入细节扫尾工作以及做好交工验收的准备。","44F92AE9400000C1F580982CCF7AEF56"]
["D33E7FF199687AEDF6903726757C7F03",0,null,"2014Y0011",-1,1,3,1,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程量100%。本项目于2014年6月份已经建成完工。","44F92AE9600000E1EE7939B9B1929372"]
["70A66041CCC548259E504B1B20578B68",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程、停车场工程已完工,综合楼地下室正在施工，附属设施、绿化工程完成100%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["10E9C43A5B639FB4B11B103CCA41D42C",0,null,"2014Y0011",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["C24EA1061A591AF9085859E92DA8F7EB",0,null,"2014Y0011",-1,{"$nulls":75},"完成征地拆迁、场地平整、围墙砌筑。","44F92AE7C000008151CBB288EBA76DE4"]
["A568EE0DBF098E85BB2EFBA639F65808",0,null,"2014Y0011",-1,{"$nulls":75},"除拆迁影响段落，主线机动车道完工通车，人行道板铺设完成50%，非机动车道沥青铺设完成30%。","46EA9A9840000021E67762482E18105E"]
["51AFE75DC6F03285A75F4064F2DFB587",0,null,"2014Y0011",-1,{"$nulls":75},"桩基施工基本完成","46EA9FBB800000213459FE5A48F06D61"]
["9EDEA97B5437CC774CB13F11510F26A2",0,null,"2014Y0011",-1,{"$nulls":75},"全幅板块处理完成80%，水稳完成60%，沥青下面层完成50%，桥梁工程完成60%。","46EA9D51A0000021F1A72CD5283EA913"]
["8D790DB799B0E46F754BF4B2B6E90860",0,null,"2014Y0011",-1,{"$nulls":75},"全幅水稳及沥青下面层完成。","46EA9EFBA0000021C04603F2E53ED447"]
["495E4E69F0FF1601DB2746FD46E1C474",0,null,"2014Y0011",-1,{"$nulls":75},"完成灌注桩100%,墩台帽完成50%,立柱完成60%.承台完成100%,系梁完成100%","494F5FA260000021C65146E6197A1225"]
["75D5C5614022AE039D91DFF2B4CA19D8",0,null,"2014Y0011",-1,{"$nulls":75},"办公用房内部装修即将结束（门厅未好），综合楼建设工程墙体正进行墙体粉刷，配电房、公共厕所施工已结束，门卫基础浇筑工作已完成；场地混凝土浇筑、室外管网铺设均已完成85%","4706D6D520000021D78B264A806E8D95"]
["DF1C26CD09D34D164E2AC77B36E9E694",0,null,"2014Y0011",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,80,240,26085,0,24,0,0,80000,0,0,0,0,0,1,0,80,200,23032,{"$nulls":15},"一标本月完成产值691.84万元，累计完成产值4.1131亿元,二标本月完成产值979.97万元，累计完成产值2.5775亿元,支线标本月完成27.57万元，累计完成产值3313.85万元.绿化标总计完成产值约5617万元。存在问题：拆迁遗留问题，特别是新增连接线的征地拆迁，正在与金庭镇加紧沟通。\n\n","4592B501E000002123E927A043947D89"]
["DABC152BE17A8DEFE2EA03FBD0919A58",0,null,"2014Y0011",-1,{"$nulls":75},"完工通车。","46EA9B7380000021C12E5F228EAB22B5"]
["3B030B1697F1381554F56A46546BFAFC",0,null,"2014Y0011",-1,{"$nulls":75}," 全线清淤完成，管桩基本完成，高压旋喷桩完成，路基填筑完成65%，全线钻孔桩完成95%，桥梁立柱完成55%、承台完成75%、墩身完成65%、系梁完成56%，盖梁完成34%,箱涵完成60%、人通完成22%、圆管涵完成86%。","46EA9C3D40000021E09CDF7BE3DADF50"]
["71885D7001FA54BD056B46E1C46FC1D4",0,null,"2014Y0011",-1,{"$nulls":75},"实施一期工程5.1公里，完成路基处理总量的95%、路面底基层总量的90%，水稳路面基层总量的90%，构造物总量的100%、排水管道总量的100%","4756E0D780000021BD984AD195D60C8A"]
["26965F7FD673F450CC42DC1C62E96130",0,null,"2014Y0011",-1,4,null,4,{"$nulls":12},4,null,4,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":27},"已完工通车","46EB7FD2000000217E9FB8B298777A5F"]
["F61A7C8CA45496A74F299B9EBBB75A8D",0,null,"2014Y0011",-1,2,null,2,{"$nulls":12},2,null,0,{"$nulls":12},2,null,2,{"$nulls":12},2,null,0,{"$nulls":27},"常胜桥变更段路基完成70%，其余段落主车道完成沥青上面层，非机动车道完成下面层","46EB8D54A00000216D988BCF50081565"]
["806FCA89ED51FB05A1770468DD93DAC2",0,null,"2014Y0011",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,231375,237427,388959,0,90,100,3,82,0,0,0,34000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,237427,388959,0,55,55,0,0,0,0,0,34000,{"$nulls":15},"一、形象进度：目前正在进行路面沥青面层、桥梁、绿化、交安、山体防护治理施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层237428平方米（100%）、面层388959平方米（90.2%）；桥涵完成投资3150万元（96.6%）；防护工程3.4万方（92.5%）；绿化工程完成1080万元（76.9%）；交通安全设施完成360万元（59.2%）；山体防护治理工程完成340万元（77.3%）。二、存在问题：无。","44F92AE80000000125D8496C7290DDFC"]
["BA11F9160E52FA0ECF07A66A71786892",0,null,"2014Y0011",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,624,10,972000,1015500,2150300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,20,0,12000,980400,144900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"路基：完成土石方开挖355.7万方（95.8%）,土石方填筑273.2万方（96.1%）;路面：水稳碎石基层101.55万平方（89.7%)，12%灰土97.25万平方（85.9%)，沥青215.13万平方(90.4%);桥梁：30980万元（78.7%）；交安1500万元（51%）；绿化4400万元（82.7%）。","44F92AE840000101423CCFA36BCE2089"]
["6D556BA7544F8318D50A44ECB0674EA0",0,null,"2014Y0011",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：目前江宁区政府启动了征地拆迁工作，已完成土地丈量、房屋拆迁调查工作，正在进行杆管线迁移调查。指挥部配合开展红线放样和路田分家工作，施工单位也开展了驻地建设和测量放样复核等施工前准备工作，待江宁区政府提供建设用地后随时开展施工工作。二、存在问题：目前横溪段（13.68公里）江宁区政府启动了征地拆迁工作，已完成土地丈量、房屋拆迁调查工作，正在进行杆管线迁移调查。指挥部配合开展红线放样和路田分家工作，施工单位也开展驻地建设和测量放样复核等施工前准备工作，待江宁区政府提供建设用地后随时开展施工工作。","452C38DB00000021D4253F83097D6579"]
["C5B445FC4D17A5A11536CEC56C409686",0,null,"2014Y0011",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,48,null,202000,153000,127000,{"$nulls":3},2,24,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},48,null,202000,153000,127000,{"$nulls":3},2,24,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["34B7AAB9029B7EF2B84B044B77F86C86",0,null,"2014Y0011",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,180,null,502000,383000,33000,{"$nulls":4},62,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},180,null,502000,383000,33000,{"$nulls":4},61,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["D4FB1223D79EBC13C3D88DE169CDACA4",0,null,"2014Y0011",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,807813,751580,698278,0,0,0,10,118,0,0,0,30740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,317393,506370,698278,0,0,0,1,0,0,0,0,5853,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["9C55DDE0CB46FF435C6C0C0F3495FD3A",0,null,"2014Y0011",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,186,null,363820,318947,null,null,100,100,null,43,{"$nulls":3},4850,null,70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,70,null,350820,305947,null,null,70,{"$nulls":6},4850,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["A2EAB32D4D70D6C7745398594CE883D5",0,null,"2014Y0011",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,99014,90670,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},9812,8560,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["195782DFBCA55E09AB85D79F71573A5D",0,null,"2014Y0011",-1,{"$nulls":75},"完成蓬青路~设计终点段（K3+035~K3+863）全幅沥青面层、标线、单立柱标志。项目建成通车。","477AAD380000002159DCBA91BD5FA484"]
["AF9145CFA1BE2C9A58BFC94196613B01",0,null,"2014Y0011",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["88B5030FC3919917C92329CC9A152116",0,null,"2014Y0011",-1,{"$nulls":75},"完成路基填筑35600m2，完成进度的100%；完成雨污水管430m，完成进度的100%；桥涵结构完成进度的100%，摊铺水稳30808m2，完成进度的12%。","476C4BC84000002168C8EFB59D88315C"]
["55320AB878FF907DAE0A6314BE215C95",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"基本建成大浦互通以南段8.7公里,大浦互通以北段除受部队影响的1.2公里外，路基基本完成。（南段8.7公里之前没纳入统计，所以本月投资额增加较多）","44F92AE7C00000E1173F4D28A6F3AF2E"]
["BA4D35D84AC5855E588629C8D2561346",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["1CE9B74E66BFC686B39D4DAE6BC4C087",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已全部完成，工程已开工建设，目前正在进行卡口及口岸大楼施工。码头水工下部结构正在进行基坑开挖及后方回填。","44F92AE800000121D51AC7AB782D4663"]
["2959EEFD4A07D0FC56910CB78F76A900",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，辅助设施建设及设备安装已基本结束，工程建设进入扫尾阶段。","44F92AE8C00000C150E871A6EE092CCD"]
["7ED433A3C17BD541C254D94D8ED5307D",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已完成灌注桩980根、平整场地3万平方、安装吊机6台、吊机平台2座，办公楼主体已封顶，工程已进入扫尾阶段。","452C38DDE00000411468534B18F06C9C"]
["DA807B091F7F751C8635BE39192A0339",0,null,"2014Y0006",-1,0,270,0,0,0,0,0,0,0,0,68,0,0,0,0,0,233,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,233,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成江宁河至锦文路段路基施工45%，完成桥梁工程施工50%。","44F92AE9A0000001A6C4B4A0FE608B65"]
["DAD74C396EAF74881D47404EADBB277D",0,null,"2014Y0007",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,139132,798812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,32590,63000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成一期工程（马群至双龙街）13.7公里主线改造、万家楼互通马群换乘中心匝道、钟学北路互通、石杨路互通、双麒路互通建设；二期工程（花神庙至刘村）7.1公里主线改造、凤翔山庄及凤翔村景观墙建设、铁心桥至油坊桥段2.5公里青奥景观带建设、铁心桥规四路至贾东地块1.8公里辅道建设、友谊路桥及黄河路桥建设、黄河路互通建设，完成马群至天保桥段绿色通道建设。正在进行一期工程监控设施的完善、二期工程监控设施的新建及新增隔音屏的建设。累计土石方160.0万方，路面底基层16.5万平米，基层13.9万平米，面层79.9万平米。本月完成投资1000万元，本年累计完成11000万元，累计完成176090万元。               \n二、存在问题：1、目前工程建设基本是在国有储备土地上实施，征地拆迁工作除雨花区段外，其它段落尚未实质性进展。\n             2、工程建设资金","44F92AE8400000A1F8CD4F6E58802DB5"]
["DCE5C84AED390D32D5F37DB3EB647A09",0,null,"2014Y0010",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,624,10,972000,1015500,2150300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,20,0,12000,980400,144900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"路基：完成土石方开挖355.5万方（95.8%）,土石方填筑273万方（96%）;路面：水稳碎石基层101.55万平方（89.7%)，12%灰土97.25万平方（85.9%)，沥青215万平方(89.9%);桥梁：30880万元（78.7%）；交安1500万元（51%）；绿化4400万元（82.7%）。","44F92AE840000101423CCFA36BCE2089"]
["DD3E4FCDEEB49114078F707F0163A205",0,null,"2014Y0010",-1,{"$nulls":75},"工程已完工","46D1152460000001B5594EC6A47326C2"]
["DD609C4BB0B383B51F62595424B540E9",0,null,"2014Y0007",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,22,108,16,968353,460868,460868,20,88,93,26,19,1,0,465,14945,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,2,25,0,250000,18000,18000,19,72,83,1,2,1,0,150,1450,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["DD99D91F1B93B4646B16564FA37F85EE",0,null,"2014Y0006",-1,0,250,0,1002220,1053482,2601204,0,0,0,0,0,0,525,525,17699,0,233,0,1002220,1045286,2279602,0,99,100,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,139,0,576525,622348,2036622,0,99,100,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1132893立方，占总量的86.75%；路基填筑1204064立方，占总量的100%；路面底基层10%灰土200444立方，占总量的100%,；水稳底基层1045286平方米，占总量的99.2%；路面沥青摊铺2279602平方米，占总量的87.63%。","44F92AE9400000C1F580982CCF7AEF56"]
["DDA83DC4420818045243CC67C32B45E7",0,null,"2014Y0010",-1,{"$nulls":75},"完工通车。","46EA9B7380000021C12E5F228EAB22B5"]
["DDE624B9443DD11D7366A4619C31A0D7",0,null,"2014Y0010",-1,{"$nulls":75},"完成路基处理60%。","48B15A89C0000021CEB0D93D0A59616D"]
["DE78D8851A4A4745152BDB2A8B448A4A",0,null,"2014Y0006",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,558,0,0,0,0,0,0,0,0,89,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,318,0,0,0,0,0,0,0,0,26,0,0,0,0,{"$nulls":15},"完成上峰至土桥段下面层沥青摊铺工作，完成土桥至湖熟段30%路基施工，完成桥梁工程施工60%。征地拆迁费用支付430万。","44F92AE9800000A15AC5660EDAD7D017"]
["DED8394E0A3C3F461804C1B87F07E0CA",0,null,"2014Y0006",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,93852,87350,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},4650,5240,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["DFD1BDA2FF66637CAF87019FC9548711",0,null,"2014Y0008",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,624,10,972000,1015500,2150300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,20,0,12000,980400,144900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"路基：完成土石方开挖354.5万方（95.5%）,土石方填筑272.9万方（96%）;路面：水稳碎石基层101.55万平方（89.7%)，12%灰土97.25万平方（85.9%)，沥青215万平方(89.9%);桥梁：30680万元（78.2%）；交安1500万元（51%）；绿化4200万元（78.9%）。","44F92AE840000101423CCFA36BCE2089"]
["DFDE3A28E1B0347C8A7755AF8022E461",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"I标段24万平方米停车场施工；办公楼内装基本完成。","452C38D960000061A773E74DF5A30C52"]
["DFEDEBD49AB6CE6E0CA86400E7DFD735",0,null,"2014Y0010",-1,43,395,43,1269900,998375,1031050,1,100,100,19,179,0,0,0,10000,43,395,43,1269900,998375,1031050,1,100,100,19,179,{"$nulls":3},10000,21,10,14,332520,164353,240080,1,17,0,2,5,0,0,0,1795,21,10,14,332520,164353,240080,1,17,0,2,5,{"$nulls":3},1795,{"$nulls":15},"形象进度：全线工程基本完成","464AE174E0000021897F83B2DBD33160"]
["E03853A5229F5718D770A7F408DBF89B",0,null,"2014Y0008",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28726E0000021457D777E03877DDB"]
["E06944EE3E44B4A03694B7E989E285F7",0,null,"2014Y0005",-1,44,417,44,543000,2063000,2047000,4,100,100,8,189,0,0,0,19712,null,380,null,400000,1800000,1500000,4,100,100,8,189,{"$nulls":3},15000,44,417,44,543000,2063000,2047000,4,100,100,8,189,{"$nulls":3},19712,null,380,null,400000,1800000,1500000,4,null,null,8,189,{"$nulls":3},15000,{"$nulls":16},"464AE306E00000210AA87B4400911FFD"]
["E07FF09AE84630B58A3E1874D4B06AEC",0,null,"2014Y0010",-1,{"$nulls":75},"完成路基处理66%、底基层50%、涵洞20%。","48171CB940000001DAB3F475A2461DC6"]
["E0A66B4EA1AF591CE3B816AAA2C03B56",0,null,"2014Y0010",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["E1222899C119FFA840341186876AA6C9",0,null,"2014Y0005",-1,{"$nulls":9},9,{"$nulls":14},0,{"$nulls":14},9,{"$nulls":14},0,{"$nulls":20},"雪松桥在建，其余桥梁已完成项目工可报告批复，正在进行施工图设计及招投标工作","45A62A6EC00000210FD9D03217C261AE"]
["E181DCBAE647F4CC49BEFD3EC4EA5C52",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成70%，安装完成35%。","44F92AE700000101C8E931F14C72B63C"]
["E1AFCB9A7E0671CE39424737A16F4D04",0,null,"2014Y0009",-1,8,147,8,273695,273695,273695,{"$nulls":3},4,11,{"$nulls":3},6498,null,77,null,19230,15187,0,{"$nulls":3},0,4,{"$nulls":3},0,null,122,null,273695,273695,189000,{"$nulls":3},4,11,{"$nulls":3},4000,null,52,null,19230,15187,0,{"$nulls":3},0,4,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1-4标段已进场，1-3标正在开展污水管线、河塘清淤、软基处理、路基填筑、桥涵及水利大坝等施工，4标正开展路面底基层和基层施工，5标已定标。","464AEA1FC0000021B52E367C631B2D38"]
["E1C135753FD20B3CB9805AAADBD6B3CD",0,null,"2014Y0010",-1,{"$nulls":75},"完成农村公路建设76公里","45A643D5200000210231D09FB0198FE4"]
["E20B9711747D0CFA7F684E93C7B78050",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已基本完成，征地拆迁已结束，工程已开工建设。","452C38DDE00000411468534B18F06C9C"]
["E2273AC3C0224E394978735D48BE0D86",0,null,"2014Y0008",-1,{"$nulls":75},"右幅水稳完成，沥青下面层完成，桥梁护栏更换完成30%。","46EA9EFBA0000021C04603F2E53ED447"]
["E2930E15EEAAA590C6B915DEB87F38C1",0,null,"2014Y0005",-1,{"$nulls":75},"目前，正在进行征地拆迁工作。","4583086800000021610D57307F655C40"]
["E36547AAE926CF185F4E33FC4A3D7685",0,null,"2014Y0007",-1,4,null,4,{"$nulls":12},4,null,4,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":28},"46EB7FD2000000217E9FB8B298777A5F"]
["E3837C8410A6290F3BC369E7364FD533",0,null,"2014Y0008",-1,{"$nulls":75},"完成农村公路建设53.7公里","45A643D5200000210231D09FB0198FE4"]
["E3B60A2BCC41CB3545F02960F9423058",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼主体工程、外装潢工程、综合楼桩基工程已完成，停车场等设施已进场施工，已完成工程量95%,附属设施完成90%，绿化工程完成95%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["E3E26FF5FAB6C53678EFABE937D97C06",0,null,"2014Y0007",-1,43,395,43,1269900,998375,1031050,1,100,100,19,179,0,0,0,10000,43,395,29,1269900,957465,790970,0,99,100,19,179,{"$nulls":3},8750,21,10,14,332520,164353,240080,1,17,0,2,5,0,0,0,1795,21,10,0,332520,123443,0,0,16,0,2,5,{"$nulls":3},545,{"$nulls":15},"形象进度：先导段11.5km已于12年11月建成通车；北澄子河大桥至车樊线段12km于13年10月建成通车；车樊线以南段5.2km基本建成，已完成交工验收质量检测；马横线以北段14.2km底基层及桥梁基本完成，基层完成75%，沥青下面层已完成试验段施工。","464AE174E0000021897F83B2DBD33160"]
["E493418E5AA04FC548F1C91622A28544",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程前期手续和设计审批已基本完成，征地拆迁已结束，工程已开工建设。","452C38DDE00000411468534B18F06C9C"]
["E4C0BFF842B0936883BD6703235333D6",0,null,"2014Y0006",-1,{"$nulls":75},"目前，完成先导段及二期路基路面、结构物及附属设施工程。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n目前，完成先导段及二期路基路面、结构物及附属设施工程。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n","4582F984A00000210B371656660E7377"]
["E4C53AB4E427870CB9CC442D74ECAC27",0,null,"2014Y0007",-1,{"$nulls":75},"目前，下部结构已完成，接线部分路基施工已完成。","47678C386000002118C05B3B7B3DACF5"]
["E50946B7489037A2190DC94B68312041",0,null,"2014Y0008",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,136,null,186070,167280,null,null,50,100,null,43,{"$nulls":3},1680,null,70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,20,null,173070,154280,null,null,20,{"$nulls":6},1680,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["E52B460BFA67E255B59DD89BECFA7B0C",0,null,"2014Y0006",-1,41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},24,11,78,53450,373390,181120,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},24,11,78,53450,373390,181120,{"$nulls":3},0,{"$nulls":21},"459779F8800000211228699830C698E7"]
["E5461CC2B5EDBC6E919187B9CB85866B",0,null,"2014Y0003",-1,20,227,20,365020,322869,610680,0,0,0,7,45,0,0,0,6622,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：未开工。二、存在问题：地方政府征地拆迁工作没有实质性开展，严重影响2014年年度计划目标任务的完成。建议地方政府按照时间节点交付建设用地，保证2014年工程建设计划顺利实施。","452C38DB00000021D4253F83097D6579"]
["E5568080F8C36BC2C7B85CE1CD5AA2BF",0,null,"2014Y0007",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,136,null,186070,167280,null,null,50,100,null,43,{"$nulls":3},1680,null,70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,20,null,173070,154280,null,null,20,{"$nulls":6},1680,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["E5F5E0782089DC94F5D575B877668468",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["E6CE8B1314421C766498F07E207F980E",0,null,"2014Y0006",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,38,null,120000,73470,34733,{"$nulls":3},2,24,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},38,null,120000,73470,34733,{"$nulls":3},2,24,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["E71995EEC541576E565B6A9413DED138",0,null,"2014Y0006",-1,{"$nulls":75},"新海新区段已建成通车；马涧通道边坡治理已开工建设；云台互通段基本完成临建施工；徐圩新区段已累计完成10公里，路基桥涵基本完成。","44F92AE7E000004126A44C796491035A"]
["E7DE9AE1E3C0A9B74CF11604D850A2C9",0,null,"2014Y0010",-1,{"$nulls":75},"目前，桥梁已建成。","47678A76C0000021CA6C39AAC7090030"]
["E8DB5124EE5617DE76619B655FA4FDA1",0,null,"2014Y0006",-1,25,1,25,30410,53630,108850,0,0,0,0,0,0,0,0,0,13,1,13,30410,38630,68749,0,0,0,0,0,0,0,0,0,25,1,25,30410,53630,108850,0,0,0,0,0,0,0,0,0,13,1,13,30410,38630,68749,0,0,0,0,0,0,0,0,0,{"$nulls":16},"45977C86A000000145F95B717A76C135"]
["E918EBA83A686FD30E946DE2A230CB2B",0,null,"2014Y0007",-1,{"$nulls":75},"排水沟、清表、施工便道已完成，路基开挖完成30%，底槽处理完成50%，第一层5%石灰土完成30%。","4756E0D780000021BD984AD195D60C8A"]
["E9317B433EC4F5B5576D8471C4F53B47",0,null,"2014Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成16个泊位港池码头和2.24公里疏港航道，完成2万米水泥搅拌桩软基处理和港池内一纵一横道路。制作完成两台40吨龙门吊，完成给排水工程、正式用电工程和前方调度楼等附属工程,完成前沿道路和堆场60%。","44F92AE740000061422D7CBDB598F0A4"]
["E980D7E7AF1518798C99B87894DED9A8",0,null,"2014Y0004",-1,{"$nulls":75},"正在进行征地拆迁。","452C38DA40000161563DFD045D6A3673"]
["E9C9B2E427A58F01C9AA93C724EF5D79",0,null,"2014Y0004",-1,{"$nulls":75},"路基：管桩完成86.66%，河塘清淤完成95%,土方填筑完成11.01%；桥涵：桩基完成79.13%，承台完成45.71%,系梁完成20.7%,立柱完成35.58%，盖梁完成19.64%,预制箱梁完成12.61%,小构完成30%","44F92AE7400000C18C5FA6F58B9A0813"]
["E9F85DA6F25D47EA2FCD083D46F708A7",0,null,"2014Y0010",-1,{"$nulls":75},"目前，桥梁主体建成。","47678C386000002118C05B3B7B3DACF5"]
["EA3C2CBB594FA208CF5C4FA63888E6F3",0,null,"2014Y0006",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,837155,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,653170,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本期完成沥青摊铺9.5万平方；绿化植色带5万平方；交安工程完成路侧1.6KM单波护栏，路面标线7200平方及剩余附属设施。\n本期完成投资1700万元（其中其他费用300万元），本年累计完成投资14900万元，累计完成投资56900万元（其中征地拆迁18000万元，其他费用1650万元）。","44F92AE8800000016600EFB6FA6DB838"]
["EAD7A97A08F3F6ACCC1E8EE9239B58CB",0,null,"2014Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已累计建成纵五路至南复堆河段及纵一路段22.8公里，剩余4.7公里因与连云港港口连接线工程线位较近，正在进行路线方案研究。","452C38DA80000041BB1AF46EF3FAECC2"]
["EBA6D73402AF79E873DBAF7938F4E060",0,null,"2014Y0010",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,640,0,0,0,0,0,0,0,0,120,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,400,0,0,0,0,0,0,0,0,57,0,0,0,0,{"$nulls":15},"完成汤山至湖熟段路基施工80%，路面施工45%，完成秦淮河桥梁下部结构施工,完成梁板浇筑8片。征地拆迁费用支付1490万。","44F92AE9800000A15AC5660EDAD7D017"]
["EBAA6F5CDDF5DF8B0EF41A7FB213E0E9",0,null,"2014Y0008",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,null,88580,93852,87350,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":13},4650,5240,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["EBFB9C77A4C02819710474E220460EA3",0,null,"2014Y0009",-1,{"$nulls":75},"半幅板块处理完成50%，水稳完成40%，沥青下面层完成30%，周湖线至莘七线段全幅沥青下面层完成。","46EA9D51A0000021F1A72CD5283EA913"]
["EC2EA350B3C0D46D34932F0325831424",0,null,"2014Y0010",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["EC4AFC35F20D244E19FCDF68841CDE87",0,null,"2014Y0009",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28A8980000021D5A75D5DAF1B946B"]
["EC75E0644E3CB7D4E961567273A07BCC",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场及辅助设施建设。","44F92AE8C00000C150E871A6EE092CCD"]
["ECC058173B8BEF031B862AC0CC45F639",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"水工主体已全部完成，正在进行道路堆场及辅助设施建设。","44F92AE8C00000C150E871A6EE092CCD"]
["ECE13AE2E3C0AD4456C1223BC41F861D",0,null,"2014Y0006",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,136,null,186070,167280,null,null,50,100,null,43,{"$nulls":3},1680,null,70,null,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,20,null,173070,154280,null,null,20,{"$nulls":6},1680,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["ED2B9C507CA169A08ED9E36A3600FCE4",0,null,"2014Y0006",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段正在进行征地拆迁工作。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n","45825CCB00000021AE879AE5EFB9B065"]
["ED67E3341700382596EA9466A4815C03",0,null,"2014Y0010",-1,{"$nulls":75},"完成部分征地拆迁工作。","48A6EC29E000000142F6B2638633E8C1"]
["ED9CC5D1425C48BB10802EBA5A50DB15",0,null,"2014Y0008",-1,8,147,8,273695,273695,273695,{"$nulls":3},4,11,{"$nulls":3},6498,null,77,null,19160,13685,0,{"$nulls":3},0,4,{"$nulls":3},0,null,122,null,273695,273695,189000,{"$nulls":3},4,11,{"$nulls":3},4000,null,52,null,19160,13685,0,{"$nulls":3},0,4,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1-4标段已进场，1-3标正在开展污水管线、河塘清淤、软基处理、路基填筑、桥涵及水利大坝等施工，4标正开展路面底基层和基层施工，5标正在招标。","464AEA1FC0000021B52E367C631B2D38"]
["EE5AB3E0DE13B55D37767F7B616024A4",0,null,"2014Y0009",-1,{"$nulls":75},"工程已完工","46D1152460000001B5594EC6A47326C2"]
["EF4505C21FD79E6CF98DB7D612AA0B61",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地拆迁、场地平整、围墙砌筑工作。","44F92AE7C000008151CBB288EBA76DE4"]
["EF4EA989E6533941B80A0268DF02CF92",0,null,"2014Y0010",-1,{"$nulls":75},"路基完成95%，路面85%,交安设施80%，总体进度完成85%。\n","477AAD380000002159DCBA91BD5FA484"]
["EFA5E2781561EE019249633CCDA3B06E",0,null,"2014Y0010",-1,{"$nulls":75},"水工工程扫尾，K0以东挡墙及后方开山石回填完工。7-14#泊位后方道堆、变电所及其它附属设施完工，综合办公楼施工；装卸设备、电缆等购置。","46D11E59C00000215FEEE684519DC4AA"]
["F06CD642FA680C1BECC9ACDD8F7E9AEC",0,null,"2014Y0004",-1,25,190,25,0,0,0,8,null,null,10,73,0,0,0,22233,0,170,0,0,0,0,0,50,90,9,72,0,0,0,0,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,null,170,{"$nulls":7},9,{"$nulls":21},"458887AF00000021883DEACA51071D92"]
["F084556948E956E7D33849B973C607C5",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成部分路基、桥涵工程。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["F08741E7B6B11676D8A6AF22B4524DFB",0,null,"2014Y0010",-1,16,44,0,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,44,0,231375,237427,388449,0,87,100,3,82,0,0,0,33000,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,237427,388449,0,52,55,0,0,0,0,0,33000,{"$nulls":15},"一、形象进度：目前正在进行路面沥青面层、桥梁、绿化、交安、山体防护治理施工。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层237428平方米（100%）、面层388449平方米（90%）；桥涵完成投资3130万元（96%）；防护工程3.3万方（89%）；绿化工程完成1000万元（71.2%）；交通安全设施完成300万元（49.3%）；山体防护治理工程完成290万元（65.9%）。二、存在问题：无。","44F92AE80000000125D8496C7290DDFC"]
["F1347D91DF6A8CB6F3DE3E6013C58C4E",0,null,"2014Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["F162548CDEAE176470335135A22FD772",0,null,"2014Y0009",-1,0,251,0,1002220,1053482,2741204,0,0,0,0,0,0,525,525,17699,0,251,0,1002220,1053482,2741204,0,99,100,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,157,0,576525,630544,2498224,0,99,100,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1305992立方，占总量的100%；路基填筑1204064立方，占总量的100%；路面底基层10%灰土200444立方，占总量的100%,；水稳底基层1053482平方米，占总量的100%；路面沥青摊铺2741204平方米，占总量的100%。目前龙华至雍庄段进入细节扫尾工作以及做好交工验收的准备。","44F92AE9400000C1F580982CCF7AEF56"]
["F163EAE571C05BC114B967C9EBF3ABF8",0,null,"2014Y0005",-1,7,150000,7,55250,55250,55250,0,0,0,0,6,0,0,0,null,7,150000,7,55250,55250,0,0,0,0,0,6,0,0,0,null,0,0,7,55250,55250,55250,0,0,0,0,0,0,0,0,null,0,0,7,55250,55250,0,0,0,0,0,0,0,0,0,{"$nulls":17},"46B8AAA3A00000217140A795E7A1AE32"]
["F183708F50D74978891FF6B1D9E2CF52",0,null,"2014Y0009",-1,{"$nulls":75},"路基完成进度95%；雨污水管完成进度95%，桥涵结构完成进度95%，总体进度完成80%。","476C4BC84000002168C8EFB59D88315C"]
["F2147D56374BB243CC909810F049496F",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成建筑工程产值1200万，征地拆迁产值1500万","44F92AE9800000A15AC5660EDAD7D017"]
["F28070E7F65B873C556F8CF09DC9120F",0,null,"2014Y0006",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,180,null,363000,230000,{"$nulls":5},50,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},180,null,363000,230000,{"$nulls":5},49,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["F2A447ED2B9C1C91C6797F9AD396EE13",0,null,"2014Y0009",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,624,10,972000,1015500,2150300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,20,0,12000,980400,144900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"路基：完成土石方开挖355万方（95.7%）,土石方填筑273万方（96%）;路面：水稳碎石基层101.55万平方（89.7%)，12%灰土97.25万平方（85.9%)，沥青215万平方(89.9%);桥梁：30780万元（78.5%）；交安1500万元（51%）；绿化4300万元（80.8%）。","44F92AE840000101423CCFA36BCE2089"]
["F31E75E15A97A4EA4846E2775E6C20D7",0,null,"2014Y0010",-1,{"$nulls":75},"除拆迁影响段落，主线机动车道完工通车，标线护栏完成。","46EA9A9840000021E67762482E18105E"]
["F4234E566C5D24850962C8E24E4FEE5E",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已累计建成纵五路至南复堆河段及纵一路段22.8公里，剩余4.7公里因与连云港港口连接线工程线位较近，正在进行路线方案研究。","452C38DA80000041BB1AF46EF3FAECC2"]
["F466B8946A4ECAD62F7FD76D2355F85D",0,null,"2014Y0005",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,682160,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,498175,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本期完成水稳8450平方；AC-20沥青217175平方；绿化2550万元；交安工程600万元。\n本期完成投资5250万元（其中其他费用300万元），本年累计完成投资13200万元，累计完成投资55200万元（其中征地拆迁18000万元，其他费用13000万元）。\n","44F92AE8800000016600EFB6FA6DB838"]
["F54BC73FF042F83C76C7B19F97949C3C",0,null,"2014Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"隧道单洞累计掘进完成84%，墟沟互通主体工程已经完成。","44F92AE720000041FD47DFFCE454F006"]
["F5C43B25E5C6EEB1F9F7EB2AB08404CA",0,null,"2014Y0004",-1,{"$nulls":75},"目前，下部结构已完成，箱梁安装基本完成，正在进行桥面系施工。","458302B080000021E4D2CC5B2F4B6514"]
["F5E4EEC28082CEC9C0677A912103781E",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体基本完工。","44F92AE9C00000A17EB254C4DA38DF41"]
["F5FD820FB47AC1EE2C45F9D6AA020570",0,null,"2014Y0004",-1,25,140,17,1336352,836248,1317741,23,null,null,28,21,2,0,510,22684,21,105,16,957353,455868,455868,19,88,93,26,19,1,0,465,14945,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,1,3,0,0,0,0,18,0,8,0,2,1,0,150,1450,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["F6585B2279FD25F6582E30CC71AF1F45",0,null,"2014Y0006",-1,{"$nulls":75},"目前，项目部驻地、拌和站场、预制场建设已完成；接线部分完成排水及管线预埋等施工。","45830701A00000018662A81FE3FB2B60"]
["F683C67A710A2D2906190DC7E60E9FE2",0,null,"2014Y0010",-1,{"$nulls":75},"货运中心集装箱场站建设及公共停车场建设。","468F5198A0000021390EE49ABE0B2CD5"]
["F6CD5E6E480783808B04BE2E9DA77663",0,null,"2014Y0006",-1,{"$nulls":75},"施工结束。","45B28A8980000021D5A75D5DAF1B946B"]
["F7494871CCDC68C4CC75F0210EB1EFE0",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体基本完工。",4.6890578e+31]
["F76CF71A3AF14FBBC3BE44E1AA4EC440",0,null,"2014Y0008",-1,1,3,1,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程量100%。本项目于2014年6月份已经建成完工。","44F92AE9600000E1EE7939B9B1929372"]
["F88A673957D0B41696BA509A217712D4",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成16个泊位港池码头和2.24公里疏港航道，完成2万米水泥搅拌桩软基处理和港池内一纵一横道路。制作完成一台40吨龙门吊，完成给排水工程、正式用电工程和前方调度楼等附属工程,完成前沿道路和堆场60%。","44F92AE740000061422D7CBDB598F0A4"]
["F894D17D09B5AD0B3019C67974999A7C",0,null,"2014Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已建成8万平方米集装箱堆场。","452C38D9200000A160383FB696401BD8"]
["F8F40C30F6C6D9C1DB0C7A9AD2ECF921",0,null,"2014Y0007",-1,{"$nulls":75},"目前，桥梁主体建成，正在进行桥面系施工。","45830129E0000021F3EEA0D7E47483E6"]
["F9194EF2BDF7EF8511EB1203B91AA4AD",0,null,"2014Y0005",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["F9487C3FFC4E143948BEB51088A8DE84",0,null,"2014Y0005",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,691690,648055,0,0,0,0,10,118,0,0,0,22740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,201270,402845,0,0,0,0,1,0,0,0,0,5053,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["F9C3FCAC49E79200FB3E0EB011F9E5AA",0,null,"2014Y0002",-1,34,0,34,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE780000001F6AE7427CA69104E"]
["FB1A599345CA7700A99241BEECAF29FC",0,null,"2014Y0008",-1,{"$nulls":75},"目前，项目部驻地、拌和站场地、预制场建设等已完成。正在进行接线底基层施工。","45830701A00000018662A81FE3FB2B60"]
["FB238C5E4D63242E41C539B062981248",0,null,"2014Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体基本完工。","44F92AE9C00000A17EB254C4DA38DF41"]
["FB46713E289684BFAC06187DBEE5F1F6",0,null,"2014Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"基本建成310国道至黄海大道的9.3公里，黄海大道至242省道段正在进行路基施工。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["FB9E1CEAA79DFC136AE70E7A0DC077E9",0,null,"2014Y0008",-1,0,251,0,1002220,1053482,2741204,0,0,0,0,0,0,525,525,17699,0,251,0,1002220,1053482,2741204,0,99,100,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,157,0,576525,630544,2498224,0,99,100,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1305992立方，占总量的100%；路基填筑1204064立方，占总量的100%；路面底基层10%灰土200444立方，占总量的100%,；水稳底基层1053482平方米，占总量的100%；路面沥青摊铺2741204平方米，占总量的100%。目前龙华至雍庄段进入细节扫尾工作以及做好交工验收的准备。","44F92AE9400000C1F580982CCF7AEF56"]
["FBA2AED8B74786CB6E68C7798CFDC483",0,null,"2014Y0009",-1,{"$nulls":75},"（1）路基：软土地基处理已完成；土石方填筑208.95万方，占总量（288.33）的72.47%。\n（2）小型结构物：累计完成管涵65道,占总量（68）的95.59%。\n（3）桥梁工程：钻孔灌注桩完成5099根，占总量（5223）的97.63%；桥梁上部预制砼安装完成2222片，占总量（4932）的52.17%。","44F92AE7400000C18C5FA6F58B9A0813"]
["FC2ECF1A9AB8A0318B2AD48FBEF7E830",0,null,"2014Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,455,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,215,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"路基土石方62万方；完成部分箱涵、涵管施工，完成桥梁梁板预制2片；完成征地拆迁费用支付870万","44F92AE9800000A15AC5660EDAD7D017"]
["FC70B3BDF5E8F04B54804D0E7C852348",0,null,"2014Y0005",-1,41,14,120,1436401,null,1305854,{"$nulls":3},12,{"$nulls":5},24,11,25,53450,null,181120,{"$nulls":3},0,{"$nulls":5},41,14,120,1436401,null,1305854,{"$nulls":3},12,{"$nulls":5},24,11,25,53450,null,181120,{"$nulls":3},0,{"$nulls":21},"459779F8800000211228699830C698E7"]
["FC7AFEFB0EBEEEE9A6636B45D56F765D",0,null,"2014Y0010",-1,1,3,1,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程量100%。本项目于2014年6月份已经建成完工。","44F92AE9600000E1EE7939B9B1929372"]
["68FAE8E8A283B8340AA6D94FE57B6510",0,null,"2014Y0011",-1,{"$nulls":75},"工程水工结构已全部完工，设备已安装完毕，正进行堆场及道路施工。","49E4B51280000021B30873068C3DFF72"]
["08DFE4FF05392157D2D80690DFD56796",0,null,"2014Y0011",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28A8980000021D5A75D5DAF1B946B"]
["770CC386552E43F7F11460BA6E0D9DC8",0,null,"2014Y0011",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,25,190,0,0,0,0,4,70,100,10,73,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,25,190,{"$nulls":4},4,70,100,10,1,{"$nulls":3},4447,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["B5798EA911B28A38295968641040B811",0,null,"2014Y0011",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,95,null,6200000,640000,2400000,null,52,75,18,52,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,35,null,200000,60000,null,null,32,35,10,20,{"$nulls":20},"4597C2C660000021C7BD96E4F6D02E66"]
["8BD142D59348612EE25A7CB0986804D9",0,null,"2014Y0011",-1,{"$nulls":75},"目前，已建成先导段2公里，剩余段路基施工已完成。","4582F984A00000210B371656660E7377"]
["70F08044C226FA09C6432DA778C421DB",0,null,"2014Y0011",-1,{"$nulls":75},"目前，桥梁建成。","45830129E0000021F3EEA0D7E47483E6"]
["FB28F9AB28E46347B66DF810874E3DEC",0,null,"2014Y0011",-1,{"$nulls":75},"目前已建成。","4583097620000021C29C88DEA1D39A75"]
["E4FDFF09E92696274697B40AFA4B8663",0,null,"2014Y0011",-1,{"$nulls":75},"目前，桥梁已建成。","47678A76C0000021CA6C39AAC7090030"]
["031D7A2D36D49861CF5F1022F1E2E8D6",0,null,"2014Y0011",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["DCAD33C13C5E814C135D8B8F6DE678A0",0,null,"2014Y0011",-1,{"$nulls":75},"完成招标工作，施工单位进场。","494F7BCEC000002123A1FDE2C282EA21"]
["43E20775BCE3B76CE7D1B732FE5937EA",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头工程和疏港航道完成100%；北侧港区排水工程、用电工程和调度楼等附属设施完成100%，码头前沿道路和堆场完成88%。","44F92AE740000061422D7CBDB598F0A4"]
["D31F760AEF05F79C95A801B394E385A9",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"基本","44F92AE9000000A114EC34ECCE42A6E8"]
["75EF6FFA8902ACD29FF636D37AE71A13",0,null,"2014Y0011",-1,5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":27},"工程基本完工，完成投资1720万。","4965922940000021CADEE47D6F615CD4"]
["9E314896CD4CF7EDD5BE21CEB388B9B5",0,null,"2014Y0011",-1,8,null,8,{"$nulls":12},8,null,8,{"$nulls":12},8,null,8,{"$nulls":12},8,null,8,{"$nulls":27},"工程基本完工，完成投资3617万元。","4978BBA1C0000021B8CD96E7C2ECBAA0"]
["716E4A3E6368146B637A83804152E3CB",0,null,"2014Y0011",-1,{"$nulls":75},"现场原沥青路面的主车道改造已经基本完成，右幅拓宽部分进行水稳施工，裴家圩桥南侧下部结构北侧8根灌注桩、1号桥南侧桥面铺装、孙家桥桩基及2号桥下部结构已完成。","4A04B92BC000006128D10F788349E5BC"]
["F496C77392557AFEDB741477BE8557A3",0,null,"2014Y0012",-1,{"$nulls":75},"阳澄湖西路至沈思港桥东侧慢车道路基及西侧水稳基层完成，沈思港桥东半幅完成，西侧开始钻桩，朝阳河桥西北侧已完成至台帽，西南侧正进行桥台施工，全线（除二标）开始主车道开挖及路基施工。","4A04D699C0000021960B6C19775B7500"]
["874185FC6F8A4EAD553A0018F84D06E4",0,null,"2014Y0012",-1,{"$nulls":75},"全线路基填筑完成70%，桥梁立柱完成65%、承台85%，墩身75%，系梁完成65%，盖梁完成45%，现浇箱梁完成40%，预制板梁完成30%，箱涵完成65%、人通完成33%、圆管涵完成。","46EA9C3D40000021E09CDF7BE3DADF50"]
["3D8E89F450C879A007DBF6CBD09FEC9E",0,null,"2014Y0012",-1,2,null,2,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":27},"已完工通车。","46EB8D54A00000216D988BCF50081565"]
["5F2869C349F4B01BFAC6EC46F45DE189",0,null,"2014Y0012",-1,{"$nulls":75},"完成路基填筑35600m2，完成进度的100%；完成雨污水管430m，完成进度的100%；桥涵结构完成进度的100%，摊铺水稳30808m2，完成进度的12%。","476C4BC84000002168C8EFB59D88315C"]
["6D8ACBBC476C1D7EC1891AD78594F25B",0,null,"2014Y0012",-1,{"$nulls":75},"桩基100％,墩台帽54.2％,立柱60％,承台系粱100％,上部预制完成29.7％。","494F5FA260000021C65146E6197A1225"]
["13651D67B629FD6CE87E96863B54E024",0,null,"2014Y0012",-1,{"$nulls":75},"锚地调整施工结束。","4A7F3877A0000021C2BA0D6D2008C665"]
["AD3B6EEAD2728859A235D57E50DD4093",0,null,"2014Y0012",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["FCC7BC4A27D0F47F969D34A89DBC15C2",0,null,"2014Y0012",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,95,42,6200000,640000,2400000,null,52,75,18,52,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,35,null,200000,60000,null,null,32,35,10,20,{"$nulls":19},"北段42.3公里建成通车，南段正在进行路基、桥梁施工.","4597C2C660000021C7BD96E4F6D02E66"]
["81A52AF82E4C3BABB8D75AB2BB0AC56C",0,null,"2014Y0012",-1,{"$nulls":75},"目前，主站房已经完成，12月份进行了标准化和售检票系统的安装。","4A846A5BE0000001857A4A36BC850D64"]
["C1379EDF95CD4C5389230C9E65452F90",0,null,"2014Y0012",-1,10,254,10,536564,496499,766766,13,100,100,5,78,{"$nulls":3},5973,null,222,{"$nulls":5},75,95,3,78,{"$nulls":5},120,{"$nulls":5},70,80,3,78,{"$nulls":5},149,{"$nulls":5},75,83,3,78,{"$nulls":19},"完成36%的土方开挖、80%的土方填筑；完成87%的桥梁上部预制砼、62%的上部现浇砼、13%的桥面铺装施工。","452C38D900000041E569F21C93091E69"]
["0700C4D32E91AB0E224D040D16AE18C8",0,null,"2014Y0012",-1,{"$nulls":75},"完成路基填筑58%、涵洞71%、桥梁灌注桩75%。","48173F21C00000213849C18090E227D5"]
["CE90A5E56154AC6442F72B5FBC964006",0,null,"2014Y0012",-1,20,424,27,{"$nulls":3},26,100,100,22,155,{"$nulls":3},14610,null,74,{"$nulls":8},100,{"$nulls":5},71,{"$nulls":8},98,{"$nulls":5},74,{"$nulls":8},100,{"$nulls":20},"469415CEC000000193285BF8DEFE5650"]
["D9F8366787B6E9EAA2F7B78A063F9899",0,null,"2014Y0012",-1,{"$nulls":75},"项目已完工","452C38DB800001017156B8849DCCB956"]
["4FC0FF254A78A3B48797D811DAC2AD47",0,null,"2014Y0012",-1,{"$nulls":75},"开展面层施工","48B15A89C0000021CEB0D93D0A59616D"]
["AC8D301FAC6B998A74ABBB54B979A0DB",0,null,"2014Y0012",-1,{"$nulls":75},"目前，已基本建成。","45825CCB00000021AE879AE5EFB9B065"]
["BF65F2999BC77E89CF1A96CEAB603C01",0,null,"2014Y0012",-1,7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":21},"481FB13480000021DF891907B35F942C"]
["5E72C6CC11295BD6EBC4241A087AD753",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头工程和疏港航道完成100%；北侧港区排水工程、用电工程和调度楼等附属设施完成100%，码头前沿道路和堆场完成90%。","44F92AE740000061422D7CBDB598F0A4"]
["03BDD46F558DED02B733B5F583931D5C",0,null,"2014Y0012",-1,{"$nulls":75},"完成码头水工部分，房建工程完成主体封顶，完成场内道路桥梁主体工程。","48169DD9600000213A760AD1A7936625"]
["F652E3DB99BF032924D343581C014C79",0,null,"2014Y0012",-1,{"$nulls":75},"桥梁主体已完工","47C9176620000021271D79C47773C13B"]
["21D34F81AF8978F2D59992F36187C577",0,null,"2014Y0011",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,64,7,212700,335000,253500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,5,null,25000,32000,20000,{"$nulls":25},"4597BDE880000021876F5E47FCCB44CC"]
["F582506333A7698E8396BD7E017768F9",0,null,"2014Y0011",-1,{"$nulls":75},"桥梁工程完成96%，接线路基完成85%","494F759FA0000021B650A21A5A0C6724"]
["6D2DE90D5ACB4B5B0E3015C50A512617",0,null,"2014Y0011",-1,{"$nulls":75},"目前桥梁已建成。","458302B080000021E4D2CC5B2F4B6514"]
["F1FE3B4CB7D0E36F07CA03BD228CD3F7",0,null,"2014Y0011",-1,{"$nulls":75},"目前，已建成通车。","458307CAE00000414A3628960FD10AB2"]
["32526195B3A0BDFFB3F6360B20945A5D",0,null,"2014Y0011",-1,{"$nulls":75},"目前，桥梁及接线道路已建成。","4767883F000000016F0AF6F671358D27"]
["9F5F2B84F750F966EE2C8218DC6EFA08",0,null,"2014Y0011",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["B4C5FAD5BCB48412BE981032A05C0197",0,null,"2014Y0011",-1,{"$nulls":75},"进入招标程序。","494F9423E0000021971B8B67E472FD4B"]
["8637FD7729B7DF04FE2DA24C69F5F80F",0,null,"2014Y0011",-1,{"$nulls":75},"完成码头水工部分，房建工程完成主体封顶，完成场内道路桥梁主体工程。","48169DD9600000213A760AD1A7936625"]
["40BD87B0F71B8E309F8F07256BE3440A",0,null,"2014Y0011",-1,{"$nulls":75},"东直立堤工程年内折合进尺60米，占年计划的3%，累计进尺185米，占总长4377米的4%，配套的预制厂已建成投产。","452C38D9600000015B091B22A009EB3A"]
["6041B7F74604982551B7451E85F8E632",0,null,"2014Y0011",-1,{"$nulls":75},"工程暂停施工","46D11F4F40000021C374A969A3743C9A"]
["DB79EE318A5A49E158EFEF45AAFC471B",0,null,"2014Y0011",-1,{"$nulls":75},"港池疏浚完工，水工主体开始施工。","46D123DB80000021DDAA88D0A2421B9E"]
["72700862A83E8631911F2421AED5EBCF",0,null,"2014Y0012",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["0BD1D86DD42AB915854614334CBC66BF",0,null,"2014Y0012",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,139132,798812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,32590,63000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成一期工程（马群至双龙街）13.7公里主线改造、万家楼互通马群换乘中心匝道、钟学北路互通、石杨路互通、双麒路互通建设；二期工程（花神庙至刘村）7.1公里主线改造、凤翔山庄及凤翔村景观墙及新增景观墙建设、铁心桥至油坊桥段2.5公里青奥景观带建设、铁心桥规四路至贾东地块1.8公里辅道建设、友谊路桥及黄河路桥建设、黄河路互通建设，完成马群至天保桥段绿色通道建设，完成一期工程、二期工程监控设施建设及路灯照明等附属工程。累计土石方160.0万方，路面底基层16.5万平米，基层13.9万平米，面层79.9万平米，中小桥5座，涵洞、通道24道，交通工程4200万元，绿化工程8900万元。项目实体工程已按交通局要求于2014年7月完工，并完成交工验收。本年完成投资13000万元，累计完成178090万元。               \n","44F92AE8400000A1F8CD4F6E58802DB5"]
["0F4F165B80A1C18CAC9E5751D5E33D82",0,null,"2014Y0012",-1,0,0,0,0,0,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"目前本工程正在进行绿化和各类管线的迁移,做好施工前的准备.存在问题:人行道私人消防栓未落实迁移和沿线三处房屋的拆迁未解决.","4A7A184320000021AC624E810D6E78FF"]
["7AB3FBE4FBBBEBAE413DB296E5909C11",0,null,"2014Y0012",-1,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,{"$nulls":15},"目前，该项目11.071公里路基、路面工程已全部完成，累计投资8500万元。正在开展下穿机场灯光路段（U槽）和边坡防护附属工程施工，12月完成波形梁钢护栏、标线、标志、边坡防护、排水沟施工，完成投资650万元。","4979BFCD200000210A165452CAEAC270"]
["85EA1D513E47A7EE3FA6E7B77D8B88F5",0,null,"2014Y0012",-1,{"$nulls":75},"办公用房内部装修完毕，进入全面保洁阶段；综合楼建设工程、场地混凝土浇筑、室外管网铺设均已进入收尾阶段；门卫建设工程正进行顶棚浇筑施工，室外电缆铺设按计划有序进行；","4706D6D520000021D78B264A806E8D95"]
["61A2A496CB4035698EAD00C6A92D932B",0,null,"2014Y0012",-1,{"$nulls":75},"实施一期工程5.1公里，完成主车道水稳路面基层总量的95%，构造物总量的100%、排水管道总量的100%，沿线路缘石总量的90%，慢车道路基处理总量的100%。","4756E0D780000021BD984AD195D60C8A"]
["93A81734A959842E181B329052CC3AA0",0,null,"2014Y0012",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"天元路至秣陵段建成通车。","45A64FE000000021EF20F17B8FB2A64B"]
["D6A722992626D88BF4604340D213C9B0",0,null,"2014Y0012",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,22,118,16,1038353,682868,682868,21,94,93,26,19,1,0,465,15995,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,2,35,0,320000,240000,240000,20,78,90,1,2,1,0,150,2500,{"$nulls":15},"安定至凤阳段已建成通车。","45886E536000002100B27DDCDF662D01"]
["137119E6B166E209DB500A8D1E681BA4",0,null,"2014Y0012",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,25,190,0,0,0,0,8,100,100,10,73,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,25,190,{"$nulls":4},8,100,100,10,1,{"$nulls":3},4447,{"$nulls":15},"路基、桥梁基本结束，正在进行路面施工。","458887AF00000021883DEACA51071D92"]
["7B06E5BFD28AE14F9C920833550D26AC",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"北固山隧道累计完成单洞掘进4800米，占总量的86%，墟沟互通完成主体工程，正在进行交安工程施工。","44F92AE720000041FD47DFFCE454F006"]
["547372477184BF85B6508A5F32A44C2A",0,null,"2014Y0012",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,178,6,19,16,44,0,0,0,0,0,0,0,0,0,6,125,6,19,16,44,0,0,0,0,50,0,0,0,0,0,125,6,19,16,44,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段基本完成路面工程，\n白马段10.2公里进行路基施工，桥梁正在施工；\n剩余洪蓝至明觉段18公里正在进行清表工作","44F92AE780000001F6AE7427CA69104E"]
["F8E7E835A5EBD0F35F5538E621779AAA",0,null,"2014Y0012",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,437800,0,{"$nulls":3},0,{"$nulls":3},25,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,437800,0,{"$nulls":3},0,{"$nulls":3},25,{"$nulls":19},"正在进行路基、涵洞桥梁施工，桥梁进行下部结构施工","45A630DD40000021758080AC865FC45B"]
["1F351197D8D3009FFD73AF8BBCED5287",0,null,"2014Y0012",-1,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,null,null,17,null,400700,1211300,{"$nulls":11},17,null,400700,1211300,{"$nulls":24},"于12月25日通过交工验收。","452C38D5A00000A1C369596A7753C333"]
["610815DDC0591460786A81EE38431DC3",0,null,"2014Y0012",-1,36,505,{"$nulls":4},13,100,100,19,111,{"$nulls":5},371,{"$nulls":5},80,90,null,106,{"$nulls":5},315,{"$nulls":5},50,100,null,111,{"$nulls":5},286,{"$nulls":5},50,90,null,106,{"$nulls":19},"完成73%的路基土方填筑、95%的小型构造物、90%的桥梁下部结构砼、68%的上部预制砼、13%的上部现浇砼施工。","452C38DBE00000616AD445E437E62A7E"]
["EDED5BC64F24682413A82EF9AE9BFC3A",0,null,"2014Y0012",-1,1,null,1,3500,3500,3500,{"$nulls":69},"已完成设计招标工作，目前正在开展征地拆迁和施工准备。","49799B6500000001CDC755BA5B4F4D55"]
["70F1F8E8D4BF5841CFDC451ACD391211",0,null,"2014Y0012",-1,6,33,6,{"$nulls":3},1,{"$nulls":3},22,{"$nulls":4},6,33,6,{"$nulls":3},1,{"$nulls":3},22,{"$nulls":4},6,1,6,{"$nulls":3},1,{"$nulls":3},2,{"$nulls":4},6,1,6,{"$nulls":3},1,{"$nulls":3},2,{"$nulls":20},"452C38D580000081E7D5234B2084D364"]
["00BB5F3CE3976BED1245B446BC6B2AAA",0,null,"2014Y0012",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,10,null,0,20700,20700,{"$nulls":3},1,37,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,10,null,0,20700,20700,{"$nulls":3},1,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["78537C0186247073C0111147E99D81BA",0,null,"2014Y0011",-1,{"$nulls":75},"剩余部分待建工程，其他已全部交工验收。","45B26F0B8000002123F9B996453503FA"]
["BE439FE85E850D4D08D428C60FE114EB",0,null,"2014Y0011",-1,{"$nulls":75},"项目完成前期报批工作，正式开工。","495AB173C0000021BD1078AE8F558A41"]
["3FB9DF7BAC9285866D13F602982AB997",0,null,"2014Y0011",-1,{"$nulls":75},"完成路基处理66%、底基层50%、涵洞20%。","48171CB940000001DAB3F475A2461DC6"]
["875DAE2D1D8BF1C4314197EAD4768DA0",0,null,"2014Y0011",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,22,118,16,1038353,682868,682868,21,94,93,26,19,1,0,465,15995,5,36,11,378999,280000,280000,21,89,100,2,2,2,0,150,9789,2,35,0,320000,240000,240000,20,78,90,1,2,1,0,150,2500,{"$nulls":16},"45886E536000002100B27DDCDF662D01"]
["1C6372FEE3B4EED133F798A34B661B3D",0,null,"2014Y0011",-1,{"$nulls":75},"目前，已建成6.9公里，剩余路段已完成路基施工。","45825CCB00000021AE879AE5EFB9B065"]
["23EA9D144139164D38ADBC6D03E1D6F6",0,null,"2014Y0011",-1,{"$nulls":75},"目前，正在进行接线道路基层施工。","45830701A00000018662A81FE3FB2B60"]
["E277724F90E031CFDB1C22799BB3048C",0,null,"2014Y0011",-1,{"$nulls":75},"目前，正在进行路基施工。","4583086800000021610D57307F655C40"]
["8936F7611AC7821DD3C965CB479F95B6",0,null,"2014Y0011",-1,{"$nulls":75},"目前，桥梁主体建成。","47678C386000002118C05B3B7B3DACF5"]
["07FB5636F9046CD261E3392591EDB6D1",0,null,"2014Y0011",-1,{"$nulls":75},"开展下部结构施工。","494F86EDE00000215894D3EF8FBDFA9B"]
["D9043FAD12D696036DDFA33869A5A0D8",0,null,"2014Y0011",-1,{"$nulls":75},"完成路基填筑50%、涵洞68%、桥梁灌注桩55%。","48173F21C00000213849C18090E227D5"]
["BC710A55AAD65EEB3616E9EAA466EFAD",0,null,"2014Y0011",-1,{"$nulls":75},"完成综合稳定土。","48B15A89C0000021CEB0D93D0A59616D"]
["CBC4A0BEE45BFAFF851B485E7D5FD526",0,null,"2014Y0012",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28A8980000021D5A75D5DAF1B946B"]
["D11ED393DB44974709102F098544D7C5",0,null,"2014Y0012",-1,{"$nulls":75},"路基方面完成软基处理，基本完成路基土方填筑，完成涵洞、通道等小型构造物施工。桥梁方面已完成钻孔灌注桩、桥梁下部结构砼施工，桥梁上部现浇砼完成约60%，桥梁上部预制砼完成约85%。","44F92AE7400000C18C5FA6F58B9A0813"]
["ABB76AFB135F07456FF5170D6BCC0E52",0,null,"2014Y0012",-1,{"$nulls":75},"地下室完成，办公楼完成一层。","47EC671F00000001C8A65242F6D76C6C"]
["3665B81F983D2D52B8928D3585579984",0,null,"2014Y0012",-1,1,3,1,4600,4137,8100,{"$nulls":3},1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,1,2,1,4600,4137,8100,0,0,0,1,0,0,0,0,0,{"$nulls":15},"截止2014年5月  土石方开挖了31873万方，已完成总工程量的100%；底基层完成了4600平方米，已完成工程量的100%;基层完成了4137平方米，已完成工程量的100%,沥青完成了8100平方米，已完成工程量100%。本项目于2014年6月份已经建成完工。","44F92AE9600000E1EE7939B9B1929372"]
["133A0DD25EE853E564902EB6AB498ABC",0,null,"2014Y0012",-1,0,251,0,1002220,1053482,2741204,5,0,0,12,6,1,525,525,17699,0,251,0,1002220,1053482,2741204,0,100,100,0,0,0,525,525,17699,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,157,0,576525,630544,2498224,0,100,100,0,0,0,525,525,9782,{"$nulls":15},"形象进度：完成土方开挖1305992立方，占总量的100%；路基填筑1204064立方，占总量的100%；路面底基层10%灰土200444立方，占总量的100%,；水稳底基层1053482平方米，占总量的100%；路面沥青摊铺2741204平方米，占总量的100%。目前开工：312国道（龙华互通）至泰山新村段及328国道泰山新村到雍庄互通段，开工路段24.088公里，剩余328国道雍庄互通至龙池段尚未开工。现本项目一期工程（起点龙华广场，终点雍庄互通）已经完成交工验收并通车。","44F92AE9400000C1F580982CCF7AEF56"]
["60F3C27DDDA070FBF64AFF4E715FD9AC",0,null,"2014Y0012",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,180,null,502000,383000,33000,{"$nulls":4},62,{"$nulls":5},239,null,622171,604198,{"$nulls":5},88,{"$nulls":5},180,null,502000,383000,33000,{"$nulls":4},61,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["55D5F7230C6D76B6F100B38CA80796B9",0,null,"2014Y0012",-1,35,358,36,700600,700600,700600,1,0,0,10,118,0,0,0,25267,0,375,0,807813,751580,700600,0,0,0,10,118,0,0,0,30740,0,72,0,210180,455390,700600,1,0,0,1,0,0,0,0,7580,0,89,0,317393,506370,700600,0,0,0,1,0,0,0,0,5853,{"$nulls":16},"452C38D8A0000041215774BA7CEB1CEE"]
["8D859184EAEA83E8E26A8849BA44DE51",0,null,"2014Y0012",-1,15,601,15,307900,294500,285420,1,100,100,{"$nulls":6},11,578,11,304500,288850,282600,1,100,100,{"$nulls":7},125,null,13900,13450,61142,null,0,8,{"$nulls":7},102,null,10500,7800,58322,null,0,8,{"$nulls":21},"除终点倪胜利鱼塘外，全线贯通。","4A7F4412C0000001B5349862C0B620EE"]
["1D3AEB3F57D192D21912F79EB652635E",0,null,"2014Y0012",-1,{"$nulls":75},"浦口区老山4A级风景区连接线一表段工程（岔虎路）段已于2014年10月完工，二表段工程正在进行前期准备工作。","4979D47E20000021B8A53946C0B2654B"]
["91ACF2F65CEF7B370519EDAC52CFAA3B",0,null,"2014Y0012",-1,14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":5},14,65,14,88580,99014,91242,1,35,65,2,{"$nulls":7},14,null,9812,9132,{"$nulls":11},14,null,9812,9132,{"$nulls":25},"452C38D940000021B2C6170F6C9D6CB6"]
["BF7BF698AA9FC4D4692CA9E7838F6E8D",0,null,"2014Y0012",-1,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,16,186,16,363820,341847,306991,1,100,100,3,43,{"$nulls":3},6140,null,70,16,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,null,70,16,350820,328847,306991,1,70,null,3,{"$nulls":4},6140,{"$nulls":16},"44F92AE7000000A12EDFE72CF5A96603"]
["B4725D37A080AE75E2D96B4305CBE52F",0,null,"2014Y0012",-1,152,null,152,{"$nulls":12},108,null,108,{"$nulls":12},152,null,152,{"$nulls":12},108,null,108,{"$nulls":27},"目前农村公路已完成约108公里，完成投资38000万元","45A62941800000214B6E50365A9AF0C1"]
["A1FCE08DE2D47AB82F1D23C85000DA71",0,null,"2014Y0012",-1,25,1,25,30410,53630,108850,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":25},"45977C86A000000145F95B717A76C135"]
["138359953AE74FB10C997B0FA8B717BD",0,null,"2014Y0012",-1,{"$nulls":9},8,{"$nulls":14},6,{"$nulls":14},8,{"$nulls":14},6,{"$nulls":20},"已完成桥梁建设","45A62A6EC00000210FD9D03217C261AE"]
["0BBFE34B069834C5CB5F9CB30AECEE7A",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["59CB67FB65D75A038615742AC0F2B8C3",0,null,"2014Y0012",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["7489963E1D0715C2447D78F5E3C6DC0B",0,null,"2014Y0012",-1,41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},41,14,120,257011,1436401,1305854,{"$nulls":3},12,{"$nulls":5},41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},41,14,120,257011,1436401,1305854,{"$nulls":3},12,{"$nulls":20},"本工程已全面完工，工程形象进度内路面底基层设计总工程量填报错误，实际为257011，本年计划完成工程量也为257011。","459779F8800000211228699830C698E7"]
["032F19DA6F706EDFDD8FF348AB9CB600",0,null,"2014Y0011",-1,0,270,0,0,0,0,0,0,0,0,68,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成锦文路至江宁河段路基施工95%，完成桥梁施工90%","44F92AE9A0000001A6C4B4A0FE608B65"]
["36E5D8D6B3773BCDBD7FFDB1BB9BC015",0,null,"2014Y0011",-1,null,54,null,108277,104521,1053340,{"$nulls":69},"天元路至秣陵段建成通车。","45A64FE000000021EF20F17B8FB2A64B"]
["96DD9659F0F313117035DCC446A0E52B",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"隧道单洞累计掘进完成85%，墟沟互通主体工程已经完成。","44F92AE720000041FD47DFFCE454F006"]
["A815D3BD656E3BC1DFA7735BCCA0C03F",0,null,"2014Y0011",-1,{"$nulls":75},"货运中心完成进口大门地磅基础建设，完成综合配套区地下管道开挖，完成集装箱场站石料回填，正地基强夯。","468F5198A0000021390EE49ABE0B2CD5"]
["145BF0216F200D2278E31AAFFFCE71B1",0,null,"2014Y0011",-1,{"$nulls":75},"新海新区段完成路基、桥涵工程，路面完成下面层；马涧通道边坡治理标段已完成施工便道整理、道口封闭等临时工程正在进行北坡除险等；云台山景区段已完成驻地建设；云台互通段已完成驻地建设，K4+760~K4+950(190米）已完成红线边沟开挖及清表工作，开始路基填筑，K5+580~K6+300（720米）正在进行清表工作。烧香河至242省道段，海军农场境内路基贯通；其余段水稳全部完成，路缘石完成11公里，沥青封层全部完成，沥青完成4公里，附属工程完成85%，下穿通道完成85%，242省道以东段已建成。","44F92AE7E000004126A44C796491035A"]
["B05AC8BDD1399599CD73BC072A098AB3",0,null,"2014Y0011",-1,{"$nulls":75},"目前，正在进行明远路至京杭运河大桥段路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["3BC50938D6516741AA9FCA8454B3CA55",0,null,"2014Y0011",-1,10,28,10,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,null,28,null,52400,101700,101900,{"$nulls":3},3,37,{"$nulls":3},800,null,8,null,0,20700,20700,{"$nulls":3},0,37,{"$nulls":3},0,{"$nulls":16},"4597805440000021F0C8DA5D0BA9C78A"]
["574428E242465FB97B81CE222F5B8D3E",0,null,"2014Y0011",-1,{"$nulls":75},"工程已完工","46D1152460000001B5594EC6A47326C2"]
["3ADEC780ECF3CEB5DD186E28CA635011",0,null,"2014Y0011",-1,{"$nulls":75},"累计完成投资3.5亿元，占总投资4.2亿元的83%，其中年内完成投资2.5亿元，占年度计划3.2亿元的78%。年内折合进尺1700米，占年度计划2000米的85%，累计折合进尺2100米，占工程总长的84%。","46EBEFA560000021402F9981E1B1599D"]
["68277501BC4B30670CFCA57A555805C6",0,null,"2014Y0011",-1,{"$nulls":75},"阳澄湖西路至沈思港桥两侧慢车道路基基本完成，开始进行水稳基层摊铺，沈思港桥东半幅桥面完成，朝阳河桥西北侧已完成至台帽，西南侧正进行桥台施工，全线便道（除二标）贯通并已完成交通分流，开始主车道开挖施工。","4A04D699C0000021960B6C19775B7500"]
["A600139B4417B63010C45364562ADF44",0,null,"2014Y0012",-1,16,44,16,231375,237427,431077,2,100,100,3,82,0,0,0,36651,16,44,16,231375,237427,431077,2,100,100,3,82,0,0,0,36651,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,0,1,0,146460,237427,431077,0,65,55,0,0,0,0,0,36651,{"$nulls":15},"一、形象进度：目前施工已完成。路基清表44.1204万平方米（100%）、挖方44.1826万方（100%）、填方53.6535万方（100%）、路面底基层231375平方米（100%）、基层237428平方米（100%）、面层431077平方米（100%）；桥涵完成投资3260万元（100%）；防护工程3.6651万方（100%）；绿化工程完成1404万元（100%）；交通安全设施完成608万元（100%）；山体防护治理工程完成440万元（100%）。二、存在问题：无","44F92AE80000000125D8496C7290DDFC"]
["01F34B3D20A33F2157CC349948890AA5",0,null,"2014Y0012",-1,{"$nulls":75},"除桃乌段其余完工通车。","46EA9B7380000021C12E5F228EAB22B5"]
["EB3D28AD4C63C487BE27B07580734075",0,null,"2014Y0012",-1,{"$nulls":75},"完成桩基施工","46EA9FBB800000213459FE5A48F06D61"]
["D6A177F4239D8F3B67924D6ADF93FED0",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼工程、附属用房、停车场工程完成100%，综合楼底板施工完毕。附属设施、绿化工程完成100%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["021B4B9DF6D89E8E0210A69CA3A605E3",0,null,"2014Y0012",-1,4,null,4,{"$nulls":12},4,null,4,{"$nulls":12},2,null,2,{"$nulls":12},2,null,2,{"$nulls":27},"已完工通车","46EB7FD2000000217E9FB8B298777A5F"]
["2F5D7E52F0CAE226F804558168B083C7",0,null,"2014Y0012",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["CD973099C6984C4F40BFED7A93F0FA5D",0,null,"2014Y0012",-1,0,0,0,31,31,31,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"44F92AE8E0000021C00DEC218D9634A0"]
["15BBF6C5B92A995B517B8E5A773D54DF",0,null,"2014Y0012",-1,35,217,35,509221,517737,552131,2,100,100,30,61,1,560,560,142136,27,190,16,398864,385076,201726,2,100,100,26,60,0,400,120,120049,8,26,19,110357,132661,350405,0,0,0,4,1,1,80,240,26085,0,24,0,0,80000,0,0,0,0,0,1,0,80,200,23032,{"$nulls":15},"一标本月完成产值182.11万元，累计完成产值4.1240亿元,二标本月完成产值224.64万元，累计完成产值2.6063亿元,支线标本月完成72万元，累计完成产值3385.85万元.绿化标本月完成产值2300万元,总计完成产值约7917万元。存在问题：拆迁遗留问题，特别是新增连接线的征地拆迁，正在与金庭镇加紧沟通。\n\n","4592B501E000002123E927A043947D89"]
["4FF470F749811A7D4D3D6A3EEEC5CFBE",0,null,"2014Y0012",-1,14,330000,14,120000,120000,120000,0,0,0,0,26,0,0,0,null,7,180000,7,60000,60000,60000,0,0,0,0,6,0,0,0,null,7,30000,7,60000,60000,60000,0,0,0,0,6,0,0,0,null,7,30000,7,60000,60000,60000,0,0,0,0,6,0,0,0,{"$nulls":16},"目前实施的故黄河沿河干线公路丰县段一期工程近7公里，沥青砼面层的施工基本结束，正在进行附属工程及养护施工。目前主要存在的问题是资金问题，省补助和地方配套资金到位不及时，资金压力较大。","46B8AAA3A00000217140A795E7A1AE32"]
["7B16292E8B016F4707C6AC22FC92E1DD",0,null,"2014Y0012",-1,{"$nulls":75},"桥梁工程完工，接线路基完成100%。","494F759FA0000021B650A21A5A0C6724"]
["FAEE4D51DE7478DFD1DF8CC3EF998ADA",0,null,"2014Y0012",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,64,7,212700,335000,253500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,5,null,25000,32000,20000,{"$nulls":24},"道路工程基本完成，正在进行吴淞江大桥施工。","4597BDE880000021876F5E47FCCB44CC"]
["25115906A3090ED78F559B6DA14F1FD4",0,null,"2014Y0012",-1,101,65,101,692100,671900,651700,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["F26D23A195422CF9F8046DB47EB9BD34",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"除受部队影响的1.2公里外，其余路段建成。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["D9209AA9E52A735A8B0E4B035DD2FC2B",0,null,"2014Y0012",-1,{"$nulls":75},"基本完成路基及疏港航道以东段一期路面工程。","44F92AE7E000004126A44C796491035A"]
["F93AC6D086DD0AACDF37EE0BB1D62CB2",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已建成通车","44F92AE700000101C8E931F14C72B63C"]
["8D78A77484978789625523BD1C8724BF",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["1FA016058A356C7821267357CC96462E",0,null,"2014Y0011",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,837155,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,653170,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本项目已于2014年6月28日通过交工验收。","44F92AE8800000016600EFB6FA6DB838"]
["A98D00CC950CA148CC8D7ADAF393C65E",0,null,"2014Y0011",-1,34,490,34,110,90,248,3,0,0,0,102,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,6,125,6,19,16,44,0,0,0,0,45,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"晶桥段基本完成路面工程，\n白马段10.2公里进行路基施工，桥梁正在施工；\n剩余洪蓝至明觉段18公里正在进行清表工作","44F92AE780000001F6AE7427CA69104E"]
["168C244E673CA060F47CD240DC2F6F06",0,null,"2014Y0011",-1,19,1366000,19,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,437800,0,{"$nulls":3},0,{"$nulls":3},25,{"$nulls":4},0,null,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":4},0,437800,0,{"$nulls":3},0,{"$nulls":3},25,{"$nulls":19},"正在进行路基、涵洞桥梁施工，桥梁进行下部结构施工","45A630DD40000021758080AC865FC45B"]
["9A0474D42C92C33AB5B2EE9DDB44563C",0,null,"2014Y0011",-1,152,null,152,{"$nulls":12},82,null,80,{"$nulls":12},152,null,152,{"$nulls":12},82,null,80,{"$nulls":27},"目前农村公路已完成约80公里，完成投资37500万元","45A62941800000214B6E50365A9AF0C1"]
["797569F4A15FC47748715751AEC77764",0,null,"2014Y0011",-1,{"$nulls":9},8,{"$nulls":14},0,{"$nulls":14},8,{"$nulls":14},0,{"$nulls":20},"施工单位进场，进行下部结构施工","45A62A6EC00000210FD9D03217C261AE"]
["26ADF56C31C9241C45D619E3681763F3",0,null,"2014Y0011",-1,41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},38,12,78,203612,930212,916110,{"$nulls":3},3,{"$nulls":5},41,14,120,1436401,1436401,1305854,{"$nulls":3},12,{"$nulls":5},38,12,78,203612,930212,916110,{"$nulls":3},3,{"$nulls":21},"459779F8800000211228699830C698E7"]
["F3B84FA0C3CBCABEE4F9C0B714F3D6D5",0,null,"2014Y0011",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["4DC73D27B7222D58F01D99B8B86FDE2B",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["7B6EE41B811EC6CCCC9032C197AE1A2B",0,null,"2014Y0011",-1,{"$nulls":75},"（1）路基：软土地基处理已完成；土石方填筑266.29万方，占总量（288.33）的93.64%。\n（2）小型结构物：累计完成管涵65道,占总量（68）的95.59%。\n（3）桥梁工程：钻孔灌注桩完成5143根，占总量（5223）的98.47%；桥梁上部预制砼安装完成3240片，占总量（4932）的65.69%。","44F92AE7400000C18C5FA6F58B9A0813"]
["4DAB8BEE41B64EE6834B80EF3FE3DB9E",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"铁路专用线施工、装卸设备购置等。","452C38D9200000A160383FB696401BD8"]
["7FF7225CFE40FEC3FFBA8BA08C2BFDB0",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["F132635C0AA5BA2324CAA6ED5BA2A35C",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主桥已合拢，正在进行引桥的箱梁预制和安装工作，预制完成80%，安装完成50%。","44F92AE700000101C8E931F14C72B63C"]
["9A6F99F389CB861E99A07EEFAFC50CA8",0,null,"2014Y0011",-1,25,1,25,30410,53630,108850,{"$nulls":9},20,1,20,30410,48630,808850,{"$nulls":9},25,1,25,30410,53630,108850,{"$nulls":9},20,1,20,30410,48630,808850,{"$nulls":25},"45977C86A000000145F95B717A76C135"]
["AD4D4D9260DE636233F93669A87B477D",0,null,"2014Y0011",-1,{"$nulls":75},"基本完工。","46D12277000000016E90CB741749DE83"]
["08E3B3D153EF4BA938E0CA3AE9C0A22B",0,null,"2014Y0011",-1,{"$nulls":75},"西防波堤工程年内进尺2500米，占年计划2200米的114%，累计进尺2500米，占总长9562米的26%。","46D12756A00000212A79E7CE74664FD9"]
["7445261A3A2ABF883D3DE6FF0372FB82",0,null,"2014Y0012",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28726E0000021457D777E03877DDB"]
["E4D9D81AE1E7008E8DC63768595D5C05",0,null,"2014Y0012",-1,{"$nulls":75},"项目施工正常。","495AB173C0000021BD1078AE8F558A41"]
["ACC9701AC57EB32774365264CD6D6F55",0,null,"2014Y0012",-1,{"$nulls":75},"完成路基处理66%、底基层50%、涵洞20%。","48171CB940000001DAB3F475A2461DC6"]
["3BA46C6C96AC9621F506FB3F682E6A62",0,null,"2014Y0012",-1,{"$nulls":75},"除拆迁影响段落，主线机动车道完工通车，人行道板铺设完成，非机动车道沥青铺设完成。","46EA9A9840000021E67762482E18105E"]
["97A3E8D08B19254643D4D5F59E0F31E9",0,null,"2014Y0012",-1,{"$nulls":75},"全幅板块处理完成，水稳完成70%，沥青下面层完成70%，桥梁工程完成80%。","46EA9D51A0000021F1A72CD5283EA913"]
["EC8FF4197F8DE81310C8F89A271DE46E",0,null,"2014Y0012",-1,{"$nulls":75},"完工通车。","46EA9EFBA0000021C04603F2E53ED447"]
["7EFF4A6AFB7A15FE773BAC8A4EC65A06",0,null,"2014Y0012",-1,{"$nulls":75},"完工通车。","4A613592E000002194B46D647ABA77F9"]
["8F4C812DFE09983A660CE6CC3FA379F0",0,null,"2014Y0012",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["B145531EB3E79BD2BDC153241DAC670A",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已建成","44F92AE8C00000C150E871A6EE092CCD"]
["145E7B2883863FFCB69C3EF375FB1463",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已全部完工,开始试运行。","44F92AE7800000C16F0E702CC0B514F4"]
["D91FFD02CF3FCE8A3FC343BB646D66DD",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"工程已完成灌注桩980根、平整场地3万平方、安装吊机6台、吊机平台2座，办公楼主体已封顶，工程已全部建成。","452C38DDE00000411468534B18F06C9C"]
["9EC2BA5CC354CE826C1FE17C91C26343",0,null,"2014Y0012",-1,{"$nulls":75},"工程已全部完成。","49E4B51280000021B30873068C3DFF72"]
["FEF6ACC746DE512BBC6B248EF6BC748C",0,null,"2014Y0012",-1,8,51,8,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":3},15413,null,51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":5},51,null,211000,184000,176000,{"$nulls":3},3,47,{"$nulls":20},"452C38D6600000415991C5B8B7842E8C"]
["E149C0B1FF94FADA89B7F03FD56EC555",0,null,"2014Y0012",-1,5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":27},"工程建成通车，完成投资1720万。","4965922940000021CADEE47D6F615CD4"]
["382A1D596AAF0437420B5FE8E263951F",0,null,"2014Y0012",-1,6,null,6,{"$nulls":6},1,10,{"$nulls":4},6,null,6,{"$nulls":6},1,10,{"$nulls":4},6,null,6,{"$nulls":12},6,null,6,{"$nulls":28},"481F8414E000002108EA911A0B7CCB27"]
["3D74707058D3984F6495121691469320",0,null,"2014Y0012",-1,36,503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":5},503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":7},929179,849170,890542,{"$nulls":12},929179,849170,890542,{"$nulls":24},"完成全部工程，开展各专项交工验收工作。","452C38D9600000C17C36891B54B019E8"]
["0001F0B5459D79D275149214858B2779",0,null,"2014Y0012",-1,5,null,5,{"$nulls":3},1,null,null,2,{"$nulls":5},5,null,5,{"$nulls":3},1,null,null,2,{"$nulls":5},5,null,5,{"$nulls":3},1,null,null,2,{"$nulls":5},5,null,5,{"$nulls":3},1,null,null,2,{"$nulls":21},"481F974900000021C1E3E41AB2DFDD19"]
["A28A79E846C9EEB55B91EDA45F3F0C37",0,null,"2014Y0012",-1,36,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,null,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,null,47,null,448217,403072,1904815,null,59,9,null,4,{"$nulls":3},67697,null,47,null,448217,403072,1904815,null,59,9,null,4,{"$nulls":3},67697,{"$nulls":15},"完成全部工程，完成房建、机电工程、档案专项交工验收工作。","452C38DCA00000A1BDA9E5BD6348A13E"]
["2732D71430A8F990B15ED4EB66994846",0,null,"2014Y0011",-1,24,339,24,652423,590283,564435,2,50,50,11,79,0,0,0,0,0,14,0,0,0,0,0,50,50,0,0,{"$nulls":5},20,0,0,0,0,0,0,20,0,2,{"$nulls":5},18,0,0,0,0,0,0,0,0,0,{"$nulls":19},"一标：清表驻地建设完成；二标便道碎石土回填，河塘清淤，回填碎石土。","45A64AD8E000002115357ED0397AE2AC"]
["B3F5C6FD6656CECC949BB5C6D78ADE80",0,null,"2014Y0011",-1,{"$nulls":75},"完成农村公路建设89公里","45A643D5200000210231D09FB0198FE4"]
["9EC24FD952B11CBF39162AD9EDC82B72",0,null,"2014Y0010",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,139132,798812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,32590,63000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成一期工程（马群至双龙街）13.7公里主线改造、万家楼互通马群换乘中心匝道、钟学北路互通、石杨路互通、双麒路互通建设；二期工程（花神庙至刘村）7.1公里主线改造、凤翔山庄及风翔村景观墙建设、五百户村及双龙街声屏障建设、铁心桥至油坊桥段2.5公里青奥景观带建设、铁心桥规四路至贾东地块1.8公里辅道建设、友谊路桥及黄河路桥建设、黄河路互通建设，完成马群至天保桥段绿色通道建设，完成全线监控设施工程建设，完成绕城公路沿线（环陵路至江山大街）景观照明工程建设。累计土石方160.0万方，路面底基层16.5万平米，基层13.9万平米，面层79.9万平米。本月完成投资2000万元，本年累计完成13000万元，累计完成178090万元。              \n二、存在问题：1、目前工程建设基本是在国有储备土地上实施，征地拆迁工作除雨花区段外，其它段落尚未实质性进展。\n    ","44F92AE8400000A1F8CD4F6E58802DB5"]
["E53C840CB1E9B01800A314BCFF45A0CA",0,null,"2014Y0011",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,139132,798812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,32590,63000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成一期工程（马群至双龙街）13.7公里主线改造、万家楼互通马群换乘中心匝道、钟学北路互通、石杨路互通、双麒路互通建设；二期工程（花神庙至刘村）7.1公里主线改造、凤翔山庄及风翔村景观墙建设、五百户村及双龙街声屏障建设、铁心桥至油坊桥段2.5公里青奥景观带建设、铁心桥规四路至贾东地块1.8公里辅道建设、友谊路桥及黄河路桥建设、黄河路互通建设，完成马群至天保桥段绿色通道建设，完成全线监控设施工程建设，完成绕城公路沿线（环陵路至江山大街）景观照明工程建设。累计土石方160.0万方，路面底基层16.5万平米，基层13.9万平米，面层79.9万平米。本月完成投资2000万元，本年累计完成13000万元，累计完成178090万元。              \n二、存在问题：1、目前工程建设基本是在国有储备土地上实施，征地拆迁工作除雨花区段外，其它段落尚未实质性进展。\n    ","44F92AE8400000A1F8CD4F6E58802DB5"]
["DFD7B8270167F90074904D5F5C015141",0,null,"2014Y0011",-1,14,330000,14,120000,120000,120000,0,0,0,0,6,0,0,0,null,14,180000,7,120000,120000,100000,0,0,0,0,6,0,0,0,null,14,180000,14,120000,120000,120000,0,0,0,0,0,0,0,0,null,7,30000,7,20000,120000,100000,0,0,0,0,0,0,0,0,{"$nulls":17},"46B8AAA3A00000217140A795E7A1AE32"]
["324410E7629E884B796073A4B2E2C058",0,null,"2014Y0011",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["A1DDCB722CCC5BEABEABC7B2C2380637",0,null,"2014Y0011",-1,{"$nulls":75},"完成征地拆迁工作及部分路基。","48A6EC29E000000142F6B2638633E8C1"]
["5A8263990F281468793F76733574988F",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已完工","452C38D6000000A1FC3424893CE810BC"]
["C32BB0BBB37DD9A9B59D7E4892417C26",0,null,"2014Y0011",-1,{"$nulls":75},"2个泊位水工主体主体基本建成","46D11FD040000021CBCE7B927205F9C4"]
["5995F82A216BBD4F70E92CC2F3A18CC4",0,null,"2014Y0011",-1,{"$nulls":75},"   车船直取工程完工；液化罐区pcc桩基施工总量约4200根，完成3700根，化工品罐区18个储罐，完成制作安装14个\n","46D12095E00000210EEE5BA374F2A089"]
["7A46425EFAE9DAD8A91D7D84BE87179E",0,null,"2014Y0011",-1,{"$nulls":75},"东斜坡堤工程年内折合进尺2100米，占年计划3000米的70%，累计进尺5300米，占总长7834米的68%。","452C38DA800000A19C9699F0088370B9"]
["58F3C94B564D09E0E058C4EEB8662A05",0,null,"2014Y0011",-1,{"$nulls":75},"建元路路至太东路除京沪高铁段下穿段主体完工。","4A0435E7A0000021E23AE18A8582F231"]
["F0C86421A65DD4091E81AA8E25E86D58",0,null,"2014Y0012",-1,{"$nulls":75},"现场原沥青路面的主车道改造已经基本完成，右幅拓宽部分进行水稳施工，裴家圩桥南侧下部结构北侧11根灌注桩、1号桥南侧桥面铺装、孙家桥桩基及2号桥下部结构已完成。","4A04B92BC000006128D10F788349E5BC"]
["D09C2666C5DA63E1E425F2283BDD604F",0,null,"2014Y0012",-1,{"$nulls":75},"完成桥梁下部结构。","494F86EDE00000215894D3EF8FBDFA9B"]
["CD4C07531F6868E538BE33052C163ED8",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["3A73825078C5E78D40606A30C69CEE84",0,null,"2014Y0012",-1,{"$nulls":75},"全线建成通车。","452C38DA40000161563DFD045D6A3673"]
["F8C7B91F895686DFE813DA8F89DB024B",0,null,"2014Y0012",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,5,55,5,105014,111070,113964,1,0,0,0,18,0,0,0,1900,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：340省道路线全长42.887公里，其中溧水段17.77公里，江宁段25.117公里。目前本项目按阶段实施建设。第一段：溧水先导段4.6公里于2012年8月开工建设，2013年9月建成通车；第二段：江宁横溪段和溧水段。2014年计划新开20公里，目前已完成江宁横溪段的施工、监理招投标，并完成了项目部的组建工作，由于征地拆迁等原因还未进场施工；溧水段完成了招标准备工作，发布了招标公告；第三段：江宁禄口段正进行施工图设计工作。\n二、存在问题：目前横溪段（13.68公里）江宁区政府启动了征地拆迁工作，已完成土地丈量、房屋拆迁调查工作，正在进行杆管线迁移调查。指挥部配合开展红线放样和路田分家工作，施工单位也开展驻地建设和测量放样复核等施工前准备工作，待江宁区政府提供建设用地后随时开展施工工作。\n","452C38DB00000021D4253F83097D6579"]
["0D8EFCCE11A3C8139203A3B6D79298F7",0,null,"2014Y0012",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,624,10,972000,1015500,2150300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,20,0,12000,980400,144900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"路基：土石方开挖355.8万立方（95.9%）,土石方填筑273.3万立方（96.1%）;路面：基层（160mm、320mm、340mm厚水泥稳定碎石）101.55万平方（89.7%)，底基层（200mm厚12%灰土）97.25万平方（85.9%)，面层（80mm、60mm、40mm厚沥青）215.23万平方(90.4%);桥梁：31080万元（79.2%）；交安：1500万元（51%）；绿化：4600万元（86.4%）。","44F92AE840000101423CCFA36BCE2089"]
["B4C742C0C54C7EBA9F3493EA4597EDB5",0,null,"2014Y0012",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,640,0,0,0,0,0,0,0,0,138,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,400,0,0,0,0,0,0,0,0,75,0,0,0,0,{"$nulls":15},"完成汤山至湖熟段路基施工100%，路面施工100%,完成梁板浇筑7片。征地拆迁费用支付350万。","44F92AE9800000A15AC5660EDAD7D017"]
["F999986199EAC655758131F5DD459177",0,null,"2014Y0012",-1,0,270,0,0,0,0,0,0,0,0,68,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,0,200,0,0,0,0,0,0,0,0,0,0,0,0,0,0,255,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成锦文路至江宁河段路基施工100%，完成桥梁施工100%","44F92AE9A0000001A6C4B4A0FE608B65"]
["DEFC76A193CB2E146F1798837548E9C0",0,null,"2014Y0011",-1,101,65,101,692100,671900,651700,{"$nulls":10},65,54,692100,470320,234640,{"$nulls":9},101,65,101,692100,671900,651700,{"$nulls":10},65,54,692100,470320,234640,{"$nulls":25},"45A62BF5200000210FE3D7CC09691BA2"]
["82890CB27E0FD3E8E4D08E58E86C48C8",0,null,"2014Y0011",-1,{"$nulls":75},"码头水工完成，一台门机安装调试结束。陆域基层施工完成。","45B27FD3A0000001E7A4DAE02DD98961"]
["EA6493CF56976329267700AD59AC8AA4",0,null,"2014Y0011",-1,{"$nulls":75},"码头施工结束，工艺管线安装。","45B28726E0000021457D777E03877DDB"]
["6319D079ECC2CF4098688CC55D8DE059",0,null,"2014Y0011",-1,0,0,0,0,2023895,1913509,0,0,0,0,229,0,0,0,0,0,640,0,0,0,0,0,0,0,0,138,0,0,0,0,0,0,0,0,0,0,0,0,0,0,null,0,0,0,0,0,400,0,0,0,0,0,0,0,0,75,0,0,0,0,{"$nulls":15},"完成汤山至湖熟段路基施工90%，路面施工70%,完成梁板浇筑6片。征地拆迁费用支付1150万。","44F92AE9800000A15AC5660EDAD7D017"]
["6F24B3BE2690BF77F6836E46397534C4",0,null,"2014Y0011",-1,1,null,1,3500,3500,3500,{"$nulls":69},"已完成设计招标工作，目前正在开展征地拆迁和施工准备。","49799B6500000001CDC755BA5B4F4D55"]
["845178B109EDD82EDD673A7B355D8EBF",0,null,"2014Y0009",-1,37,774,14,875953,815956,3476561,12,0,0,63,93,0,0,0,0,25,160,0,165060,139132,798812,0,0,0,5,24,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,20,0,22910,32590,63000,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：完成一期工程（马群至双龙街）13.7公里主线改造、万家楼互通马群换乘中心匝道、钟学北路互通、石杨路互通、双麒路互通建设；二期工程（花神庙至刘村）7.1公里主线改造、凤翔山庄及风翔村景观墙建设、五百户村及双龙街声屏障建设、铁心桥至油坊桥段2.5公里青奥景观带建设、铁心桥规四路至贾东地块1.8公里辅道建设、友谊路桥及黄河路桥建设、黄河路互通建设，完成马群至天保桥段绿色通道建设，完成全线监控设施工程建设，完成绕城公路沿线（环陵路至江山大街）景观照明工程建设。累计土石方160.0万方，路面底基层16.5万平米，基层13.9万平米，面层79.9万平米。本月完成投资2000万元，本年累计完成13000万元，累计完成178090万元。              \n二、存在问题：1、目前工程建设基本是在国有储备土地上实施，征地拆迁工作除雨花区段外，其它段落尚未实质性进展。\n    ","44F92AE8400000A1F8CD4F6E58802DB5"]
["790E97F8B70A4A076A2D4286EE648027",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"I标段24万平方米停车场施工；办公楼内装基本完成。","452C38D960000061A773E74DF5A30C52"]
["38FF01100048A63E51D0BE028491C4C1",0,null,"2014Y0011",-1,{"$nulls":75},"快车道施工完毕,已开放通车，正在施工慢车道。","452C38DA40000161563DFD045D6A3673"]
["6B27927166B90AD7017EACD596DAFF4D",0,null,"2014Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"已累计建成纵五路至南复堆河段及纵一路段22.8公里，剩余4.7公里因与连云港港口连接线工程线位较近，正在进行路线方案研究。","452C38DA80000041BB1AF46EF3FAECC2"]
["B914FEF29E160E590F14929D6A8647A8",0,null,"2014Y0011",-1,{"$nulls":75},"水工主体基本完工","46D1249420000001088D6938CA880F4D"]
["17CDC03D98D3B776CB58B2A864FA36BB",0,null,"2014Y0011",-1,{"$nulls":75},"工程主体完工，铁路工程主体完工；接轨方案审查会于8月15日在上海路局召开。\n","46D11DA8E0000021390F8E6CD9239F6A"]
["423125717C7AD97E932729B4E0E7E582",0,null,"2014Y0011",-1,{"$nulls":75},"水工工程扫尾，K0以东挡墙及后方开山石回填完工。7-14#泊位后方道堆、变电所及其它附属设施完工，综合办公楼施工；装卸设备、电缆等购置。","46D11E59C00000215FEEE684519DC4AA"]
["622824F74D7CF053688BE87E881DC8B9",0,null,"2014Y0011",-1,{"$nulls":75},"浦口区老山4A级风景区连接线一表段工程（岔虎路）段已于2014年10月完工，二表段工程正在进行前期准备工作。","4979D47E20000021B8A53946C0B2654B"]
["E2FDFC38DF21D2F98D70F987F9A21C9F",0,null,"2014Y0012",-1,{"$nulls":75},"建元路路至太东路主体完工。","4A0435E7A0000021E23AE18A8582F231"]
["2A32919A53D5618D0DACD25D4FBB2270",0,null,"2014Y0012",-1,{"$nulls":75},"剩余部分待建工程，其他已全部交工验收。","45B26F0B8000002123F9B996453503FA"]
["C9D9B82CA45CBDC75DB5DAAE8BCC1598",0,null,"2014Y0012",-1,{"$nulls":75},"完成征地拆迁、场地平整、围墙砌筑。","44F92AE7C000008151CBB288EBA76DE4"]
["528991392E071D7C87933B16403370DC",0,null,"2014Y0012",-1,{"$nulls":75},"项目建成通车。","477AAD380000002159DCBA91BD5FA484"]
["E080206DAB17756865462DF4EA9FB8D0",0,null,"2014Y0012",-1,{"$nulls":75},"集散中心已封顶，正在室内安装工程，仓储中心B2钢结构封顶，正在进行墙板安装，集散中心B1主钢结构封顶，正在进行次结构吊装，综合楼框架封顶，正在进行墙体砌筑。","4A09BB5320000021A7468129AEC6112D"]
["C5AF4C25D703D875580E9D3B746F0166",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头后方道路、堆场硬化、管网、电力供应等已部分完成，目前正在进行卡口幕墙及口岸大楼主体施工。已建成仓库二个，配套办公用房主体建设及外装正在进行。码头水工下部结构正在进行基坑开挖及后方回填。","44F92AE800000121D51AC7AB782D4663"]
["273C9C215CCA9932B324548B7401ABDF",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"基本完成水工结构物施工,完成后方堆场30%，完成装卸设备加工50%。","44F92AE9000000A114EC34ECCE42A6E8"]
["FB84ABB101CFE808C16244ED8DBBCF91",0,null,"2014Y0011",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,{"$nulls":16},"44F92AE8200000012E397C1249910A7C"]
["EA1E4275AD564E29306D6202D351D9C6",0,null,"2014Y0012",-1,24,201,24,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,201,0,480019,477196,2031526,4,0,0,8,102,0,0,0,2231,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,0,0,0,0,0,624526,4,0,0,8,0,0,0,0,0,{"$nulls":15},"项目已建成通车。","44F92AE8200000012E397C1249910A7C"]
["8C0C2D4971DBD47CCB41B921ACD363A0",0,null,"2014Y0012",-1,{"$nulls":75},"完成农村公路建设90.6公里","45A643D5200000210231D09FB0198FE4"]
["B293F71DB8F55E8DA279D6DE7AB099D4",0,null,"2014Y0012",-1,24,339,24,652423,590283,564435,2,50,50,11,79,0,0,0,0,0,20,0,0,0,0,0,50,50,0,0,{"$nulls":5},20,0,0,0,0,0,0,20,0,2,{"$nulls":5},20,0,0,0,0,0,0,0,0,0,{"$nulls":20},"45A64AD8E000002115357ED0397AE2AC"]
["0FBA2DC840D8FA14D8B07B5BE3E44AF5",0,null,"2014Y0012",-1,16,121,0,287625,433000,834000,0,0,0,7,91,0,0,0,0,0,105,0,245000,433000,837155,0,0,0,7,91,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,3,0,21850,157280,653170,0,0,0,0,0,0,0,0,0,{"$nulls":15},"本项目于2012年11月正式开工建设，于2014年6月28日交工并通车。","44F92AE8800000016600EFB6FA6DB838"]
["B162F83F1C405E9683693ABED543452D",0,null,"2014Y0012",-1,36,519,null,965,852,930,9,100,100,17,164,{"$nulls":3},21300,null,519,null,965,555,null,8,100,100,17,164,{"$nulls":3},21300,null,53,null,965,510,null,8,31,23,17,{"$nulls":4},21300,null,53,null,965,555,null,8,28,23,17,{"$nulls":4},21300,{"$nulls":15},"完成路基、桥涵工程及路面底基层施工，完成65%的基层施工，基本完成房建主体工程。","452C38D720000081C14CEFA6969A8D06"]
["A004AEC0E1CC1912DB8E4639ED792D47",0,null,"2014Y0012",-1,5,95,5,208954,196309,573301,4,100,100,5,26,{"$nulls":3},4978,{"$nulls":61},"452C38DBA0000101EE35873CD541EA02"]
["0E8C673FBA8EE8A9854236CE6E20DE72",0,null,"2014Y0012",-1,{"$nulls":75},"目前，已基本建成。","4582F984A00000210B371656660E7377"]
["241095134DD061F2315DD225465EC68E",0,null,"2014Y0012",-1,{"$nulls":75},"目前，桥梁建成。","45830129E0000021F3EEA0D7E47483E6"]
["5D417793E777A3D036129D37853B8E0E",0,null,"2014Y0012",-1,{"$nulls":75},"目前，已建成通车。","458307CAE00000414A3628960FD10AB2"]
["E2EA6E995FD9AB1859B537873E009D12",0,null,"2014Y0012",-1,{"$nulls":75},"目前已建成。","4583097620000021C29C88DEA1D39A75"]
["96379D100EA1B54A458563AC5E4D4CAD",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地拆迁及路基填筑。","452C38DA80000041BB1AF46EF3FAECC2"]
["B1250D875819FA181EEAEF0480C183E6",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"因资金短缺，目前处于停工状态。","452C38DB200000A1415A7142D9E7FC04"]
["74D07FF3024130DB19F1A2830AC95CF5",0,null,"2014Y0012",-1,{"$nulls":75},"完成招标","494F9423E0000021971B8B67E472FD4B"]
["E2E2CBB6F651CBF0B70EA8150B97C6E8",0,null,"2014Y0012",-1,{"$nulls":75},"目前桥梁已建成。","458302B080000021E4D2CC5B2F4B6514"]
["ACAA12634DC6CEBD7266F8B28B69CE38",0,null,"2014Y0012",-1,{"$nulls":75},"目前，桥梁已建成。","47678A76C0000021CA6C39AAC7090030"]
["989F009F30AF795881FC7B70599C75AE",0,null,"2014Y0012",-1,{"$nulls":75},"目前，桥梁建成。","47678C386000002118C05B3B7B3DACF5"]
["D21CC09CC20B46369A37CA142B1A7A97",0,null,"2014Y0012",-1,{"$nulls":75},"东斜坡堤工程年内折合进尺2100米，占年计划3000米的70%，累计进尺5300米，占总长7834米的68%。","452C38DA800000A19C9699F0088370B9"]
["AC062B78CC2FCFA2918CCBC49E41948D",0,null,"2014Y0012",-1,{"$nulls":75},"西防波堤工程年内进尺2500米，占年计划2200米的114%，累计进尺2500米，占总长9562米的26%。","46D12756A00000212A79E7CE74664FD9"]
["855DD4D2F97404461664D7BE9FE5D54A",0,null,"2014Y0012",-1,{"$nulls":75},"工程主体完工，铁路工程主体完工；接轨方案审查会于8月15日在上海路局召开。\n","46D11DA8E0000021390F8E6CD9239F6A"]
["3523074C475200F11034BA0409AAF485",0,null,"2014Y0011",-1,43,395,43,1269900,998375,1031050,1,100,100,19,179,0,0,0,10000,43,395,43,1269900,998375,1031050,1,100,100,19,179,{"$nulls":3},10000,21,10,14,332520,164353,240080,1,17,0,2,5,0,0,0,1795,21,10,14,332520,164353,240080,1,17,0,2,5,{"$nulls":3},1795,{"$nulls":15},"形象进度：全线工程基本完成","464AE174E0000021897F83B2DBD33160"]
["A55C559AD607EA2F41F89DDC8FBD6084",0,null,"2014Y0011",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":15},"全线已完成","464AE565800000215C9C09C8A0BE8932"]
["A0A75AC6A85BFB3151217421282CC003",0,null,"2014Y0012",-1,43,395,43,1269900,998375,1031050,1,100,100,19,179,0,0,0,10000,43,395,43,1269900,998375,1031050,1,100,100,19,179,{"$nulls":3},10000,21,10,14,332520,164353,240080,1,17,0,2,5,0,0,0,1795,21,10,14,332520,164353,240080,1,17,0,2,5,{"$nulls":3},1795,{"$nulls":15},"形象进度：全线工程基本完成","464AE174E0000021897F83B2DBD33160"]
["61D09A0C56EC4E92A86139D876B49564",0,null,"2014Y0012",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":15},"全线已完成","464AE565800000215C9C09C8A0BE8932"]
["B63F243B305576C9641169A2B67B36D6",0,null,"2014Y0012",-1,8,147,8,273694,273694,273694,1,100,100,4,11,{"$nulls":3},6498,2,99,1,19230,19159,19159,{"$nulls":3},0,8,{"$nulls":3},0,8,81,8,254464,258507,272326,null,100,100,4,7,{"$nulls":3},6498,2,33,1,3972,17791,{"$nulls":4},0,4,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1-4标段已进场，1-3标正在开展污水管线、河塘清淤、软基处理、路基填筑、桥涵及水利大坝等施工，4标正开展路面底基层和基层施工，5标已定标。","464AEA1FC0000021B52E367C631B2D38"]
["C6DC3D41E56956AF5836131C38BA83CE",0,null,"2014Y0012",-1,{"$nulls":75},"推进前期工作，完成征地拆迁。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["4956C62916896D91A4406B4FA5017282",0,null,"2014Y0012",-1,{"$nulls":75},"因选址问题，尚未开工。","4A943350E0000001A6DE703711B423A7"]
["848B2F40FF3A010B8D8D2A813FC7F9C1",0,null,"2014Y0012",-1,{"$nulls":75},"因选址问题，尚未开工。","4A954A9DA0000001C7610DB35073150F"]
["1313844C43C281BCF99AEB1E104A95ED",0,null,"2014Y0012",-1,{"$nulls":75},"完成征地拆迁，完成路基处理90%、构造物100%。","4A98BD0D800000212D60BD89CB35D858"]
["796C180A57646111255282E4643D5CB5",0,null,"2015Y0001",-1,{"$nulls":75},"开展征地拆迁。","44F92AE7C000002175F300290A52D82C"]
["BA904F345E5B5B7832F358E0ECB92CF7",0,null,"2015Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,27,166,16,398864,305076,201726,2,100,100,26,59,0,320,-80,97017,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一标本月完成产值87万元，累计完成产值4.1327亿元,二标本月完成产值224.64万元，累计完成产值2.6063亿元,支线标本月完成295万元，累计完成产值3787.19万元.绿化标本月完成产值1300万元,总计完成产值约9217万元。存在问题：基本没有问题.","4592B501E000002123E927A043947D89"]
["806747B71783B1D2C8FF595B9BE0C166",0,null,"2015Y0001",-1,36,519,null,965,852,930,9,100,100,17,164,{"$nulls":3},21300,null,519,null,965,555,null,8,100,100,17,164,{"$nulls":3},21300,null,53,null,965,510,null,8,31,23,17,{"$nulls":4},21300,null,53,null,965,555,null,8,28,23,17,{"$nulls":4},21300,{"$nulls":16},"452C38D720000081C14CEFA6969A8D06"]
["4374E2A40858566BBA8742234088FBDC",0,null,"2015Y0001",-1,{"$nulls":75},"路基：已完成软基处理，预压土完成68.35万方，占总量的99.34%。桥梁：已基本完成钻孔灌注桩、桥梁下部结构砼施工，桥梁上部现浇砼完成约60%，桥梁上部预制砼完成约80%；防撞护栏完成27.77%。","44F92AE7400000C18C5FA6F58B9A0813"]
["709C960613CEC694C972C124EAEED7B4",0,null,"2015Y0001",-1,36,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,null,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,{"$nulls":46},"452C38DCA00000A1BDA9E5BD6348A13E"]
["82D962A2BDDF72744797898A152A9D66",0,null,"2015Y0002",-1,{"$nulls":75},"集散中心已封顶，进行各项收尾工作，正在室内安装工程，仓储中心B1/B2钢结构封顶，正在进行墙板安装和楼层板混凝土浇筑，综合楼框架封顶，进行幕墙安装。","4A09BB5320000021A7468129AEC6112D"]
["D98B5E73AF3A48240EA98A5E1A83037D",0,null,"2015Y0002",-1,7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":21},"481FB13480000021DF891907B35F942C"]
["0574C51C71916C0C4A21E63A9BDC7DC8",0,null,"2015Y0002",-1,34,490,34,{"$nulls":3},3,{"$nulls":3},102,{"$nulls":4},17,178,6,{"$nulls":3},0,{"$nulls":3},50,{"$nulls":4},17,280,10,{"$nulls":3},0,{"$nulls":3},52,{"$nulls":4},0,0,0,{"$nulls":3},0,{"$nulls":3},0,{"$nulls":19},"本月基本无","44F92AE780000001F6AE7427CA69104E"]
["9CB29DDC9D594700DADBE6D906BCCFDA",0,null,"2015Y0002",-1,{"$nulls":75},"完成部分水工结构。","497EC8FBA00000219339AD552530ADAF"]
["D05B3F38AADBE839FE5B524A8866D8B9",0,null,"2015Y0002",-1,{"$nulls":75},"尚未开工。","4B2FD99E000000217EF51296349F80B0"]
["D7987ED52F03817F3BB4B0FFB80B7005",0,null,"2015Y0002",-1,{"$nulls":75},"尚未开工。","4B2FE5AB600000211F6D440BC42C931E"]
["1CE33991143BA547C7190C08DE375CCA",0,null,"2015Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["8DF33151E4789BB70E3C721757BC1EA8",0,null,"2015Y0002",-1,{"$nulls":75},"未开工","4596D75C6000002113AB2207297BA0CF"]
["B458F14CA7A641FF6A19AAB24E79349B",0,null,"2015Y0002",-1,{"$nulls":75},"建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["0B7A59AFFCB52BD299CCB3160059D8DA",0,null,"2015Y0002",-1,{"$nulls":75},"主车道老路范围沥青下面层完成，右幅拓宽段进行平侧石施工，左幅拓宽段进行路基土方施工；裴家圩桥完成右幅铰缝浇筑、左幅下部结构，1号桥完成右幅桥面铺装及中幅台帽、孙家桥及2号桥完成下部结构。","4A04B92BC000006128D10F788349E5BC"]
["BE6A27EF0B955DE9E4C8C7A27A8CFF6E",0,null,"2015Y0001",-1,7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":21},"481FB13480000021DF891907B35F942C"]
["D1C893165EFB9EAAFB6765B7F182F7D9",0,null,"2015Y0002",-1,{"$nulls":75},"立交部分：全部完成，                  道路部分：桩基248根（100%），承桥台15只（94%），立柱96（100%），盖梁40榀（100%），空心板梁544片（94%）；           湿喷桩165000米（100%），石灰土160000m3（89%），水稳43000吨（61%），沥青15000吨（50%）","4568470820000021D98D8A6D5DA358BA"]
["DE7310403AB660FDD01A18A3F2DC295B",0,null,"2015Y0002",-1,{"$nulls":75},"三层施工","4A286098C00000211684976214B403C2"]
["33E8EE50F0F1E8680EF86021DCD1AA5D",0,null,"2015Y0002",-1,3,44,8,114650,107100,202540,3,100,100,null,20,{"$nulls":3},1280,3,44,null,114650,107100,null,null,92,100,null,20,{"$nulls":3},640,null,2,null,114650,107100,null,null,60,23,{"$nulls":5},800,null,2,null,114650,107100,null,null,63,23,{"$nulls":5},640,{"$nulls":16},"497E9E23600000218DA200E95CCB2352"]
["2837266B1949347258065B719D9FAA6B",0,null,"2015Y0002",-1,{"$nulls":75},"项目施工正常。","495AB173C0000021BD1078AE8F558A41"]
["F6D6A37071ECAC52328181E518C62B30",0,null,"2015Y0002",-1,8,null,8,{"$nulls":12},8,null,8,{"$nulls":12},8,null,8,{"$nulls":12},8,null,8,{"$nulls":27},"工程已经建成通车，完成投资3617万元。","4978BBA1C0000021B8CD96E7C2ECBAA0"]
["58A3C13248AEB8EFAD2FFC949FC562E3",0,null,"2015Y0001",-1,{"$nulls":75},"目前，正在进行路基施工。","4583086800000021610D57307F655C40"]
["86AACE78F2A0DEF0A13D373A70D83AA1",0,null,"2015Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"站场主体建成，正在铁路专用线施工。","452C38D9200000A160383FB696401BD8"]
["83D2C49AC1DC526DA47C2275774E345D",0,null,"2015Y0002",-1,{"$nulls":75},"目前，正在进行路基施工。","4583086800000021610D57307F655C40"]
["892519918B45D3266482370A8DFF1E4D",0,null,"2015Y0002",-1,{"$nulls":75},"完成全线驻地建设；便道累计完成19.5km，占总量（各标段累计19.94km，有重叠部分，比全线全长长一些）97.8%；桥梁钻孔桩除受前期影响的6根外，其余全部完成；桥梁承台浇筑累计完成126个，占总量98.4%；桥梁墩柱累计完成208个，占总量96.3%；系梁累计完成24个，占总量92.3%；台帽累计完成48个，占总量92.3%；盖梁累计完成78个，占总量92.9%；预应力现浇箱梁累计完成73幅，占总量86.9%；完成预制梁板18片，累计完成615片，占总量80.8%；完成挂篮悬浇8节段，累计完成39节段，占总量28.5%；清表累计完成749208m2，占总量91.6%；路基挖方累计完成500301m3，占总量105.7%；完成路基填方55242m3，累计完成1222876m3，占总量83.6%，湿喷桩全部完成；雨水管累计完成15500m，占总量97.0%。","45835A3940000021498FFD174D21DCE8"]
["14DCA5CC392EF1B97BA56437503C5274",0,null,"2015Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地拆迁及路基填筑。","452C38DA80000041BB1AF46EF3FAECC2"]
["CC726E55857282874A2AE720B4397D05",0,null,"2015Y0002",-1,{"$nulls":75},"完成综合配套区南区主体结构建设，开展综合配套区北区招标工作。","468F5198A0000021390EE49ABE0B2CD5"]
["325444457559CE85F5BB6958502F1B91",0,null,"2015Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成隧道掘进30米，累计完成4810米，隧道右线贯通。基本完成互通主体工程，完成交安工程约80%。","44F92AE720000041FD47DFFCE454F006"]
["D6AE9917532DA1D4666A4DBBD004A451",0,null,"2015Y0002",-1,{"$nulls":75},"尚未开工。","4A847B5C800000014545309CA6FC8CB7"]
["EB69197EAE02A8BBFB99DEE8535EDF49",0,null,"2015Y0002",-1,{"$nulls":75},"路基施工全部完成，桥梁施工全部完成，基本完成防护、排水工程；路面底基层完成100%，基层主线施工完成85%；房建区儒林、上黄收费站办公楼、宿舍楼完成二层框架及屋面施工，中关村、溧阳北、长荡湖收费站综合楼基础分部完成施工；隔离栅施工完成75%；边沟外乔木种植完成40%。","44F92AE780000061E689426EB5202CA4"]
["461A5765712B071BEC4E3E5FBA6B74C3",0,null,"2015Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头工程和疏港航道完成100%；北侧港区排水工程、用电工程和调度楼等附属设施完成100%，码头前沿道路和堆场完成92%。","44F92AE740000061422D7CBDB598F0A4"]
["518A08854E92140E1F73C17553C19127",0,null,"2015Y0002",-1,{"$nulls":75},"完成码头水工部分，房建工程开展装饰施工，完成场内道路桥梁主体工程。","48169DD9600000213A760AD1A7936625"]
["0000701FAA10B5904D444B4608AEA296",0,null,"2015Y0002",-1,{"$nulls":75},"完成征地拆迁，开展路基施工。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["30EC808F9790754FE171D6C1CD68D70D",0,null,"2014Y0012",-1,{"$nulls":75},"完成路基桥涵工程。","4ADC3C87A00000211C3BE7E0F8EA4A3E"]
["63A87027E67BC0189BF146229DFA9084",0,null,"2015Y0001",-1,{"$nulls":75},"全线主车道开挖及路基施工，沈思港桥东半幅完成、西侧桥台施工，朝阳河桥西半幅准备架梁施工。","4A04D699C0000021960B6C19775B7500"]
["26AB35B694BE2AB29A9A8DD21A0F26EF",0,null,"2015Y0001",-1,{"$nulls":75},"钻孔灌注桩完成进度的97%；完成施工承台8个， 完成进度的82%；立柱10根，完成进度的40%；桥台3个，完成进度的74%；盖梁4个，完成进度的85%；路基填筑5100m3，完成进度的25%；湿喷桩施工20630m，完成进度的100%。","4B2547D8C0000021EA2F1D310FA63F35"]
["543A1A14EA70A74426E34E2A86DDB2D4",0,null,"2015Y0001",-1,{"$nulls":75},"项目施工正常。","495AB173C0000021BD1078AE8F558A41"]
["10C6F2559A6C3ACB84E805E1F64DD657",0,null,"2015Y0002",-1,{"$nulls":75},"未开工","4596B7A960000021619092F5D6908C5A"]
["81075DEC0DB62200D173BBA199C39E0B",0,null,"2015Y0002",-1,{"$nulls":75},"未开工","4596CE63A0000021B9EF1E5E417B9CA3"]
["EAF6726002E7B76CDDF68BEC7628C899",0,null,"2015Y0002",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["B32FDD104F36533C86F7A24FCFA57E4E",0,null,"2015Y0002",-1,{"$nulls":75},"实施一期工程5.1公里，完成主车道路基处理总量的100%、沥青混凝土面层总量的100%，构造物总量的100%，排水管道总量的100%，沿线路路缘石总量的90%，慢车道路基处理总量100%，慢车道路面底基层完成90%。","4756E0D780000021BD984AD195D60C8A"]
["78C49FC36DEA33E5F22408B0FD2E4011",0,null,"2015Y0002",-1,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,{"$nulls":15},"目前，该项目11.071公里路基、路面工程已全部完成，累计投资9210万元。正在开展下穿机场灯光路段（U槽）工程施工，2月完成喷射混凝土护坡195立方米，非预应力钢筋网9.7吨，混凝土垫层400立方米，混凝土底板1133立方米，浇筑混凝土墙身140立方米，非预应力钢筋249吨，铺设防水卷材1000平方米，完成投资260万元。","4979BFCD200000210A165452CAEAC270"]
["C3E9A16385BC33A7BE25DBCEE122C722",0,null,"2014Y0012",-1,{"$nulls":75},"目前，桥梁及接线道路已建成。","4767883F000000016F0AF6F671358D27"]
["74B91012E7DE7540929F8A16D2FF76A4",0,null,"2014Y0012",-1,8,null,8,{"$nulls":12},8,null,8,{"$nulls":12},8,null,8,{"$nulls":12},8,null,8,{"$nulls":27},"工程基本完工，完成投资3617万元。","4978BBA1C0000021B8CD96E7C2ECBAA0"]
["AC15E95E5AA8C7D91FDD7A398D2847B3",0,null,"2014Y0012",-1,22,{"$nulls":75},"49E0DFA940000021DE73460C8BA04095"]
["E38FAD1412BDF26C2848805433B2A2E8",0,null,"2014Y0012",-1,{"$nulls":75},"全年完成道路588公里，桥梁82座。","4A9F137F20000021759A4A13AE0F2C2E"]
["59D784DF4783FB3D46A0E3B491E1556D",0,null,"2015Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"基本完成水工结构物施工,完成后方堆场30%,完成道路30%，完成装卸设备加工50%。","44F92AE9000000A114EC34ECCE42A6E8"]
["59A25296BA2330E29DA829CBC923B4AE",0,null,"2015Y0001",-1,{"$nulls":75},"办公用房、综合楼各项工作已基本完成；场地混凝土浇筑、室外管网铺设均已进入收尾阶段；室外电缆铺设已完成；消防管道及生活用水管道已接通；门卫工程进入墙体施工和贴面阶段。","4706D6D520000021D78B264A806E8D95"]
["2E867C924492589BBF625E10EDECE774",0,null,"2015Y0002",-1,10,254,10,536564,496499,766766,13,100,100,5,78,{"$nulls":3},5973,null,222,{"$nulls":5},75,95,3,78,{"$nulls":5},120,{"$nulls":5},70,80,3,78,{"$nulls":5},149,{"$nulls":5},75,83,3,78,{"$nulls":20},"452C38D900000041E569F21C93091E69"]
["C69B1EF749BEA479D097BF65953684B0",0,null,"2015Y0002",-1,{"$nulls":75},"码头水工完成。方案设计变更。","45B27FD3A0000001E7A4DAE02DD98961"]
["9636C2D3C2ABC2049ADF4B3D22497364",0,null,"2015Y0002",-1,{"$nulls":75},"地下室完成，办公楼完成一层。","47EC671F00000001C8A65242F6D76C6C"]
["53E84C2166D906E45B4A6C7A60FFCA32",0,null,"2014Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成办公楼装修，完成8.5万平方米场地建设并投入试营运。","452C38D960000061A773E74DF5A30C52"]
["EA9115DAA1E1A32E172D7372F5B5FC9E",0,null,"2014Y0012",-1,{"$nulls":75},"工程已完工","46D1152460000001B5594EC6A47326C2"]
["3D9883B7026EB3677F10D48F168505AF",0,null,"2015Y0001",-1,5,95,5,208954,196309,573301,4,100,100,5,26,{"$nulls":3},4978,{"$nulls":61},"452C38DBA0000101EE35873CD541EA02"]
["9E07939E26DBDDC0A53D6F545E7028A4",0,null,"2015Y0001",-1,36,505,{"$nulls":4},13,100,100,19,111,{"$nulls":5},371,{"$nulls":5},80,90,null,106,{"$nulls":5},315,{"$nulls":5},100,100,null,111,{"$nulls":5},286,{"$nulls":5},50,90,null,106,{"$nulls":20},"452C38DBE00000616AD445E437E62A7E"]
["D0255A498ADFDAFF25095D75788C05E1",0,null,"2015Y0001",-1,{"$nulls":75},"基本完成路基及疏港航道以东段一期路面工程。","44F92AE7E000004126A44C796491035A"]
["47F4FACDD8FB900A73ED545207EF659B",0,null,"2015Y0001",-1,{"$nulls":75},"已累计完成90公里，一月份完成纵三东路、连云新城段沥青摊铺及跨铁路桥、环山公路桥桥梁预制假设。","4A953E3E000000613D13CA6F74E1236C"]
["3A0B23FB542CF0E532E25A76BD336328",0,null,"2015Y0001",-1,{"$nulls":75},"完成桩基施工","46EA9FBB800000213459FE5A48F06D61"]
["BD5B028CF6FC3E882C9C9BE0FC090AE1",0,null,"2015Y0001",-1,{"$nulls":75},"完成路基填筑60%、涵洞75%、桥梁灌注桩75%。","48173F21C00000213849C18090E227D5"]
["C21A13B8AFF127B24965BB441A16D3BB",0,null,"2014Y0012",-1,{"$nulls":75},"目前，正在进行明远路至京杭运河大桥段路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["EE5F221B796D1A9FE653E3AA20BC8F18",0,null,"2014Y0011",-1,8,147,8,273695,273695,273695,{"$nulls":3},4,11,{"$nulls":3},6498,null,77,null,19230,15187,1368,{"$nulls":3},0,4,{"$nulls":3},0,null,122,null,273695,273695,189000,{"$nulls":3},4,11,{"$nulls":3},4000,null,52,null,19230,15187,1368,{"$nulls":3},0,4,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1-4标段已进场，1-3标正在开展污水管线、河塘清淤、软基处理、路基填筑、桥涵及水利大坝等施工，4标正开展路面底基层和基层施工，5标已定标。","464AEA1FC0000021B52E367C631B2D38"]
["C43B18D73ACEBA9B1DCF3635C8892FDC",0,null,"2014Y0012",-1,{"$nulls":75},"320公里农路、229座农桥已全部完成。159公里农路安保工程已完成。","4A9F60AE000000213657F37A33E553C2"]
["EE11547708C348EB61BA91B6D063C1FE",0,null,"2015Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼工程、附属用房、停车场工程完成100%。附属设施、绿化工程完成100%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["54FF3FB0A9416BA8C9036E740491F296",0,null,"2015Y0001",-1,{"$nulls":75},"主车道老路范围沥青下面层完成，右幅拓宽段进行平侧石施工，左幅拓宽段进行路基土方施工；裴家圩桥完成右幅铰缝浇筑、左幅下部结构，1号桥完成右幅桥面铺装及中幅台帽、孙家桥及2号桥完成下部结构。","4A04B92BC000006128D10F788349E5BC"]
["0636FA3B1CFC415764850FD721692F53",0,null,"2015Y0001",-1,{"$nulls":75},"完成征地拆迁及路基桥涵工程。","48A6EC29E000000142F6B2638633E8C1"]
["CF73F6E02913A3E62D94E13536945D64",0,null,"2015Y0001",-1,{"$nulls":75},"除桃乌段其余完工通车；桃乌段待开工。","46EA9B7380000021C12E5F228EAB22B5"]
["8B8541B85ECB5579109D373ACBB32F4A",0,null,"2015Y0001",-1,{"$nulls":75},"桩基100％,墩台帽54.2％,立柱60％,承台系粱100％,主桥系杆拱肋、风撑完成，上部预制完成29.7％。","494F5FA260000021C65146E6197A1225"]
["38A5084CA1E19E7CF942B46105DED893",0,null,"2015Y0001",-1,{"$nulls":75},"完成路基处理总量的90%、路面底基层总量的80%，水稳路面基层总量的65%，沥青面层总量的65%，构造物100%，排水管道完成总量的80%。","4A98BD0D800000212D60BD89CB35D858"]
["96F3D6D5D361C044EC7EDC35B99B7C97",0,null,"2014Y0012",-1,null,100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":14},100,{"$nulls":29},"459307CF60000021FC7F08A5CEC30386"]
["D4C3563091429F28755C5568D3C71859",0,null,"2015Y0001",-1,{"$nulls":75},"未开工","4596E669A00000212657F1C116794095"]
["3C0179ABFCCD27ECCE4BE935183DA03A",0,null,"2015Y0001",-1,{"$nulls":75},"未开工","4597A8468000002121A18819522EF243"]
["2C8A06BBB53152C58C2E9DD53B197477",0,null,"2015Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成隧道掘进30米，累计完成4810米，隧道右线贯通。基本完成互通主体工程，完成交安工程约80%。","44F92AE720000041FD47DFFCE454F006"]
["E09476BB71A5FB0E3091CF3C47D55F3A",0,null,"2015Y0001",-1,{"$nulls":75},"尚未开工。","4B2FE5AB600000211F6D440BC42C931E"]
["F49B8CF2FD9AEF1AAF529975553AB3CD",0,null,"2015Y0002",-1,{"$nulls":75},"全线沥青下面层完成，临时通车。","46EA9D51A0000021F1A72CD5283EA913"]
["020AF370B9DF0E93BB71DF9E30C24362",0,null,"2015Y0002",-1,{"$nulls":75},"完成选址及方案设计，完成初步方案报批及设计方案优化，完成概算评审、稳评、环保审批，项目立项。","4A613592E000002194B46D647ABA77F9"]
["F18161920CDEFA7D99B68EAE942D9BA4",0,null,"2015Y0002",-1,36,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,null,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,{"$nulls":46},"452C38DCA00000A1BDA9E5BD6348A13E"]
["05934FF65DF6211C63204B92C3F96AB2",0,null,"2015Y0001",-1,{"$nulls":75},"完成桥梁下部结构。","494F86EDE00000215894D3EF8FBDFA9B"]
["E137E713B7E869B551982E36376520E3",0,null,"2015Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头后方堆场回填、硬化、幕墙施工、码头主体连续施工、配套联检大楼建设到二层，海关用房装修。码头水工下部结构正在进行基坑开挖及后方回填。","44F92AE800000121D51AC7AB782D4663"]
["FBE74B3BE30E6D8458725540D30F607C",0,null,"2015Y0002",-1,{"$nulls":75},"钻孔灌注桩完成进度的97%；完成施工承台8个， 完成进度的82%；立柱10根，完成进度的40%；桥台3个，完成进度的74%；盖梁4个，完成进度的85%；路基填筑5100m3，完成进度的25%；湿喷桩施工20630m，完成进度的100%。","4B2547D8C0000021EA2F1D310FA63F35"]
["630C367D0DE45B702437B83BB76F83D4",0,null,"2015Y0002",-1,22,{"$nulls":75},"49E0DFA940000021DE73460C8BA04095"]
["F6434AA27E43B7C24CCB70F421FD6295",0,null,"2015Y0002",-1,14,330000,14,120000,120000,120000,0,0,0,0,26,0,0,0,null,7,180000,7,60000,60000,60000,0,0,0,0,6,0,0,0,null,7,150000,7,60000,60000,60000,0,0,0,0,20,0,0,0,null,7,30000,7,60000,60000,60000,0,0,0,0,6,0,0,0,{"$nulls":16},"目前二期工程正在进行施工图设计审查，待施工图批复完成后进行招投标相关工作。","46B8AAA3A00000217140A795E7A1AE32"]
["3B418E953FF6351DACA513F820281766",0,null,"2015Y0001",-1,{"$nulls":75},"目前，正在进行明远路至京杭运河大桥段路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["3809D072E0F632F6C01ED048B3809521",0,null,"2015Y0002",-1,{"$nulls":75},"目前，已基本建成。","4582F984A00000210B371656660E7377"]
["D409FC617E90D43BCE88C6D5057CA62A",0,null,"2015Y0002",-1,{"$nulls":75},"尚未开工。推进前期工作，完成征地拆迁。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["55AFC6118081B35046EAFC8662597442",0,null,"2015Y0002",-1,{"$nulls":75},"尚未开工。","4B2FF7D380000021FF48FF8FCEED99B8"]
["5B6ED630256475747815E04EA350A5C9",0,null,"2015Y0003",-1,{"$nulls":75},"东直立堤工程年内进尺75米，占年计划2000米的4%，累计进尺1000米，占总长4674米的21%。","452C38D9600000015B091B22A009EB3A"]
["E9636D0F0B5E707EB13CD6728717149B",0,null,"2015Y0003",-1,{"$nulls":75},"东斜坡堤工程年内进尺100米，占年计划1400米的4%，累计进尺6450米，占总长7834米的82%。","452C38DA800000A19C9699F0088370B9"]
["73DD2D25B4F022BBEEF789200070FD82",0,null,"2015Y0003",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,95,42,6200000,640000,2400000,null,52,75,18,52,{"$nulls":4},3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,35,null,200000,60000,null,null,32,35,10,20,{"$nulls":19},"北段42.3公里建成通车，南段正在进行路基、桥梁施工.","4597C2C660000021C7BD96E4F6D02E66"]
["8E995EEA59392DD57C06850AB770D4D1",0,null,"2015Y0003",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["ABD7DAE785782D313C5152F2B30D7955",0,null,"2015Y0003",-1,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,{"$nulls":15},"目前，该项目累计完成投资9700万元。正在开展下穿机场灯光路段（U槽）工程施工，3月完成U型槽现浇混凝土底板1850立方米，U型槽现浇混凝土侧墙1240立方米，非预应力钢筋410吨，侧墙变形缝208米，底板变形缝220米，完成投资490万元。\n","4979BFCD200000210A165452CAEAC270"]
["39F0F64BAF032B525F29703C93047A80",0,null,"2015Y0003",-1,17,null,17,{"$nulls":73},"45C531BE200000219CD9EF28C8D31E82"]
["09D2A0FD2FA13F48531F7DACA581D382",0,null,"2015Y0001",-1,{"$nulls":75},"基本完工。","46D12277000000016E90CB741749DE83"]
["F07059B1CF8D1B206FB1D5BBD96A6015",0,null,"2015Y0003",-1,{"$nulls":75},"4个泊位水工主体完工，后方罐区主体建成。","46D12095E00000210EEE5BA374F2A089"]
["2640F2476581F4DDD244A74CB071BEBA",0,null,"2015Y0003",-1,{"$nulls":75},"集散中心已封顶，进行各项收尾工作，正在室内安装工程，仓储中心B1/B2钢结构封顶，正在进行墙板安装和楼层板混凝土浇筑，综合楼框架封顶，进行幕墙安装。","4A09BB5320000021A7468129AEC6112D"]
["4E850EA366B8904FEE042AE9EAA4032F",0,null,"2015Y0002",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"基本完成水工结构物施工,完成后方堆场35%,完成道路35%，完成装卸设备加工50%。","44F92AE9000000A114EC34ECCE42A6E8"]
["E62B28A0973C548B55D690737800BC3B",0,null,"2015Y0003",-1,{"$nulls":75},"码头水工完成。方案设计变更。","45B27FD3A0000001E7A4DAE02DD98961"]
["9F0C20987098EFF014DC9295B5E9CF77",0,null,"2015Y0004",-1,{"$nulls":75},"项目建成通车。","477AAD380000002159DCBA91BD5FA484"]
["8E85F6269CEF79C5B718FE89DE90BD41",0,null,"2015Y0004",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,25,190,25,0,0,0,8,100,100,10,73,0,0,0,4447,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,25,190,25,{"$nulls":3},8,100,100,10,1,{"$nulls":3},4447,{"$nulls":15},"路基、桥梁基本结束，正在进行路面施工。","458887AF00000021883DEACA51071D92"]
["FFCF8F5B693C42B8397935159BC5E8B7",0,null,"2015Y0001",-1,{"$nulls":75},"西防波堤工程年内进尺300米，占年计划2500米的12%，累计进尺3500米，占总长9804米的35.7%。","46D12756A00000212A79E7CE74664FD9"]
["09B14A43C2AC6D1FB7947814A3A582A5",0,null,"2015Y0002",-1,{"$nulls":75},"东直立堤工程年内进尺75米，占年计划2000米的4%，累计进尺1000米，占总长4674米的21%。","452C38D9600000015B091B22A009EB3A"]
["4E7069CD244C3FE74427A6008782DEB8",0,null,"2015Y0003",-1,{"$nulls":75},"地下室人防墙体完成，地下室2区墙体完成90%，一层墙体完成40%，四层墙体完成30%，安装人防地下照明穿线完成50%，地下室天棚抹灰完成20%\n","47EC671F00000001C8A65242F6D76C6C"]
["5CD87B95C00309FCE3D2569B4B64E278",0,null,"2015Y0003",-1,{"$nulls":75},"建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["B92905F1845D8AA01E42025B42DBA815",0,null,"2015Y0003",-1,{"$nulls":75},"全线主车道开挖及路基施工，沈思港桥东半幅完成、西侧桥台施工，朝阳河桥西半幅准备架梁施工。","4A04D699C0000021960B6C19775B7500"]
["928F1B546D64774E3FBFC294C456C4B4",0,null,"2015Y0003",-1,{"$nulls":75},"尚未开工。推进前期工作，完成征地拆迁。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["DB451489C605525ECC2D79921F0ED960",0,null,"2015Y0003",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"互通主体完成，隧道右线贯通。","44F92AE720000041FD47DFFCE454F006"]
["EF6994ED11C3E18972C57FE74CCD2D87",0,null,"2015Y0003",-1,{"$nulls":75},"除桃乌段其余完工通车；桃乌段待开工。","46EA9B7380000021C12E5F228EAB22B5"]
["BE5C905091641E4592E6B32E7A88F0CC",0,null,"2015Y0003",-1,{"$nulls":75},"完成部分附属设施。","46EA9D51A0000021F1A72CD5283EA913"]
["8931612939E1BA70734AB57FB272304F",0,null,"2015Y0003",-1,36,503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":5},503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":7},929179,849170,890542,{"$nulls":12},929179,849170,890542,{"$nulls":25},"452C38D9600000C17C36891B54B019E8"]
["70C81E7B962FB42CFD1DEAFF4F2AD9C0",0,null,"2015Y0003",-1,{"$nulls":75},"未开工","459798044000002173FE5313B1674A84"]
["B643D1C1B9A8B0432675F12A65899432",0,null,"2015Y0003",-1,8,147,8,273694,273694,273694,1,100,100,4,11,{"$nulls":3},6498,2,99,1,19230,19159,19159,{"$nulls":3},0,8,{"$nulls":3},0,8,81,8,254464,258507,272326,null,100,100,4,7,{"$nulls":3},6498,2,33,1,null,3972,17791,{"$nulls":3},0,4,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1-4标段已进场，1-3标正在开展污水管线、河塘清淤、软基处理、路基填筑、桥涵及水利大坝等施工，4标正开展路面底基层和基层施工，5标已定标。","464AEA1FC0000021B52E367C631B2D38"]
["E4A6B8F3F4FEFBBF0941640ED19A4816",0,null,"2015Y0003",-1,{"$nulls":75},"尚未开工。","4A847B5C800000014545309CA6FC8CB7"]
["2426CABDE43225B12A872A701B8FF0CE",0,null,"2015Y0003",-1,{"$nulls":75},"完成路基桥涵工程。","4ADC3C87A00000211C3BE7E0F8EA4A3E"]
["B016EEEB59DFF28198E649A2A683D308",0,null,"2015Y0004",-1,42,null,42,{"$nulls":73},"45C546C200000021547764ADF0037399"]
["6FAD0326B4EF6D213E17EC8B757F2442",0,null,"2015Y0002",-1,42,null,42,{"$nulls":73},"45C546C200000021547764ADF0037399"]
["94A5D0F46776803312A95EB3C8591C19",0,null,"2015Y0004",-1,{"$nulls":75},"建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["7B4BAB873122FC7FC8211281B91297FC",0,null,"2015Y0002",-1,{"$nulls":75},"4个泊位水工主体完工，后方罐区主体建成。","46D12095E00000210EEE5BA374F2A089"]
["FCE905D75BDAF70289218B9E28158477",0,null,"2015Y0003",-1,{"$nulls":75},"2个泊位水工主体主体基本建成，后方道堆真空联合堆载预压施工中\n","46D11FD040000021CBCE7B927205F9C4"]
["7C0271D1B49C2E2CA241ED22C463DBCC",0,null,"2015Y0003",-1,{"$nulls":75},"完成路基填筑95%、涵洞100%、桥梁工程40%。","48173F21C00000213849C18090E227D5"]
["E5EC4986F413E25C5AA970BA939DE3F3",0,null,"2015Y0003",-1,{"$nulls":75},"完成征地拆迁，开展路基施工。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["A29D2E6AA5731ACF6F22F2F2CCB3B813",0,null,"2015Y0004",-1,{"$nulls":75},"目前，该项目已完成前期准备，正在进行拆迁安置工作，4月底已完成投资1500万元。","4CD4D282E000002179AFC485C3C50F33"]
["5576ADD9F5ABD39309A5E117725A4E1C",0,null,"2015Y0004",-1,{"$nulls":75},"正进行路基、路面施工。","45D5A240A0000021D818821C8141EA27"]
["A90587FA5709EDAB63FC20742DCB3E69",0,null,"2015Y0002",-1,96,{"$nulls":75},"45AB8817400000218E63FD22BDA91CE1"]
["AE8387BEB597F04A3A4353A013F4B552",0,null,"2015Y0004",-1,{"$nulls":75},"码头水工完成。陆域方案设计正在报请省厅变更。","45B27FD3A0000001E7A4DAE02DD98961"]
["4CEACC502A3DFEAA6AC1B3C0D22B0716",0,null,"2015Y0004",-1,{"$nulls":75},"路基施工全部完成，桥梁施工全部完成，完成防护、边沟工程；路面底基层完成100%，基层主线施工完成100%；路面项目完成下面层试铺及总结，累计完成下面层占总量的34%，完成中分带填土、路侧拦水带及路肩填土施工；房建单位主体框架结构全部完成，开展砌墙等施工；隔离栅施工基本完成；绿化工程完成边沟外、互通区乔木种植，中分带防眩树完成100%，开展互通区灌木施工；三大系统完成联合设计，开展设备采购工作；路基单位进行交工档案集中整理。","44F92AE780000061E689426EB5202CA4"]
["7F1CD823AAF8D455A746C97D70698535",0,null,"2015Y0003",-1,{"$nulls":75},"项目建成通车。","477AAD380000002159DCBA91BD5FA484"]
["4DC265BDBF31A1BBA8D14C8F5B5AE160",0,null,"2015Y0003",-1,{"$nulls":75},"K4+200-K11+400完成路基85%，面层77%，头兴港河大桥主体建成。","45D4A12B00000021B86B31C7A15832ED"]
["E4A515B9746ED5CCDE3F4CE56ABF9F9F",0,null,"2015Y0003",-1,{"$nulls":75},"工程完工。","494F759FA0000021B650A21A5A0C6724"]
["78E3C8E5C270D9C88A97DF7F90270711",0,null,"2015Y0003",-1,7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":21},"481FB13480000021DF891907B35F942C"]
["4A6142713C25EEB0A18115068840B86D",0,null,"2015Y0004",-1,20,424,27,{"$nulls":3},26,100,100,22,155,{"$nulls":3},14610,null,74,{"$nulls":8},100,{"$nulls":5},71,{"$nulls":8},98,{"$nulls":5},74,{"$nulls":8},100,{"$nulls":20},"469415CEC000000193285BF8DEFE5650"]
["E3F10D7B5E20515F9F6DF02682117B3E",0,null,"2015Y0004",-1,{"$nulls":75},"集散中心已封顶，进行各项收尾工作，正在室内安装工程，仓储中心B1/B2封顶，正在进行墙板安装、楼层板混凝土浇筑和消防水电安装，综合楼框架封顶，进行幕墙安装和消防水电安装。二期开始报建手续和地基处理。","4A09BB5320000021A7468129AEC6112D"]
["B1003AA78A91A2282A34591C363D8CFD",0,null,"2015Y0004",-1,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,{"$nulls":15},"目前，该项目累计完成投资9963万元。4月份完成情况：1.下穿机场灯光路段（U槽）工程挖土方1800立方米，4%水泥土路基4140立方米，5%水泥土路基5280立方米，利用土方8094立方米，现浇混凝土侧墙425立方米，混凝土垫层2812立方米，防水卷材2900平方米，完成投资205万元；2.道路工程完成清表15000平方米，原土压实15000平方米，4%水泥土路基11000立方米，完成投资58万元。","4979BFCD200000210A165452CAEAC270"]
["CB53D09009EB0759C33FE162DF091173",0,null,"2015Y0004",-1,{"$nulls":75},"桩基100％,墩台帽80％,立柱80％,承台系粱100％,主桥系杆拱肋、风撑全部完工，上部预制完成65％。","494F5FA260000021C65146E6197A1225"]
["E797B312F129C81F16493E612596EDC3",0,null,"2015Y0001",-1,{"$nulls":75},"工程主体完工，铁路工程主体完工；接轨方案审查会于8月15日在上海路局召开。\n","46D11DA8E0000021390F8E6CD9239F6A"]
["46A38D63C21C58CF4DE751FB395CD0BD",0,null,"2015Y0003",-1,{"$nulls":75},"累计折合进尺2188米，占二期工程准备工程总长2488m的88%。","46EBEFA560000021402F9981E1B1599D"]
["FC572C88AC520CB2B2D1800B615CC75A",0,null,"2015Y0003",-1,{"$nulls":75},"尚未开工。","4B2FE5AB600000211F6D440BC42C931E"]
["F3C3527247FDDE90684603EAC028EBC1",0,null,"2015Y0003",-1,{"$nulls":75},"完成部分水工结构。","497EC8FBA00000219339AD552530ADAF"]
["942D31C37A85C18AA40295B2874F4819",0,null,"2015Y0004",-1,{"$nulls":75},"完成路面基层。","48171CB940000001DAB3F475A2461DC6"]
["7CA128D50081CAD199973AB6BB9EB125",0,null,"2015Y0004",-1,{"$nulls":75},"地下室人防墙体完成，地下室2区墙体完成90%，一层墙体完成40%，四层墙体完成30%，安装人防地下照明穿线完成50%，地下室天棚抹灰完成20%\n","47EC671F00000001C8A65242F6D76C6C"]
["FE437B65EC65117FFCA38B34AE4695E2",0,null,"2015Y0004",-1,{"$nulls":75},"完成两层楼面框架结构，局部三层在建","46EA9FBB800000213459FE5A48F06D61"]
["18E6DB5513B136D9750CFCF1CA87889B",0,null,"2015Y0004",-1,{"$nulls":75},"桃乌段开始施工。","46EA9B7380000021C12E5F228EAB22B5"]
["E048AF20CC1206CAC426E8B0BFD7E333",0,null,"2015Y0004",-1,{"$nulls":75},"4个泊位水工主体完工，后方罐区主体建成。","46D12095E00000210EEE5BA374F2A089"]
["3277BA3215B5A168E372164ED0B7AD40",0,null,"2015Y0004",-1,{"$nulls":75},"尚未开工。","4B2FE5AB600000211F6D440BC42C931E"]
["ED695E49C2F0912DC084B12067096ED7",0,null,"2015Y0004",-1,{"$nulls":75},"水工主体建成","4C2FB609C0000021E347BA6BB8D8C1EF"]
["6872D7B20C9EF421D6A5021097670BE7",0,null,"2015Y0005",-1,{"$nulls":75},"未开工","4596CE63A0000021B9EF1E5E417B9CA3"]
["8D043A0FA1C8CDE21F4492CC8FFDC780",0,null,"2015Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体、挡墙连续施工，口岸大楼基坑防水处理，联检大楼主体建设。","44F92AE800000121D51AC7AB782D4663"]
["D55E84B974E03588FDDFA7B06B20FAED",0,null,"2015Y0005",-1,{"$nulls":4},2023895,1913509,{"$nulls":4},229,{"$nulls":64},"水泥稳定碎石基层30000方.","44F92AE9800000A15AC5660EDAD7D017"]
["74FCACEB02226990EDFCB6F540C6EDF7",0,null,"2015Y0005",-1,{"$nulls":75},"地下室人防墙体完成，地下室2区墙体完成90%，一层墙体完成40%，四层墙体完成30%，安装人防地下照明穿线完成50%，地下室天棚抹灰完成20%\n","47EC671F00000001C8A65242F6D76C6C"]
["BDC4338BD6E06711B3ECC95D92DB5ADF",0,null,"2015Y0005",-1,{"$nulls":75},"二层结构结束，三层完成30%","46EA9FBB800000213459FE5A48F06D61"]
["665224A5D89E10EE119F92CD496BD9E6",0,null,"2015Y0005",-1,{"$nulls":75},"完成路基填筑98%、路面底基层42%、基层28%、桥梁工程60%。","48173F21C00000213849C18090E227D5"]
["0376EBDD6BABAD2677BF41C5B9A5653C",0,null,"2015Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["3133D00B3C466CC3088D8C90966F031B",0,null,"2015Y0005",-1,{"$nulls":75},"交通运输局段征地拆迁完成95%，房屋拆迁完成95%，路基基本贯通；徐圩段完成疏港航道大桥及中桥伸缩缝598米；交通工程波形梁钢护栏7000米；铁路下穿段横截沟工程。","44F92AE7E000004126A44C796491035A"]
["2FED81F80BA0A3E5A5B82AE05DFC691D",0,null,"2015Y0005",-1,{"$nulls":75},"已经建成22.8公里，剩余路段完成征地拆迁及路基填筑。","452C38DA80000041BB1AF46EF3FAECC2"]
["236B083F93D06C10FF9578015140EF03",0,null,"2015Y0005",-1,{"$nulls":75},"已实现贯通119.41公里，跨海大桥基本贯通，跨铁路桥完成桥面铺装及水稳。","4A953E3E000000613D13CA6F74E1236C"]
["080C0321F3B2001AF3C0EA49410E5CC4",0,null,"2015Y0005",-1,{"$nulls":75},"4个泊位水工主体完工，后方罐区主体建成。","46D12095E00000210EEE5BA374F2A089"]
["B06B0DD2224132C35E8B8A773C8B25A3",0,null,"2015Y0005",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["AAEB2E98F720FD547184AA599E0FC856",0,null,"2015Y0005",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,27,166,16,398864,305076,201726,2,100,100,26,59,0,320,-80,97017,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一标本月完成产值92.9万元;二标本月完成产值112.28万元;绿化标总计完成产值约8768.645万元。存在问题：基本没有问题.","4592B501E000002123E927A043947D89"]
["63511A5AC9870F310136BAEA8C10305A",0,null,"2015Y0006",-1,34,490,34,1100000,900000,2480000,3,{"$nulls":3},102,{"$nulls":4},17,229,6,413000,320000,340000,0,{"$nulls":3},70,{"$nulls":4},17,280,10,770000,450000,1240000,0,{"$nulls":3},52,{"$nulls":4},0,51,0,260000,180000,0,0,{"$nulls":3},20,{"$nulls":19},"1、晶桥段  除上面层沥青未摊铺，其余全部完成  2、白马段  完成水稳摊铺50%  3、晶桥-明觉段 路基土石方施工、特大桥等桥梁进行桩基施工。","44F92AE780000001F6AE7427CA69104E"]
["4C5874A978F4817C3FD942EBF622C8E5",0,null,"2015Y0004",-1,{"$nulls":75},"目前，正在进行路基施工。","4583086800000021610D57307F655C40"]
["281F6B33813BD4E768759C4465B00B9C",0,null,"2015Y0004",-1,{"$nulls":75},"目前，南接线已完成，正在进行桥梁项目部建设。","4810580020000001F6CBFBB8B8D6F9E1"]
["814A4E5626DA650294893FF023EAA68D",0,null,"2015Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主体已完成，正在侯工楼A内外装修，停车场施工。","452C38D960000061A773E74DF5A30C52"]
["264DF7D5A2F7EF083B2F029E10A332D0",0,null,"2015Y0004",-1,{"$nulls":75},"基本完成路基及疏港航道以东段一期路面工程。","44F92AE7E000004126A44C796491035A"]
["4EA7F296CA7776A07AAAB16769CEFD13",0,null,"2015Y0005",-1,42,null,42,{"$nulls":72},"已全面开工，工程进展较好。","45C546C200000021547764ADF0037399"]
["60F53E47CE69A67BFFD4BCBEB73B42C9",0,null,"2015Y0005",-1,17,null,17,{"$nulls":72},"用地手续未批复，已停工。","45C531BE200000219CD9EF28C8D31E82"]
["38F3FA2D05613E19E400DAB069852D15",0,null,"2015Y0005",-1,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,{"$nulls":15},"进度：道路、桥梁主体工程基本结束，正在开展照明等扫尾工作。存在问题：无","4D70707C00000001E077DAB59B768AFF"]
["8DA7CCB4C4EB26E72C7D4CC4AA152DD3",0,null,"2015Y0005",-1,{"$nulls":75},"目前，该项目已完成前期研究，正在开展拆迁安置工作，至5月底完成投资2000万元。","4CDB1D29200000214CA3D9F6DE183F12"]
["6636D05799887D48AF8C276D62CF54A3",0,null,"2015Y0005",-1,{"$nulls":75},"完成设计方案深化，即将招标","494F9423E0000021971B8B67E472FD4B"]
["33C44B05254983542302D97E2CBE9213",0,null,"2015Y0005",-1,{"$nulls":75},"该项目正在进行前期准备工作。","4D935B05A00000212B96F38D231EA5C3"]
["3B8D9136FCA1EBF5063AABB7CA12D66B",0,null,"2015Y0004",-1,{"$nulls":75},"水工工程扫尾，1-6#泊位后方道堆工程施工中。\n","46D11E59C00000215FEEE684519DC4AA"]
["4BED8EAC93861EB2389109978D263C10",0,null,"2015Y0004",-1,{"$nulls":75},"尚未开工。","4A847B5C800000014545309CA6FC8CB7"]
["A4D0357BDD16022048F5C9D63F915A61",0,null,"2015Y0005",-1,{"$nulls":75},"完成路面基层100%、面层40%。","48171CB940000001DAB3F475A2461DC6"]
["13C67DCD8D78CD710B5786ABD795733E",0,null,"2015Y0005",-1,{"$nulls":75},"建成通车","494F86EDE00000215894D3EF8FBDFA9B"]
["6AA4D3351BF50AA78FF2AEEEF7112AE9",0,null,"2015Y0005",-1,{"$nulls":75},"目前，正在进行路基施工。","4583086800000021610D57307F655C40"]
["91396CACF2DDD0573B89A8F2A4292F69",0,null,"2015Y0005",-1,{"$nulls":75},"斜坡式结构东防波堤工程本年进尺200米，累计折合进尺6600米，占斜坡式结构东防波堤工程总长7834米的84%。","452C38DA800000A19C9699F0088370B9"]
["132EBA4881FEBC93EF03D2538603591F",0,null,"2015Y0005",-1,{"$nulls":75},"钻孔灌注桩完成进度的98%；承台完成进度的100%；墩身完成进度的100%；立柱完成进度的85%；桥台完成进度的76%；盖梁完成进度的75%；箱梁完成进度的35%；路基填筑9000m3，完成进度的30%；湿喷桩完成进度的100%；PTC管桩施工19988m，完成进度的92%。","4B2547D8C0000021EA2F1D310FA63F35"]
["B48051D10A77579B65A00341FBEA01D0",0,null,"2015Y0006",-1,45,17,45,825867,894111,1692770,{"$nulls":3},22,44,{"$nulls":4},45,16,45,815867,880000,1650000,{"$nulls":3},22,42,{"$nulls":5},1,null,4000,8000,20000,{"$nulls":4},2,{"$nulls":14},2,{"$nulls":20},"45D0907940000021FB535CC8BFCB797E"]
["D734F9181B36B708C5AC08BC11E11D63",0,null,"2015Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头主体、挡墙连续施工、口岸大楼地下室钢筋绑扎，支模板，联检大楼主体完工，拆脚手架，卡口进行内部装修。","44F92AE800000121D51AC7AB782D4663"]
["649044CD2955A4A1F6FDFD43AF34D347",0,null,"2015Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成征地128.7亩，候车楼工程、附属用房、停车场工程完成100%。附属设施、绿化工程完成100%。","44F92AE8600000A1FCC5AC1CC54E3B96"]
["E8624A30CA76AC9D8F1B731479FEF819",0,null,"2015Y0004",-1,{"$nulls":75},"已经建成22.8公里，剩余路段完成征地拆迁及路基填筑。","452C38DA80000041BB1AF46EF3FAECC2"]
["0D871E94A1B7694BE8E1F43C1933846F",0,null,"2015Y0004",-1,{"$nulls":75},"工程复工","46D11F4F40000021C374A969A3743C9A"]
["7B7013458E63547B6AE1EE8867F256AF",0,null,"2015Y0005",-1,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,null,null,17,null,400700,1211300,{"$nulls":11},17,null,400700,1211300,{"$nulls":25},"452C38D5A00000A1C369596A7753C333"]
["432BFCFC0801AE5EB9ADE33C2E9D8D3A",0,null,"2015Y0005",-1,{"$nulls":75},"尚未开工。","4B2FD99E000000217EF51296349F80B0"]
["637D620F804D86E77B5B935F9E27FFA6",0,null,"2015Y0006",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":65},"45D5A240A0000021D818821C8141EA27"]
["9BFC13C367742B7BDB9E7FB8715C1B80",0,null,"2015Y0006",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,5,55,5,105014,111070,113964,1,0,0,0,18,0,0,0,1900,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：340省道路线全长42.890公里，其中溧水段17.773公里，江宁段25.117公里。目前本项目按阶段实施建设。第一段：溧水先导段4.6公里于2012年8月开工建设，2013年9月建成通车；第二段：江宁横溪段和溧水段。2015年计划新开24公里，目前已完成江宁横溪段的施工、监理招投标，并完成了项目部的组建工作，由于征地拆迁等原因还未进场施工；溧水段已完成了施工、监理招投标；第三段：江宁禄口段正进行施工图设计工作。\n二、存在问题：目前横溪段（13.68公里）江宁区政府启动了征地拆迁工作，已完成土地丈量、房屋拆迁调查工作，正在进行杆管线迁移调查。指挥部配合开展红线放样和路田分家工作，施工单位也开展驻地建设和测量放样复核等施工前准备工作，待江宁区政府提供建设用地后随时开展施工工作。","452C38DB00000021D4253F83097D6579"]
["3E50464E08FBE7CF008095CCBC2BF67D",0,null,"2015Y0003",-1,{"$nulls":75},"立交部分：全部完成，                  道路部分：桩基248根（100%），承桥台15只（94%），立柱96（100%），盖梁40榀（100%），空心板梁544片（94%）；           湿喷桩165000米（100%），石灰土160000m3（89%），水稳43000吨（61%），沥青15000吨（50%）","4568470820000021D98D8A6D5DA358BA"]
["C7EFBBCE25DFF9AA18D0E6081947B312",0,null,"2015Y0004",-1,{"$nulls":75},"未开工","459798044000002173FE5313B1674A84"]
["78E8C12EDA1F25E1EA869C1439D9DBA7",0,null,"2015Y0005",-1,36,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,null,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,{"$nulls":46},"452C38DCA00000A1BDA9E5BD6348A13E"]
["E5D8AEC83FFE05B73A4E4A79C319E48F",0,null,"2015Y0005",-1,{"$nulls":75},"项目已交工。","495AB173C0000021BD1078AE8F558A41"]
["7E8436C722C381D2A35172C135F5D790",0,null,"2015Y0003",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":15},"全线已完成","464AE565800000215C9C09C8A0BE8932"]
["0A96F18B0919E334E476666029AF5128",0,null,"2015Y0005",-1,{"$nulls":75},"路基施工全部完成，桥梁施工全部完成，完成防护、边沟工程；路面底基层完成100%，基层施工完成100%；路面项目完成下面层施工，开展桥面抛丸和防水施工，完成中面层试铺并展开摊铺；房建单位开展水电施工、外墙保温层、层面保湿、内部粉刷等施工；隔离栅、主线标志基础施工完成，护栏立柱打设累计完成70%；互通区绿化乔、灌木种植基本完成；三大系统开展光缆敷设；完成声屏障、供配电、照明工程的招标；路基单位完成交工档案集中整理。","44F92AE780000061E689426EB5202CA4"]
["87C9B0010AF08DE3B0321C448611E51B",0,null,"2015Y0005",-1,{"$nulls":75},"完成征地拆迁，开展路基施工。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["B10282DCEA5D274FB7795EF1BAFD6AA9",0,null,"2015Y0004",-1,{"$nulls":75},"直立式结构东防波堤本月进尺420米，累计折合进尺1490米，占东直立堤总长4674米的32%，徐圩港区预制厂原建设工程已完成。","452C38D9600000015B091B22A009EB3A"]
["F410FE0A2A649E20C49CFFD33413DFB1",0,null,"2015Y0005",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,5,55,5,105014,111070,113964,1,0,0,0,18,0,0,0,1900,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"一、形象进度：340省道路线全长42.890公里，其中溧水段17.773公里，江宁段25.117公里。目前本项目按阶段实施建设。第一段：溧水先导段4.6公里于2012年8月开工建设，2013年9月建成通车；第二段：江宁横溪段和溧水段。2015年计划新开24公里，目前已完成江宁横溪段的施工、监理招投标，并完成了项目部的组建工作，由于征地拆迁等原因还未进场施工；溧水段已完成了施工、监理招投标；第三段：江宁禄口段正进行施工图设计工作。\n二、存在问题：目前横溪段（13.68公里）江宁区政府启动了征地拆迁工作，已完成土地丈量、房屋拆迁调查工作，正在进行杆管线迁移调查。指挥部配合开展红线放样和路田分家工作，施工单位也开展驻地建设和测量放样复核等施工前准备工作，待江宁区政府提供建设用地后随时开展施工工作。","452C38DB00000021D4253F83097D6579"]
["3F16F96EB5A5ADD1F86CD19DE0FC72B7",0,null,"2015Y0004",-1,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,12,96,12,260000,243000,303000,{"$nulls":4},24,{"$nulls":3},1005,{"$nulls":15},"全线已完成","464AE565800000215C9C09C8A0BE8932"]
["42E390B423225BAF1A80B155BA721038",0,null,"2015Y0005",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,64,7,212700,335000,253500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,null,5,null,25000,32000,20000,{"$nulls":24},"道路工程基本完成，正在进行吴淞江大桥施工。","4597BDE880000021876F5E47FCCB44CC"]
["22418BE07DD4F19A158FC5532BB4FDA3",0,null,"2015Y0005",-1,6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":5},17,{"$nulls":6},57,null,2,{"$nulls":5},17,{"$nulls":6},57,null,2,{"$nulls":5},17,{"$nulls":6},57,null,2,{"$nulls":20},"4D6F1C538000000151F6EA761DDE2303"]
["B185A53F084B370D9F2F83D92600C5E5",0,null,"2015Y0005",-1,49,null,49,{"$nulls":12},49,null,47,{"$nulls":58},"452C38D5E00000A1458C8685967F617B"]
["247F20A022EE5B2FD2A15CA829E46E6D",0,null,"2015Y0005",-1,{"$nulls":75},"桃乌段路基施工。","46EA9B7380000021C12E5F228EAB22B5"]
["C5D4878F639113C987EB755DD6229113",0,null,"2015Y0004",-1,{"$nulls":75},"北幅路基开挖完成1100米（全长2220米），占开挖总工程量的50%；路基回填完成1000米，占回填总工程量的45%。","48A6EC29E000000142F6B2638633E8C1"]
["2F193E2FA646E46306086C8DB805748D",0,null,"2015Y0004",-1,{"$nulls":75},"建成通车。","494F7BCEC000002123A1FDE2C282EA21"]
["ED889E0D500CBB9EE37D7D002B742D94",0,null,"2015Y0004",-1,{"$nulls":75},"主体结构完工，内装招投标","4A286098C00000211684976214B403C2"]
["E020D7305D050D6D845D38A1B00FA989",0,null,"2015Y0005",-1,36,505,{"$nulls":4},13,100,100,19,111,{"$nulls":5},371,{"$nulls":5},80,90,null,106,{"$nulls":5},315,{"$nulls":5},100,100,null,111,{"$nulls":5},286,{"$nulls":5},50,90,null,106,{"$nulls":20},"452C38DBE00000616AD445E437E62A7E"]
["55724E61C9448781D8390332B700D14E",0,null,"2015Y0005",-1,{"$nulls":75},"该工程已建成通车。","4D89796D80000041D88FE961D2A1C0BB"]
["9439AD273609922E966FB0BB6B24F616",0,null,"2015Y0005",-1,{"$nulls":75},"2015年4月15日交工验收。","495E9EC900000001730FB4206020269D"]
["8F5E7B6FEB54320097CCF42AFF848348",0,null,"2015Y0005",-1,{"$nulls":75},"建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["EBA6E787646B644415832D19D5722EE2",0,null,"2015Y0005",-1,{"$nulls":75},"全线主车道开挖及路基施工，沈思港桥东半幅完成、西侧准备架梁，朝阳河桥西半幅桥面铺装完成，2个箱涵施工完毕。","4A04D699C0000021960B6C19775B7500"]
["02667D8AA13C9552387A4EA2DF5120F4",0,null,"2015Y0005",-1,14,330000,14,120000,120000,120000,0,0,0,0,26,0,0,0,null,7,280000,7,60000,60000,60000,0,0,0,0,6,0,0,0,null,7,150000,7,60000,60000,60000,0,0,0,0,20,0,0,0,null,0,100000,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"目前二期工程正在进行路基开挖，已开挖部分正在回填素土","46B8AAA3A00000217140A795E7A1AE32"]
["ABCDF5A4306EE7ABC32C619688E5D187",0,null,"2015Y0006",-1,{"$nulls":75},"未开工","4596CE63A0000021B9EF1E5E417B9CA3"]
["DB40DF75743C5B0AD61F2E25BD285CFC",0,null,"2015Y0006",-1,{"$nulls":75},"全线进行主车道路基施工，除华元路到朝阳河桥南基本施工至路基最后一层土方；沈思港桥东半幅完成，西半幅板梁架设完毕，朝阳河桥西侧桥面铺装结束，进行护栏施工；2处箱涵施工完毕。","4A04D699C0000021960B6C19775B7500"]
["27B3BFDDEE92B950A09762AE7F63C553",0,null,"2015Y0006",-1,39,227,44,674902,737869,1227090,6,null,null,26,73,{"$nulls":4},39,227,431,674902,737869,1185920,6,null,null,26,73,{"$nulls":19},39,227,431,674902,737869,1185920,6,null,null,26,73,{"$nulls":19},"基本完工","45AB627080000021CEFA9CCF57B58538"]
["649FA91820A241602BC52FA429C0915C",0,null,"2015Y0006",-1,{"$nulls":75},"项目已交工。","495AB173C0000021BD1078AE8F558A41"]
["8A15748C8C56B4F3F033C7349B46E500",0,null,"2015Y0006",-1,{"$nulls":75},"外墙仿石涂料施工完成，屋面防水施工完成。室内外管线基本完成，室外石材铺装基本完成。\n\n","4B1483D320000021B4530B84A599C456"]
["A59EEFB9B68ECAFA3AD267EC082D1688",0,null,"2015Y0006",-1,{"$nulls":75},"弱电、网络线路已基本排布完毕，正在进行调试；道闸、绿化、地下线网、场地道路标志标线等辅助设施建设正在进行，并不断完善；同时正在着手进行综合验收，相关验收材料已上报主管部门，等待验收","4706D6D520000021D78B264A806E8D95"]
["780F07AD85F6A6E2C2B5787B2560AED6",0,null,"2015Y0006",-1,{"$nulls":75},"完成路基填筑98%、路面底基层48%、基层42%、桥梁工程68%。","48173F21C00000213849C18090E227D5"]
["8ABD6F78F13F5A1D0104429A0B2746E9",0,null,"2015Y0006",-1,{"$nulls":75},"实施一期工程阜建高速建湖西互通至建宝路段5.1公里，开展路面施工，建湖西互通至发展大道段完成招标。","4756E0D780000021BD984AD195D60C8A"]
["95656F48CBF4A242B4821A153F92A7FD",0,null,"2015Y0006",-1,{"$nulls":75},"建成通车。","494F7BCEC000002123A1FDE2C282EA21"]
["6B0C4AFF8FEFC2F2C8F13F641531AC55",0,null,"2015Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主体已完成，正在铁路专用线及综合办公楼施工。","452C38D9200000A160383FB696401BD8"]
["767C217CB1B679EAB863709DF7C94875",0,null,"2015Y0006",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["6602A6B47134DDE5B40AD6689F7111B4",0,null,"2015Y0006",-1,{"$nulls":75},"2个泊位水工主体已完工，加快后方道堆真空联合堆载预压施工。","46D11FD040000021CBCE7B927205F9C4"]
["9660D3BD143F4285B70ED49B7ECE203C",0,null,"2015Y0006",-1,{"$nulls":75},"4个泊位水工主体均完工，液化码头车船直取工程通过设计变更审查，基本具备正式投用条件。","46D12095E00000210EEE5BA374F2A089"]
["043303254A40314EA59149DFD0F47E16",0,null,"2015Y0006",-1,{"$nulls":75},"航道疏浚基本完成，正式开通使用","4C2FA45660000021000F98E3BD85A821"]
["1CD5376A9862A49E71D8CBE966FFAB90",0,null,"2015Y0007",-1,66,{"$nulls":74},"用地手续未批复，目前组织路基、路面施工单位进场施工，S5标濉河大桥施工桥面系。","45C5231CE0000021BC17A82CFFD70F54"]
["7B8E7080C65EF770471C331C39A9CE24",0,null,"2015Y0007",-1,36,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,null,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,{"$nulls":46},"452C38DCA00000A1BDA9E5BD6348A13E"]
["C16DABC1958653FB1851585457CB2E44",0,null,"2015Y0007",-1,36,505,{"$nulls":4},13,100,100,19,111,{"$nulls":5},371,{"$nulls":5},80,90,null,106,{"$nulls":5},315,{"$nulls":5},100,100,null,111,{"$nulls":5},286,{"$nulls":5},50,90,null,106,{"$nulls":20},"452C38DBE00000616AD445E437E62A7E"]
["0F038681898E8D7C897913A0646873D6",0,null,"2015Y0007",-1,{"$nulls":75},"项目已交工。","495AB173C0000021BD1078AE8F558A41"]
["63292F07673A53AE6F5A5601B6453176",0,null,"2015Y0007",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6498,2,137,1,43791,23357,21967,null,10,60,1,11,{"$nulls":3},0,8,81,8,254464,258507,312453,null,100,100,4,7,{"$nulls":3},6498,2,71,1,24561,8170,20599,null,10,60,1,7,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1标无矛盾段落进入路基顶施工，底基层已开展施工，迎春河桥板梁架设已完成30%、反坎河桥完成桥面铺装，新桥港桥桩基完成60%；2标堆载预压已卸载50%,正在开展路基顶；主干河桥板梁架设已完成；5标钻孔灌注桩已完成，承台完成60%，箱梁预制完成35片。存在问题：S462广陵段部分标段交地及房屋拆迁总体偏慢，影响总体推进。","464AEA1FC0000021B52E367C631B2D38"]
["0EC75DA79F37C2CF9EC6A5AA49A32CA7",0,null,"2015Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头水工部分已完成总工程量的40%，西侧翼墙正在施工、码头轨道灌注桩已完成10支。附属设施部分，联检大楼已封顶，正进行内部分区施工；口岸大楼地下室已完成，现进行回填；卡口内部装修已基本完成。","44F92AE800000121D51AC7AB782D4663"]
["893025A69B97A0FAEAECB2F5C1A9B0E6",0,null,"2015Y0007",-1,{"$nulls":75},"水工部分连续施工。","4E1F625000000001D7539342E28423AB"]
["DFE83101FC8F5F370F44409004226DEE",0,null,"2015Y0007",-1,2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":5},11,null,0,0,0,null,36,91,{"$nulls":7},31,null,61824,15931,63992,null,50,40,null,1,{"$nulls":5},10,{"$nulls":5},20,35,{"$nulls":21},"                            ","4640A568A0000021A2BC879912C9A53C"]
["A81CF7E53C007E0491C92EAA0A71E7B0",0,null,"2015Y0007",-1,8,68,8,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,65,7,212700,335000,253500,2,100,100,4,7,{"$nulls":3},3700,1,6,1,35529,57699,44383,{"$nulls":8},375,0,6,null,25000,32000,20000,{"$nulls":24},"道路工程基本完成，正在进行吴淞江大桥施工。","4597BDE880000021876F5E47FCCB44CC"]
["6F3ADCDD431C1654E63F2022CCC633CC",0,null,"2015Y0006",-1,{"$nulls":75},"未开工","4596B7A960000021619092F5D6908C5A"]
["C5B18E2CB115977456EBBD5AAE3BC45B",0,null,"2015Y0006",-1,{"$nulls":75},"路基施工全部完成，桥梁施工全部完成，完成防护、边沟工程；路面底基层、基层施工完成100%；路面项目完成下面层施工，完成中面层主线施工，完成上面层试铺，完成收费广场混凝土浇筑；房建单位完成屋面瓦安装及内外墙水泥砂浆粉刷，开展场地施工；隔离栅、主线标志基础施工完成，护栏立柱打设累计完成85%；互通区绿化乔、灌木种植基本完成，完成地被施工；三大系统开展光缆敷设，基本完成设备采购；完成房建区空调设备的招标。","44F92AE780000061E689426EB5202CA4"]
["CA1A9BC7DE245E90191052B627FD9728",0,null,"2015Y0006",-1,{"$nulls":75},"下部结构完成100%，梁板预制结束，梁板安装32.7%，行车道板安装55%。","494F5FA260000021C65146E6197A1225"]
["66FD8F6C7D920F0A895967D2B897A8C0",0,null,"2015Y0006",-1,{"$nulls":75},"目前，324省道徐州东段一期工程睢邳路以西基本完成拆迁，正在开展招标文件及标底编制工作，至6月底完成投资3000万元。","4CDB1D29200000214CA3D9F6DE183F12"]
["C6A00B321E5D00C1E8F1FB532A4A87E3",0,null,"2015Y0006",-1,36,503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":5},503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":7},929179,849170,890542,{"$nulls":12},929179,849170,890542,{"$nulls":25},"452C38D9600000C17C36891B54B019E8"]
["7885C00F382BB7D842AFE4D7BA5AEC6A",0,null,"2015Y0006",-1,{"$nulls":75},"全线完成清表87万平方，占总量100%；完成路基42万方，其中挖方1.8万，填方40万，占总量16%；桥梁工程共完成钻孔桩656根，占总量73%，完成板梁337片，占总量14%。","45FEE20920000001DB1994300FA9DCE3"]
["4154AB60DDE17D231A7707BBF3CB2287",0,null,"2015Y0006",-1,{"$nulls":75},"完成招投标。","494F9423E0000021971B8B67E472FD4B"]
["C5BA77484E91B082E2AC667ECD38F785",0,null,"2015Y0007",-1,{"$nulls":75},"完工。","46EA9D51A0000021F1A72CD5283EA913"]
["20A7934BF9209A0228E21366E66D2481",0,null,"2015Y0006",-1,{"$nulls":75},"南环段已建成，上跨长深高速公路大桥已完成下部结构，正在进行上部结构施工。","4D746069A0000021424848A8623D4A12"]
["4DA1FF4F9F4D329477AC6738C912C87C",0,null,"2015Y0006",-1,{"$nulls":4},2023895,1913509,{"$nulls":4},229,{"$nulls":64},"沥青下面层88000平方","44F92AE9800000A15AC5660EDAD7D017"]
["75222959E7161322AD160FA1F5A831A4",0,null,"2015Y0006",-1,14,330000,14,120000,120000,120000,0,0,0,0,26,0,0,0,null,7,180000,7,60000,60000,60000,0,0,0,0,6,0,0,0,null,7,150000,7,60000,60000,60000,0,0,0,0,20,0,0,0,null,5,130000,0,0,0,0,0,0,0,0,10,0,0,0,{"$nulls":16},"目前二期工程正在进行路槽分层回填，目前已基本填至路基顶部，准备做路面底基层","46B8AAA3A00000217140A795E7A1AE32"]
["E57F0C76490C1B40B13AF0C7ACE955F0",0,null,"2015Y0006",-1,{"$nulls":75},"交通运输局段征地拆迁完成95%，房屋拆迁完成95%，路基基本贯通；徐圩段完成疏港航道大桥及中桥伸缩缝598米；交通工程波形梁钢护栏7000米；铁路下穿段横截沟工程。","44F92AE7E000004126A44C796491035A"]
["86C4BF026C9BA475ED3A59A7D21F7DA2",0,null,"2015Y0006",-1,{"$nulls":75},"尚未开工。","4B2FF7D380000021FF48FF8FCEED99B8"]
["75F8533465A8485F4CD60AD603DC7383",0,null,"2015Y0006",-1,{"$nulls":75},"因选址问题，尚未开工。","4A954A9DA0000001C7610DB35073150F"]
["9368FCD50DB76CABEC22DB336B29A9AA",0,null,"2015Y0006",-1,{"$nulls":75},"正在路基施工。","4D743B53C0000021D528DB4DEF96D439"]
["878DE17C0FF8EA25EEDB43102EDF4EBA",0,null,"2015Y0007",-1,{"$nulls":75},"建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["DF525385E4D88AF060AD977B4A1BF91C",0,null,"2015Y0007",-1,23,317,23,1004360,870174,814407,8,100,100,21,36,{"$nulls":3},2688,null,63,{"$nulls":5},18,33,null,19,{"$nulls":5},269,null,854800,null,null,6,60,68,16,17,{"$nulls":5},15,{"$nulls":6},2,null,3,{"$nulls":20},"4640B76E000000210EEA29218A8BE108"]
["D0F04F323DF5AE9B96D462CB67641137",0,null,"2015Y0006",-1,{"$nulls":75},"三层基建基本结束","46EA9FBB800000213459FE5A48F06D61"]
["31DC54735EDDEBD7EF27A8315E6B0B23",0,null,"2015Y0006",-1,{"$nulls":75},"完成全线驻地建设；便道累计完成19.5km，占总量（各标段累计19.94km，有重叠部分，比全线全长长一些）97.8%；完成桥梁钻孔桩6根，累计完成668根，占总量100%；完成桥梁承台浇筑2个，累计完成128个，占总量100%；桥梁墩柱累计完成208个，占总量96.3%；系梁累计完成24个，占总量92.3%；台帽累计完成48个，占总量92.3%；盖梁累计完成78个，占总量92.9%；预应力现浇箱梁累计完成73幅，占总量86.9%；完成预制梁板32片，累计完成729片，占总量95.8%；完成挂篮悬浇28节段，累计完成158节段，占总量87.7%；完成清表12200 m2，累计完成780408m2，占总量95.4%；完成路基挖方8780m3累计完成543735m3，占总量114.9%；完成路基填方37500m3，累计完成1402042m3，占总量95.9%，湿喷桩和雨水管全部完成。","45835A3940000021498FFD174D21DCE8"]
["7D24FA0D168E5C86228B31E6A3D97696",0,null,"2015Y0006",-1,22,{"$nulls":75},"49E0DFA940000021DE73460C8BA04095"]
["60172D21BB66D19FE3BA7B0104CB45F2",0,null,"2015Y0006",-1,{"$nulls":75},"路基完成填筑117万方，已全部完成；路面底基层已摊铺46万平方，占总量80%，基层摊铺完成28万平方，占总量52%；路面完成18万平方，占总量35%；桥涵结构物已基本完成。","45FECF71600000215E4D818AE95457DF"]
["578A24101681408AEB0124B0DE9C81CB",0,null,"2015Y0006",-1,{"$nulls":75},"505省道新沂西北绕城段除铁路下穿及引道外已基本完成，主线已交工并试运营","45FEF32D00000021423E6CF783387D9D"]
["84E9EA4C8AA12E9F975959B976276E26",0,null,"2015Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"累计完成7公里的路面及附属设施，桥梁完成1座，涵洞完成2个，粉喷桩完成24万延米，第二层水稳完成1.7公里。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["B20469FA4B23CEF3BDEDB4D418090514",0,null,"2015Y0006",-1,{"$nulls":75},"土方工程：清淤完成98%，素土完成80%，灰土完成86%；\n下部结构：墩身完成95%，承台完成99%，立柱完成99%，系梁完成99%，盖梁完成95%；\n上部结构：现浇箱梁完成80%，预制板梁完成78%；\n独立工程：箱涵完成85%，人通完成78%，圆管涵完成96%。","46EA9C3D40000021E09CDF7BE3DADF50"]
["8311229F9C380E199F5F0BA2254A3AE7",0,null,"2015Y0006",-1,{"$nulls":75},"目前，正在进行路基施工。","4E0AAEDB80000001A21A3E3285F69BC1"]
["64C9DA9BB4FF2510DF0BF83756E149AB",0,null,"2015Y0006",-1,{"$nulls":75},"目前，淮阴区段正在进行路基施工。","4D989A7680000021CAE7FBD451FCC003"]
["F21FB0295DF8FEADF61E9447D46EE116",0,null,"2015Y0006",-1,96,{"$nulls":74},"泗洪段已全部复工。","45AB8817400000218E63FD22BDA91CE1"]
["F30FE584E37A85659A0808FEB40E8884",0,null,"2015Y0006",-1,{"$nulls":75},"完成征地拆迁等前期工作，完成桩基施工,开始现浇横梁，预制纵梁","4C53E8ABA00000211ABB7531249DFDBD"]
["3FCBE500399F45AAFB0EFE4BD4E38429",0,null,"2015Y0006",-1,40,null,40,{"$nulls":12},26,null,26,{"$nulls":12},10,null,10,{"$nulls":42},"建成通车一期工程G204至S229段25.96公里。","45930AC0A00000013A88F40431F8C61A"]
["D17604BF8CA908F65C06DF8C5345EE21",0,null,"2015Y0006",-1,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,null,null,17,null,400700,1211300,{"$nulls":11},17,null,400700,1211300,{"$nulls":25},"452C38D5A00000A1C369596A7753C333"]
["7E34B6E4F7D67200B024798B584147D1",0,null,"2015Y0006",-1,5,95,5,208954,196309,573301,4,100,100,5,26,{"$nulls":3},4978,{"$nulls":61},"452C38DBA0000101EE35873CD541EA02"]
["5E2C2CB338697F3B6D087533BAE49D8A",0,null,"2015Y0007",-1,11,5,11,837817,768716,868818,1,100,100,5,12,{"$nulls":4},11,4,11,837817,627887,709688,1,100,100,4,10,{"$nulls":5},1,null,153488,140828,159130,{"$nulls":4},2,{"$nulls":5},1,null,153488,{"$nulls":5},1,2,{"$nulls":20},"45D4A12B00000021B86B31C7A15832ED"]
["D184F13DFDB4FCE7038E978390008B39",0,null,"2015Y0007",-1,{"$nulls":75},"目前，一期已建成。","4582F984A00000210B371656660E7377"]
["346C6FBC57BEC703112AA4FD49BEA41D",0,null,"2015Y0007",-1,{"$nulls":75},"建成通车。","494F7BCEC000002123A1FDE2C282EA21"]
["CE4D8584609CD562FFAF18BE1DFE9571",0,null,"2015Y0008",-1,5,95,5,208954,196309,573301,4,100,100,5,26,{"$nulls":3},4978,{"$nulls":61},"452C38DBA0000101EE35873CD541EA02"]
["345117A04B75B37E7C5F8E847C283C22",0,null,"2015Y0008",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,629,10,972500,1015500,2154300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,25,0,12500,980400,148900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"全线后半段坟头至终点约11公里段落除了1处部队矛盾节点影响约700米辅道段落外，其余全部建成；前半段起点至坟头约10公里段落进行路基、桥梁、路面及附属工程施工。\n路基：完成土石方开挖356.4万方（96%），土石方填筑274万方（96.3%）；\n路面：水稳碎石基层102万平方（89.8%)，12%灰土97.25万平方（85.9%)，沥青215.83万平方(90.7%)；\n桥梁：31180万元（79.5%）；\n交安5450万元（42%）；\n绿化4700万元（88.3%）。","44F92AE840000101423CCFA36BCE2089"]
["12B57F5A0C5225310E82646E632A97AB",0,null,"2015Y0008",-1,2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":5},16,null,0,0,0,null,40,91,{"$nulls":7},31,null,61824,15931,63992,null,50,40,null,1,{"$nulls":5},15,{"$nulls":5},24,35,{"$nulls":21},"                            ","4640A568A0000021A2BC879912C9A53C"]
["0C3D7BBDF6DBA366A8B48CEF88CF0DC9",0,null,"2015Y0008",-1,{"$nulls":75},"工程完工。","494F759FA0000021B650A21A5A0C6724"]
["3E11A8849E9C7C918F110D37601B85F1",0,null,"2015Y0008",-1,null,null,28,165408,162616,160382,{"$nulls":3},1,{"$nulls":7},24,141778,139385,137470,{"$nulls":3},1,{"$nulls":7},28,165408,162616,160382,{"$nulls":3},1,{"$nulls":7},24,141778,139385,137470,{"$nulls":3},1,{"$nulls":21},"45977C86A000000145F95B717A76C135"]
["CE518550F829CA301FF9BF7E616DFFE0",0,null,"2015Y0008",-1,34,490,34,1100000,900000,2480000,3,{"$nulls":3},102,{"$nulls":4},17,329,6,563000,470000,340000,0,{"$nulls":3},80,{"$nulls":4},17,280,10,770000,450000,1240000,0,{"$nulls":3},52,{"$nulls":4},0,151,0,410000,330000,0,0,{"$nulls":3},30,{"$nulls":19},"1、晶桥段  除上面层沥青未摊铺，其余全部完成  2、白马段  基本完成水稳摊铺  3、晶桥-明觉段 路基土石方施工、特大桥等桥梁进行桩基施工。","44F92AE780000001F6AE7427CA69104E"]
["D40A77C436520D633F1E07A117C45706",0,null,"2015Y0008",-1,{"$nulls":75},"项目已交工。","495AB173C0000021BD1078AE8F558A41"]
["B912237B0CBB9E1F7704CB233A511B75",0,null,"2015Y0008",-1,36,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,null,412,null,448217,403072,1904815,11,100,100,8,62,{"$nulls":3},67697,{"$nulls":46},"452C38DCA00000A1BDA9E5BD6348A13E"]
["B385E9B065B1A0A701FF6F3AAD42C9AB",0,null,"2015Y0008",-1,23,65,23,768644,2112420,2518604,2,100,100,4,11,{"$nulls":3},10640,5,43,5,192161,528105,629651,1,40,40,2,7,{"$nulls":4},5,43,5,192161,528105,629651,1,70,90,3,8,{"$nulls":3},10640,5,43,5,192161,528105,629651,1,null,40,2,7,{"$nulls":20},"4D897AEAA00000212EF01FB341272DCF"]
["A701BEBAD3E8549F4B6CCBA668F98157",0,null,"2015Y0008",-1,11,5,11,837817,768716,868818,1,100,100,5,12,{"$nulls":4},11,4,11,837817,670135,709688,1,100,100,4,10,{"$nulls":5},1,null,153488,140828,159130,{"$nulls":4},2,{"$nulls":5},1,null,153488,42248,{"$nulls":4},1,2,{"$nulls":20},"45D4A12B00000021B86B31C7A15832ED"]
["D881DB49166AB8C40C490924DE09D083",0,null,"2015Y0008",-1,{"$nulls":75},"已完工","4B1483D320000021B4530B84A599C456"]
["801153C27752487910832BB3440B5025",0,null,"2015Y0008",-1,{"$nulls":75},"\n综合楼墙体砌筑完成，门窗开始安装，停保楼屋顶水泥浇筑完成，墙体砌筑完成","4B14884340000021189A7EFB592151AB"]
["F31D274F087E9FB16467568795C1E96D",0,null,"2015Y0008",-1,{"$nulls":75},"目前沛县段（28.918公里）完成清表90万平方，占总量105%；完成路基56万方，占总量21%；桥梁工程共完成钻孔桩710根，占总量82%，完成板梁663片，占总量27%。铜山段（25.366公里）由于征地拆迁未启动，施工图设计无法开展。","45FEE20920000001DB1994300FA9DCE3"]
["A8435B8933D45439AD616E8A991DEE35",0,null,"2015Y0008",-1,{"$nulls":75},"码头水工完成。陆域方案设计正在报请省厅变更。","45B27FD3A0000001E7A4DAE02DD98961"]
["E709CD35BC5378CABBB424A96F855360",0,null,"2015Y0008",-1,7,72,8,295475,268617,244197,1,100,100,0,12,{"$nulls":3},7276,null,43,null,67959,29548,0,0,10,50,0,8,{"$nulls":3},0,7,72,8,295475,268617,244197,1,100,100,0,12,{"$nulls":3},7276,null,43,null,67959,29548,0,0,10,50,0,8,{"$nulls":3},0,{"$nulls":15},"形象进度：路基正在开展开挖回填施工，路面基层施工进展顺利，桥梁正在开展下部基础桩基施工。存在问题：暂无。","4D70741A20000021FFF8CC821D5CE7DB"]
["5B838048F0F377BF24FC1D90BDE8BE33",0,null,"2015Y0008",-1,40,null,40,{"$nulls":12},26,null,26,{"$nulls":12},10,null,10,{"$nulls":42},"建成通车一期工程G204至S229段25.96公里。","45930AC0A00000013A88F40431F8C61A"]
["20EC4806B1D0C2F8FE5B593FD3450BF5",0,null,"2015Y0008",-1,{"$nulls":75},"目前，南接线已完成，正在进行桥梁桩基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["B45A6CF2D1D1DACE5BCABBE079874208",0,null,"2015Y0008",-1,{"$nulls":75},"505省道新沂西北绕城段除铁路下穿及引道外已基本完成，主线已交工并试运营","45FEF32D00000021423E6CF783387D9D"]
["EBC10AC8CE50BBF00B0A82119FD82080",0,null,"2015Y0008",-1,{"$nulls":75},"开展半幅老路挖除和雨污水管施工","4EDD9C40A0000021AB18D369C57D514A"]
["DE70AB78AC359EDDEF94106A1AF43D14",0,null,"2015Y0008",-1,{"$nulls":75},"    集散中心已封顶，进行各项收尾工作，正在进行消防电气等设备调试工作；仓储中心B1/B2封顶，正在进行室内墙体砌筑、消防水电和门窗等安装，综合楼框架封顶，进行幕墙安装和消防水电安装。二期开始报建手续和地基处理。","4A09BB5320000021A7468129AEC6112D"]
["451DC8A5A929CF66D4EC97FDD413F0B1",0,null,"2015Y0008",-1,{"$nulls":75},"正在进行码头水工结构建设","45976E9000000021C54DD05DD7B93E65"]
["0B0C91405ADE6AD8C53F20A05A89FA4A",0,null,"2015Y0008",-1,{"$nulls":75},"项目前期工作基本完成；市区段和灌南段已确定施工、监理单位，灌云县已完成灌云北段招投标工作，东海县正在进行招标工作；征地拆迁工作已同步启动。","4D742EF9800000214C6FE56D1F577720"]
["E572B9D1646A481F17E42ED451321104",0,null,"2015Y0007",-1,{"$nulls":75},"已完成119.41公里实现贯通，跨海大桥基本贯通，跨铁路桥完成桥面铺装及水稳。","4A953E3E000000613D13CA6F74E1236C"]
["53273522F939AD7ECE03D27AB7E1AF45",0,null,"2015Y0007",-1,{"$nulls":75},"尚未开工。","4B2FD99E000000217EF51296349F80B0"]
["D6D464D400B7266E527874653EE2A6B9",0,null,"2015Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头工程和疏港航道完成100%；北侧港区排水工程、用电工程和调度楼等附属设施完成100%，码头前沿道路和堆场完成97%，完成龙门吊底梁及轨道安装,建成港池内三纵一横道路，完成雨水管道约600米、污水约300米、自来水等给排水工程，完成专变内变压器安装就位，完成约1.5万平方米的堆场仓库，调度楼内装基本完成。","44F92AE740000061422D7CBDB598F0A4"]
["779C67AE86197DF5F9F9C35F30A9CCB0",0,null,"2015Y0007",-1,{"$nulls":75},"除盐河三桥两侧及新兴北路以东液化气站外，已全线贯通。","4D74230D8000002178E3CF444AE9AE57"]
["6EC2BFCFC3765E56E1E2F612BB1F72C7",0,null,"2015Y0008",-1,14,136,14,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,112,0,{"$nulls":3},0,{"$nulls":3},35,{"$nulls":4},14,86,14,{"$nulls":3},2,{"$nulls":3},13,{"$nulls":5},72,0,{"$nulls":3},0,{"$nulls":3},10,{"$nulls":19},"正在进行路基施工，桥梁正在进行梁板架设。","45A630DD40000021758080AC865FC45B"]
["2A87804B184884DDCC56238D98B7E420",0,null,"2015Y0008",-1,42,null,42,{"$nulls":73},"45C546C200000021547764ADF0037399"]
["043131EA23F5FC405C5CE74A5501B5CE",0,null,"2015Y0008",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":65},"45D5A240A0000021D818821C8141EA27"]
["AFB773452357F074F6D9327E22EF544A",0,null,"2015Y0008",-1,{"$nulls":75},"路基完成填筑117万方，已全部完成；路面底基层已摊铺57万平方，占总量98%，基层摊铺完成33万平方，占总量90%；路面完成32万平方，占总量60%；桥涵结构物已基本完成。","45FECF71600000215E4D818AE95457DF"]
["073060A0384B22649616019253F6E1C1",0,null,"2015Y0007",-1,{"$nulls":75},"工程完工。","494F759FA0000021B650A21A5A0C6724"]
["FD8D0621893E12828BA7111875DCEE73",0,null,"2015Y0007",-1,6,52,6,214000,196000,367000,2,32,68,1,8,{"$nulls":3},858,3,26,3,107000,98000,183500,2,32,68,1,8,{"$nulls":4},2,20,2,100000,40000,150000,2,32,68,1,8,{"$nulls":4},3,26,3,107000,98000,90000,2,32,68,1,8,{"$nulls":19},"建成通车","4D75CB95E0000021F0C08F4C2B0DAD01"]
["C6123716BF703F4375A1E4D179EEF28E",0,null,"2015Y0007",-1,{"$nulls":75},"目前，正在进行路基和桥梁下部结构施工。","4583086800000021610D57307F655C40"]
["6B2B47771800E3D448D8167E9AE9394B",0,null,"2015Y0007",-1,{"$nulls":75},"建成通车","48B15A89C0000021CEB0D93D0A59616D"]
["4E6BFE38E3C6CD0403D312EB2F8E7B51",0,null,"2015Y0007",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["04F1581A40A156BA90E9245FF90E18CE",0,null,"2015Y0007",-1,{"$nulls":75},"该项目正在进行前期准备工作。","4D935B05A00000212B96F38D231EA5C3"]
["E2DDE83F4FD7095242F69142C8798FB1",0,null,"2015Y0008",-1,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,null,null,17,null,400700,1211300,{"$nulls":11},17,null,400700,1211300,{"$nulls":25},"452C38D5A00000A1C369596A7753C333"]
["C4E8469AC5E14835C98133399D10513E",0,null,"2015Y0008",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6498,2,137,1,78895,50222,34319,null,60,90,1,11,{"$nulls":3},0,8,81,8,254464,258507,312453,null,100,100,4,7,{"$nulls":3},6498,2,71,1,59665,35035,32951,null,60,90,1,7,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1标无矛盾段落进入路基顶施工，底基层已完成500米，迎春河桥板梁架设已完成30%、反坎河桥完成桥面铺装，新桥港桥桩基完成60%；2标路基顶完成50%,；主干河桥主体已完成；5标钻孔灌注桩已完成，箱梁预制完成41片。存在问题：S462广陵段部分标段交地及房屋拆迁总体偏慢，影响总体推进。","464AEA1FC0000021B52E367C631B2D38"]
["DDA77E7E4DCC7EFBA9D1147EE15CD4CF",0,null,"2015Y0008",-1,27,30,27,122766,613829,613829,2,null,null,22,{"$nulls":66},"4CDEBC14800000214E9C959259B62979"]
["C3B76E73B5ECFEE43F9F664F2CEB0853",0,null,"2015Y0007",-1,{"$nulls":75},"正在进行岸线审批准备工作。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["B4FF0690309FEF0BE0D24DC87D4550B8",0,null,"2015Y0007",-1,24,340,24,652423,590283,564435,2,100,100,11,79,{"$nulls":4},21,241,0,65242,0,0,0,70,100,2,72,{"$nulls":4},15,274,24,652423,590283,564435,2,80,70,11,72,{"$nulls":4},12,205,0,65242,0,0,0,50,70,2,65,{"$nulls":19},"路基、桥涵施工。","45A64AD8E000002115357ED0397AE2AC"]
["1BA745B4722CA810E0B752F834B58F8C",0,null,"2015Y0007",-1,{"$nulls":75},"未开工","4596CE63A0000021B9EF1E5E417B9CA3"]
["EB4AAE201EBC89052FE343CD18238DE3",0,null,"2015Y0007",-1,{"$nulls":75},"已建成通车。","4D7436E9200000216F6AB840E6468357"]
["D99F2F6C334B58D515579669DFD411E2",0,null,"2015Y0007",-1,{"$nulls":75},"水工工程扫尾，1-6#泊位后方堆场、7-14#泊位后方堆场、变电所及其它附属设施、综合办公楼完工；装卸设备、电缆等购置安装等。","46D11E59C00000215FEEE684519DC4AA"]
["25D1B0F4E4F15BD5CAF8FE1FBB513728",0,null,"2015Y0007",-1,{"$nulls":75},"码头水工主体完工，加快后方陆域施工","4C2FD279600000213429D9E7E0D2E66E"]
["9F8240ACC7FE946691E0F39EDDD77FBE",0,null,"2015Y0007",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["E3DC16B84E841B5EEAA5393823B7AC39",0,null,"2015Y0007",-1,{"$nulls":75},"桃乌段路基施工。","46EA9B7380000021C12E5F228EAB22B5"]
["47DD9F2AD0526C2F0EE27313D3B88886",0,null,"2015Y0007",-1,{"$nulls":75},"三层基建结束，室内场地硬化","46EA9FBB800000213459FE5A48F06D61"]
["3B1EC7970EDDA97EA4854361A361AEC9",0,null,"2015Y0007",-1,49,310,49,1200000,920000,1100000,8,52,48,9,159,{"$nulls":4},48,310,42,1000000,920000,1100000,8,52,48,9,159,{"$nulls":49},"盐都段已建成G204至盐龙段6.5公里，盐龙至楼王段完成路面面层100%、绿化88%、交通工程90%；建湖段已完成路面底基层65%、基层30%、桥梁工程91%。","452C38D5E00000A1458C8685967F617B"]
["0023AB7FCDAE77AEC70C545125B2710B",0,null,"2015Y0007",-1,{"$nulls":75},"完成征地拆迁等前期工作，完成桩基施工,完成横梁施工，安装纵梁","4C53E8ABA00000211ABB7531249DFDBD"]
["E34F99553AD111E4188284E841C3F0C5",0,null,"2015Y0007",-1,21,42,24,475676,782162,2600093,13,100,100,4,289,{"$nulls":4},21,33,22,458460,756732,2274240,13,100,100,4,288,{"$nulls":4},3,13,5,107216,124681,421143,0,null,null,1,1,{"$nulls":4},3,36,22,505250,819724,2326499,0,null,null,1,{"$nulls":20},"江阴大道：完工    世纪大道段：1、澄鹿路以南（K18+600-K20+139.66）右幅主车道K18+700-K20+098完成至一层沥青；左幅主车道K18+700-K20+098完成至一层沥青，左幅纵向雨水管全部完成。  2、澄鹿路至周庄西大街（K20+139.66-K21+480）左右幅主车道完成至两层沥青；左右幅辅车道完成至水稳基层。  3、周庄西大街至芙蓉大道（K21+480-K24+056.959）中央带及侧分带处理完成。   4、 桥梁情况：芦墩浜桥东侧施工全部完成，西侧灌注桩施工全部完成。","463C21FC8000000100F79216FB20DD61"]
["AB5F563AF1709818458A0A38EE308DCD",0,null,"2015Y0007",-1,7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":21},"481FB13480000021DF891907B35F942C"]
["62AEBA2FE74AF7FD53507CEFD5C0D658",0,null,"2015Y0008",-1,23,317,23,1004360,870174,814407,8,100,100,21,36,{"$nulls":3},2688,null,66,{"$nulls":5},18,34,null,19,{"$nulls":5},269,null,854800,null,null,6,60,68,16,17,{"$nulls":5},18,{"$nulls":6},3,null,3,{"$nulls":20},"4640B76E000000210EEA29218A8BE108"]
["5AA669DBAD7BE074EC7BE7115C610B8D",0,null,"2015Y0008",-1,24,340,24,652423,590283,564435,2,100,100,11,79,{"$nulls":4},22,271,0,87000,2500,0,0,85,100,2,75,{"$nulls":4},15,274,24,652423,590283,564435,2,80,70,11,72,{"$nulls":4},13,235,0,87000,2500,0,0,65,70,2,68,{"$nulls":19},"路基、底基层、基层试验段施工；桥涵（部分桥梁进入桥面铺装阶段）施工。","45A64AD8E000002115357ED0397AE2AC"]
["DC7052F8BD14325DA1B3716C71289AD6",0,null,"2015Y0008",-1,{"$nulls":75},"项目建成通车。","477AAD380000002159DCBA91BD5FA484"]
["2F30E940AEEB72BC381E3910609FB4B7",0,null,"2015Y0007",-1,{"$nulls":75},"已完工。","4583615A60000021DC0FF956ED7DE8A7"]
["DD33950E47E4DE53FFB0AF298B220463",0,null,"2015Y0007",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主体已完成，正在侯工楼A内外装修，停车场施工。","452C38D960000061A773E74DF5A30C52"]
["82541504B6DD04D242475BA584CBE24C",0,null,"2015Y0007",-1,null,270,{"$nulls":8},68,{"$nulls":64},"路基填筑完成4.4万方，梁板安装18片，雨水管道完成3000米，污水管道完成800米","44F92AE9A0000001A6C4B4A0FE608B65"]
["F6DB0823F0DA73E8901B2BA333DF7A37",0,null,"2015Y0007",-1,{"$nulls":75},"完成路面基层100%、面层60%。","48171CB940000001DAB3F475A2461DC6"]
["A0FA9E0317823791F911F582D1E48480",0,null,"2015Y0007",-1,{"$nulls":75},"东海段已建成，市区段路基完成清表约4.5km，完成山场碎石土回填约11万方。","4596D75C6000002113AB2207297BA0CF"]
["39CB2413CA96123429C84CFD4501D527",0,null,"2015Y0007",-1,{"$nulls":75},"正在路基施工。","4D743B53C0000021D528DB4DEF96D439"]
["E32FA03E5EDECE8F738FCDFB36154E83",0,null,"2015Y0007",-1,{"$nulls":75},"目前沛县段（28.918公里）完成清表90万平方，占总量105%；完成路基44万方，占总量17%；桥梁工程共完成钻孔桩710根，占总量79%，完成板梁517片，占总量21%。铜山段（25.366公里）由于征地拆迁未启动，施工图设计无法开展。","45FEE20920000001DB1994300FA9DCE3"]
["88F41EEFB9D22016DF58C201EB8C1683",0,null,"2015Y0008",-1,{"$nulls":75},"除盐河三桥两侧及新兴北路以东液化气站外，已全线贯通。","4D74230D8000002178E3CF444AE9AE57"]
["74F5DA099555C135F58BF49AB9180BF6",0,null,"2015Y0008",-1,{"$nulls":75},"徐新公路市交通运输局段征地拆迁完成98%，新海新区段800米已完成路面工程，其余路段完成路面基层1.5公里，上跨连徐高速主线桥完成桩基77%，箱梁架设完成5片；徐圩段已全线贯通，完成22公里路面工程。","44F92AE7E000004126A44C796491035A"]
["4668D723B0B16BD0FDB7A5EC79BCCDBD",0,null,"2015Y0008",-1,{"$nulls":75},"2个泊位水工主体已完工，后方61万方米场地地基处理工程基本完工。\n","46D11FD040000021CBCE7B927205F9C4"]
["01B2C0DDE5EC86B08A76AE65A004A3AA",0,null,"2015Y0009",-1,23,317,23,1004360,870174,814407,8,100,100,21,36,{"$nulls":3},2688,null,107,{"$nulls":5},30,38,null,23,{"$nulls":5},269,null,854800,null,null,6,60,68,16,17,{"$nulls":5},59,{"$nulls":5},12,7,null,7,{"$nulls":20},"4640B76E000000210EEA29218A8BE108"]
["AAE020813273FC60CBF512888278DAA6",0,null,"2015Y0009",-1,{"$nulls":75},"已完成672根桩基施工,完成年度计划;上部结构完成1.81万方,为年度计划的87.4%;护岸、护坡工程完成360米，完成年度计划；航道疏浚完成50万方，为年度计划的62.5%。","4B965806A000000167CD9E21EF5CA9FB"]
["0870DD9EF10E1269E9FA63CCC7595A33",0,null,"2015Y0009",-1,16,10,16,130000,122000,112500,{"$nulls":4},18,{"$nulls":4},16,10,0,130000,70000,0,{"$nulls":4},12,{"$nulls":4},16,10,16,130000,122000,112500,{"$nulls":4},18,{"$nulls":4},16,10,0,130000,70000,0,{"$nulls":4},12,{"$nulls":19},"水稳摊铺7公里。","4A846A5BE0000001857A4A36BC850D64"]
["56F85733DA6768217CB477F58C538642",0,null,"2015Y0009",-1,{"$nulls":75},"码头水工主体完工，加快后方陆域施工","4C2FD279600000213429D9E7E0D2E66E"]
["029CF0FBCFA9EFDB5731F157F70C7EF5",0,null,"2015Y0009",-1,{"$nulls":75},"已经建成22.8公里，完成纵三至纵五段图纸设计，正在办理招投标手续。","452C38DA80000041BB1AF46EF3FAECC2"]
["917A3AF6B4A1BBF50315BB367232159A",0,null,"2015Y0009",-1,{"$nulls":75},"已开工202公里、完工81公里，桥梁开工20座，完工7座。","4A847B5C800000014545309CA6FC8CB7"]
["75A5D0C0FCCBD65F1C60EE9CAEC6052E",0,null,"2015Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主体已完成，铁路专用线开通，综合办公楼施工。\n","452C38D9200000A160383FB696401BD8"]
["DEE37FA4672F451D0A787236FC2F8FE2",0,null,"2015Y0008",-1,{"$nulls":75},"建成通榆河大桥和射阳河大桥。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["B89210C21C12255E8B0BF6C50444951A",0,null,"2015Y0008",-1,{"$nulls":75},"面层浇筑完毕","44F92AE8C0000061CA99E73B5A18BBB6"]
["C3085BCBAE0A8240C9AB93F461B466BB",0,null,"2015Y0008",-1,{"$nulls":75},"完成桩基施工157根,为年度计划的33.3%;完成疏浚164.4万方,为年度计划的76.1%","4B96568F00000021E184EC6C9CE9F9DC"]
["C238457912C0B275E3BB3D5519FCD300",0,null,"2015Y0008",-1,{"$nulls":75},"已开工159.4公里、完工65公里，桥梁开工16座，完工7座。","4A847B5C800000014545309CA6FC8CB7"]
["FF1B83D496B0D94BE82C70CD4AD68C90",0,null,"2015Y0008",-1,{"$nulls":75},"正在推进前期工作。","4B2FF7D380000021FF48FF8FCEED99B8"]
["A1834B445A1ECA65BF3972A026D7B092",0,null,"2015Y0008",-1,{"$nulls":75},"航道疏浚基本完成，正式开通使用","4C2FA45660000021000F98E3BD85A821"]
["0B89DA9D993720C0005CB58F973D29E2",0,null,"2015Y0008",-1,{"$nulls":75},"主体工程施工","4FA5A5A2000000216A85C1E239B9DBA7"]
["09099FAC57F8A5C82A5292F149FD30F9",0,null,"2015Y0008",-1,{"$nulls":75},"该项目已建成，投入使用","4FA5D27D20000021E0A020F454722DD5"]
["182C5972C1A24FF913FA847B9D5A2143",0,null,"2015Y0009",-1,null,null,28,165408,162616,160382,{"$nulls":3},1,{"$nulls":7},24,141778,139385,137470,{"$nulls":3},1,{"$nulls":7},28,165408,162616,160382,{"$nulls":3},1,{"$nulls":7},24,141778,139385,137470,{"$nulls":3},1,{"$nulls":21},"45977C86A000000145F95B717A76C135"]
["B7229506835B32C599656C3D5A850C84",0,null,"2015Y0008",-1,{"$nulls":75},"建成通车。","494F7BCEC000002123A1FDE2C282EA21"]
["B72F09B1A171DB5F4CB403A2E651B745",0,null,"2015Y0009",-1,36,503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":5},503,null,929179,849170,890542,14,100,100,18,192,{"$nulls":7},929179,849170,890542,{"$nulls":12},929179,849170,890542,{"$nulls":25},"452C38D9600000C17C36891B54B019E8"]
["2419063DBCEA23560DAF0A6FDD477D5A",0,null,"2015Y0009",-1,34,490,34,1100000,900000,2480000,3,{"$nulls":3},102,{"$nulls":4},34,339,6,583000,490000,340000,0,{"$nulls":3},85,{"$nulls":4},17,280,10,770000,450000,1240000,0,{"$nulls":3},52,{"$nulls":4},17,161,0,430000,350000,0,0,{"$nulls":3},35,{"$nulls":19},"1、晶桥段  除上面层沥青未摊铺，其余全部完成  2、白马段  基本完成水稳摊铺  3、晶桥-明觉段 路基土石方施工、特大桥等桥梁进行桩基施工。","44F92AE780000001F6AE7427CA69104E"]
["7898D2FA179D282CBA8C68744C6AADBA",0,null,"2015Y0009",-1,{"$nulls":75},"主体工程完工,配套设施施工","46EA9FBB800000213459FE5A48F06D61"]
["515D52D963E0E2AFEFBE69B6CEABDDCD",0,null,"2015Y0009",-1,{"$nulls":75},"    全线除华元路到朝阳河桥南主车道路基管道施工，其余主车道贯通；沈思港桥主体完成，朝阳河桥西侧完成，东侧已拆除；2处箱涵施工完毕。\n","4A04D699C0000021960B6C19775B7500"]
["D6CD90AC6A5C42063A9EB0A9E095D8ED",0,null,"2015Y0009",-1,{"$nulls":75},"建成通车","494F86EDE00000215894D3EF8FBDFA9B"]
["09B3E5AA7E869E7D920359E05EA866DB",0,null,"2015Y0009",-1,{"$nulls":75},"建成通车。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["A755435B3021620B1A6C216F51E93562",0,null,"2015Y0009",-1,6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":5},17,{"$nulls":6},57,null,2,{"$nulls":5},17,{"$nulls":6},57,null,2,{"$nulls":5},17,{"$nulls":6},57,null,2,{"$nulls":20},"4D6F1C538000000151F6EA761DDE2303"]
["14792C4B66EF103FFF23DD5D6742BE06",0,null,"2015Y0008",-1,{"$nulls":75},"结合围填开展疏浚","452C38DAC0000021F1078262468FCCED"]
["23988FB6E654739EFE22DC1EDE4440DA",0,null,"2015Y0008",-1,{"$nulls":75},"斜坡式结构东防波堤工程今年折合进尺800米，累计折合进尺7200米，占斜坡式结构东防波堤工程总长7834米的92%。","452C38DA800000A19C9699F0088370B9"]
["5BA101AA9FB173677877EC3D438698ED",0,null,"2015Y0009",-1,10,254,10,536564,496499,766766,13,100,100,5,78,{"$nulls":3},5973,null,222,{"$nulls":5},75,95,3,78,{"$nulls":5},120,{"$nulls":5},70,80,3,78,{"$nulls":5},149,{"$nulls":5},75,83,3,78,{"$nulls":20},"452C38D900000041E569F21C93091E69"]
["6EFFA972B5EEC4ED352313524AE96CC8",0,null,"2015Y0009",-1,3,44,8,114650,107100,202540,3,100,100,null,20,{"$nulls":3},1280,3,44,null,114650,107100,null,null,92,100,null,20,{"$nulls":3},640,null,2,null,114650,107100,null,null,60,23,{"$nulls":5},800,null,2,null,114650,107100,null,null,63,23,{"$nulls":5},640,{"$nulls":16},"497E9E23600000218DA200E95CCB2352"]
["DD2B7219A5992B4CD2EAE0C28E0BB420",0,null,"2015Y0009",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6498,6,137,1,101338,50222,34319,null,60,90,1,11,{"$nulls":3},0,8,81,8,254464,258507,312453,null,100,100,4,7,{"$nulls":3},6498,6,71,1,82108,35035,32951,null,60,90,1,7,{"$nulls":3},0,{"$nulls":15},"形象进度：全线分为5个标段，1标无矛盾段落路面底基层已完成65%，水稳试验段已完成，迎春河桥、坎河桥主体完成；2标路面底基层完成90%,；3标路面底基层完成75%，主干河桥主体已完成；5标桩基、下部结构和梁板预制已完成，正在进行南北桥头接线的施工和梁板的安装，约完成工程量的70%。存在问题：S462广陵段部分标段房屋拆迁总体偏慢，影响总体推进。","464AEA1FC0000021B52E367C631B2D38"]
["4941CBBEA06D23153F644BFA283167AB",0,null,"2015Y0009",-1,{"$nulls":75},"完成征地拆迁等前期工作，完成桩基施工,完成横梁施工，完成纵梁安装，开始码头面施工。完成道路、堆场20%","4C53E8ABA00000211ABB7531249DFDBD"]
["1ABCB206487D9EBC02B0C2C58632D7B4",0,null,"2015Y0009",-1,{"$nulls":75},"全线完成清表52万平方，完成路基土石方125万方，其中填筑101万方，占总量98%；挖方13.5万方，全部完成。已完成路面工程水泥稳定碎石底基层摊铺7.4万方，占总量的95%，基层摊铺12.3万方，占总量90%。桥梁工程钻孔桩已全部完成；梁板预制完成392片，已全部预制完毕。下面层已完成单幅16公里，中面层单幅14公里，准备进行上面层试验路。","45FE71CB2000002194A74D73D6EB648C"]
["480A23077F3325AB823F0D096A037A30",0,null,"2015Y0009",-1,{"$nulls":75},"505省道新沂西北绕城段除铁路下穿及引道外已基本完成，主线已交工并试运营","45FEF32D00000021423E6CF783387D9D"]
["D2F61A6006968F80AF496D883541D94A",0,null,"2015Y0009",-1,42,null,42,{"$nulls":73},"45C546C200000021547764ADF0037399"]
["2E8915FDF85122501524D5FD55BDF3F3",0,null,"2015Y0009",-1,{"$nulls":75},"因该项目地块土地未确权，目前只能进行至选址阶段，待完成土地确权后开始报建手续。","4A613592E000002194B46D647ABA77F9"]
["A579370032636B48F52E348934118466",0,null,"2015Y0009",-1,{"$nulls":75},"完成路面基层100%、面层65%。\n","48171CB940000001DAB3F475A2461DC6"]
["41537D0D615EEAA70C0DC6A685C4150D",0,null,"2015Y0009",-1,6,52,6,214000,196000,367000,2,32,68,1,8,{"$nulls":3},858,6,52,6,214000,196000,367000,2,32,68,1,8,{"$nulls":3},858,2,20,2,100000,40000,150000,2,32,68,1,8,{"$nulls":4},6,52,6,214000,196000,367000,2,32,68,1,8,{"$nulls":19},"建成通车","4D75CB95E0000021F0C08F4C2B0DAD01"]
["BFA4B5A62E0659E1B790D5756FC31072",0,null,"2015Y0009",-1,{"$nulls":75},"该项目正在进行前期准备工作。","4D935B05A00000212B96F38D231EA5C3"]
["169D1203607BD58259922467E8615642",0,null,"2015Y0009",-1,21,42,24,475676,782162,2600093,13,100,100,4,289,{"$nulls":4},21,37,22,458970,756820,2305378,13,100,100,4,288,{"$nulls":4},3,13,5,107216,124681,421143,0,null,null,1,1,{"$nulls":4},3,36,22,505250,819724,2326499,0,null,null,1,1,{"$nulls":19},"江阴大道：完工    世纪大道段：1道路完成情况：主车道沥青基本摊铺完成（除芦墩浜桥东侧）。    2 桥梁情况：芦墩浜桥西侧全部完成，东侧除搭板和伸缩缝外全部完成。","463C21FC8000000100F79216FB20DD61"]
["DA48AE4EF88739FD21BE714BEF792E82",0,null,"2015Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,27,166,16,398864,305076,201726,2,100,100,26,59,0,320,80,97017,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"目前绿化工程已结束,进入收尾工作,预计年底全部完工.","4592B501E000002123E927A043947D89"]
["14D05721C955AA549F324DBE119B65FD",0,null,"2015Y0009",-1,{"$nulls":75},"斜坡式结构东防波堤工程今年折合进尺1000米，累计折合进尺7400米，占斜坡式结构东防波堤工程总长7834米的94%。","452C38DA800000A19C9699F0088370B9"]
["C556129686717F21BE5FFA959436405A",0,null,"2015Y0008",-1,{"$nulls":75},"建成通车","48B15A89C0000021CEB0D93D0A59616D"]
["6B864A09E63787B61244708288DB0022",0,null,"2015Y0009",-1,36,519,null,965,852,930,9,100,100,17,164,{"$nulls":3},21300,null,519,null,965,555,null,8,100,100,17,164,{"$nulls":3},21300,null,53,null,965,510,null,8,31,23,17,{"$nulls":4},21300,null,53,null,965,555,null,8,28,23,17,{"$nulls":4},21300,{"$nulls":16},"452C38D720000081C14CEFA6969A8D06"]
["7D1259283AB054C8A1BEB3EDD62B6889",0,null,"2015Y0009",-1,{"$nulls":75},"码头水工完成。陆域方案设计正在报请省厅变更。","45B27FD3A0000001E7A4DAE02DD98961"]
["DCF2A448919675096960CA7A9F5E0175",0,null,"2015Y0009",-1,{"$nulls":75},"工程完工。","494F759FA0000021B650A21A5A0C6724"]
["5FAD1C0E1269E5E47F7193E502A9E4BB",0,null,"2015Y0009",-1,{"$nulls":75},"工程已基本完工。","4E1F625000000001D7539342E28423AB"]
["0FF39A6DA96BED229102E58FDEC90F27",0,null,"2015Y0009",-1,12,96,12,260000,243000,303000,1,null,null,4,24,{"$nulls":3},1005,12,96,12,260000,243000,303000,1,null,null,4,24,{"$nulls":3},1005,12,96,12,260000,243000,303000,1,null,null,4,24,{"$nulls":3},1005,12,96,12,260000,243000,303000,1,null,null,4,24,{"$nulls":3},1005,{"$nulls":15},"全线已完成","464AE565800000215C9C09C8A0BE8932"]
["1D0061161E235F7980B52471FAF21235",0,null,"2015Y0009",-1,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,11,22,11,104329,97608,94652,{"$nulls":3},1,18,{"$nulls":3},300,{"$nulls":15},"目前，该项目累计完成投资10557万元。9月份完成情况：道路工程开展面层施工，完成粘层3998平方米，封层4126平方米，细粒式沥青混凝土3958平方米，中粒沥青混凝土4019平方米施工，完成投资45万元。","4979BFCD200000210A165452CAEAC270"]
["4CE12829094E149E097D21DBBDBB223D",0,null,"2015Y0009",-1,{"$nulls":75},"\"目前沛县段（28.918公里）完成清表90万平方，占总量105%；完成路基70万方，占总量26%；桥梁工程共完成钻孔桩794根，占总量88%，完成梁板730片，占总量30%。铜山段（25.366公里）由于征地拆迁未启动，施工图设计无法开展。\n\"\n","45FEE20920000001DB1994300FA9DCE3"]
["F40DA56BC35917661A799888CCDFE7CB",0,null,"2015Y0009",-1,{"$nulls":75},"西斜坡堤工程本年折合进尺2000米，累计折合进尺5400米，占西防波堤总长9804米的55%；西直立堤工程本月开展预制厂扩建工程，主要开展打桩及预制厂设备采购等工作。","46D12756A00000212A79E7CE74664FD9"]
["423362D851CBD0DD372AC8A7B1FEB9A0",0,null,"2015Y0008",-1,{"$nulls":75},"正在加快推进前期工作。","4B2FD99E000000217EF51296349F80B0"]
["4C1661A8E1CD8FD34C8725D276AF118E",0,null,"2015Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"墟沟互通建成通车，北固山隧道右线贯通，左线剩余400米，隧道机电工程已全部进场施工，完成约30%。","44F92AE720000041FD47DFFCE454F006"]
["6EC5E22D6993C72040720C36892E8C53",0,null,"2015Y0009",-1,{"$nulls":75},"水工主体结构完工","44F92AE8C0000061CA99E73B5A18BBB6"]
["58B0ABBAC6143A3FDCDC963391727F78",0,null,"2015Y0009",-1,{"$nulls":75},"正在进行地基处理","452C38D6A0000061E78CB00451B63144"]
["CDD948CA4A1236BBA637E21E4DC96B6A",0,null,"2015Y0009",-1,{"$nulls":75},"防波堤C段主体抛填完成，扭王字块预制累计完成8万件，扭王字块安装累计完成4万件，挡浪墙施工累计完成4000m。\n","4C2FAFDCA0000021C4BD69F74D4CF3C4"]
["89F3985BA388EE86AD0282143BFEAFF4",0,null,"2015Y0009",-1,{"$nulls":75},"码头水工主体基本完工","4F82916F60000021573E0740F78BAAD0"]
["FBF3C602FDF53333DDBAAF8CC8E4B5ED",0,null,"2015Y0009",-1,{"$nulls":75},"正在开展扫尾工程，即将建成。","48169DD9600000213A760AD1A7936625"]
["4E68623E66693A5675F83E849D33731D",0,null,"2015Y0009",-1,{"$nulls":75},"目前，正在进行桥梁下部结构施工。","45830701A00000018662A81FE3FB2B60"]
["6C64E9E8AB4F160337B13FB94E3EADE0",0,null,"2015Y0009",-1,7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":5},7,null,7,{"$nulls":3},2,null,null,1,{"$nulls":21},"481FB13480000021DF891907B35F942C"]
["DC0CEF54C738E30D934AC5595F1DD54A",0,null,"2015Y0010",-1,34,{"$nulls":75},"49E0A430600000219E2DB09B16BE71BE"]
["2EDD3CEE73926C41F3692557E83FC69A",0,null,"2015Y0010",-1,7,72,8,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,null,65,null,88642,147738,12210,0,20,70,0,12,{"$nulls":3},0,7,72,8,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,null,65,null,88642,147738,12210,0,20,70,0,12,{"$nulls":3},0,{"$nulls":15},"形象进度：路基正在开展开挖回填施工，路面基层施工进展顺利，桥梁正在开展下部基础桩基施工。存在问题：暂无。","4D70741A20000021FFF8CC821D5CE7DB"]
["B901B600A3319518ED263404903A270F",0,null,"2015Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"码头水工部分已完成总工程量的45%，西侧翼墙和码头固定吊砼浇筑完工。附属设施部分，联检大楼主体验收，部分异形梁浇筑和地下室坡道施工基本完工。","44F92AE800000121D51AC7AB782D4663"]
["4AC6279F5508643DDD68DB3BDBD0802C",0,null,"2015Y0010",-1,{"$nulls":75},"目前，正在进行桩基施工。","50A749104000002111B1BD6A84FDACB7"]
["E3D84F59FD746DB609607051B93F7658",0,null,"2015Y0010",-1,{"$nulls":75},"完成路面基层60%、面层35%、桥梁工程93%。","48173F21C00000213849C18090E227D5"]
["BE0394CC9554382679F64BAF74F2B06D",0,null,"2015Y0010",-1,{"$nulls":75},"目前完成主车道沥青施工，非机动车道下面层施工，正在进行人行道施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["E01F0D47D6116F6386A1226CEAF8AC6C",0,null,"2015Y0010",-1,{"$nulls":75},"路面工程水稳碎石底基层完成总量的94.7%，路面基层完成总量的89.8%；沥青砼下面层完成67.6%，沥青砼中面层完成59.7%，沥青砼上面层完成24.3%。桥梁工程，中小桥全部完成；桩基285根（铁路桥除外）全部完成；梁板预制392片全部完成；跨济徐高速大桥已基本完工；S322上跨主线大桥已完成桥梁主体施工结束，除了伸缩缝施工还未结束。涉铁工程，跨陇海铁路大桥桩基完成36.2%；下穿符夹铁路桥正在进行箱体预制施工。\n","45FE71CB2000002194A74D73D6EB648C"]
["120DF442DA7A7BDAF7F6F43A1D4807C8",0,null,"2015Y0010",-1,{"$nulls":75},"除集镇段外完成主体工程。","4A98BD0D800000212D60BD89CB35D858"]
["E95BF10CC8A8BF23F8501F2277E6F849",0,null,"2015Y0010",-1,45,17,45,825867,894111,1692770,{"$nulls":3},22,44,{"$nulls":4},45,17,45,819867,888000,1650000,{"$nulls":3},22,42,{"$nulls":5},1,null,4000,8000,20000,{"$nulls":4},2,{"$nulls":5},1,null,4000,8000,{"$nulls":5},2,{"$nulls":20},"45D0907940000021FB535CC8BFCB797E"]
["B20EC38FA183459B1A19CB0D204AF925",0,null,"2015Y0010",-1,{"$nulls":75},"该项目2015年10月开工建设，10月份开展沿线征地拆迁、树木及杆线迁移工作，完成投资286万元，开展清表工作，部分路段进行路基施工，完成投资214万元。10月份共完成投资500万元。","50A2E87680000021494BCC0A662835C1"]
["E4DBC39ED8EEFCA4CB14A068943D2CD1",0,null,"2015Y0010",-1,{"$nulls":75},"建成通榆河大桥和射阳河大桥。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["A0C9D589BBE95134854F5377455E9555",0,null,"2015Y0010",-1,{"$nulls":75},"进行桥梁上部结构施工，箱梁完成92%；路基完成90%。","4B2547D8C0000021EA2F1D310FA63F35"]
["E1A248AA838209A231E49B5FD77F5751",0,null,"2015Y0010",-1,{"$nulls":75},"该项目正在交工验收前准备。","45FE914600000021AFD71F50CFE22B15"]
["86B2E4354921D05DDE713AAE9FB85ABA",0,null,"2015Y0010",-1,{"$nulls":75},"已完成征地拆迁补偿，驻地建设，正在进行道路清表及试验准备。","4D935B05A00000212B96F38D231EA5C3"]
["5E3626693F700844F0C4C52302F2562F",0,null,"2015Y0010",-1,{"$nulls":75},"完成疏浚量930万m3，为总疏浚量的100%","44F92AE7400000013A0A1F9A656A1EA4"]
["E2A412C49EB7EFB2659C12FEF5264EAA",0,null,"2015Y0009",-1,{"$nulls":75},"目前，正在进行路基和桥梁下部结构施工。","4583086800000021610D57307F655C40"]
["3FBB6593E906021F49D8203C7117A897",0,null,"2015Y0009",-1,{"$nulls":75},"未开工","4596B7A960000021619092F5D6908C5A"]
["383C2B9F300DDF3F2FFD1612D0DA6D5A",0,null,"2015Y0010",-1,17,null,17,{"$nulls":72},"2标未开工。","45C531BE200000219CD9EF28C8D31E82"]
["EF26B5D43ED0A240810959C0B324CEAA",0,null,"2015Y0010",-1,11,5,11,837817,768716,868818,1,100,100,5,12,{"$nulls":4},11,4,11,837817,768715,787824,1,100,100,4,10,{"$nulls":5},1,null,153488,140828,159130,{"$nulls":3},1,2,{"$nulls":5},1,null,153488,140828,78136,{"$nulls":3},1,2,{"$nulls":20},"45D4A12B00000021B86B31C7A15832ED"]
["A6E9782D9D1A298909B309618979B3E9",0,null,"2015Y0010",-1,14,136,14,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},0,120,0,{"$nulls":3},1,{"$nulls":3},38,{"$nulls":4},14,86,14,{"$nulls":3},2,{"$nulls":3},13,{"$nulls":4},10,80,0,{"$nulls":3},1,{"$nulls":3},13,{"$nulls":19},"路基施工基本完成，部分段进行路面施工，完成水稳试验段，桥梁基本完成。","45A630DD40000021758080AC865FC45B"]
["020BDE05ABF385648A813165131F604C",0,null,"2015Y0010",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,186,null,526000,433000,33000,{"$nulls":4},66,{"$nulls":5},239,null,622171,604198,{"$nulls":5},26,{"$nulls":5},186,null,526000,433000,33000,{"$nulls":4},4,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["FA398851E84A173424804ABC9BD23CAE",0,null,"2015Y0010",-1,{"$nulls":75},"2个泊位水工主体已完工，后方61万方米场地地基处理工程基本完工。\n","46D11FD040000021CBCE7B927205F9C4"]
["4BE0BC2282D59ACAFD54BA8115249017",0,null,"2015Y0010",-1,{"$nulls":75},"累计折合进尺2188米，占二期工程准备工程总长2488m的88%。","46EBEFA560000021402F9981E1B1599D"]
["6C12A6FA03A49794A68B7F77B6E81B42",0,null,"2015Y0010",-1,{"$nulls":75},"完成征地拆迁等前期工作，完成桩基施工,完成横梁施工，完成纵梁安装，完成码头面施工。完成道路、堆场35%","4C53E8ABA00000211ABB7531249DFDBD"]
["312C18E5908FFC4E001654CB0378FCC0",0,null,"2015Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"墟沟互通已建成通车，北固山隧道右线贯通，左线剩余约319米。隧道机电工程已全部进场施工，完成约40%。","44F92AE720000041FD47DFFCE454F006"]
["92EFBA12037D0F40E73E002E73F12B43",0,null,"2015Y0009",-1,{"$nulls":75},"已完工。","4583615A60000021DC0FF956ED7DE8A7"]
["705DF99B2CFD55A8F12586CDA31080B4",0,null,"2015Y0010",-1,{"$nulls":75},"    主体完工通车。","4A04B92BC000006128D10F788349E5BC"]
["8465C8BFBE89409505C67802CF702472",0,null,"2015Y0010",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["4C05B9D3B370A25F014EB36454E9EE2A",0,null,"2015Y0010",-1,{"$nulls":75},"码头水工主体基本完工","4F82916F60000021573E0740F78BAAD0"]
["96597FCD0C829D929CFFAC131BECB166",0,null,"2015Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"部队用地1.2公里完成路基及水稳一层，其余路段已完成沥青路面。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["7CE80D749372C173C323620030A607CA",0,null,"2015Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"停车场主体、候工楼A及信息大厅完工；配电房等构建筑物单体施工、地基处理II标段工程施工。","452C38D960000061A773E74DF5A30C52"]
["8F203D05C28CF56DEC2B050BCC0FCEDD",0,null,"2015Y0010",-1,{"$nulls":75},"水工主体结构已完工。","4B9659D1C0000021C1262A201075DCCA"]
["9993B57143D391874EE7A7E6530D125E",0,null,"2015Y0011",-1,14,136,14,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},12,120,0,{"$nulls":3},1,{"$nulls":3},38,{"$nulls":4},14,86,14,{"$nulls":3},2,{"$nulls":3},13,{"$nulls":4},12,80,0,{"$nulls":3},1,{"$nulls":3},13,{"$nulls":19},"路基施工基本完成，进行路面，完成水稳施工，桥梁基本完成。","45A630DD40000021758080AC865FC45B"]
["8445C2803201DDBA2FE660870E9168C8",0,null,"2015Y0010",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,629,10,972500,1015500,2154300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,25,0,12500,980400,148900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"全线后半段坟头至终点约11公里段落除了1处部队矛盾节点影响约700米辅道段落外，其余全部建成；前半段起点至坟头约10公里段落进行路基、桥梁、路面及附属工程施工。\n路基：完成土石方开挖356.6万方（96.1%），土石方填筑274万方（96.4%）；\n路面：水稳碎石基层101.55万平方（89.7%)，12%灰土97.25万平方（85.9%)，沥青215.48万平方(90.7%)；\n桥梁：33000万元（84.1%）；\n交安5450万元（42%）；\n绿化4700万元（88.3%) ；\n声屏障约470万元；","44F92AE840000101423CCFA36BCE2089"]
["A7A2B979172EF9B1BD7D907B7E8EE02C",0,null,"2015Y0010",-1,{"$nulls":75},"1-6#泊位后方堆场待验收（简易投入使用）；7-14#泊位后方堆场通过质量鉴定。\n","46D11E59C00000215FEEE684519DC4AA"]
["64F8187A37B81AB069D34409A0D26612",0,null,"2015Y0010",-1,{"$nulls":75},"已开工266公里、完工138.3公里，桥梁开工22座，完工11座。","4A847B5C800000014545309CA6FC8CB7"]
["EA9DD2C42950099076E43B1857D1F579",0,null,"2015Y0010",-1,{"$nulls":75},"北幅路基完成2800米，路基回填完成2500米，南幅路基完成2500米，路基回填完成2100米。","48A6EC29E000000142F6B2638633E8C1"]
["B4B057BD4FF348E42F4CF9C717E3668C",0,null,"2015Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成投入运营","44F92AE8600000A1FCC5AC1CC54E3B96"]
["8B5408AFF439FAF55285771F9421C43C",0,null,"2015Y0011",-1,5,95,5,208954,196309,573301,4,100,100,5,26,{"$nulls":3},4978,{"$nulls":61},"452C38DBA0000101EE35873CD541EA02"]
["0FF089C5E57435507CC2843C9EA82AE0",0,null,"2015Y0011",-1,34,{"$nulls":75},"49E0A430600000219E2DB09B16BE71BE"]
["0682E5D5ABA1E555F2FB1B028A95D001",0,null,"2015Y0007",-1,{"$nulls":75},"目前，324省道徐州东段一期工程睢邳路以西基本完成拆迁，正在开展招标文件及标底编制工作，至6月底完成投资3000万元。","4CDB1D29200000214CA3D9F6DE183F12"]
["C91F0F64A8C9E170F662A62653DF6113",0,null,"2015Y0009",-1,{"$nulls":75},"正在进行路基施工","4E0AFF3720000021DE9FAC037F3216EF"]
["45DC4163E3EF20ED08A7747A3EB23B5F",0,null,"2015Y0010",-1,{"$nulls":75},"该工程已建成通车。","4D89796D80000041D88FE961D2A1C0BB"]
["33CD3F7816B024B50A6637574ABA147D",0,null,"2015Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["51826F140B99D0151AD003D816CABDA9",0,null,"2015Y0010",-1,{"$nulls":75},"未开工","4596CE63A0000021B9EF1E5E417B9CA3"]
["856355CE739321FC4F86F2A9BD86F6B4",0,null,"2015Y0010",-1,{"$nulls":75},"完成桩基施工472根,为年度计划的100%;完成疏浚215.9万方,为年度计划的100%；完成上部结构0.5万方，占年度计划的20%","4B96568F00000021E184EC6C9CE9F9DC"]
["AE8930AA09D9AA6EE66DA558198D16BF",0,null,"2015Y0010",-1,{"$nulls":75},"目前，324省道徐州东段一期工程睢邳路以西基本完成拆迁，正在开展招标文件及标底编制工作，至6月底完成投资3000万元。","4CDB1D29200000214CA3D9F6DE183F12"]
["5046D70E638E2687FC51FFE3D4B07D47",0,null,"2015Y0011",-1,{"$nulls":75},"该项目11月份完成沿线征地拆迁赔偿、树木及杆线迁移等工作，完成投资229万元，开展路基灰土施工，完成投资92万元。11月共完成投资321万元。","50A2FE9980000021F648F0B8FAE5BDEF"]
["8C922937B7E525F0A88FB362F987B40A",0,null,"2015Y0011",-1,{"$nulls":75},"码头水工完成。陆域方案设计正在报请省厅变更。","45B27FD3A0000001E7A4DAE02DD98961"]
["9A355F5D9FB205574E05D3890282671A",0,null,"2015Y0010",-1,66,{"$nulls":75},"45C5231CE0000021BC17A82CFFD70F54"]
["8EA419F75CD5045ABC6CA77E00A1FEEF",0,null,"2015Y0010",-1,{"$nulls":75},"因该项目地块土地未确权，目前只能进行至选址阶段，待完成土地确权后开始报建手续。","4A613592E000002194B46D647ABA77F9"]
["5054808C71C8BF5DB5C7EF64D93BFA22",0,null,"2015Y0010",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["788093E52049788B8AE3F2AC15994848",0,null,"2015Y0010",-1,25,190,25,0,0,0,8,100,100,10,73,0,0,0,22233,25,190,25,0,0,0,8,100,100,10,73,0,0,0,11116,25,190,25,{"$nulls":3},8,100,100,10,1,0,0,0,22233,25,190,25,{"$nulls":3},8,100,100,10,1,{"$nulls":3},11116,{"$nulls":15},"路基、桥梁基本结束，正在进行路面施工。","458887AF00000021883DEACA51071D92"]
["2686AE51D3358D291200F783F2CC5A64",0,null,"2015Y0010",-1,21,42,24,475676,782162,2600093,13,100,100,4,289,{"$nulls":4},21,37,22,458970,756820,2305378,13,100,100,4,288,{"$nulls":4},3,13,5,107216,124681,421143,0,null,null,1,1,{"$nulls":4},3,36,22,505250,819724,2326499,0,null,null,1,1,{"$nulls":19},"江阴大道：完工    世纪大道段：1道路完成情况：主车道沥青基本摊铺完成（除芦墩浜桥东侧）。    2 桥梁情况：芦墩浜桥西侧全部完成，东侧除搭板和伸缩缝外全部完成。","463C21FC8000000100F79216FB20DD61"]
["C2E93FAF062B2F8215A03BE35E51832C",0,null,"2015Y0010",-1,{"$nulls":75},"完工","47EC671F00000001C8A65242F6D76C6C"]
["A29EB304F0375A72EACE34AB05C15E82",0,null,"2015Y0010",-1,{"$nulls":75},"建成通车。","494F7BCEC000002123A1FDE2C282EA21"]
["98DBD0388742D8E1EF89DB87C84C4805",0,null,"2015Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"完成疏港航道、港池码头和北侧港区堆场建设，南侧港区完成项目部建设，启动设备采购工作。","44F92AE740000061422D7CBDB598F0A4"]
["458F20153F362BC59178210B3548503F",0,null,"2015Y0009",-1,{"$nulls":75},"已完成赣马镇区及官河大街段4.5公里征地拆迁工作，并已完成赣马镇区段西半幅路基开挖回填3.5公里，东半幅路基开挖回填1公里。","4D743B53C0000021D528DB4DEF96D439"]
["D9CC98DA401BE9CA2E20D10854769C40",0,null,"2015Y0009",-1,null,270,{"$nulls":8},68,{"$nulls":64},"由于拆迁矛盾暂缓施工","44F92AE9A0000001A6C4B4A0FE608B65"]
["C40181AE7EA7D3DAFA905344FF455FCA",0,null,"2015Y0010",-1,22,{"$nulls":75},"49E0DFA940000021DE73460C8BA04095"]
["1DEDC7929B731B2A02BC88B8F0B782E9",0,null,"2015Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成投入运营","44F92AE8600000A1FCC5AC1CC54E3B96"]
["3159269D5EF5A775A2474183614F7529",0,null,"2015Y0010",-1,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,{"$nulls":15},"工程已完成","4D70707C00000001E077DAB59B768AFF"]
["50A1C6ECDFE31C6FE63E2D6E2B64E4BA",0,null,"2015Y0010",-1,39,227,44,674902,737869,1227090,6,null,null,26,73,{"$nulls":3},5,39,227,431,674902,737869,1185920,6,null,null,26,73,{"$nulls":18},5,39,227,431,674902,737869,1185920,6,null,null,26,73,{"$nulls":19},"104国道宜兴段改建工程（潘归段、环科园段、梅塍段）目前已完成竣工验收，交付市公路处管养、使用。104国道宜兴段改建工程（绿园-梅园段）目前已完成交工验收，宜兴市已完成综合验收。104国道宜兴段改建工程（104-5标）目前已完成交工验收。","45AB627080000021CEFA9CCF57B58538"]
["5C828ADC10C40E05E1F62030415DAA03",0,null,"2015Y0010",-1,{"$nulls":75},"建成通车。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["F65523A729C564C7CAFD6ECEDB8671AA",0,null,"2015Y0010",-1,{"$nulls":75},"未开工","4596B7A960000021619092F5D6908C5A"]
["635A771D594A72E2E80FA9AF686FF6E0",0,null,"2015Y0011",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,629,10,972500,1015500,2154300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,25,0,12500,980400,148900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"全线后半段坟头至终点约11公里段落除了1处部队矛盾节点影响约700米辅道段落外，其余全部建成；前半段起点至坟头约10公里段落进行路基、桥梁、路面及附属工程施工。\n路基：完成土石方开挖356.6万方（96.1%），土石方填筑274万方（96.4%）；\n路面：水稳碎石基层102万平方（90%)，12%灰土97.25万平方（85.9%)，沥青215.48万平方(90.7%)；\n桥梁：33100万元（85%）；\n交安5450万元（42%）；\n绿化4700万元（88.3%) ；\n声屏障约470万元；","44F92AE840000101423CCFA36BCE2089"]
["644E83688175998B4E991FA02A719203",0,null,"2015Y0011",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,25,140,16,1336352,836248,1222510,21,94,93,26,19,1,0,465,15995,5,36,11,378999,153380,634873,21,89,100,2,2,2,0,150,9789,5,36,9,378999,153380,539642,20,78,90,1,2,1,0,150,2500,{"$nulls":15},"安定至凤阳段已建成通车。","45886E536000002100B27DDCDF662D01"]
["F9B7704AE436B87FE150EE876C7008E9",0,null,"2015Y0012",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,5,200,5,105014,111070,113964,1,0,50,0,46,0,0,0,7500,0,143,0,0,0,0,0,0,50,0,26,0,0,0,5528,0,145,0,0,0,0,0,0,50,0,28,0,0,0,5600,{"$nulls":15},"一、形象进度：340省道路线全长42.983公里，其中溧水段17.328公里，江宁段25.655公里。目前本项目按阶段实施建设。第一段：溧水先导段4.6公里于2012年8月开工建设，2013年9月建成通车；第二段：江宁横溪段和溧水段。目前正进行路基清表、河塘清淤、软基处理、路基填挖方以及桥梁桩基础等施工工作。完成工程量：路基挖方54.7663万方（22.82%），填方57.9527万方（18.1%）；路面底基层12%灰土2.1万方（9.99%），基层水泥稳定碎石11.304万平方米（5.38%），沥青面层21.6831万平方米（11.24%）；桥梁完成投资1466.3万（8.33%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。","452C38DB00000021D4253F83097D6579"]
["A3F68636DFE24DF771BC2B48F6ABFF1F",0,null,"2015Y0012",-1,81,207,81,null,1014,808,{"$nulls":9},81,207,81,null,1014,808,{"$nulls":9},81,207,81,null,1014,808,{"$nulls":9},81,207,81,null,1014,808,{"$nulls":25},"5189C9BEC0000021B9C2449894BD6820"]
["616F1FC7C841478E3581A057603DF97B",0,null,"2015Y0012",-1,25,140,17,1336352,836248,1317741,23,100,100,28,21,2,0,510,22684,25,140,16,1336352,836248,1222510,21,94,93,26,19,1,0,465,15995,5,36,11,378999,153380,634873,21,89,100,2,2,2,0,150,9789,5,36,9,378999,153380,539642,20,78,90,1,2,1,0,150,2500,{"$nulls":15},"安定至凤阳段已建成通车。","45886E536000002100B27DDCDF662D01"]
["3A551A919F9FFBDA8F19C580E5ED7623",0,null,"2015Y0012",-1,{"$nulls":75},"该工程已建成通车。","4D89796D80000041D88FE961D2A1C0BB"]
["7A5FAADE8657F24D858BE0D1C58CAA76",0,null,"2015Y0012",-1,{"$nulls":75},"建成通车。","48171CB940000001DAB3F475A2461DC6"]
["7B7147518DAFF91B66522855326E4E01",0,null,"2015Y0011",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,0,0,0,21580,5,159,5,105014,111070,113964,1,0,0,0,34,0,0,0,4400,0,143,0,0,0,0,0,0,50,0,26,0,0,0,5528,0,104,0,0,0,0,0,0,0,0,16,0,0,0,2500,{"$nulls":15},"一、形象进度：340省道路线全长42.890公里，其中溧水段17.773公里，江宁段25.117公里。目前本项目按阶段实施建设。第一段：溧水先导段4.6公里于2012年8月开工建设，2013年9月建成通车；第二段：江宁横溪段和溧水段。2015年计划新开24公里，目前施工、监理单位已进场，已完成驻地建设、工地试验室组建，申报质量监督申请、设计交底、现场交桩复测等前期工作，现正进行路基清表、河塘清淤、软基处理、路基填挖方以及桥梁桩基础等施工工作；第三段：江宁禄口段正进行施工图设计审查工作。\n二、存在问题：（1）因拆迁和杆管线迁移影响，江宁横溪段仅能施工5公里，施工段落不连续，严重影响工程进展；（2）禄口段2.4公里土地仅交付300米，影响连续开展施工；（3）340省道红线内宁台创业园涉及土地、附着物及部分拆迁，需要地方政府协调。建议地方政府针对以上问题能予以协调解决，为大面积施工创造条件。","452C38DB00000021D4253F83097D6579"]
["26A245C92CC7FF8FE9D81BA888ABFE7D",0,null,"2015Y0011",-1,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,{"$nulls":15},"工程已完成","4D70707C00000001E077DAB59B768AFF"]
["20D0DDA0487BBA47D2925AE23C645573",0,null,"2015Y0008",-1,19,null,19,{"$nulls":12},19,null,19,{"$nulls":57},"已建成通车","4ED31C1CC0000021ADB78CA5ED3CAE54"]
["44107405EA802E8006557277A89020E9",0,null,"2015Y0010",-1,19,null,19,{"$nulls":12},19,null,19,{"$nulls":57},"已建成通车","4ED31C1CC0000021ADB78CA5ED3CAE54"]
["9453D6176AF7F1578751B7FC856F438C",0,null,"2015Y0011",-1,null,251,35,1002220,1053482,2741204,5,null,null,12,6,1,525,525,17699,null,251,24,1002220,1053482,2741204,null,100,100,{"$nulls":3},525,525,17699,{"$nulls":45},"本年度部分高架路段安装声屏障共计2900米。","44F92AE9400000C1F580982CCF7AEF56"]
["4760F692491AE07003ED88BC43AB62D4",0,null,"2015Y0011",-1,{"$nulls":75},"项目已完工","477A862140000021A1462498F8403658"]
["673A84C9BA4583794DBB4757033EFA28",0,null,"2015Y0011",-1,{"$nulls":75},"建成通车","48B15A89C0000021CEB0D93D0A59616D"]
["34DC5073D10101C494F184CC591F6219",0,null,"2015Y0011",-1,39,227,44,674902,737869,1227090,6,null,null,26,73,{"$nulls":3},5,39,227,431,674902,737869,1185920,6,null,null,26,73,{"$nulls":18},5,39,227,431,674902,737869,1185920,6,null,null,26,73,{"$nulls":19},"104国道宜兴段改建工程（潘归段、环科园段、梅塍段）目前已完成竣工验收，交付市公路处管养、使用。104国道宜兴段改建工程（绿园-梅园段）目前已完成交工验收，宜兴市已完成综合验收。104国道宜兴段改建工程（104-5标）目前已完成交工验收。","45AB627080000021CEFA9CCF57B58538"]
["6A987A58DE06178238B44D81A654538E",0,null,"2015Y0011",-1,{"$nulls":75},"该项目南段已于2011年7月30日前完工，建成里程5.415km。","458884DF20000021A1CC02ABD339638E"]
["89F762BA16D4FDEE5A4C7065F1D064C5",0,null,"2015Y0009",-1,15,null,15,{"$nulls":12},12,null,12,{"$nulls":57},"工程进场施工，征地拆迁基本完成。","4A7F4412C0000001B5349862C0B620EE"]
["0A36B7E248A95CCA1AFC88EF5D35747A",0,null,"2015Y0011",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,42,95,42,7000000,700000,3420000,null,60,80,20,58,{"$nulls":3},10000,3,40,null,1000000,120000,3000000,null,40,40,12,26,{"$nulls":3},10000,0,35,null,1000000,120000,1020000,null,40,40,12,26,{"$nulls":3},10000,{"$nulls":15},"北段42.3公里建成通车，南段正在进行路基、桥梁施工.","4597C2C660000021C7BD96E4F6D02E66"]
["1581BBEE1C284DC22E7BFF1E9878B24F",0,null,"2015Y0011",-1,{"$nulls":75},"未开工","4596B7A960000021619092F5D6908C5A"]
["3E8331A05FCACDA7AF82643805F2383E",0,null,"2015Y0011",-1,{"$nulls":75},"东海段已建成，市区段路基完成清表约4.5km，完成山场碎石土回填约18.2万方。","4596D75C6000002113AB2207297BA0CF"]
["625889A355F4F0388D01E8D48D1FE0ED",0,null,"2015Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,27,166,16,398864,305076,201726,2,100,100,26,59,0,320,80,97017,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"目前除A标施工未完成外,其余均完工,进入收尾工作,预计年底全部完工.","4592B501E000002123E927A043947D89"]
["A5CF0352977D58199A0A0F5F736BE79C",0,null,"2015Y0011",-1,{"$nulls":75},"完成1072根桩基施工，为年度计划的100%","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["7CDCC9FC154217C67B208B3E17D4F1D4",0,null,"2015Y0011",-1,{"$nulls":75},"目前，路基已完成。","4E0AEB3D8000002111BF5B44419783F7"]
["AFDD009DF10D8FBB0B1DE025A6CE7540",0,null,"2015Y0011",-1,{"$nulls":75},"目前，路基基本完成，正在进行路面基层施工","4E0AFF3720000021DE9FAC037F3216EF"]
["B7FAB86E7190A7E55179386CA460393B",0,null,"2015Y0011",-1,2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":5},32,null,40186,21446,58762,null,61,100,null,1,{"$nulls":5},31,null,61824,21446,63992,null,50,45,null,1,{"$nulls":5},31,null,40186,21446,58762,null,45,44,null,1,{"$nulls":19},"                            ","4640A568A0000021A2BC879912C9A53C"]
["A38BE85E06506EB0C0B79EF513D202CA",0,null,"2015Y0011",-1,{"$nulls":75},"完成全部的主体工程及现场清理；房建项目完成场外施工，室内完成清理，进行验收移交。三大系统完成设备安装、调试。完成项目交工验收","44F92AE780000061E689426EB5202CA4"]
["0922AFE991A02CAF72BA00995C82272E",0,null,"2015Y0011",-1,{"$nulls":75},"工程已全部完工。","4E1F625000000001D7539342E28423AB"]
["9436B28FBD2C3E101B7A09086439DE9F",0,null,"2015Y0011",-1,40,null,40,{"$nulls":12},26,null,26,{"$nulls":12},10,null,10,{"$nulls":42},"建成通车一期工程G204至S229段25.96公里。","45930AC0A00000013A88F40431F8C61A"]
["0A7F6598F655F7D5AC5D17ACABD590D5",0,null,"2015Y0011",-1,{"$nulls":75},"完工。","46EA9D51A0000021F1A72CD5283EA913"]
["C14EDD5B01E9390B7B4E1BA88B59BEFB",0,null,"2015Y0011",-1,{"$nulls":75},"西斜坡堤工程本月折合进尺300米，累计折合进尺5950米，占西防波堤总长9804米的61%；西直立堤工程本月开展预制厂扩建及新桶体预制等工作。","46D12756A00000212A79E7CE74664FD9"]
["3966704FD0C02F4738ABA3F7A8B9FED3",0,null,"2015Y0011",-1,{"$nulls":75},"完成招投标，施工单位即将进场施工。","5156819540000001E42DD4EFA2CA58A7"]
["56FCFCD8B1A7F0C1F6B0BF7DCA213FE8",0,null,"2015Y0011",-1,{"$nulls":75},"正在进行岸线审批。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["7C0D8033CE5E67D5FBE814101A0FC5AB",0,null,"2015Y0012",-1,20,424,27,744000,722000,907000,26,100,100,22,155,{"$nulls":3},14610,null,424,{"$nulls":4},26,98,100,22,155,{"$nulls":3},8766,null,424,{"$nulls":4},26,95,100,22,155,{"$nulls":3},8500,null,424,{"$nulls":4},26,98,100,22,155,{"$nulls":3},8766,{"$nulls":16},"469415CEC000000193285BF8DEFE5650"]
["0ADFDEF021949FF571DE7279722D128E",0,null,"2015Y0011",-1,29,207,29,623240,1174391,1077452,2,100,100,5,163,{"$nulls":3},16409,29,207,29,623240,1174391,1077452,2,100,100,5,163,{"$nulls":3},6563,29,51,29,623240,1174391,1077452,null,100,100,5,163,{"$nulls":3},16409,29,51,29,623240,1174391,1077452,null,100,100,5,163,{"$nulls":3},6563,{"$nulls":15}," 形象进度：全线道路、桥涵主体工程完成，正在开展交安、防护排水等附属工程施工。","4D7071D66000002165416ADF246EF2BE"]
["CB6C0D6EE35F8C56D89111205E1DD2C2",0,null,"2015Y0011",-1,{"$nulls":75},"完成码头、服务中心主楼验收，完成附属工程建设和主楼四周及南侧绿化.","48169DD9600000213A760AD1A7936625"]
["CE54143C8AC4EAC98E81714F173F29FD",0,null,"2015Y0011",-1,{"$nulls":75},"建成通车。","48171CB940000001DAB3F475A2461DC6"]
["E754A6CE871BFA91B8D44772367AC15F",0,null,"2015Y0011",-1,{"$nulls":75},"完成土地征用、房屋拆迁、河堤占用补偿和项目部建设，施工单位已进场。","494F9423E0000021971B8B67E472FD4B"]
["161F91232848267F61C6EAB7F0C0C7E5",0,null,"2015Y0011",-1,{"$nulls":75},"工程已开工建设","513D48A080000021F6ECE2A883127397"]
["4F9EE4A18FBF9BA2645D22FAE343FF24",0,null,"2015Y0011",-1,{"$nulls":75},"南环段已建成，上跨长深高速公路大桥已完成。西延段招标工作已结束。","4D746069A0000021424848A8623D4A12"]
["74C694699EE447FC8C0AEBDF42162481",0,null,"2015Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":16},"468905766000000160F36C381A6439C6"]
["8D88AA26D2315C509853D3406A9B91D6",0,null,"2015Y0011",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":65},"45D5A240A0000021D818821C8141EA27"]
["EC0D9EB4435B74194342C97ACF7377D7",0,null,"2015Y0011",-1,27,30,27,122766,613829,613829,2,null,null,22,{"$nulls":66},"4CDEBC14800000214E9C959259B62979"]
["E4197C9227ABCEFB6961B4FC207A0C90",0,null,"2015Y0011",-1,{"$nulls":75},"除涉铁跨陇海铁路大桥正在做桥面铺装，主线已全部完成。","45FECF71600000215E4D818AE95457DF"]
["2875AA44CC789FAE01BA4D0027F110C8",0,null,"2015Y0011",-1,{"$nulls":75},"陆域地基处理自开工累计完成总产量100%,施工单位自检完成，目前第三方检测已完成，等待验收。口岸开放配套设施工程累计完成总工程量的90%,仅剩桥梁尚未施工。后方陆域预算基本完成，下一步签署合同。","452C38D6A0000061E78CB00451B63144"]
["88A449D57DFA49DDF10C90AAAD8BCD39",0,null,"2015Y0011",-1,{"$nulls":75},"已完成征地拆迁补偿，驻地建设，正在进行道路清表及试验准备。","4D935F2340000021767F74AFEF8958B9"]
["DF3E7BB30F0918DADAA5B5B0A2C65792",0,null,"2015Y0011",-1,{"$nulls":75},"该项目正在进行前期准备。","4D93720CA0000021255B319F74F769D3"]
["19AD34704DAC0C8060D5BC64B1612119",0,null,"2015Y0011",-1,{"$nulls":75},"直立式结构东防波堤本月进尺84米，今年折合进尺2938米，累计折合进尺3863米，占东直立堤总长4674米的83%，徐圩港区预制厂原建设工程已完成。","452C38D9600000015B091B22A009EB3A"]
["3C725AC04161608EE30C88EC461703B4",0,null,"2015Y0011",-1,{"$nulls":75},"1-6#泊位后方堆场待验收（简易投入使用）；7-14#泊位后方堆场通过质量鉴定。\n","46D11E59C00000215FEEE684519DC4AA"]
["1C5E5364A4CD66EFB9D404E3186D3ABE",0,null,"2015Y0011",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"部队用地1.2公里完成路基及水稳二层，其余路段已完成沥青路面。","44F92AE7C00000E1173F4D28A6F3AF2E"]
["A4F6D1615F54E00882285C85C0B3563C",0,null,"2015Y0011",-1,{"$nulls":75},"正在加快推进前期工作。","4B2FD99E000000217EF51296349F80B0"]
["29D9F787B14B3E16F0137D52DA2B3ADB",0,null,"2015Y0011",-1,{"$nulls":75},"防砂导流堤已完工，待吕四10万吨级航道一期工程完工后，完成疏浚。","4ED76E5EA0000021C2FF39A1BE0258B9"]
["326E26DC95131FABFF26F173F168AF1A",0,null,"2015Y0011",-1,null,null,28,165408,162616,160382,{"$nulls":3},1,{"$nulls":7},26,153593,151000,148926,{"$nulls":3},1,{"$nulls":7},28,165408,162616,160382,{"$nulls":3},1,{"$nulls":7},26,153593,151000,148926,{"$nulls":3},1,{"$nulls":21},"45977C86A000000145F95B717A76C135"]
["4C009C0A759BA0BF2765E2BF26BC9053",0,null,"2015Y0011",-1,{"$nulls":75},"码头水工主体基本完工","4F82916F60000021573E0740F78BAAD0"]
["91498215118F5A0078BFD13B06B0356E",0,null,"2015Y0011",-1,{"$nulls":75},"已完成119.41公里实现贯通，海滨大道跨海大桥下部结构已完成，上部结构盖梁已全部完成，预制箱梁完成99%，箱梁安装完成85%，主通航孔累计完成88%，辅通航孔累积完成98%，完成工程总量的89%。辅通航孔桥左幅已合龙。","4A953E3E000000613D13CA6F74E1236C"]
["EDA33F1B0703EC1BB9A00A17F74EF78D",0,null,"2015Y0012",-1,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,15,225,17,500100,400700,1211300,9,100,100,5,60,{"$nulls":3},13828,null,null,17,null,400700,1211300,{"$nulls":11},17,null,400700,1211300,{"$nulls":25},"452C38D5A00000A1C369596A7753C333"]
["2FF63CF27FE553EA287D0C381AB51BF9",0,null,"2015Y0012",-1,36,519,null,965,852,930,9,100,100,17,164,{"$nulls":3},21300,null,519,null,965,555,null,8,100,100,17,164,{"$nulls":3},21300,null,53,null,965,510,null,8,31,23,17,{"$nulls":4},21300,null,53,null,965,555,null,8,28,23,17,{"$nulls":4},21300,{"$nulls":16},"452C38D720000081C14CEFA6969A8D06"]
["CACB618C51177ED815925C7B78F40462",0,null,"2015Y0012",-1,3,44,8,114650,107100,202540,3,100,100,null,20,{"$nulls":3},1280,3,44,null,114650,107100,null,null,92,100,null,20,{"$nulls":3},640,null,2,null,114650,107100,null,null,60,23,{"$nulls":5},800,null,2,null,114650,107100,null,null,63,23,{"$nulls":5},640,{"$nulls":16},"497E9E23600000218DA200E95CCB2352"]
["3D71AD41F1173C64308DFD16F784189F",0,null,"2015Y0011",-1,{"$nulls":75},"地基处理","4FF7CAEF60000001B886392D3D7B79BC"]
["683D53608CF1C116B04BDD3D3723C4EE",0,null,"2015Y0012",-1,{"$nulls":75},"主体工程施工","4FA5A5A2000000216A85C1E239B9DBA7"]
["E875B3AAA2B947D8855300807B8BB24D",0,null,"2015Y0012",-1,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},6575,{"$nulls":15},"工程已完成","4D70707C00000001E077DAB59B768AFF"]
["94F337F30D30D6DA69AC3241D69CBCB5",0,null,"2015Y0012",-1,{"$nulls":75},"征地、拆迁清障，工程已开工建设","513D48A080000021F6ECE2A883127397"]
["95A0B9336A5A020B2C7A431571A3DC55",0,null,"2015Y0012",-1,38,738,38,1051000,9500000,1163000,14,null,null,27,181,{"$nulls":3},55366,38,738,38,1051000,9500000,1163000,14,null,null,27,181,{"$nulls":3},55366,0,0,null,270610,6866280,1163000,{"$nulls":9},0,0,null,270610,6866280,1163000,{"$nulls":24},"完成所有工程施工，包括路面工程、桥梁伸缩缝安装、安全设施工程、绿化工程、照明工程及收费站等房建和收费大棚工程，完成三大系统工程的安装与调试，完善环境整治、排水工程、线外工程，完成项目交工验收。2015年9月26日正式通车。项目进入缺陷责任期维修状态。","44F92AE780000061E689426EB5202CA4"]
["0997A919EE8B0D8A1663BD69B5F9C405",0,null,"2015Y0012",-1,{"$nulls":75},"项目完工已交工验收并投入试运营。","45FECF71600000215E4D818AE95457DF"]
["C8198C3FDA7B89690F1D4D14ABDD6CAC",0,null,"2015Y0012",-1,{"$nulls":6},5,null,null,44,{"$nulls":11},5,null,null,44,{"$nulls":11},5,null,null,44,{"$nulls":11},5,null,null,44,{"$nulls":20},"建成通车","51E6523060000021D514BF96504AC9E7"]
["616A1F484C407A06C57AD017A3B71406",0,null,"2016Y0001",-1,25,190,25,{"$nulls":3},8,null,null,10,73,{"$nulls":3},22233,0,170,0,{"$nulls":3},7,0,0,9,72,{"$nulls":3},0,25,20,25,{"$nulls":3},1,null,null,1,1,{"$nulls":3},22233,null,1,{"$nulls":29},"458887AF00000021883DEACA51071D92"]
["670507C4F3F50ED45FCAB4D3338AF1F5",0,null,"2015Y0012",-1,{"$nulls":75},"建成通榆河大桥和射阳河大桥，路基施工单位已进场。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["E6DAF33BB8A59D1368BC3B495B8A19F7",0,null,"2015Y0012",-1,22,239,22,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,239,null,622171,604198,1078980,{"$nulls":4},88,{"$nulls":3},63700,null,239,null,622171,604198,{"$nulls":5},26,{"$nulls":5},239,null,622171,604198,1078980,{"$nulls":4},26,{"$nulls":20},"452C38D8400000219DE485E94FD07CED"]
["4557059D717B6AAB23F28AB434FFFE3C",0,null,"2015Y0012",-1,{"$nulls":75},"    主体完工。","4EB93D3E80000001DFB979AE35EE8D86"]
["0F8CDA1EEC1423AB94E18C61188308A4",0,null,"2015Y0012",-1,{"$nulls":75},"目前，正在进行桥梁下部结构施工。","45830701A00000018662A81FE3FB2B60"]
["2C2144AEB9D44B3639734FCAB26BF58A",0,null,"2015Y0012",-1,{"$nulls":75},"水工主体已建成。","46D123DB80000021DDAA88D0A2421B9E"]
["27131EBF97EB7A327E6EF30038C32E33",0,null,"2015Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"主体已完成，铁路专用线开通，综合办公楼施工。\n","452C38D9200000A160383FB696401BD8"]
["D0CFE0F1D31E903D736FAAF353A29696",0,null,"2015Y0012",-1,{"$nulls":75},"已开工建设。","497EC8FBA00000219339AD552530ADAF"]
["B5CA82F800F059D42CC6A1919D4FF693",0,null,"2015Y0012",-1,{"$nulls":75},"已经建成22.8公里，剩余纵三至纵五段已完成招投标手续。","452C38DA80000041BB1AF46EF3FAECC2"]
["1DE5B348DAE8046AF4A1E9227B986B9B",0,null,"2015Y0012",-1,110,36,110,647802,625843,603884,{"$nulls":9},110,36,110,647802,625843,603884,{"$nulls":9},110,36,110,647802,625843,603884,{"$nulls":9},110,36,110,647802,625843,603884,{"$nulls":25},"51D7BD0B60000001BBAC52381B0BA743"]
["5E3FDD17F473852B8198D5AB6EDCE312",0,null,"2015Y0012",-1,188,52205,172,819423,1101833,978733,{"$nulls":9},188,52205,172,819423,1101833,978733,{"$nulls":9},188,52205,172,819423,1101833,978733,{"$nulls":9},188,52205,172,819423,1101833,978733,{"$nulls":24},"全部建成通车","518A86AA600000019993651BCCFF915C"]
["43471D5E505F7E26B3245210099E3E0E",0,null,"2015Y0012",-1,{"$nulls":6},7,300,300,29,{"$nulls":11},7,300,300,29,{"$nulls":11},7,300,300,29,{"$nulls":11},7,300,300,29,{"$nulls":21},"518A88910000000129831B0FD2734AA7"]
["551373CA7E96213252EB32CDB2467601",0,null,"2015Y0012",-1,40,18,40,314340,298220,282100,{"$nulls":3},6,{"$nulls":5},40,18,40,314340,298220,282100,{"$nulls":3},6,{"$nulls":5},40,18,40,314340,298220,282100,{"$nulls":3},6,{"$nulls":5},40,18,40,314340,298220,282100,{"$nulls":3},6,{"$nulls":21},"519015C08000002130E579AD8DF26965"]
["D523C491DEB5D83D745737D52D16E9A1",0,null,"2015Y0012",-1,{"$nulls":75},"正在进行路基施工。","4D935B05A00000212B96F38D231EA5C3"]
["283BC9F6C79203616B92BEBCBB44315B",0,null,"2015Y0012",-1,47,38,47,218574,1036343,1003990,3,null,null,50,151,{"$nulls":65},"45D59738E0000001479BFE10E68B1A62"]
["7F5DA30B12F1C49AA282B49ECB4EDF70",0,null,"2015Y0012",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":65},"45D5A240A0000021D818821C8141EA27"]
["39A217D3A6CB78EF425CC6CA9E57AFAF",0,null,"2015Y0012",-1,27,30,27,122766,613829,613829,2,null,null,22,{"$nulls":66},"4CDEBC14800000214E9C959259B62979"]
["658D1C84E778310E553BD4B8F6C4EA78",0,null,"2015Y0012",-1,{"$nulls":75},"建成通车","48B15A89C0000021CEB0D93D0A59616D"]
["0BE6F7B4091AE47FE42338E53A29A2BE",0,null,"2015Y0011",-1,80,3195300,null,null,2023895,1913509,{"$nulls":4},229,{"$nulls":64},"省道337本月完成投资1200万元，完成湖熟非集镇段绿化土方施工，完成半幅道路路缘石铺装，本年累计完成投资1.89亿元，其中建安费1.55亿元。\n","44F92AE9800000A15AC5660EDAD7D017"]
["27E0002F5C4F8280FC8C3756692CB6FA",0,null,"2015Y0012",-1,null,270,{"$nulls":8},68,{"$nulls":64},"由于拆迁矛盾暂缓施工","44F92AE9A0000001A6C4B4A0FE608B65"]
["AC47FE1B878FE1DB1F570C4C85EA887C",0,null,"2015Y0012",-1,{"$nulls":75},"    建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["D0AB2F9F8D9DFC6519E1E6604D78A28F",0,null,"2015Y0012",-1,29,{"$nulls":14},3,{"$nulls":14},3,{"$nulls":14},3,{"$nulls":29},"已完成赣马镇区及官河大街段4.5公里征地拆迁工作，并已完成赣马镇区段西半幅路基开挖回填3.5公里，东半幅路基开挖回填1公里；水稳底基层及水稳下基层西半幅2.3公里。","4D743B53C0000021D528DB4DEF96D439"]
["D7A6F4897C6B21A5BC941873E204343A",0,null,"2015Y0012",-1,{"$nulls":75},"目前，主体建成。","4E0AEB3D8000002111BF5B44419783F7"]
["6A166A53EFFFE172674D838F987A0453",0,null,"2015Y0012",-1,{"$nulls":75},"工程复工，加快水工主体施工","46D11F4F40000021C374A969A3743C9A"]
["EDD5DA3B7975198E865B5F2893DF1C0E",0,null,"2015Y0012",-1,35,null,35,{"$nulls":8},1,{"$nulls":3},35,null,35,{"$nulls":8},1,{"$nulls":3},2,null,2,{"$nulls":8},1,{"$nulls":3},2,null,2,{"$nulls":8},1,{"$nulls":18},"建成通车","452C38D8A0000041215774BA7CEB1CEE"]
["911655D4480BB7CCE44726004F8133B2",0,null,"2015Y0012",-1,{"$nulls":75},"已完成征地拆迁补偿，驻地建设，正在进行道路清表及试验准备。","4D935F2340000021767F74AFEF8958B9"]
["340F0C63456FFACAB1AA88DA781D6045",0,null,"2015Y0012",-1,507,165,507,2992852,2891399,2789947,{"$nulls":9},507,165,507,2992852,2891399,2789947,{"$nulls":9},507,165,507,2992852,2891399,2789947,{"$nulls":9},507,165,507,2992852,2891399,2789947,{"$nulls":25},"51D7BAF9000000212458C575722090B8"]
["793FF566F261E9505863CF7938921E18",0,null,"2015Y0012",-1,{"$nulls":75},"陆域地基处理自开工累计完成总产量100%,施工单位自检完成，目前第三方检测已完成，等待验收。口岸开放配套设施工程累计完成总工程量的90%,仅剩桥梁尚未施工。后方陆域预算基本完成，下一步签署合同。","452C38D6A0000061E78CB00451B63144"]
["2642A6478E3AB293CC2BAF01F68EF177",0,null,"2015Y0012",-1,267,null,267,{"$nulls":73},"51E7562640000021865603B7AFD7BD77"]
["7845EF74CBDB9B1437E22B639C7042C9",0,null,"2015Y0012",-1,69,305,69,1350000,1300000,1650000,7,69,31,2,143,{"$nulls":4},21,100,23,400000,400000,null,1,32,8,null,45,{"$nulls":5},152,19,400000,400000,null,null,32,null,null,80,{"$nulls":34},"建湖G204至建宝路段19.64km,该段道路及桥涵工程已全部结束。S234至S331段完成征地拆迁90%、路基填筑4%、涵洞16%、桥梁工程6%；射阳段基本完成土地征用和施工项目部建设，完成清表2公里。\n","459307CF60000021FC7F08A5CEC30386"]
["D1D86A2A3827AB294211150769723D1A",0,null,"2015Y0012",-1,5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":12},5,null,5,{"$nulls":28},"51CD5CFBE000002123A5EE6D1EE1BAD6"]
["ECF58BF032B88A869634B998D81A62FE",0,null,"2015Y0012",-1,{"$nulls":75},"基本建成","452C38DA800000A19C9699F0088370B9"]
["7B3DF5A339430AC8FBFD6340DD048D15",0,null,"2015Y0012",-1,{"$nulls":75},"目前，主体建成。","4E0AFF3720000021DE9FAC037F3216EF"]
["EA2CB06D61E1D9F29324C73E152C4BFD",0,null,"2015Y0012",-1,{"$nulls":6},2,null,null,66,{"$nulls":11},2,null,null,66,{"$nulls":11},2,null,null,66,{"$nulls":11},2,null,null,66,{"$nulls":21},"51D1954640000021E8C90B111885020D"]
["40C7E08397946395943264755FC4F0A7",0,null,"2015Y0012",-1,{"$nulls":75},"完成1072根桩基施工，为年度计划的100%","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["BA428CC9E0EA4D1BCC374F631BE97A10",0,null,"2015Y0012",-1,{"$nulls":75},"防砂导流堤已完工，待吕四10万吨级航道一期工程完工后，完成疏浚。","4ED76E5EA0000021C2FF39A1BE0258B9"]
["9BFB258F2ED987AB9DD9992D197498A1",0,null,"2015Y0012",-1,108,null,108,{"$nulls":12},108,null,108,{"$nulls":12},108,null,108,{"$nulls":12},108,null,108,{"$nulls":27},"建成通车","51E64D914000002160D0B066246342B9"]
["3F75FE5B6CD1E2B87C9CA3FE00A1143E",0,null,"2015Y0012",-1,{"$nulls":75},"基本通过综合验收；基本完成了与土建方和业主方的房屋交接手续；沥青路面摊铺完毕，围墙建设正在进行；着手进行场地路面划线；道闸、弱电等设施设备正在进行收尾调试工作。","4706D6D520000021D78B264A806E8D95"]
["A886F476FC9BEE085759D3E858942CC4",0,null,"2015Y0012",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,27,166,16,398864,305076,201726,2,100,100,26,59,0,320,80,97017,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"除未完成的工程外，其余均交工验收，工程进入扫尾阶段","4592B501E000002123E927A043947D89"]
["ACA5F142CFCF29ADAD124C09D5FDD117",0,null,"2015Y0012",-1,{"$nulls":75},"该项目黄圩至苏皖界2.915公里路段12月完成5%石灰土填筑3165立方米，完成投资15.2万元，完成碎石填筑840立方米，完成投资11.8万元，正在开展黄南小桥墩台立柱施工，完成投资3万元，12月共完成投资30万元。","50A30D9880000021822D064F6E714B8D"]
["4638C42E59CBD7644D820C44749F5889",0,null,"2015Y0012",-1,16,10,16,130000,122000,112500,{"$nulls":4},18,{"$nulls":4},16,10,16,130000,122000,112500,{"$nulls":4},18,{"$nulls":4},16,10,16,130000,122000,112500,{"$nulls":4},18,{"$nulls":4},16,10,16,130000,122000,112500,{"$nulls":4},18,{"$nulls":19},"主体工程已完工。","4A846A5BE0000001857A4A36BC850D64"]
["E89E1A102B050C4318B4002F32984032",0,null,"2015Y0012",-1,{"$nulls":75},"折合进尺3000米，累计折合进尺3925米，占东直立堤总长4674米的84%，徐圩港区预制厂原建设工程已完成。","452C38D9600000015B091B22A009EB3A"]
["6C4C2C757177AA3EC22537EB05B2C84B",0,null,"2015Y0012",-1,{"$nulls":75},"累计折合进尺2188米，占二期工程准备工程总长2488m的88%。","46EBEFA560000021402F9981E1B1599D"]
["1321E5C7D007293E4CCE8976497FE65C",0,null,"2015Y0012",-1,{"$nulls":75},"目前，正在进行桩基施工。","51D1D49260000021FCEEDB7A127D7731"]
["854EB39D075D1E6810B4B618E117AA5F",0,null,"2015Y0012",-1,{"$nulls":75},"海滨大道跨海大桥已全桥贯通，正在加快护栏、桥面铺装等桥梁附属工程建设，具备通车条件，其余路段已建成通车。","4A953E3E000000613D13CA6F74E1236C"]
["A2987DC259CB786A0B4B207253604B23",0,null,"2015Y0012",-1,{"$nulls":75},"全部建成。","47C9176620000021271D79C47773C13B"]
["EBA3CF02D2E5D40B2DD1CB5E7F3611AD",0,null,"2015Y0012",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6498,6,137,2,197060,240244,112975,null,90,100,2,11,{"$nulls":3},650,8,81,8,254464,258507,312453,null,100,100,4,7,{"$nulls":3},6498,6,71,2,177830,225057,111607,null,90,100,2,7,{"$nulls":3},650,{"$nulls":15},"形象进度：全线分为5个标段，1标无矛盾段落路面底基层已基本结束，沥青下面层摊铺已完成，迎春河桥、坎河桥主体完成，新桥刚桥半幅桥面铺装已完成，正在进行桥面系施工；2标3标沥青下面层已完成，上面层完成50%；5标沙河大桥正在开展护栏、桥头南北接线的水稳施工。","464AEA1FC0000021B52E367C631B2D38"]
["E6A627F9E08D3C2616CC0F6FB365DD20",0,null,"2015Y0012",-1,7,72,8,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,null,72,null,265928,147738,48839,0,50,90,0,12,{"$nulls":3},0,7,72,8,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,null,72,null,265928,147738,48839,0,50,90,0,12,{"$nulls":3},0,{"$nulls":15},"形象进度：路基完成100%，路面基层面层施工进展顺利，桥梁施工进展顺利。存在问题：暂无。","4D70741A20000021FFF8CC821D5CE7DB"]
["497261EEE8B97BBD73E6227BB947D77F",0,null,"2015Y0012",-1,{"$nulls":75},"已完工。","452C38DA600000A11BD445B64B129BB2"]
["41CC606FEDA82F1D80A4E913F1182801",0,null,"2015Y0012",-1,{"$nulls":75},"完成征地拆迁等前期工作，完成桩基施工,完成横梁施工，完成纵梁安装，完成码头面施工。完成道路、堆场45%,完成部分设备购置和安装","4C53E8ABA00000211ABB7531249DFDBD"]
["801C5D0412D8312986162384D22A5025",0,null,"2016Y0001",-1,47,null,47,{"$nulls":73},"51E7518D80000021D841D35C0F43F308"]
["CCED2859CB682C34B48549C634ED65B8",0,null,"2016Y0001",-1,267,null,267,{"$nulls":73},"51E7562640000021865603B7AFD7BD77"]
["1C0791105300333A123F4D4954AFAFF3",0,null,"2016Y0001",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,{"$nulls":3},21580,5,202,5,105014,111070,113964,1,null,50,null,47,{"$nulls":3},9500,null,200,null,342098,684197,314172,null,50,50,9,40,{"$nulls":3},8000,null,2,{"$nulls":8},1,{"$nulls":3},2000,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）路基清表、河塘清淤、软基处理、路基填挖方、非矛盾段小型结构物以及桥梁桩基础钻孔灌注桩施工等工作。路基挖方61.6481万方（25.68%），填方64.2142万方（20.06%）；路面底基层12%灰土2.1万方（9.99%），基层水泥稳定碎石11.304万平方米（5.38%），沥青面层21.6831万平方米（11.24%）；桥梁完成投资1657.3万（9.42%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。\n二、存在问题：2015年12月29日市督查办对江宁段横溪、禄口段进行督查推进，指挥部按照会上要求与江宁区有关部门主动对接，争取早日完成会上制定的征地拆迁计划目标，截止目前征地拆迁进展情况依旧缓慢。\n  ","452C38DB00000021D4253F83097D6579"]
["621BE9217253F9B9469A9346B1F45C8E",0,null,"2016Y0001",-1,{"$nulls":75},"建成通榆河大桥和射阳河大桥，其余路段开工建设。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["F37A37AF757763FA7F2633B00AF59FE1",0,null,"2015Y0012",-1,{"$nulls":75},"完工","46EA9A9840000021E67762482E18105E"]
["7D198BD0E3CDEABA3D4BEE43366FF686",0,null,"2015Y0012",-1,{"$nulls":75},"完工","46EA9FBB800000213459FE5A48F06D61"]
["D3B24C3818D9A675188511CFB8716E45",0,null,"2015Y0012",-1,74,55,74,685581,685581,685581,{"$nulls":9},74,55,74,685581,685581,685581,{"$nulls":9},74,55,74,685581,685581,685581,{"$nulls":9},74,55,74,685581,685581,685581,{"$nulls":24},"无","51D18C4240000021CCF847A86C6D84AC"]
["72ED8FDB597FD583913B786108351869",0,null,"2015Y0012",-1,null,173,21,{"$nulls":3},2,{"$nulls":3},50,{"$nulls":5},13,{"$nulls":14},13,{"$nulls":14},13,{"$nulls":29},"4D995D0A4000002140CCB1DD8A7C0CD9"]
["0C8E85F5795D5A2EAFC2C3969F9998C3",0,null,"2015Y0012",-1,{"$nulls":75},"建成通车。","4ADC3C87A00000211C3BE7E0F8EA4A3E"]
["8ADFADE377D21E2FBCC7F8D03B87754E",0,null,"2015Y0012",-1,197,null,197,{"$nulls":12},197,null,197,{"$nulls":12},197,null,197,{"$nulls":12},197,null,197,{"$nulls":27},"建成通车","51E64F5200000021A697D3A1745A283D"]
["9893F9F0130BCDDAE5E4044B4A387D32",0,null,"2015Y0012",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["695D05F56A6094CF0631921C561FA303",0,null,"2016Y0001",-1,{"$nulls":15},15,225,0,500100,0,0,9,100,100,5,60,{"$nulls":3},13828,{"$nulls":46},"452C38D5A00000A1C369596A7753C333"]
["E07175254BA8583B159777E230FA5999",0,null,"2016Y0001",-1,{"$nulls":75},"除集镇段外完成主体工程。","4A98BD0D800000212D60BD89CB35D858"]
["438C034C1734433B9AF26DA23D6052F4",0,null,"2016Y0001",-1,{"$nulls":75},"完成桥梁灌注桩40%","494F9423E0000021971B8B67E472FD4B"]
["58C5F676E4C78DD24D4C24D27CE04233",0,null,"2016Y0001",-1,{"$nulls":75},"2个泊位水工主体已完工，后方61万方米场地地基处理工程基本完工。\n","46D11FD040000021CBCE7B927205F9C4"]
["A4199C63989E9D93F213E4A5B3F7EAA3",0,null,"2016Y0002",-1,{"$nulls":75},"完成小箱梁湿接缝；完成小箱梁中、端横梁；完成小箱梁护栏。","4B2547D8C0000021EA2F1D310FA63F35"]
["069771ECAEA6E950D1320342B2DFA89A",0,null,"2016Y0002",-1,{"$nulls":75},"进出港航道疏浚完成总计划的87.5%，桩基完成总计划的67.5%，上部结构完成总计划的91.25%。","4B965806A000000167CD9E21EF5CA9FB"]
["E9A0726CF173F82E82BC163DEC59EE02",0,null,"2016Y0003",-1,7,72,8,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,null,72,null,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,7,72,8,29547,120879,195358,1,50,10,1,0,{"$nulls":3},7276,{"$nulls":3},29547,120879,195358,1,50,10,1,{"$nulls":4},7276,{"$nulls":15},"全线主体工程已完成并通车。","4D70741A20000021FFF8CC821D5CE7DB"]
["5663E5B34871F8A0736E3510A02777F8",0,null,"2016Y0002",-1,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,{"$nulls":46},"4D70707C00000001E077DAB59B768AFF"]
["F2699F50448C4DC25FF1F20FF4267204",0,null,"2016Y0003",-1,96,null,96,{"$nulls":12},50,null,50,{"$nulls":12},17,null,17,{"$nulls":12},7,null,0,{"$nulls":27},"已开工67km,交竣工50km。","45AB8817400000218E63FD22BDA91CE1"]
["3DED911C1613605D96091E9C5714C872",0,null,"2016Y0003",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["3007F1D819D7A72F3FA43BB4D3D6B6F5",0,null,"2016Y0003",-1,{"$nulls":75},"正在进行路基施工及沟塘回填。完成黄南小乔下部结构，完成33片空心板梁。","4D935B05A00000212B96F38D231EA5C3"]
["CC9BDFEE6262F6E75BA6FB3E82F86D9E",0,null,"2016Y0001",-1,10,393,null,614740,483910,766766,13,100,100,5,78,{"$nulls":3},25680,null,393,null,614740,482500,null,null,100,100,5,78,{"$nulls":3},25680,{"$nulls":3},60550,68910,766766,{"$nulls":12},60550,67500,{"$nulls":26},"452C38D900000041E569F21C93091E69"]
["2207F809F5904434353786F9B083BB17",0,null,"2016Y0002",-1,17,null,17,{"$nulls":72},"2标未开工。","45C531BE200000219CD9EF28C8D31E82"]
["26B66B9A41D431E6D0743EAD0B15A277",0,null,"2016Y0002",-1,{"$nulls":16},85,null,0,0,null,0,30,0,0,0,{"$nulls":3},0,{"$nulls":46},"452C38DBE00000616AD445E437E62A7E"]
["615F7D456A87969062EBC7DB0B697AAD",0,null,"2016Y0001",-1,{"$nulls":75},"形象进度：                                                                                                                1、组织工程验收小组对已发包工程进行验收；\n2、与华厦建设监理公司做好已发包工程决算初稿事宜；\n3、取得农业公路信息港一期项目招投标中标通知书；\n4、提交昂马汽贸遗留经费开支材料至审计局进行审计；\n5、准备市委市政府年度招商工作考核材料；\n6、准备2016年徐州市服务业工作绩效考核物流园项目材料；\n7、配合临沂物流协会做好招商方案制定工作。\n","53501AC0A00000214C61D99A65A2E081"]
["286E2574BC78E6CD164C38E292DE0034",0,null,"2016Y0001",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6489,6,137,2,197060,240244,112975,null,90,100,2,11,{"$nulls":3},650,2,10,6,76634,93428,200846,1,10,0,2,0,{"$nulls":3},5848,{"$nulls":31},"464AEA1FC0000021B52E367C631B2D38"]
["AF687936B43CDCBC14A52AB855D30E9E",0,null,"2016Y0003",-1,{"$nulls":75},"完成河塘处理，正开展路基填筑和桥梁施工。","4D08381440000021025FCF5FDA219DA7"]
["1B1DDF50F69FD466299DD696CBB236A0",0,null,"2016Y0001",-1,{"$nulls":75},"已完成征地拆迁补偿，驻地建设，正在进行道路清表及试验准备。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t","4D935F2340000021767F74AFEF8958B9"]
["12544691ED13339C1DD62C97C5F1FA6A",0,null,"2016Y0001",-1,{"$nulls":75},"    全线除华元路到朝阳河桥南外主车道贯通；沈思港桥完成，朝阳河桥西侧完成，朝阳河桥东侧及2标新建桥下部结构施工完成；2处箱涵施工完毕。","4A04D699C0000021960B6C19775B7500"]
["61B43DA491E58B9C9D08F0347D142664",0,null,"2016Y0001",-1,{"$nulls":75},"开展半幅老路挖除和雨污水管施工","4EDD9C40A0000021AB18D369C57D514A"]
["EF7A780447D90DA4D443A6976F1002B2",0,null,"2016Y0001",-1,{"$nulls":75},"工程复工，加快水工主体施工","46D11F4F40000021C374A969A3743C9A"]
["266C2E374001739C5DC4F22E2BE6ABA8",0,null,"2016Y0002",-1,{"$nulls":75},"    建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["9D8AB57156F5C6A451AD751CF6372D9C",0,null,"2016Y0002",-1,{"$nulls":75},"    集散中心已封顶，进行各项收尾工作，正在进行消防电气等设备调试工作；仓储中心B1/B2封顶，正在进行室内墙体砌筑、消防水电和门窗等安装，综合楼框架封顶，进行幕墙安装和消防水电安装。二期正在报建手续和地基处理。","4A09BB5320000021A7468129AEC6112D"]
["047E26984D4CAE474A4504DC050CDB68",0,null,"2016Y0002",-1,{"$nulls":75},"工程复工，加快水工主体施工","46D11F4F40000021C374A969A3743C9A"]
["E81FBF4105793F2801FDB9A7911725A4",0,null,"2016Y0001",-1,{"$nulls":75},"主体已完成，正在附属实施施工。","468F5198A0000021390EE49ABE0B2CD5"]
["2392C1406BC4CFA67D073467E75C178C",0,null,"2016Y0003",-1,{"$nulls":75},"征地、拆迁清障，工程开工建设。","513D48A080000021F6ECE2A883127397"]
["61A8F596D8FB168D069DAD9C4CECB4EF",0,null,"2016Y0003",-1,{"$nulls":75},"正在开展黄圩至苏皖界段2.915公里改扩建工程施工，3月完成黄南小桥桥梁支座垫石施工，完成黄南小桥梁板预制28片，完成黄南小桥0#、3#桥台锥坡填筑及浆砌片石护坡施工，正在开展路基工程5%石灰土填筑施工，完成排水管涵施工工作，3月完成投资50万元，共完成投资652万元。","50A30D9880000021822D064F6E714B8D"]
["6B4E188311FDA35D4CC826CFDBFDBCF1",0,null,"2016Y0001",-1,{"$nulls":75},"基本完成路基、桥梁施工。路面底基层施工完成75%。房建工程：完成服务区综合楼主体工程；完成收费站站房的基础施工。","44F92AE7400000C18C5FA6F58B9A0813"]
["D9B88A01437B88A953821A0563FEDED3",0,null,"2016Y0002",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,629,10,972500,1015500,2154300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,25,0,12500,980400,148900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"工程全长20.976公里，分为前半段“起点-坟头”10.176公里和后半段“坟头-终点”10.8公里两个段落。工程除部队矛盾节点影响约1.7公里(含前半段1.2公里及后半段0.5公里)外，其余全部建成。后半段10.8公里已于2013年9月完成交工验收；前半段除西村战术场段落外，主线2015年底已全部贯通，辅道需待征拆完成后完成。\n","44F92AE840000101423CCFA36BCE2089"]
["1773284F5A1D4FFB26155C12610D8D9F",0,null,"2016Y0003",-1,25,190,25,{"$nulls":3},8,{"$nulls":3},73,{"$nulls":3},22233,25,189,{"$nulls":4},7,80,100,9,72,{"$nulls":5},1,{"$nulls":4},1,{"$nulls":3},1,{"$nulls":3},22233,{"$nulls":31},"458887AF00000021883DEACA51071D92"]
["069606672CA102A10C2F336C14F8B2A5",0,null,"2016Y0003",-1,{"$nulls":75},"该项目3月开展峰山大桥、朱湾大桥桩基施工，共完成钻孔灌注桩50根，完成水利涵洞2座，开展部分路段下路床施工，3月完成投资1000万元，共完成投资8300万元。","4CDB1D29200000214CA3D9F6DE183F12"]
["DDEDE10B39E1E9AE81A77A4A57DA17AF",0,null,"2016Y0003",-1,45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":4},45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":19},45,{"$nulls":30},"53A223CAE0000021EAC73238C8A7294A"]
["A2117FCA0920A24B24A1324FA91BD467",0,null,"2016Y0003",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":4},26,30,26,137962,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC"]
["2A65051B006935EC94A88CEEA07BA924",0,null,"2016Y0003",-1,{"$nulls":75},"2015年已建成通车。","53A7794A60000021276A0B287F7176E4"]
["8EC3EF9CC3AA0B935B0A0FC165232EFD",0,null,"2016Y0001",-1,{"$nulls":75},"目前，桥南接线已完成，正在进行桥梁桩基和北接线路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["708F145529DD7AA033D60CF1B320C0DB",0,null,"2016Y0001",-1,{"$nulls":75},"目前，正在进行桩基施工。","51E882EC80000021B9C40721EDEC0F47"]
["804A5C3527616D016482E90218EA89FD",0,null,"2016Y0001",-1,{"$nulls":75},"结合围填开展疏浚","4ED76E5EA0000021C2FF39A1BE0258B9"]
["5893465D59A8D92B13A3718FB440A249",0,null,"2016Y0001",-1,{"$nulls":75},"码头水工主体完工，加快后方陆域施工","4C2FD279600000213429D9E7E0D2E66E"]
["A04A73DB43D1A1F5572E7950C9F89070",0,null,"2016Y0002",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,{"$nulls":3},21580,5,203,5,105014,111070,113964,1,null,50,null,49,{"$nulls":3},9700,null,200,null,342098,684197,314172,null,50,50,9,40,{"$nulls":3},8000,null,3,{"$nulls":8},3,{"$nulls":3},2200,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）路基清表、河塘清淤、软基处理、路基填挖方、非矛盾段小型结构物以及桥梁桩基础钻孔灌注桩施工等工作。路基挖方62.2235万方（25.92%），填方64.2514万方（20.07%）；路面底基层12%灰土2.1万方（9.99%），基层水泥稳定碎石11.304万平方米（5.38%），沥青面层21.6831万平方米（11.24%）；桥梁完成投资1729.3万（9.83%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。\n二、存在问题：2015年12月29日市督查办对江宁段横溪、禄口段进行督查推进，指挥部按照会上要求与江宁区有关部门主动对接，争取早日完成会上制定的征地拆迁计划目标，截止目前征地拆迁进展情况依旧缓慢，影响路基施工进度。\n  ","452C38DB00000021D4253F83097D6579"]
["6DDFA503534188A8AD1A32B3B3DA8DFD",0,null,"2016Y0002",-1,7,68,7,237229,383699,295883,2,100,100,4,7,{"$nulls":3},4075,7,68,6,237229,383699,295883,2,100,100,4,7,{"$nulls":3},3700,null,null,1,{"$nulls":11},375,null,null,1,{"$nulls":11},125,{"$nulls":16},"4597BDE880000021876F5E47FCCB44CC"]
["7316DE05A7F49A4A3158AD5EB83C5512",0,null,"2016Y0001",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,629,10,972500,1015500,2154300,7,0,0,15,47,0,0,0,41000,10,51,11,171535,196437,374600,5,0,0,7,2,0,0,0,40343,0,25,0,12500,980400,148900,3,0,0,5,2,0,0,0,0,{"$nulls":15},"工程全长20.976公里，分为前半段“起点-坟头”10.176公里和后半段“坟头-终点”10.8公里两个段落。工程除部队矛盾节点影响约1.7公里(含前半段1.2公里及后半段0.5公里)外，其余全部建成。后半段10.8公里已于2013年9月完成交工验收；前半段除西村战术场段落外，主线2015年底已全部贯通，辅道需待征拆完成后完成。\n","44F92AE840000101423CCFA36BCE2089"]
["AE5349905B5424A8F54F95D26571E41E",0,null,"2016Y0002",-1,{"$nulls":75},"2个泊位水工主体建成","4C2FCA8B60000021201D5B07BBD59C1F"]
["12FEA7AD4690F90B528FEEA1FBCBE0BC",0,null,"2016Y0002",-1,344,null,344,{"$nulls":3},16,null,null,165,{"$nulls":20},344,null,344,{"$nulls":3},16,null,null,165,{"$nulls":36},"531C0B09800000213AEF0095AEB1C8E4"]
["51D1B1C00C8FCF16660A6EE54069DF1B",0,null,"2016Y0002",-1,{"$nulls":75},"实施一期工程6.7公里，完成路基施工。","4A942AA500000021C0375E5C302345B2"]
["1114BB9242DDCF5B066BA89B41B77A00",0,null,"2016Y0001",-1,{"$nulls":75},"正在进行路基施工。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t","4D935B05A00000212B96F38D231EA5C3"]
["69C8505C190122D0BF79108CF5DC11C7",0,null,"2016Y0002",-1,{"$nulls":75},"西斜坡堤工程本月折合进尺50米，西直立堤工程本月折合进尺63米，西防波堤工程累计折合进尺6436米，占西防波堤总长9804米的66%。","46D12756A00000212A79E7CE74664FD9"]
["EAF9EBC6D89F6AFD1BC80808C19DB8C7",0,null,"2016Y0002",-1,{"$nulls":75},"主体已完成，正在附属实施施工。","468F5198A0000021390EE49ABE0B2CD5"]
["C2C8CF160AA02C4E20726E64A239B945",0,null,"2016Y0002",-1,29,207,29,623240,1174391,1077452,2,100,100,5,163,{"$nulls":3},16409,29,207,29,623240,1174391,1077452,2,100,100,5,163,{"$nulls":3},6563,{"$nulls":14},9846,{"$nulls":31},"4D7071D66000002165416ADF246EF2BE"]
["9CE5696056972F60D809FEB67271CC46",0,null,"2016Y0001",-1,{"$nulls":75},"目前，正在进行项目建议书编制。","51E8967480000021790847B05E2E0A04"]
["E42D061EBB11BD694220A781470236C2",0,null,"2016Y0003",-1,{"$nulls":75},"桥南接线已完成，正在进行桥梁桩基和北接线路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["BE89A5B7CE243F5A2B6F7F6DAD6A5B1A",0,null,"2016Y0003",-1,{"$nulls":75},"淮阴区段已建成；涟水段完成路基施工。","4D989A7680000021CAE7FBD451FCC003"]
["1151CD18CF8A10710465932C26C44A6E",0,null,"2016Y0003",-1,{"$nulls":75},"正在进行桩基施工。","51E882EC80000021B9C40721EDEC0F47"]
["465CA43B722DAB191181A54E2A586432",0,null,"2016Y0003",-1,{"$nulls":75},"正在进行桩基施工。","51E8A48140000021EF9FCE54477087FB"]
["8506705526350B1F36D6C67B08F378E8",0,null,"2016Y0001",-1,{"$nulls":16},0,{"$nulls":5},0,0,null,0,{"$nulls":50},"49E0DFA940000021DE73460C8BA04095"]
["82991757ED3E990756F55A7822C9F91F",0,null,"2016Y0001",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["8F368C0F5A634211F3A924E675EBF309",0,null,"2016Y0002",-1,{"$nulls":75},"该项目本月进行黄南小桥施工。正在进行黄南小桥梁板预制工作，完成投资20万元。","50A30D9880000021822D064F6E714B8D"]
["BA2A2FB94F034EDAFA09D34603A49C57",0,null,"2016Y0002",-1,{"$nulls":75},"码头水工部分继续施工，已完成部分浇筑护轮坎、安装锚桩、系船柱。联检大楼主体进行内外粉刷，口岸大楼六层立模，浇筑，会所二层砼施工。","44F92AE800000121D51AC7AB782D4663"]
["249FF1A3B945E13322EC3A749A784894",0,null,"2016Y0002",-1,{"$nulls":75},"建成通车。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["3771C827B7802C18A42998434A006BF0",0,null,"2016Y0002",-1,{"$nulls":75},"基本完成土建施工。","5282380740000021A728411E3120FA27"]
["96AE59C00996E809176D98327228EE0F",0,null,"2016Y0002",-1,7,72,8,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,null,72,null,265928,147738,48839,0,50,90,0,12,{"$nulls":3},0,7,72,8,29547,120879,195358,1,50,10,1,0,{"$nulls":3},7276,{"$nulls":31},"4D70741A20000021FFF8CC821D5CE7DB"]
["83F611EA50692931E4B838D80A61709D",0,null,"2016Y0004",-1,{"$nulls":75},"工可编制已完成，岸线申请已报至省交通运输厅。","544C5641800000213203D4F23F47635D"]
["00943985F274539662F116A06C358FF5",0,null,"2016Y0005",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,{"$nulls":3},21580,5,283,5,105014,111070,113964,1,null,58,null,65,{"$nulls":3},10500,null,200,null,342098,684197,314172,null,50,50,9,40,{"$nulls":3},8000,null,83,{"$nulls":6},8,null,19,{"$nulls":3},3000,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）路基清表、河塘清淤、软基处理、路基填挖方、非矛盾段小型结构物以及桥梁桩基础和梁板预制施工等工作。路基挖方83.5365万方（34.8%），填方111.8002万方（34.92%）；路面底基层12%灰土2.1万方（9.99%）；基层水泥稳定碎石11.304万平方米（5.38%）；沥青面层21.6831万平方米（11.24%）；桥梁完成投资2319.3万（13.18%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。\n二、存在问题：1、横溪段剩余20户房屋未拆迁，1480米土地未交付，杆线迁移进度特别缓慢，已经严重影响工程进展；2、溧水段联民社区东满园林苗圃影响长度100米，红星社区苗圃影响长度200米，便道无法贯通，严重影响路基施工和贯通。","452C38DB00000021D4253F83097D6579"]
["39A844990F148A66D15665A06F869FFA",0,null,"2016Y0005",-1,{"$nulls":75},"码头主体继续施工，龙门吊基础施工，绑扎钢筋、浇筑砼。联检大楼水电安装、内部装修进行中，口岸大楼施工至21层主体，会所二层钢结构施工。","44F92AE800000121D51AC7AB782D4663"]
["E1F1C98E6E597EBED94A3E79C682F126",0,null,"2016Y0005",-1,25,190,25,{"$nulls":3},8,null,null,9,73,{"$nulls":3},22233,25,190,{"$nulls":4},8,80,100,9,73,{"$nulls":5},1,25,{"$nulls":3},1,{"$nulls":3},1,{"$nulls":3},22233,null,1,{"$nulls":4},1,{"$nulls":3},1,{"$nulls":20},"458887AF00000021883DEACA51071D92"]
["54495CA83846EA2547880E037D6A5F75",0,null,"2016Y0005",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,57,165,42,7030000,646000,2587000,null,96,100,27,70,{"$nulls":3},12000,17,5,17,2450000,220000,1100000,null,10,null,3,{"$nulls":4},5000,15,2,null,1030000,66000,187000,null,16,null,2,{"$nulls":4},2000,{"$nulls":16},"4597C2C660000021C7BD96E4F6D02E66"]
["8B5EC58420ED26402A43295A302A3027",0,null,"2016Y0005",-1,{"$nulls":75},"建湖G204至建宝线段19.64km建成通车。建湖234省道至331省道段21.2km全线各标段征地拆迁已全部完成，土方开挖100%，路基回填46%，涵洞100%，桥梁66%。建湖G204以东段正在进行征地拆迁，已完成工作量的60%；正在进行项目部组件工作。射阳段8.881km已基本完成征地工作，土方开挖全部完成；PC管桩已完成76%，涵洞完成97%，路基完成68%，桥梁完成81.6%。","459307CF60000021FC7F08A5CEC30386"]
["6C176842A24332C8C2B7C54972A82BBA",0,null,"2016Y0003",-1,{"$nulls":15},10,79,19,{"$nulls":3},1,50,95,4,21,{"$nulls":49},"施工水稳基层和绿化土方，进行路缘石的安装；桥梁全部完工。","45835A3940000021498FFD174D21DCE8"]
["685E8B2B625FC66DB9A5210B40ADC3B1",0,null,"2016Y0002",-1,{"$nulls":75},"正在加快推进岸线审批。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["2D49485E9CE88024FEF6C24B30AF8680",0,null,"2016Y0003",-1,{"$nulls":75},"主体已完成，铁路专用线开通，综合办公楼施工。","452C38D9200000A160383FB696401BD8"]
["65BEB1CDD42B00D9538A229CD523BBB0",0,null,"2016Y0003",-1,{"$nulls":16},466,{"$nulls":5},72,77,null,164,{"$nulls":50},"452C38D720000081C14CEFA6969A8D06"]
["0349AA436F17E7C8FECB15006189895B",0,null,"2016Y0003",-1,{"$nulls":16},85,{"$nulls":5},30,{"$nulls":53},"452C38DBE00000616AD445E437E62A7E"]
["A22A814AB14CD93F0F725FE8260C58D5",0,null,"2016Y0003",-1,{"$nulls":75},"完成码头、引桥桩基施工，完成上部结构6.6万方，占总工程量的74.2%","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["FFFEBCCF52F8487B3F71B61D12697AF4",0,null,"2016Y0003",-1,{"$nulls":75},"已完工，正在申请重大设计变更","4B965806A000000167CD9E21EF5CA9FB"]
["9A1E8F054083D6588ACAC897FAFDB590",0,null,"2016Y0003",-1,{"$nulls":75},"前期工作","52A533ECA00000214B6B31C829927789"]
["F73F8B4536D83ABB17D6ECD7E6D71682",0,null,"2016Y0004",-1,15,200,15,620063,493677,2661698,{"$nulls":3},5,18,{"$nulls":64},"   目前全线砍伐和景观树木的移植工作除东阳社区段以外，其余基本完成，开始红线内清表工作；主线交通组织方案已经交管部门认可并通过，全线围挡工作已陆续展开；部分路段老路人行道及路缘石开始破除，346国道段人行保通便道填筑及面层砼浇筑开始施工；部分可施工断面软基湿喷桩、桥梁钻孔灌注桩已经开始施工，其余段落由于受拆迁、林木移植及杆管线迁移、当地百姓阻挠现场施工等原因，导致实体建设无法大面积开展。\n存在问题：1、346国道东阳社区段树木迁伐进度严重滞后；\n2、房屋、沟渠、加油站、市区属以下杆管线等拆迁无实质进展；\n3、交通组织分流工作还需栖霞区、经开区给予支持；\n4、油气迁改或保护方案产权单位至今仍未明确，严重影响及制约工程建设推进；\n5、港华燃气管位至今仍无法控明，请产权单位尽快交接。","531760190000002142470E176A03162D"]
["EE9009CDC38F100E812B453602C24CF1",0,null,"2016Y0003",-1,35,249,null,901675,814568,1313351,4,100,100,21,91,{"$nulls":3},32535,2,42,null,30000,45000,44000,null,20,40,3,27,{"$nulls":3},0,35,249,null,631172,488740,656675,1,50,80,15,91,{"$nulls":3},15000,2,42,null,30000,45000,44000,null,20,40,3,27,{"$nulls":3},0,{"$nulls":15},"高邮先导段已交工，二期工程正在进行土方填筑、涵洞和桥梁桩基施工。向阳河特大桥下部结构完成约80%，上部结构约60%。邗江段正在进行桥梁桩基施工和“三场”建设。","53AB5E72800000219F8F0ED14F139BBE"]
["BA69FE78E5C5233D65277F238859F279",0,null,"2016Y0004",-1,{"$nulls":75},"开展路基和雨污水管施工","4EDD9C40A0000021AB18D369C57D514A"]
["C8C015DCFC418A3ADC3702D641DF9691",0,null,"2016Y0004",-1,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,{"$nulls":45},"全线已通车。","4D70707C00000001E077DAB59B768AFF"]
["06AA4C7284503278873E44EF00A9D0DA",0,null,"2016Y0004",-1,45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":4},45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":19},45,{"$nulls":30},"53A223CAE0000021EAC73238C8A7294A"]
["9EBA4EA1FF461EC8044C0D78AEFD2EC7",0,null,"2016Y0003",-1,{"$nulls":76},"5450A07920000021D638F48B122F2CC9"]
["AF72C444BCDEDF4886794816E80E04BC",0,null,"2016Y0004",-1,{"$nulls":75},"目前，一期已建成。","4582F984A00000210B371656660E7377"]
["A43E187B0F8985D6E5CFB2495101F2D8",0,null,"2016Y0004",-1,{"$nulls":75},"该项目正在进行前期工作。","53ACB85FC00000013E93FD3AD08F08F0"]
["2655516CB96D801A86D788B31592E66B",0,null,"2016Y0003",-1,{"$nulls":75},"完成接岸段4km抛填，加快延伸段施工，赣榆港区初步形成了双堤环抱雏形。\n","4C2FAFDCA0000021C4BD69F74D4CF3C4"]
["A59AFAE22C67E33C30F74F3F686B0898",0,null,"2016Y0004",-1,{"$nulls":75},"码头水工主体完工，加快后方陆域施工","4C2FD279600000213429D9E7E0D2E66E"]
["66B332FE3E1CAFCC4A54784A8C506085",0,null,"2016Y0004",-1,{"$nulls":75},"水电安装完成95%。幕墙完成98%。内装完成95%。设备安装98%。市政完成60%。","48AC14EDE0000021742CF36A7A1280AB"]
["1F2097D4C70B96D018C48859FB62AB6A",0,null,"2016Y0004",-1,{"$nulls":75},"完成路基清表和河塘处理，正开展路基填筑","4D08381440000021025FCF5FDA219DA7"]
["3F0CEAF6C89FE58BEC85E63EAA3C980D",0,null,"2016Y0004",-1,{"$nulls":75},"草庙以东段13km已完成路基挖方95.5%，路基回填67.13%，箱涵100%，桥梁93.5%；草庙至沿海高速段已完成招标工作，正在组建项目部。","53A6915A00000021AD1AD66B463B498A"]
["35D63A3EC46B6329AE7BB6AE4F17A506",0,null,"2016Y0004",-1,{"$nulls":75},"一期全部完成，目前二期因资金未到位征地拆迁工作尚未启动","46A37B7E80000021FCCC83E6275E4C98"]
["02A67E583826E446445A85964960E7DD",0,null,"2016Y0004",-1,5,112,5,208954,196309,573301,4,100,100,5,30,{"$nulls":3},3381,4,88,{"$nulls":5},70,30,5,30,{"$nulls":3},1176,1,31,null,208954,196309,573301,null,69.6,30,{"$nulls":5},2204,1,7,{"$nulls":12},1102,{"$nulls":16},"452C38DBA0000101EE35873CD541EA02"]
["F090B84DE00008A2AB31575C61494366",0,null,"2016Y0004",-1,{"$nulls":75},"苏州南路至长深高速段已全面建成，其他段落暂未实施。","4D746069A0000021424848A8623D4A12"]
["FC898D29F4FD03914BE5F1C40D530A16",0,null,"2016Y0004",-1,{"$nulls":75},"建成通榆河大桥、射阳河大桥和先导段3.1公里，其余路段完成路基填筑50%、涵洞35%、桥梁工程17%。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["F12F0D63F0EBDA16746278487EBDBCC7",0,null,"2016Y0004",-1,{"$nulls":75},"正在进行桩基施工。","51E88CC1C000000135D9837102FD2D41"]
["73FE17F2CE7670C952EB1A4D98FDCD6C",0,null,"2016Y0002",-1,{"$nulls":75},"已建成通车。","4E0AAEDB80000001A21A3E3285F69BC1"]
["04F648EE43158E11AE1FE341D09C7A43",0,null,"2016Y0004",-1,96,null,96,{"$nulls":12},50,null,50,{"$nulls":12},17,null,17,{"$nulls":12},7,null,0,{"$nulls":27},"已交工通车50公里。","45AB8817400000218E63FD22BDA91CE1"]
["5C0F41C5E11442D8C3F1E9F5B3174D44",0,null,"2016Y0004",-1,{"$nulls":75},"建湖G204至建宝线段19.64km建成通车。建湖234省道至331省道段21.2km全线各标段征地拆迁已全部完成，土方开挖90%，路基回填27%，涵洞87%，桥梁55%。建湖G204以东段已完成施工单位招标工作，近期进场。射阳段8.881km已基本完成征地工作，原设计涵洞已基本完成；PC管桩已完成25%，土方开挖全部完成，路基完成60%，桥梁完成78%。","459307CF60000021FC7F08A5CEC30386"]
["C14976D6E343AE1A790E99DD73EB1ED8",0,null,"2016Y0004",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":4},26,30,26,137962,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC"]
["27F58FF370E9A76A5F19521A3648A50F",0,null,"2016Y0004",-1,{"$nulls":75},"完成小箱梁湿接缝；完成小箱梁中、端横梁；完成小箱梁护栏；完成60m护栏；完成拼宽段8%灰土1000方,累计完成94%。","4B2547D8C0000021EA2F1D310FA63F35"]
["5FD30AEED59080FA18521CAB7F5E5102",0,null,"2016Y0004",-1,{"$nulls":75},"建成通车。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["F3BF33728DF6CFC5149CB593DC6015D7",0,null,"2016Y0004",-1,{"$nulls":75},"完成桥梁灌注桩50%。","494F9423E0000021971B8B67E472FD4B"]
["4B83C6E1184A443C30D10965BF08BF70",0,null,"2016Y0004",-1,{"$nulls":75},"桥南接线已建成，正在进行桥梁桩基和北接线路基施工。","4810580020000001F6CBFBB8B8D6F9E1"]
["2541CE8AF4757CF6A922A1F49F5524F2",0,null,"2016Y0004",-1,{"$nulls":75},"该项目正在进行前期工作。","53ACBF2A800000214F643D4640E1B023"]
["E1A67F4607B009742BF0789DE8B031FF",0,null,"2016Y0003",-1,{"$nulls":75},"完成桥梁下部结构和梁板安装，正在开展桥面铺装和桥头接线施工。","458CAF86E00000216E3944578E65ACF2"]
["9DD38BD9584D0477FED95CD718C387E5",0,null,"2016Y0003",-1,{"$nulls":75},"已完成全线清表，正在进行原地面处理、沟塘回填、桥涵施工。","53ACCC31E0000021BC10B730109E9543"]
["55E64E82A42123FB4E6B395AB5DE4CFF",0,null,"2016Y0003",-1,{"$nulls":75},"全线征地拆迁工作已全面启动，施工单位均已进场；赣马镇区段3.5公里已完成赣马镇区段西半幅路基、水稳及沥青下面层工程；东半幅路基开挖回填已基本完成;赣马老路段路面破碎已全面启动。","4D743B53C0000021D528DB4DEF96D439"]
["7427D92EC5CC7E117B7B73ED247D9245",0,null,"2016Y0004",-1,{"$nulls":75},"亭湖段基本完成项目部及监理部的组建工作，完成房屋拆除工作，正在进行征地工作。大丰段已成立项目管理办公室，已启动征拆工作，确定招标代理并进行施工单位招标工作。","53A68FC1C0000021651B0CEA5D438D57"]
["CEAA324E84FA2E1C429C86A2E3AC0421",0,null,"2016Y0004",-1,2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":4},2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":50},"4640A568A0000021A2BC879912C9A53C"]
["E4FB017C42D27921FBBCD1BE0AF477CB",0,null,"2016Y0004",-1,{"$nulls":75},"4月份1标路基工程基本完成，正在进行基层低剂量水稳摊铺，水利涵洞还未回填，峰山桥、张楼桥、朱湾桥正在进行桥梁下部结构施工；2标正在进行标准化建设和路基清表工作，局部进行土石方开挖并进行原地面压实。4月完成投资5000万元，共完成总投资1.33亿元。","4CDB1D29200000214CA3D9F6DE183F12"]
["91072F208006D4A3059CB0E8AE4CE805",0,null,"2016Y0004",-1,{"$nulls":16},466,{"$nulls":5},72,77,null,164,{"$nulls":50},"452C38D720000081C14CEFA6969A8D06"]
["3D53D2026C9BAF81399045FDA8C85690",0,null,"2016Y0004",-1,{"$nulls":75},"已基本完成全线桥涵构造物施工；已完成路基填方65万方，占总量69%，已完成全部挖方24万；路面底基层已完成31.2万平方，占总量61.5%，完成基层26.6万平方，占总量56.5%。","53ACA437E00000213FD16E4DA5646D14"]
["FA07A3ED6B94CA05C1ABC2CC0FE6FC97",0,null,"2016Y0003",-1,{"$nulls":75},"进行航道疏浚。","452C38DBA00000A1D9FAC753CD299992"]
["0E615143F2F32A0F2891952E1661D6D4",0,null,"2016Y0003",-1,{"$nulls":75},"导堤工程正在安装扭王块与空心块，航道开始正常疏浚施工。","4A85A54EA000002149498783DFAF6BB9"]
["0E3427F7682A42FDDB8F908C1C3DC885",0,null,"2016Y0004",-1,{"$nulls":75},"该项目睢宁段已完成路基挖方71.3万方，占总量的52%，已完成路基填方84.6万方，占总量的35.8%；桥涵构造物施工已完成桩基138根，涵洞35道。","53ACAFBC8000002136D28ECA19D46BF2"]
["CDB4FDB26A1C9F08C58859E7A92D6ED3",0,null,"2016Y0004",-1,{"$nulls":75},"目前已建成22.8公里，剩余纵三至纵五段已完成招投标手续。","452C38DA80000041BB1AF46EF3FAECC2"]
["91439C2D286034204977B40F8146454A",0,null,"2016Y0004",-1,{"$nulls":75},"初步设计已审查完毕，正在编制施工图，进入招投标程序。","4B2FF7D380000021FF48FF8FCEED99B8"]
["6B1C26F84E360937BB785A0A5BF33AB0",0,null,"2016Y0004",-1,{"$nulls":75},"完成抛泥区选划评审","44F92AE7400000013A0A1F9A656A1EA4"]
["D6034C334386B6D60D93ADEDC612A8E8",0,null,"2016Y0005",-1,24,340,24,652423,590283,564435,2,100,100,11,79,{"$nulls":4},22,331,21,645899,584380,541858,2,100,100,11,79,{"$nulls":4},2,27,10,65242,59028,225774,0,0,0,0,0,{"$nulls":4},0,18,7,58718,53125,203197,0,0,0,0,0,{"$nulls":19},"对主体工程已完段落约20.6公里进行交安及附属工程扫尾；对三座铁路下穿桥梁开始架梁；对因拆迁问题滞留的约200米段落已完成基层水稳施工，正在养护同时进行路缘石施工；绿化施工单位正在施工。","45A64AD8E000002115357ED0397AE2AC"]
["39868BEDABA44BF4613DE3DB36EF2F84",0,null,"2016Y0004",-1,{"$nulls":75},"水工主体建成","4C2FB609C0000021E347BA6BB8D8C1EF"]
["FE4C7C47FE2006C236088FB1FDB831CE",0,null,"2016Y0003",-1,{"$nulls":75},"正在进行道路清表、原地面处理以及沟塘回填。苗成河大桥正在进行桩基施工，已完成丰徐河中桥及复新河大桥进行桥面系施工。","4D935F2340000021767F74AFEF8958B9"]
["DAEBC4FD1B29CFA8ECADA10D72648568",0,null,"2016Y0003",-1,{"$nulls":75},"全线路基工程已完成；已完成全部水泥搅拌桩3.1万延米；已完成全部614根钻孔桩；完成梁板预制1262片，占总量的91.7%；完成路面底基层11.2万方，占总量86%，水稳基层9.2万方，占总量38%。","4D93664AE00000210AF21F9AA5BF0167"]
["D9F244EACC567E46D950F48DCE79EB19",0,null,"2016Y0003",-1,{"$nulls":75},"建成通榆河大桥、射阳河大桥和先导段2.4公里，其余路段完成清表90%、路基填筑20%。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["7E704B85AAE440B63F110CE388AC9856",0,null,"2016Y0003",-1,{"$nulls":75},"袁坎大桥完成桥梁灌注桩45%。","494F9423E0000021971B8B67E472FD4B"]
["495D370C976D414B4BED31AE20E24CAB",0,null,"2016Y0003",-1,{"$nulls":75},"盐河三桥正在进行施工图设计；其他已完成。","4D74230D8000002178E3CF444AE9AE57"]
["D9158B91CE0543630570F25B5305082E",0,null,"2016Y0003",-1,{"$nulls":75},"苏州南路至长深高速段已全面建成，其他段落暂未实施。","4D746069A0000021424848A8623D4A12"]
["7D9A25BE8B2BA988E8847F77B19BBBAD",0,null,"2016Y0003",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["B1E5E699929C837F0EDEFBA0D0A01075",0,null,"2016Y0004",-1,{"$nulls":75},"码头水工主体基本完工","4F82916F60000021573E0740F78BAAD0"]
["7BF22D983EDC3B5215B9C94A68E6382D",0,null,"2016Y0005",-1,14,136,14,null,null,322623,2,{"$nulls":3},38,{"$nulls":4},12,131,11,null,null,200000,2,{"$nulls":3},38,{"$nulls":4},14,10,14,null,null,322623,2,{"$nulls":3},0,{"$nulls":4},12,2,11,null,null,200000,2,{"$nulls":3},0,{"$nulls":19},"公路段已完成主体工程，市政段正在进行路基施工","45A630DD40000021758080AC865FC45B"]
["A7F62BD4AD8BF2DC6CB7391B5830882B",0,null,"2016Y0004",-1,34,490,34,1100000,900000,2480000,3,{"$nulls":3},102,{"$nulls":4},34,420,16,953000,590000,1274000,0,{"$nulls":3},99,{"$nulls":4},17,90,18,177000,410000,1206,0,{"$nulls":3},7,{"$nulls":4},17,20,0,30000,100000,0,0,{"$nulls":3},4,{"$nulls":4},"\n","\n","\n","\n","\n","\n","\n","\n","\n","\n","\n",{"$nulls":4},"1、晶桥段 、白马段完成沥青施工 2、晶桥-明觉段 路基贯通，特大桥等桥梁进行桩基及上部结构施工，至省道123段完成路基、底基层施工。","44F92AE780000001F6AE7427CA69104E"]
["575F00AD8CC19183758658A9B58506CA",0,null,"2016Y0009",-1,{"$nulls":75},"码头主体继续施工，码头前沿部分轨道梁浇筑完成，正在铺轨，开挖回填正在进行 。联检大楼水电安装完成。口岸大楼内部施工。商业部分基坑开挖。","44F92AE800000121D51AC7AB782D4663"]
["380EF30E2AD413ED08FBD20304F20597",0,null,"2016Y0012",-1,{"$nulls":75},"水工结构部分已完成。","49A73D126000002155483EE2E2B96514"]
["FE52AF1D9D88EB00455185CEFDBC78E8",0,null,"2016Y0011",-1,{"$nulls":75},"324省道西段（一标）进行梁板架设，沥青路面摊铺等；东段（二标）进行路基施工，桥梁下部结构基本完成，进行桥梁立柱施工；徐洪河大桥进行浇筑上部结构等施工。本月完成投资2000万元，累计完成投资3.59亿元。","4CDB1D29200000214CA3D9F6DE183F12"]
["B33D837A7593B5803F5EE03FDFAF4448",0,null,"2016Y0011",-1,{"$nulls":75},"附属工程施工。本月完成投资20万元，累计完成投资2220万元。","50A2E87680000021494BCC0A662835C1"]
["81A85E83F29A023D1AC133F9EDEAF2CE",0,null,"2016Y0012",-1,47,null,47,null,1036343,1003990,3,null,null,50,151,{"$nulls":6},47,null,1036343,1003990,3,null,null,50,151,{"$nulls":50},"53A2269420000021B4EDBBA7A0728BF8",350,27,350,27]
["2AEEBE3BE9728D3D2355AA129C160871",0,null,"2016Y0012",-1,2,{"$nulls":3},52308,146983,9,{"$nulls":3},1,{"$nulls":4},2,{"$nulls":3},52308,146983,9,{"$nulls":3},1,{"$nulls":50},"4640A568A0000021A2BC879912C9A53C"]
["682735CB9C44DB3F48EB42BE51B825AD",0,null,"2016Y0012",-1,{"$nulls":19},624000,{"$nulls":55},"已基本完成全线桥涵构造物施工；已完成路基填方80.4万方，占总量86%，已完成全部挖方24万；路面底基层已完成32.2万平方，占总量64%，完成基层30.2万平方，占总量64%。开始进行面层试验段施工。","53ACA437E00000213FD16E4DA5646D14",null,null,80,24]
["9A320D31B99009605DE50A81CDA3F468",0,null,"2016Y0012",-1,{"$nulls":75},"已开工建设，正在进行桩基施工。","5907064B40000021ECE6CC8FCE2185AD"]
["978AEBC1663DAC27ACA0452098BDF14F",0,null,"2016Y0012",-1,{"$nulls":4},281530,686313,{"$nulls":4},36,{"$nulls":8},281530,{"$nulls":5},27,{"$nulls":8},281530,{"$nulls":5},25,{"$nulls":8},281530,{"$nulls":5},27,{"$nulls":20},"53AC3FB1600000218B373CD92BC2F7DE",58,null,58,null,57,null,58]
["8E81E427ADB72D6FD5BBFB71D7FD9E11",0,null,"2016Y0012",-1,35,{"$nulls":3},814568,1313351,4,null,null,21,123,{"$nulls":3},32535,22,{"$nulls":3},219933,328338,1,null,null,15,96,{"$nulls":3},8134,35,{"$nulls":3},488740,656675,1,null,null,15,123,{"$nulls":3},15000,22,{"$nulls":3},219933,328338,1,null,null,15,96,{"$nulls":3},8134,{"$nulls":15},"高邮段、向阳河特大桥已完成；邗江段路基完成50%，涵洞完成78%，桩基完成88%，预制箱梁完成47%。","53AB5E72800000219F8F0ED14F139BBE",214,73,145,67,145,67,145,67]
["BDDA3958A5A3632811DF9F3345412A99",0,null,"2016Y0012",-1,10,null,10,null,284127,240262,0,null,null,1,37,0,0,null,1012,10,null,10,null,284127,240262,0,null,null,1,37,0,0,null,1012,{"$nulls":46},"49A73E800000002172C0CDF6658536D7",26,20,26,20]
["7E629A928F3B95599E0A331542B5A389",0,null,"2016Y0012",-1,8,null,8,null,104000,96188,{"$nulls":3},5,20,{"$nulls":3},960,8,null,8,null,90000,0,{"$nulls":3},5,20,{"$nulls":3},0,8,null,8,null,104000,96188,{"$nulls":3},5,20,{"$nulls":3},960,8,null,8,null,90000,0,{"$nulls":3},5,20,{"$nulls":3},0,{"$nulls":16},"4E2F4AFE80000021EC1E6A8AD11A72D8",373000,188000,370000,188000,373000,188000,370000,188000]
["0047CE51E3052C15E64BBF0C69E25473",0,null,"2016Y0011",-1,{"$nulls":75},"目前完成路基填方79万方，挖方16.6万方，占填挖总量的83%；已完成全部涵洞63道；桥梁施工已基本完成下部结构，梁板预制139片，占总量的90%，白马河桥悬浇段已完成26块段，占比74%。已完成路面底基层5800方，占总量10%。","53ACC562C00000014BFF8225C085F8AB"]
["158F7165571247C2F924903826C983AB",0,null,"2016Y0011",-1,{"$nulls":75},"已建成通车。","56BA9BAD600000219B3C61DDA7A002DD"]
["BC301C3B4A24A01115C1881B15D06054",0,null,"2016Y0011",-1,{"$nulls":75},"北段已建成，南段完成完成路面基层50%。","4A942AA500000021C0375E5C302345B2"]
["8D7EFE722D96EC7B9562013FEDF96672",0,null,"2016Y0011",-1,{"$nulls":75},"工程完工，准备验收","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["AEDF22E23711DB6393757A32471E87BC",0,null,"2016Y0011",-1,{"$nulls":75},"建成主体工程，完成交安设施90%。","48173F21C00000213849C18090E227D5"]
["047FFBA9FE9302E08F400D908A816267",0,null,"2016Y0012",-1,8,null,8,null,333672,313821,1,null,null,4,11,{"$nulls":3},6489,6,null,2,null,300305,282439,{"$nulls":3},4,11,{"$nulls":3},6489,2,null,6,null,93428,200846,1,null,null,2,0,{"$nulls":3},5848,{"$nulls":4},60061,169464,{"$nulls":3},2,0,{"$nulls":3},5839,{"$nulls":15},"1-5标已完成","464AEA1FC0000021B52E367C631B2D38"]
["32CB76A8796B1481893EC246F8A79D27",0,null,"2016Y0012",-1,{"$nulls":15},3,null,4,null,209847,568814,2,null,null,2,14,{"$nulls":3},13150,{"$nulls":45},"全线已通车。","4D70707C00000001E077DAB59B768AFF"]
["B7CAD4912C047A3A5636F6FF86648F61",0,null,"2016Y0006",-1,{"$nulls":75},"进行疏浚工作，完成疏浚1950万方","452C38DBA00000A1D9FAC753CD299992"]
["7A51BAB7ED22BFE120FA520AE0D98BE0",0,null,"2016Y0007",-1,2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":4},2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":50},"4640A568A0000021A2BC879912C9A53C"]
["3CB700E8CFFABA586FDB22B879A97315",0,null,"2016Y0010",-1,{"$nulls":75}," 件杂区：生活污水处理站及周边场地完工、1#仓库和2#仓库完成90%","46D11E59C00000215FEEE684519DC4AA"]
["EA6FD579044FE0FE1C998CCB2D2E2E44",0,null,"2016Y0010",-1,{"$nulls":75},"已基本完成全线桥涵构造物施工；已完成路基填方80.4万方，占总量86%，已完成全部挖方24万；路面底基层已完成32.2万平方，占总量64%，完成基层30.2万平方，占总量64%。开始进行面层试验段施工。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t","53ACA437E00000213FD16E4DA5646D14"]
["B5B215247AF1E74E76D9D644178E1034",0,null,"2016Y0010",-1,{"$nulls":75},"已基本完成桥涵施工；路面下面层已基本完成。","53ACCC31E0000021BC10B730109E9543"]
["DD15A7E3A8BD52913C91710E7B2EB101",0,null,"2016Y0011",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,{"$nulls":3},21580,5,359,5,122314,112370,113964,1,null,80,null,73,{"$nulls":3},11500,null,200,null,342098,684197,314172,null,50,50,9,40,{"$nulls":3},8000,null,159,null,17300,1300,{"$nulls":3},30,null,27,{"$nulls":3},4000,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）河塘清淤、路基填挖方、非矛盾段小型结构物以及桥梁桩基础、下部结构墩台和上部结构梁板预制及吊装等工作。路基挖方109.0227万方（45.42%），填方155.5207万方（48.58%）；路面底基层12%灰土3.83万方（18.23%）；基层水泥稳定碎石11.434万平方米（5.44%）；沥青面层21.6831万平方米（11.24%）；桥梁完成投资5043.3万（28.65%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。二、存在问题①江宁横溪段剩余红旗社区1户未拆除；石塘社区增加1.3公里辅道土地尚未提供；高压线6道、纵向400米高压线尚未拆除。 ②溧水段剩余两道部队光缆、3道横穿340省道高压线、一处纵向900米高压线尚未拆除。","452C38DB00000021D4253F83097D6579"]
["8A9AF0F8BC5A778407D26A3A24263B4A",0,null,"2016Y0011",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6489,6,144,2,268220,300305,282439,null,100,100,4,11,{"$nulls":3},6489,2,10,6,76634,93428,200846,1,10,0,2,0,{"$nulls":3},5848,null,7,null,71160,60061,169464,null,10,0,2,0,{"$nulls":3},5839,{"$nulls":15},"1-5标已完成。","464AEA1FC0000021B52E367C631B2D38"]
["91C8950CD88841D6BA470D6C83A2E9AE",0,null,"2016Y0012",-1,{"$nulls":75},"DZL-SG2标段主体工程4100米已基本完成，东八字口门累计完成进尺238米，4674米直立式结构东防波堤工程已基本完成。","452C38D9600000015B091B22A009EB3A"]
["8504EC1A5CCD3997A13D64E6CBA16BF3",0,null,"2016Y0012",-1,{"$nulls":76},"557C62C7E00000216B026DFC0627A4CE"]
["EE6EE1DD8B0ED5CE29F16D52EA9AF131",0,null,"2016Y0012",-1,2,null,2,null,57686,83651,{"$nulls":9},1,null,0,null,0,0,{"$nulls":9},2,null,2,null,57686,83651,{"$nulls":9},1,null,0,null,0,0,{"$nulls":25},"544B45F160000021B581CCDA4EBA59DC",20,4,6,2,19,4,5,2]
["FB937C21E1568674886586537A418141",0,null,"2016Y0011",-1,{"$nulls":75},"雨污管道完成80%,镇区段完成半幅沥青下面层，正开展另半幅灰土施工，野外段完成全幅下面层施工和部分上面层的施工","4EDD9C40A0000021AB18D369C57D514A"]
["494602C4CD162C67E13A375EB77CD71C",0,null,"2016Y0011",-1,35,214,null,901675,814568,1313351,4,100,100,21,123,{"$nulls":3},32535,20,136,null,243452,219933,13133,null,60,90,12,95,{"$nulls":3},325,35,214,null,631172,488740,656675,1,50,100,15,123,{"$nulls":3},15000,20,136,null,243452,219933,13133,null,60,90,12,95,{"$nulls":3},325,{"$nulls":15},"高邮先导段已交工，二期工程沥青混凝土下面层完成35%施工。向阳河特大桥全桥主体工程基本完成。邗江段路基完成45%，涵洞完成70%，桩基完成83%，预制箱梁完成35%。","53AB5E72800000219F8F0ED14F139BBE"]
["6CA46F1D3DBC4CE8B9562FF80F3C9A78",0,null,"2016Y0011",-1,24,98,24,334460,326350,280060,3,100,100,18,98,{"$nulls":3},22036,null,55,null,16723,0,0,null,30,65,8,96,{"$nulls":3},22,24,98,12,234122,195810,154030,3,100,100,12,75,{"$nulls":3},11000,null,55,null,16723,0,0,null,30,65,8,96,{"$nulls":3},22,{"$nulls":15},"先导段累计完成路基土方填筑92%，箱梁58%，盖梁台帽65%；盐邵河大桥主桥悬浇施工完成83%。二期工程累计完成路基土方填筑16%，涵洞50%。","53AB6008E0000021100DBB3E8C074665"]
["5BEA83F1811C49267008156F7E4E8114",0,null,"2016Y0012",-1,26,null,26,null,314100,287925,{"$nulls":9},26,null,26,null,314100,287925,{"$nulls":9},26,null,26,null,314100,287925,{"$nulls":9},26,null,26,null,314100,287925,{"$nulls":24},"已建成通车","5920B3DC20000021578C73E56F1F4523",22,null,22,null,22,null,22]
["B15EE6BD13AA2ED69AD575AAF8E002A3",0,null,"2016Y0012",-1,5,null,5,null,107300,104200,{"$nulls":9},0,null,0,null,0,0,{"$nulls":9},2,null,2,null,21675,40411,{"$nulls":9},0,null,0,null,0,0,{"$nulls":24},"路基：完成2.96公里，中部填土7.69万立方米，涵洞：完成3道盖板涵，2道圆管涵.","592976DE60000021AFE58D581D02D2AF",25,28,8,8,10,12,8,8]
["89DE53BEAE0C547CBC6BA74B7F705EEC",0,null,"2016Y0012",-1,{"$nulls":75},"完成投资4600万元，充电桩完成施工","557C81AEE0000021757781722BC05529"]
["F9DCEF3AE0A4F072F2A50D42A676B4D3",0,null,"2016Y0012",-1,{"$nulls":75},"已建成","557C86BC800000017C577605BC3CAD46"]
["C1AE756A8DB3891F6A2CA5CD282B28FD",0,null,"2016Y0012",-1,{"$nulls":4},314400,314400,{"$nulls":13},314400,314400,{"$nulls":13},314400,314400,{"$nulls":13},314400,314400,{"$nulls":24},"已建成通车","59207BAEA00000216D36C44834239B65",16,16,16,16,16,16,16,16]
["1A2BFC5D802C6E31F468A5AF1C20FAF9",0,null,"2016Y0012",-1,{"$nulls":75},"建成通榆河大桥、射阳河大桥和接线3.1公里，全线完成路面底基层97%、基层63%、面层34%。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["E2527659D426F6683F54DFBDA534D1E4",0,null,"2016Y0005",-1,{"$nulls":75},"基本完成征地拆迁工作，路基工程完成83%，路面及桥涵已开工建设。","4D743B53C0000021D528DB4DEF96D439"]
["D7C8ABB8E0968FB35E06B2B03D3EE39F",0,null,"2016Y0005",-1,{"$nulls":75},"建成通榆河大桥、射阳河大桥和先导段3.1公里，其余路段完成路基填筑68%、桥梁工程60%。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["9B939BB6D1D278ACB8FA316692B30640",0,null,"2016Y0011",-1,{"$nulls":75},"物流园的主干道路还有18米宽，100米左右的道路未施工，门岗亭施工完成60%，B1，B2烟感调试，防火卷帘及风机调试中，预计月底调试完成，11月底消防正式对接，12月初消防泵调试工作，本周将进行消防检测（委托第三方检测）月初拿消防检测报告。11月3日质监站来项目进行了预验收，B1，B2集散中心，综合楼，零星整改工作。总承包方目前进行库内灯具调试工作，12月初安监站电梯验收工作。二期钢结构全部完成，进行墙体砌筑施工，等拿钢结构检测报告后进行钢结构主体验收工作，屋顶的彩钢板已铺设完成。","4A09BB5320000021A7468129AEC6112D"]
["4E2DAF04CEE1D196BB3B65F0ABD3B0B4",0,null,"2016Y0012",-1,{"$nulls":75},"324省道徐州东段工程一标段：进行桥梁盖梁，及桥板安装，及部分路面铺设；二标段：进行路基施工，徐洪河大桥悬浇。本月完成投资1300万元。","4CDB1D29200000214CA3D9F6DE183F12"]
["3463655250344F46F6492AD113E11F34",0,null,"2016Y0005",-1,{"$nulls":75},"项目建议书已批复，规划选址、环评等已批复，正在进行洪评报批工作，方案设计已报省厅待审。","51E8967480000021790847B05E2E0A04"]
["9B6BFED04A11D64C728D7DD2F13D4424",0,null,"2016Y0005",-1,{"$nulls":75},"已建成通车。","4E0AAEDB80000001A21A3E3285F69BC1"]
["72A864140CE96D9AE7B8235495AFC817",0,null,"2016Y0005",-1,{"$nulls":75},"水工主体已建成。","46D123DB80000021DDAA88D0A2421B9E"]
["EA70F1E1F40042CE4AD9131AD6F852FA",0,null,"2016Y0007",-1,17,null,17,{"$nulls":12},0,null,0,{"$nulls":12},17,null,0,{"$nulls":12},0,null,0,{"$nulls":27},"B标段已招标，施工单位已进场施工。","45C531BE200000219CD9EF28C8D31E82"]
["A52D52D224FA0A0CA53080B3FA9B98D9",0,null,"2016Y0007",-1,35,249,null,901675,814568,1313351,4,100,100,21,91,{"$nulls":3},32535,2,75,null,63117,45000,44000,null,35,60,4,55,{"$nulls":3},325,35,249,null,631172,488740,656675,1,50,80,15,91,{"$nulls":3},15000,2,75,null,63117,45000,44000,null,35,60,4,55,{"$nulls":3},325,{"$nulls":15},"高邮先导段已交工，二期工程路基已基本完成，底基层完成18%，水稳基层完成8%施工。向阳河特大桥全桥主体工程基本完成。邗江段正在进行路基、桥梁桩基施工和“三场”建设。","53AB5E72800000219F8F0ED14F139BBE"]
["F40EA1992DAAB621416266E84605FC4E",0,null,"2016Y0007",-1,25,140,27,1336352,836248,1317741,23,null,null,28,21,{"$nulls":3},22684,25,140,25,1336352,836248,1317741,23,100,100,28,21,2,null,510,22684,0,5,2,null,null,300118,{"$nulls":10},5,{"$nulls":3},300118,{"$nulls":25},"45886E536000002100B27DDCDF662D01"]
["D9177D5BDC0D6E3DCE205D1746809266",0,null,"2016Y0007",-1,{"$nulls":75},"南环段已建成，上跨长深高速公路大桥已完成，西延段招标工作已结束，正在落实征地拆迁工作。","4D746069A0000021424848A8623D4A12"]
["58E93255CCE4D38CEDE4F93A70F011B1",0,null,"2016Y0007",-1,{"$nulls":75},"连申线灌河西段航道整治工程工可已批复，初步设计通过省发改委会审。市交通运输局已成立连申线灌河西段航道整治工程建设管理办公室，人员、办公场所等已到位。","537D60FE00000021BC8658DA66B79814"]
["B364FD04FD7CA715B3776325902A3A7B",0,null,"2016Y0007",-1,{"$nulls":75},"完成辅建区工程建设并完成交工验收，物流园南停车场智能化安装并投入运营，完成物流园北停车场工程建设。","468F5198A0000021390EE49ABE0B2CD5"]
["80473BC43D26428FEAA8FA41DE6FB90F",0,null,"2016Y0009",-1,{"$nulls":75},"目前，一期已建成。","4582F984A00000210B371656660E7377"]
["4237D357F249E69E016541AF62240725",0,null,"2016Y0009",-1,{"$nulls":75},"目前已获得国家岸线批复，工程初步设计通过审批，施工图待审及招投标工作，海州区及板浦镇政府对工程用地正在进行审批。","4B2FF7D380000021FF48FF8FCEED99B8"]
["20ADEE40AFBB0C2A5A66E68A2340360C",0,null,"2016Y0009",-1,25,140,27,1336352,836248,1317741,23,null,null,28,21,{"$nulls":3},22684,25,140,27,1336352,836248,1317741,23,100,100,28,21,2,null,510,22684,0,5,2,null,null,300118,{"$nulls":10},5,2,null,null,300118,{"$nulls":25},"45886E536000002100B27DDCDF662D01"]
["80EDDD0F7A58DAE2ECCCAED73B2A929E",0,null,"2016Y0009",-1,{"$nulls":75},"正在进行上部结构、堆场和球形仓施工","52A51FB6400000217BBD3E37D9F8ED17"]
["9F9562BCE2CDEB7D40B869DC7261D0D7",0,null,"2016Y0009",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":4},26,30,26,137962,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC"]
["80A9D8883DAF0484CFA92A00115368B1",0,null,"2016Y0009",-1,{"$nulls":75},"已建成通车","452C38D8A0000041215774BA7CEB1CEE"]
["886FC35E50A569B3BBFED8BF739B3DEC",0,null,"2016Y0009",-1,{"$nulls":75},"项目完工，投入运行。","48AC14EDE0000021742CF36A7A1280AB"]
["12C2889DC7DEF2A714779408F9907B3B",0,null,"2016Y0012",-1,{"$nulls":19},415000,null,13,null,null,5,78,{"$nulls":3},25680,{"$nulls":45},"建成通车。","452C38D900000041E569F21C93091E69"]
["9C8802AA3A1A7E440AC118BBF220AF8D",0,null,"2016Y0012",-1,{"$nulls":25},164,{"$nulls":49},"工程扫尾和费用清理，做好缺陷责任期维护工作。","452C38D720000081C14CEFA6969A8D06"]
["ED18911F0BB7876598391F8FAEE3BC4D",0,null,"2016Y0009",-1,10,393,null,614740,483910,766766,13,100,100,5,78,{"$nulls":3},25680,null,393,null,614740,482500,null,13,100,100,5,78,{"$nulls":3},25680,{"$nulls":3},60550,68910,766766,{"$nulls":12},60550,67500,{"$nulls":26},"452C38D900000041E569F21C93091E69"]
["EF5D2FD3D0D6E39A7790D0CB4F7A25A3",0,null,"2016Y0009",-1,{"$nulls":75},"配电房等构建筑物单体施工、地基处理II标段工程施工","452C38D960000061A773E74DF5A30C52"]
["01AEF3BE982AF5135EDF9B64C39E1150",0,null,"2016Y0009",-1,{"$nulls":75},"草庙以东段13km已完成除附属工程外的全部工作；草庙至沿海高速段已完成便道施工62%、清表完成67%、土方开挖31%；3标征地拆迁工作基本完成，正在进行清除表土、土方开挖工作。","53A6915A00000021AD1AD66B463B498A"]
["6B7BA334F8D6EE9F92492B52348A2DC7",0,null,"2016Y0009",-1,{"$nulls":75},"正在进行上部结构、堆场和球形仓施工","452C38DC80000001ADB05FB1C69E6A31"]
["1023E4194BFF9B8C4196FA4383A367CD",0,null,"2016Y0009",-1,45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":4},45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":19},45,{"$nulls":30},"53A223CAE0000021EAC73238C8A7294A"]
["4F3BEF739973ACB948019494423E4227",0,null,"2016Y0009",-1,{"$nulls":15},10,79,19,{"$nulls":3},1,50,95,4,21,{"$nulls":49},"面层摊铺全部结束。","45835A3940000021498FFD174D21DCE8"]
["319022C41CEA5666C073B97B93A3AF9F",0,null,"2016Y0006",-1,{"$nulls":75},"前期工作","52A533ECA00000214B6B31C829927789"]
["6DF84EEB09290E21E9B51CF1D7A31DF7",0,null,"2016Y0007",-1,42,null,42,{"$nulls":12},42,null,42,{"$nulls":12},0,null,27,{"$nulls":12},0,null,27,{"$nulls":27},"全线建成已交工通车。","45C546C200000021547764ADF0037399"]
["36C8DE2EF582909A6DDE12468AC7FE34",0,null,"2016Y0007",-1,{"$nulls":75},"草庙以东段13km已完成路基挖方100%，路基回填89.72%，混凝土挡墙100%，箱涵100%，桥梁99.18%；草庙至沿海高速段已完成项目部组建工作，征地拆迁基本结束。","53A6915A00000021AD1AD66B463B498A"]
["E7FD73F91BBC2CD768FA333058CAF822",0,null,"2016Y0007",-1,{"$nulls":75},"黄圩段正在进行路基施工及沟塘回填，已完成填挖土方7.7万方，占总量的57%，已开始路面基层施工，已完成黄南小桥单幅，共36片梁板安装。其余段落正在进行招标前准备。","4D935B05A00000212B96F38D231EA5C3"]
["77E51F23A9D4BA061BC1286CEF7C699C",0,null,"2016Y0007",-1,{"$nulls":75},"    集散中心已封顶，电缆及电气柜已安装到位，消防电气等设备调试工作；仓储中心B2电梯安装完成，消防管，消防风管安装完成，外围环网消防管生活用水管道敷设完成。B2的窗户安装完成，仓储中心B1电梯井道砌筑完成，一层地坪绑钢筋完成。B1及综合楼电梯正施工安装中，集散中心的卸货平台已安装完成，玻璃幕墙吊篮等前期准备工作完成，开始安装玻璃幕墙。外围道路下雨天积水较多，下周天晴了室外道路施工,预计6月底完成室外道路。二期承台开挖，绑钢筋承台柱，模板安装，防雷接地工作。","4A09BB5320000021A7468129AEC6112D"]
["42E15EE6615D1601FE8B86E5CB179C16",0,null,"2016Y0007",-1,{"$nulls":75},"完成接岸段4km抛填，延伸段设计变更通过审查。","4C2FAFDCA0000021C4BD69F74D4CF3C4"]
["1B89CFFF8C0825F0BDAED435677D526D",0,null,"2016Y0007",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["F5C1FBAE72D4D47DAC5A30A87BD9DC81",0,null,"2016Y0012",-1,{"$nulls":75},"进行桥梁上部结构施工。","51E882EC80000021B9C40721EDEC0F47"]
["D0F2046546BB0743C8D2EF97D427BCA6",0,null,"2016Y0011",-1,{"$nulls":75},"已完成安评、环评、用海、通航、工可报告，获安全审查意见、通航批文、岸线批文，环评已召开专家评审会，用海申请正在办理。勘察和初步设计已完成招标，正在编制初步设计文件。","5596AF04200000010063731208F43EE3"]
["B37C2CEFD2D9D6E997F33B9255D00C07",0,null,"2016Y0011",-1,{"$nulls":75},"    建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["F1763D524711D54E8957A9C4CB8B4407",0,null,"2016Y0011",-1,{"$nulls":75},"无","56BF67C9E0000021BC1B2AEA0891915D"]
["74AFD24DCA6CB47A4A055052C8F300B5",0,null,"2016Y0011",-1,{"$nulls":75},"完成桩基、桥梁下部结构，正在进行箱梁预制和主桥箱梁现浇，北接线路基基本完成，南接线建成。","4810580020000001F6CBFBB8B8D6F9E1"]
["6FF27628945F395354E647C67EE9AAE1",0,null,"2016Y0012",-1,3,null,4,null,96228,103750,1,null,null,1,11,0,0,null,2632,3,null,0,null,16000,0,1,null,null,1,11,0,0,null,0,3,null,0,null,0,0,1,null,null,1,11,0,0,null,0,3,null,0,null,16000,0,1,null,null,1,11,0,0,null,0,{"$nulls":15},"完成主体工程。","4810580020000001F6CBFBB8B8D6F9E1",10,8,10,8,10,8,10,8]
["F60CE3F7B20DA18D0C30530641484E6C",0,null,"2016Y0012",-1,43,null,43,null,2101463,1929915,3,null,null,9,115,{"$nulls":3},21580,5,null,5,null,112370,113964,1,{"$nulls":3},86,{"$nulls":3},15500,{"$nulls":4},684197,314172,{"$nulls":3},9,40,{"$nulls":3},8000,{"$nulls":4},1300,{"$nulls":5},40,{"$nulls":3},8000,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）路基填挖方、非矛盾段小型结构物、桥梁下部结构墩台、上部结构梁板预制和吊装等工作。路基：挖方111.578万方（46.48%），填方162.5166万方（50.77%）；路面：底基层12%灰土3.83万方（18.23%）；基层水泥稳定碎石11.4340万平方米（5.44%）；沥青面层21.6831万平方米（11.24%）；桥梁：完成投资5414.3万（30.76%）；绿化：完成投资300万（11.96%）；交安：完成投资281万（6.58%）。二、存在问题：1、江宁段石塘社区零星问题约200米征地问题尚未解决，增加1.3公里辅道土地尚未提供；宁丹路至宁马界横跨340省道高压线5道、纵向400米高压线尚未拆除。2、溧水段剩余两道部队光缆、一处900米高压线尚未拆除。","452C38DB00000021D4253F83097D6579"]
["FBACF49976D87E40834C33D40D45DE77",0,null,"2016Y0012",-1,9,null,9,null,65572,375709,{"$nulls":3},1,6,{"$nulls":3},1714,9,null,8,null,65572,375709,{"$nulls":3},1,6,{"$nulls":3},1714,{"$nulls":46},"4D996E10C000000126B2FCB43502A681",65,null,65]
["F355CB1524ACCF21062783FCEE9896DF",0,null,"2016Y0012",-1,{"$nulls":75}," 防风抑尘网工程完工，2#引桥改造","4C2FCA8B60000021201D5B07BBD59C1F"]
["3FEFDA94958434B68A21520CD6CC7775",0,null,"2016Y0012",-1,1,null,1,null,39420,123520,{"$nulls":4},4,{"$nulls":4},1,null,1,null,39420,123520,{"$nulls":4},4,{"$nulls":8},39420,84000,{"$nulls":13},39420,84000,{"$nulls":25},"545A9D02E0000021DDCE427712FDA0AC",9,4,9,4,2,null,2]
["CD745AD31FF86BD3D1C57CD0056E1576",0,null,"2016Y0005",-1,{"$nulls":75},"亭湖段基本完成项目部及监理部的组建工作，完成房屋拆除工作，正在进行征地工作。大丰段正在进行征拆工作，已完成施工、监理单位招标工作。","53A68FC1C0000021651B0CEA5D438D57"]
["C32C9C084473564475D30F08A0707955",0,null,"2016Y0005",-1,35,249,null,901675,814568,1313351,4,100,100,21,91,{"$nulls":3},32535,2,52,null,54000,45000,44000,null,25,50,4,36,{"$nulls":3},325,35,249,null,631172,488740,656675,1,50,80,15,91,{"$nulls":3},15000,2,52,null,54000,45000,44000,null,25,50,4,36,{"$nulls":3},325,{"$nulls":15},"高邮先导段已交工，二期工程路基已基本完成。向阳河特大桥下部结构完成，上部结构约85%。邗江段正在进行路基、桥梁桩基施工和“三场”建设。","53AB5E72800000219F8F0ED14F139BBE"]
["E13C83507F02F2F2E6F12090D93283B0",0,null,"2016Y0005",-1,{"$nulls":75},"三期堆场完成混凝土面层浇筑，龙门吊轨道梁基础施工","4CFE0113000000218421ACE490EA386A"]
["B5ABC1E3ACBBE652AA1E701053C0BE3F",0,null,"2016Y0005",-1,{"$nulls":75},"    建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["FE58ACEFFEA77E78F03F03A9052D1B7D",0,null,"2016Y0005",-1,{"$nulls":75},"    件杂区污水处理场主体完工，污水处理设备于3月29日开标；散货区围堰清除工程招标工作启动\n\n","46D11E59C00000215FEEE684519DC4AA"]
["E4565ED84DB992026A315FC92B302FD1",0,null,"2016Y0005",-1,{"$nulls":75},"    地基处理2-1区完工； 路基二次处理桩基施工中\n","54FF8480C0000021DE12D878DF626FB5"]
["592CCF458CD7F3B68DD3E31E8E9B86A2",0,null,"2016Y0010",-1,{"$nulls":75},"已完工","5775684A600000212C2E7D77F2FF6A6E"]
["EEBF4E1F96BDC159D9BCC5CE7B9122C2",0,null,"2016Y0010",-1,{"$nulls":75},"全线征地拆迁基本完成，路基工程完成95%，中小桥涵完成90%，大桥完成85%，路面底基层完成50%，基层完成35%、沥青下面层完成25%，沥青上面层完成10%。","4D743B53C0000021D528DB4DEF96D439"]
["0CB5F297294154CFE64BA6B1A6B5DF58",0,null,"2016Y0010",-1,{"$nulls":75},"桩基施工基本完成，正在进行桥梁下部结构施工。","51D1D49260000021FCEEDB7A127D7731"]
["5C724F53B0D263CF98B4388604703E90",0,null,"2016Y0008",-1,{"$nulls":75},"路基土方完成20%，桥梁下部结构完成20%。","46A37B7E80000021FCCC83E6275E4C98"]
["AC01B3B89BAF605CC34E2662DE41C293",0,null,"2016Y0009",-1,5,112,5,208954,196309,573301,4,100,100,5,30,{"$nulls":3},3381,4,88,{"$nulls":5},70,30,5,30,{"$nulls":3},1176,1,31,null,208954,196309,573301,null,69.6,30,{"$nulls":5},2204,1,7,{"$nulls":12},1102,{"$nulls":16},"452C38DBA0000101EE35873CD541EA02"]
["C1B18BFB21A226AB9BF1CA15EC214C6F",0,null,"2016Y0011",-1,{"$nulls":75},"工可编制已完成，进行航道影响、通航安全论证。","544C5641800000213203D4F23F47635D"]
["08645B75B848D568034A2F9BCED64455",0,null,"2016Y0011",-1,{"$nulls":75},"项目已完工，正在试运行","529BC5F4A0000001199EEF6E770F959B"]
["67DF2518A8425924067A41A9D0CF6337",0,null,"2016Y0011",-1,11,65,11,192161,528105,629651,2,100,100,4,11,{"$nulls":3},10640,6,43,6,192161,528105,629651,1,60,100,2,7,{"$nulls":3},-2119,null,13,null,10530,0,0,null,40,50,1,1,{"$nulls":3},10640,{"$nulls":7},24,50,{"$nulls":22},"4D897AEAA00000212EF01FB341272DCF"]
["CCD4BC337FC7E3A7F07CCAB6910AC8E8",0,null,"2016Y0011",-1,{"$nulls":75},"已建成通车","4E43951720000021FBA265633212A975"]
["D32F2EB8F50E380EB7924B46B3ACB2D1",0,null,"2016Y0005",-1,{"$nulls":75},"完成下部结构施工，完成箱梁预制10片。","50A749104000002111B1BD6A84FDACB7"]
["171195D202A322F90D6CFC1C8974CA64",0,null,"2016Y0005",-1,{"$nulls":75},"正在进行桩基施工。","51D1B60C60000021547E4A7724FD4535"]
["B4625D2C155B131B8D5BE31719CBFE26",0,null,"2016Y0005",-1,{"$nulls":75},"已交工","452C38DCA0000041AF6C7C4A1C59D11A"]
["1766095369E3C5EF9D34747E0885D3DE",0,null,"2016Y0005",-1,{"$nulls":75},"该项目正在进行前期工作。","53ACB85FC00000013E93FD3AD08F08F0"]
["F7281942DF5052116DBFF5AEE7A97834",0,null,"2016Y0005",-1,{"$nulls":75},"水工主体建成","4C2FB609C0000021E347BA6BB8D8C1EF"]
["D3FFEC774331AB28E549CBE9DD0C38D5",0,null,"2016Y0005",-1,{"$nulls":75},"码头水工主体基本完工","4F82916F60000021573E0740F78BAAD0"]
["635E6A5771D6B309DD908FB5D8793DEC",0,null,"2016Y0010",-1,{"$nulls":75},"一突堤总长约3000米，完成抛填进尺975米；二突堤长约2900米，完成抛填进尺410米","54FF6D5820000021298A28081FBDF9AC"]
["C29B42093560BB50148FD95F9459683F",0,null,"2016Y0010",-1,{"$nulls":75},"亭湖西城桥桥梁施工已完成，正进行接线施工。","458CAF86E00000216E3944578E65ACF2"]
["15DF533B01E2978093BAC479CD899A32",0,null,"2016Y0006",-1,{"$nulls":75},"完工","4A98BD0D800000212D60BD89CB35D858"]
["A30C1BBF908CE0ECB5CDDFDEAB5D4330",0,null,"2016Y0006",-1,{"$nulls":75},"进行路基、桥梁桩基施工。本月完成投资50万元，共完成投资1950万元。","50A2E87680000021494BCC0A662835C1"]
["64EB1617E99464890FDE41392E3F49E4",0,null,"2016Y0006",-1,{"$nulls":75},"盐都段已分期建成229省道至大纵湖风景区段25.392km，大纵湖风景区至兴化交界段8.5km暂无实施计划，当前正在新建229省道至204国道段，229省道至204国道段8.7km当前水泥搅拌桩完成91%，土方开挖完成100%，路基回填完成64%，涵洞完成62%，大中小桥完成98%。城南新区段3km目前施工单位已进场，拆迁工作全部结束，正在进行征地补偿工作，累计完成箱涵3道，全线中桥1座梁板安装全部结束。","452C38D5E0000101955840B450CF8800"]
["70EFA02B96DA0F45467AB2DEA0326DF4",0,null,"2016Y0011",-1,6,30,3,153018,143500,670147,1,100,100,1,23,{"$nulls":5},5,{"$nulls":14},30,{"$nulls":5},30,60,null,13,{"$nulls":5},5,{"$nulls":29},"4640B199A0000021EB976A9433EF07F4"]
["703A9711B8055BB1D2C7E05C38CC168F",0,null,"2016Y0012",-1,244,null,244,{"$nulls":3},9,null,null,76,{"$nulls":5},244,null,244,{"$nulls":3},9,null,null,76,{"$nulls":5},244,null,244,{"$nulls":3},9,null,null,76,{"$nulls":5},244,null,244,{"$nulls":3},9,null,null,76,{"$nulls":20},"全长2.24公里，已完工1.67公里，剩余路段正在进行挡土墙施工。","531C0B09800000213AEF0095AEB1C8E4"]
["0C5D742974E56070E2732047C6CCA605",0,null,"2016Y0012",-1,{"$nulls":75},"高水河桥累计完成承台89%，墩台86%，现浇箱梁完成12联，金湾河桥箱梁架设已完成，古运河桥预制箱梁全部完成，架设完成80%。江都龙城路至金湾河大桥道路工程：引江河桥完成灌注桩53%，雨污水管道工程完成55%，土方填筑完成15%；江都境内其余道路标段施工单位已确定。下穿文昌路隧道工程完成地道主体砼94%，路基填筑40%；下穿韩许河路地道工程桩基完成6%；科技生态新城范围内其他路基标段已上网招标。","53BC14FC6000002160234E94DA94BAFF"]
["A8718F8C2B1E247250630DB5D4EB305F",0,null,"2016Y0009",-1,{"$nulls":75},"该项目睢宁段已完成路基挖方147万方，占总量的106%，已完成路基填方144万方，占总量的64%；桥涵构造物施工已完成全部桩基216根，完成涵洞44道。西段完成底基层3.3万方，开始路面基层施工。","53ACAFBC8000002136D28ECA19D46BF2"]
["6BEBD92E22232BE7B6AA6D7564824238",0,null,"2016Y0009",-1,500,27,500,3568219,3568219,3026273,{"$nulls":9},500,27,500,3568219,3568219,3026273,{"$nulls":9},500,27,500,3568219,3568219,3026273,{"$nulls":9},500,21,365,3568219,3568219,2269705,{"$nulls":25},"5774DA90E0000021955F838DE13DD727"]
["B035028E5A5BCCCAEE411B5C7A50A60F",0,null,"2016Y0010",-1,47,38,47,218574,1036343,1003990,3,null,null,50,151,{"$nulls":65},"53A2269420000021B4EDBBA7A0728BF8"]
["71BF85BC4EA8D31BC262951C523EB6A6",0,null,"2016Y0010",-1,{"$nulls":75},"完成里程4000公里","5754FB0DC000002123E5B69E7013258D"]
["138A1667CC06D9F2DA19551B73E6A68E",0,null,"2016Y0011",-1,{"$nulls":75},"一期工程G204以西段25.96公里建成通车。二期工程G204以东段已完成施工图审查，今年实施新204国道至老204国道段6.027公里，当前已完成监理招标和征地拆迁调查工作，正在进行青苗补偿工作，项目部及监理组的组建工作已经完成。","45930AC0A00000013A88F40431F8C61A"]
["256CAF2BC9D797721A8F2095F000A015",0,null,"2016Y0011",-1,{"$nulls":15},3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,{"$nulls":45},"全线已通车。","4D70707C00000001E077DAB59B768AFF"]
["D29C3261F0336072A5EAB854DFB4B837",0,null,"2016Y0011",-1,{"$nulls":75},"熏蒸仓K1全部完成，K2完成三分之二","4CFE0113000000218421ACE490EA386A"]
["8B4E3CF57F20411374F9C63857AA9E5E",0,null,"2016Y0011",-1,{"$nulls":75},"目前沛县段（28.918公里）完成路基填筑243万方，占总量92%；桥梁工程共完成钻孔桩892根，占总量99%，完成梁板2341片，占总量91%。完成路面底基层62万平方，下基层完成49万平方，上基层完成37万平方，下面层完成25万平方。铜山段（25.366公里）PPP招标已开始，计划启动征地拆迁。","45FEE20920000001DB1994300FA9DCE3"]
["4CB45B734FCD43DFB831E619D568BA45",0,null,"2016Y0005",-1,45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":4},45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":19},45,{"$nulls":30},"53A223CAE0000021EAC73238C8A7294A"]
["5A9C7D1F647045E9915C36450B0B8BBA",0,null,"2016Y0005",-1,{"$nulls":75},"完成路基清表和河塘处理，正开展路基填筑","4D08381440000021025FCF5FDA219DA7"]
["D5058F291743A7405B8C60C4773E06A6",0,null,"2016Y0005",-1,{"$nulls":75},"亭湖西城桥正在开展桥面铺装和接线施工。","458CAF86E00000216E3944578E65ACF2"]
["89F54607B78A9407A16AB33FB62FF75E",0,null,"2016Y0005",-1,{"$nulls":75},"已基本完成桥涵施工；路面基层施工已基本完成，进行下面层试验段。","53ACCC31E0000021BC10B730109E9543"]
["09C06BC6676D6609BE717952B777C7EC",0,null,"2016Y0005",-1,{"$nulls":75},"完成1630万方疏浚，为总工程量的50.9%","4ED76E5EA0000021C2FF39A1BE0258B9"]
["6B4445170D00D2B03A485111D0BCA27F",0,null,"2016Y0007",-1,{"$nulls":75},"项目完成主体工程建设100%","557C880820000021E6B80B97DEA5406F"]
["2DA818C6AA33E4320DA04FC449A05560",0,null,"2016Y0007",-1,{"$nulls":15},22,313,14,587181,531255,338661,2,100,100,11,79,{"$nulls":49},"20.6公里下面层结束，已完成上面层约20%；交安及附属工程完工；绿化完成90%。","45A64AD8E000002115357ED0397AE2AC"]
["6721A6CD7943AE51A506F61A33875BB1",0,null,"2016Y0007",-1,{"$nulls":75},"航道已疏浚土方量785万方；导堤工程仅剩余3500件扭王块未安装。","4A85A54EA000002149498783DFAF6BB9"]
["F47717C85652A526C3823DE1F5DECAE5",0,null,"2016Y0007",-1,{"$nulls":16},85,{"$nulls":5},30,{"$nulls":53},"452C38DBE00000616AD445E437E62A7E"]
["51681594648826B55A9EF2042C910A98",0,null,"2016Y0007",-1,{"$nulls":75},"主体建成，正在进行桥面系施工。","50A749104000002111B1BD6A84FDACB7"]
["2DFF0BA78809BBE0233B702ADD754D00",0,null,"2014Y0009",-1,{"$nulls":75},"沭阳百盟物流产业园项目位于沭阳县南部新城宿沭一级路与上海路交汇处，项目规划总占地面积605.05亩。其中一期占地264亩，于2012年5月8日正式开工建设，规划新建一栋2层的汽修中心5706平方米，两栋6层的司机之家16898平方米，信心交易中心40370平方米、专线物流配送中心12312平方米、零担中心25644平方米、总部经济楼及招商楼11984平方米，仓储中心15700平方米，地下水泵房340平方米等共计13.02万平方米。截止到2014年9月底，项目市场部分已竣工，商户全面进场装修，开始试营业。仓储中心正式动工","57417879400000214FD767D51772E78A"]
["293D80EDAC8361EFE3866F502F502E1D",0,null,"2016Y0010",-1,{"$nulls":75},"完工","4A98BD0D800000212D60BD89CB35D858"]
["BE7C9D897E1F2595626D0F7B64EAEE87",0,null,"2016Y0010",-1,{"$nulls":75},"锦文路至江宁河路段软基处理，部分路段涵洞建设。由于拆迁矛盾，施工暂缓。","44F92AE9A0000001A6C4B4A0FE608B65"]
["E53723A6A87785DCA24FA0C2666EE4A8",0,null,"2016Y0010",-1,{"$nulls":75},"码头沉桩48根；17根灌注桩全部浇筑完成；预制纵梁459件；预制面板81件；现浇下横梁4榀；后方堆场开沟降水。6台门机抓紧制造中。","52A51020400000219F26349145A4F022"]
["110C40840AEE4CD3DC637B03801B31D4",0,null,"2016Y0010",-1,{"$nulls":75},"正在进行箱梁预制施工。","51D1B60C60000021547E4A7724FD4535"]
["91570F59B311FD7BD5F3F43ED49D1740",0,null,"2016Y0010",-1,{"$nulls":75},"已建成通车。","4583086800000021610D57307F655C40"]
["3F41A788152E7B1242B497892F3DFFE1",0,null,"2016Y0010",-1,{"$nulls":75},"       工程扫尾：电气设备购置安装等\n","550039AE60000021602B74992B9B08AE"]
["9171803065F0B8BFAB1CFC61FD8B0BC7",0,null,"2016Y0010",-1,{"$nulls":75},"建成主体工程，完成交安设施85%。","48173F21C00000213849C18090E227D5"]
["3BD5AFD532FD926F8F9CC2DFBAB67C50",0,null,"2016Y0009",-1,{"$nulls":75},"该项目正在进行前期工作。","53ACBF2A800000214F643D4640E1B023"]
["290DE5B1110F79F65FA6DDA67ACFF036",0,null,"2016Y0009",-1,{"$nulls":75},"完成设备安装","4B96568F00000021E184EC6C9CE9F9DC"]
["1475AC2E5B629B49438A207080BA64B4",0,null,"2016Y0009",-1,{"$nulls":75},"水工主体建成","4C2FB609C0000021E347BA6BB8D8C1EF"]
["D1AF73B4390B18F94396D20033B1CC53",0,null,"2016Y0006",-1,{"$nulls":75},"桩基施工基本完成，正在进行桥梁下部结构施工。","51E882EC80000021B9C40721EDEC0F47"]
["5CF80CB8B770BBE26F926C54C5E4A749",0,null,"2016Y0006",-1,{"$nulls":75},"规划建设信息交易中心、配套服务中心、电子商务中心、零担快运中心、智能车源中心以及管理服务中心等5+1功能模块。\n其中信息交易中心（暨管理服务中心）3.3万平方米；配套服务中心1.9万平方米；电子商务中心0.87万平方米；零担快递中心 2.7 万平方米；另停车场10.0万平方米，大货车停车位 550个，小车停车位449个。汽修汽配0.13万平方米。工程主体已经基本完工。存在问题：工程前期投资较大，融资较困难，希望得到政府的支持。","533B436000000021E259D2573B1BB703"]
["20527675DF46D7535B9412C7F67B86AB",0,null,"2016Y0006",-1,{"$nulls":75},"    集散中心已封顶，电缆及电气柜已安装到位，消防电气等设备调试工作；仓储中心B2电梯安装完成，消防管，消防风管安装完成，外围环网消防管生活用水管道敷设完成。B2的窗户安装完成，仓储中心B1电梯井道砌筑完成，一层地坪绑钢筋完成。B1及综合楼电梯正施工安装中，集散中心的卸货平台已安装完成，玻璃幕墙吊篮等前期准备工作完成，开始安装玻璃幕墙。外围道路下雨天积水较多，下周天晴了室外道路施工,预计6月底完成室外道路。二期承台开挖，绑钢筋承台柱，模板安装，防雷接地工作。","4A09BB5320000021A7468129AEC6112D"]
["8215594B410939FA6080C0455BDF7AE0",0,null,"2016Y0007",-1,{"$nulls":15},3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,{"$nulls":45},"全线已通车。","4D70707C00000001E077DAB59B768AFF"]
["78F0F08290B38B9565011AA1503DB84C",0,null,"2016Y0007",-1,{"$nulls":75},"一标（251以西）进行路基施工，梁板预制及桥梁桩基和承台施工；二标（251以东）进行路基施工，徐洪河大桥及其他桥梁的桩基和承台施工。本月完成投资3000万元。","4CDB1D29200000214CA3D9F6DE183F12"]
["F4C0BEB0E347D5503EC0DC869EC4DAC3",0,null,"2016Y0010",-1,{"$nulls":75},"已建成通车","4E43951720000021FBA265633212A975"]
["859281257BA71C8BEF26E23694D2F36A",0,null,"2016Y0010",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":4},26,30,26,137962,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC"]
["F873B22203442866ACAB09B9CF226241",0,null,"2016Y0006",-1,45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":4},45,17,45,825867,894111,1692770,0,null,null,22,44,{"$nulls":19},45,{"$nulls":30},"53A223CAE0000021EAC73238C8A7294A"]
["4628820D7A92AA134158F22B6B440C07",0,null,"2016Y0006",-1,{"$nulls":75},"正在进行路基施工及沟塘回填，已完成填挖土方5.8万方，占总量的43%。已完成黄南小桥单幅，共36片梁板安装。","4D935B05A00000212B96F38D231EA5C3"]
["F1F6A16271CBF0CEC7918789C5B7BC7D",0,null,"2016Y0006",-1,{"$nulls":75},"该项目睢宁段已完成路基挖方115万方，占总量的83%，已完成路基填方109万方，占总量的48%；桥涵构造物施工已完成桩基174根，涵洞37道。西段完成底基层3.1万方，开始路面基层施工。","53ACAFBC8000002136D28ECA19D46BF2"]
["5C2DF8473380FBE991C7C2BEC6BB8DE0",0,null,"2016Y0006",-1,{"$nulls":75},"已基本完成桥涵施工；路面下面层已基本完成。","53ACCC31E0000021BC10B730109E9543"]
["0E6565CD306CA4A194F86589A9A41315",0,null,"2016Y0006",-1,{"$nulls":75},"路基已完成，正在进行路面施工。","545A9D02E0000021DDCE427712FDA0AC"]
["B877392D5AEAA40BDF707245F806B5EE",0,null,"2016Y0008",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,629,19,1072800,1015900,2154700,9,0,0,17,47,0,0,0,70000,10,26,2,59035,116037,225700,0,0,0,0,0,0,0,0,11343,0,1,0,800,900,900,0,0,0,0,0,0,0,0,200,{"$nulls":15},"工程全长20.976公里，分为前半段“起点-坟头”10.176公里和后半段“坟头-终点”10.8公里两个段落。工程除部队矛盾节点影响约1.7公里(含前半段1.2公里及后半段0.5公里)外，其余全部建成。后半段10.8公里已于2013年9月完成交工验收；前半段除西村战术场段落外，主线2015年底已全部贯通，辅道需待征拆完成后完成。","44F92AE840000101423CCFA36BCE2089"]
["107A14DD3DF4BE5D91D256CD6A748337",0,null,"2016Y0008",-1,35,214,null,901675,814568,1313351,4,100,100,21,123,{"$nulls":3},32535,2,95,null,189350,45000,0,null,40,65,4,61,{"$nulls":3},325,35,214,null,631172,488740,656675,1,50,100,15,123,{"$nulls":3},15000,2,95,null,189350,45000,0,null,40,65,4,61,{"$nulls":3},325,{"$nulls":15},"高邮先导段已交工，二期工程路基已基本完成，底基层完成89%，水稳基层完成8%施工。向阳河特大桥全桥主体工程基本完成。邗江段路基完成17%，软基处理完成50%，涵洞完成51%，桩基完成60%，桥梁下部结构已开展施工。","53AB5E72800000219F8F0ED14F139BBE"]
["01C9DAAC9B0CCBA10D90DF4BA0BF80B6",0,null,"2016Y0008",-1,24,98,24,334460,326350,280060,3,100,100,18,98,{"$nulls":3},22036,null,28,null,0,0,0,null,20,40,0,67,{"$nulls":3},22,24,98,12,234122,195810,154030,3,100,100,12,75,{"$nulls":3},11000,null,28,null,0,0,0,null,20,40,0,67,{"$nulls":3},22,{"$nulls":15},"累计完成路基回填28万方，涵洞67道，桥梁桩基159根，箱梁112片。","53AB6008E0000021100DBB3E8C074665"]
["17D1F8D96F3E0F717D8EB8698AA7339A",0,null,"2016Y0006",-1,{"$nulls":75},"码头主体继续施工，码头前沿轨道梁浇筑，挡土墙施工。联检大楼水电安装完成80%。口岸大楼施工主体完工。商业部分桩基础施工完成","44F92AE800000121D51AC7AB782D4663"]
["44B4F6A85E44A6DFBE2C6931C2B2047F",0,null,"2016Y0006",-1,{"$nulls":75},"目前沛县段（28.918公里）完成路基填筑211万方，占总量82%；桥梁工程共完成钻孔桩892根，占总量99%，完成梁板1992片，占总量81%。完成路面底基层试验段施工。铜山段（25.366公里）由于征地拆迁未启动，施工图设计无法开展。","45FEE20920000001DB1994300FA9DCE3"]
["239BA561170C14B1018B999A79D35641",0,null,"2016Y0006",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成通车","44F92AE720000041FD47DFFCE454F006"]
["350C79C83DDD3285B4F5FB605CA203CF",0,null,"2016Y0006",-1,{"$nulls":75},"盐河三桥正在进行施工图设计；其他已完成。","4D74230D8000002178E3CF444AE9AE57"]
["636669CE894F421086AE18A54B68303D",0,null,"2016Y0006",-1,{"$nulls":75},"码头水工主体完工，加快后方陆域施工","4C2FD279600000213429D9E7E0D2E66E"]
["625E387E4A838C7EC8B1B0F15AADD4BC",0,null,"2016Y0006",-1,{"$nulls":75},"正在办理规划方案审查，第一轮方案规划局要求修改，目前正在按照规划局要求修改总平图。","557C645500000021E5F8ECFB3FBFD566"]
["95AA88A0903F6BA3B374AD4A5AD1E15E",0,null,"2016Y0006",-1,{"$nulls":75},"已取得概算批复；招标公告已发，预计7月11日开标。","557C90AF00000021D97DFED87AEB9B2C"]
["83BC72DFF2DD35442ABB46D93C11A15A",0,null,"2016Y0006",-1,{"$nulls":75},"488亩项目地块已全部摘牌，预计二季度落实土地证；开工手续筹备中，总平图已完成设计，相关图审手续正在办理中。","550AAC86A0000021B1EAED5B6BCEE228"]
["C9C9CA31F4EBC0A29FA45A73F13958C3",0,null,"2016Y0008",-1,{"$nulls":75},"工可编制已完成，进行航道影响、通航安全论证。","544C5641800000213203D4F23F47635D"]
["82AAB1CB2AC90E6A2619EDD98CD592F7",0,null,"2016Y0008",-1,{"$nulls":15},17,400,16,923000,490000,1274000,{"$nulls":4},95,{"$nulls":49},"该项目晶桥、白马段完成；晶桥至明觉段部分段落进行路面施工，桥梁进行上部结构施工，完成交安绿化招投标工作。","44F92AE780000001F6AE7427CA69104E"]
["443587FBC4ED98917F343391612B8939",0,null,"2016Y0008",-1,{"$nulls":75},"路基已完成，正在进行路面施工。","545A9D02E0000021DDCE427712FDA0AC"]
["D326EC18C6EA90818F78D85F74BC2657",0,null,"2016Y0008",-1,{"$nulls":75},"建成通榆河大桥、射阳河大桥和先导段3.1公里，全线完成路基填筑90%、路面基层34%、面层18%、桥梁工程90%。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["AD68AB6CD8DA65BA6317E2222FF3CDF7",0,null,"2016Y0008",-1,{"$nulls":75},"目前已获得国家岸线批复，工程初步设计通过审批，施工图待审及招投标工作，海州区及板浦镇政府对工程用地正在进行审批。","4B2FF7D380000021FF48FF8FCEED99B8"]
["E7C42551AA9899EDD74122869DEFA185",0,null,"2016Y0008",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["FB21E0AD1D1B344BA4AA6EEC31882AC2",0,null,"2016Y0008",-1,{"$nulls":75},"已基本完成桥涵施工；路面下面层已基本完成。","53ACCC31E0000021BC10B730109E9543"]
["0B7B491CB1CA01B3749C546F22649255",0,null,"2016Y0008",-1,{"$nulls":75},"工程复工，加快水工主体施工","46D11F4F40000021C374A969A3743C9A"]
["FA37F55B1F5B8DBFA3B816B4A5A6B58A",0,null,"2016Y0006",-1,{"$nulls":75},"全线路面已实现贯通，跨连徐高速主线桥主体工程已完成。","44F92AE7E000004126A44C796491035A"]
["93B8EAF01EC9FABFE40576BC623F69D2",0,null,"2016Y0006",-1,{"$nulls":75},"主体已完成，正在附属设施施工。","468F5198A0000021390EE49ABE0B2CD5"]
["6AE41B58A9FF4E6F6DF7F3F83C7A851F",0,null,"2016Y0006",-1,{"$nulls":75},"已交工","452C38DCA0000041AF6C7C4A1C59D11A"]
["938F4DEDD50DE070A81C5AB6E9A73819",0,null,"2016Y0006",-1,{"$nulls":75},"水工主体已建成。","46D123DB80000021DDAA88D0A2421B9E"]
["0E18A98385AF1FF3505A33DF79A09C49",0,null,"2016Y0006",-1,{"$nulls":16},85,{"$nulls":5},30,{"$nulls":53},"452C38DBE00000616AD445E437E62A7E"]
["CF85CA6BDAE931B22D1C4F0AFACA4537",0,null,"2016Y0006",-1,{"$nulls":75},"桥梁下部结构已完成，正在进行桥梁上部结构和接线路基施工。","45830701A00000018662A81FE3FB2B60"]
["90ECAD7084F1084B3E82D1DB5BA61DD1",0,null,"2016Y0009",-1,{"$nulls":75},"建成桥梁主体工程，正在施工接线。","5770F9C3C000000173423052150A38E1"]
["176953358F7D219879592CC1696B766D",0,null,"2016Y0009",-1,{"$nulls":75},"集散中心已封顶，电缆及电气柜已安装到位，卫生间洁具安装完成，消防电气等设备调试工作；仓储中心b2电梯安装完成，消防管，消防风管安装完成，外围环网消防管生活用水管道敷设完成，电气柜,电缆已安装完成，B1B2阔福门卸货平台系统已安装完成， B1B2的窗户安装完成，仓储中心B1电梯安装中完成，综合楼电梯安装完成，玻璃幕墙已完成，集散中心的卸货平台已安装完成，物流园内主干道完成50%，预计在本月底基本完成，正式自来水，消防水已开通。二期钢结构吊装完成,综合楼消防控制室消防主机未安装到位，静电地板未铺设，室外电缆未铺设，南侧门岗亭基础完成，个单体内清理，清扫工作基本完成。","4A09BB5320000021A7468129AEC6112D"]
["06B01BFE78238DC0CE6233D350D0C91A",0,null,"2016Y0009",-1,{"$nulls":75},"开展港池疏浚","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["3EB7184E006BE4D9BFEDC3041099E9AD",0,null,"2016Y0008",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["03F299101DC41505015A0FB32C2D91F6",0,null,"2016Y0008",-1,{"$nulls":75},"  一突堤总长约3000米，完成抛填770米；二突堤长约2900米，完成抛填67米","54FF6D5820000021298A28081FBDF9AC"]
["782D04B645DAA94B7ED955EA321DB6C7",0,null,"2016Y0007",-1,{"$nulls":76},"46A37B7E80000021FCCC83E6275E4C98"]
["C2DBCFCEBC01BE4A512E89AAC10862FE",0,null,"2016Y0009",-1,{"$nulls":16},85,{"$nulls":5},30,{"$nulls":53},"452C38DBE00000616AD445E437E62A7E"]
["1AA36F803FB62EEBBB91836F5E71E492",0,null,"2016Y0009",-1,{"$nulls":75},"完成灰土9000m3。","4B2547D8C0000021EA2F1D310FA63F35"]
["103E104820F2C4625B59AA9B9092084F",0,null,"2016Y0009",-1,6,30,3,153018,143500,670147,1,100,100,1,23,{"$nulls":5},5,{"$nulls":14},30,{"$nulls":5},30,60,null,13,{"$nulls":5},5,{"$nulls":29},"4640B199A0000021EB976A9433EF07F4"]
["A8CA683FB9A3EBE5F6D5C83DD0A54471",0,null,"2016Y0009",-1,{"$nulls":75},"项目已建成完工。","531CA9B120000021BEA7261286438186"]
["1FB23F9A820B8BD2083ECD2B273A5985",0,null,"2016Y0001",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["A0F750920A8DC67BA3C23B8893877F81",0,null,"2016Y0009",-1,{"$nulls":75},"2个泊位水工主体建成","4C2FCA8B60000021201D5B07BBD59C1F"]
["4E7D2B623E9F7548E697E51FB215BE07",0,null,"2016Y0009",-1,{"$nulls":75},"港池疏浚已完工","56DF7C02A00000214F3976CFEAB3E5C7"]
["395D9269392BD4AD8B17B0B1B600720E",0,null,"2016Y0009",-1,{"$nulls":6},1,null,null,97,{"$nulls":11},1,null,null,61,{"$nulls":11},1,null,null,97,{"$nulls":11},1,null,null,61,{"$nulls":21},"5774DCAB00000021EB87AD7BCCD977FA"]
["A7DD2429A49F077E486F064360EEA10E",0,null,"2016Y0010",-1,{"$nulls":75},"已交工","452C38DCA0000041AF6C7C4A1C59D11A"]
["7F54259CD9DB165937AD1435EE1BB023",0,null,"2016Y0010",-1,{"$nulls":75},"收费大棚及场站用房监理标完成，施工标拟计划10月26日开评标。完成灰土6000m3，覆盖土清除4500m3，水稳7390m3。","4B2547D8C0000021EA2F1D310FA63F35"]
["6FE8179B322CAF5657F64A19F44DFF4F",0,null,"2016Y0011",-1,{"$nulls":75},"水深扫测完成，准备布标，深化设计已完成","5808EA68E0000021896E3DBC2DF8DE84"]
["0DCB935197F3F7476A7215269A70A364",0,null,"2016Y0011",-1,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,59,168,59,8450000,800000,3500000,null,100,100,28,70,{"$nulls":3},15000,17,5,17,2450000,220000,1100000,null,20,null,3,{"$nulls":4},5000,17,5,17,2450000,220000,1100000,null,20,null,3,{"$nulls":4},5000,{"$nulls":16},"4597C2C660000021C7BD96E4F6D02E66"]
["0C2E7F7753DC5ADCBC4186CF69111DEC",0,null,"2016Y0011",-1,{"$nulls":75},"物流园南、北停车场投入试运营。","468F5198A0000021390EE49ABE0B2CD5"]
["6CAB6BE093696CEF3BABEB76AB5495BB",0,null,"2016Y0009",-1,{"$nulls":75},"已完成沈海高速以西段施工图审查，完成东台北绕城段12.64公里、高兴东段9.33公里和机械产业园段0.9公里。本年开工建设串场河大桥及其引桥3公里，累计完成土方开挖100%、路及回填48%、桥梁32%。","53A69343800000016330E2AAE727C4C0"]
["325189C299198A6E2F630293AE8808BC",0,null,"2016Y0009",-1,{"$nulls":75},"路基96区施工，黄南小桥右半幅桩基和水泥稳定层，左半幅沥青混凝土施工。9月完成投资600万元，累计完成投资2092万元。","50A30D9880000021822D064F6E714B8D"]
["C7E49920966BAB5C0D55C6BD6EC09565",0,null,"2016Y0009",-1,{"$nulls":75},"实施项目灰土水稳施工、沥青砼铺设及绿化栽植。","4A7F4412C0000001B5349862C0B620EE"]
["FE7BD11058E171CC0CF2278436E0C7F2",0,null,"2016Y0010",-1,5,112,5,208954,196309,573301,4,100,100,5,30,{"$nulls":3},3381,4,88,{"$nulls":5},70,30,5,30,{"$nulls":3},1176,1,31,null,208954,196309,573301,null,69.6,30,{"$nulls":5},2204,1,7,{"$nulls":12},1102,{"$nulls":16},"452C38DBA0000101EE35873CD541EA02"]
["0BC3907BF247674705D5062E5076C8CF",0,null,"2016Y0011",-1,{"$nulls":75},"水工结构已完成，准备交工验收。输运系统建设和调试，厂房内部结构和设备安装，水电安装和其他附属设施，以及港池疏浚等","452C38DC80000001ADB05FB1C69E6A31"]
["D3DECF5F8DA92C0FF1C0DABE3CFD56F2",0,null,"2016Y0011",-1,{"$nulls":75},"已交工","452C38DA00000041340F0FC19EDA1410"]
["3DF8C2A98A272DCB49866307DACE5EE1",0,null,"2016Y0011",-1,{"$nulls":75},"2个泊位水工主体建成","4C2FCA8B60000021201D5B07BBD59C1F"]
["13B10BA666120037A7ACB58BC46E86AE",0,null,"2016Y0011",-1,{"$nulls":75},"码头水工主体基本完工","4F82916F60000021573E0740F78BAAD0"]
["F3634454235B6BFB2B835D3BDE86D2E9",0,null,"2016Y0007",-1,{"$nulls":75},"规划建设信息交易中心、配套服务中心、电子商务中心、零担快运中心、智能车源中心以及管理服务中心等5+1功能模块。\n其中信息交易中心（暨管理服务中心）3.3万平方米；配套服务中心1.9万平方米；电子商务中心0.87万平方米；零担快递中心 2.7 万平方米；另停车场10.0万平方米，大货车停车位 550个，小车停车位449个。汽修汽配0.13万平方米。工程主体已经基本完工。存在问题：工程前期投资较大，融资较困难，希望得到政府的支持。","533B436000000021E259D2573B1BB703"]
["FDD99CC3607738D728A4C51048994192",0,null,"2016Y0010",-1,{"$nulls":75},"中港大道以北段建成通车，以南段完成路基施工。","5451C27DE0000021B0ADD733CA89E359"]
["5846EF1497C9F35E7CAFFD740C28CC0D",0,null,"2016Y0011",-1,10,393,null,614740,483910,766766,13,100,100,5,78,{"$nulls":3},25680,null,393,null,614740,482500,null,13,100,100,5,78,{"$nulls":3},25680,{"$nulls":3},60550,68910,766766,{"$nulls":12},60550,67500,{"$nulls":26},"452C38D900000041E569F21C93091E69"]
["00358943B2C9B9BAB96ADE2DC5AC3EAE",0,null,"2016Y0011",-1,15,200,15,620063,493677,2661698,{"$nulls":3},5,18,{"$nulls":64},"截止目前，346国道段钻孔灌注桩已全面开始施工,湿喷桩进入推进阶段，少量路基工作开始实施；312国道段以承台和墩身施工为主，部分路段湿喷桩已经正常施工,油气管线挡墙施工准备，逐步展开路基拓宽施工，打通齐民路为交通分流作准备。\n累计完成临时便道1.42km，清表17.22万m2,围挡20km，水马10.7km，清淤0.1万m3,挖土方0.57万m3,湿喷桩180237m，1.2m陆上钻孔灌注桩27根，1.5m陆上钻孔灌注桩280根，1.8m陆上钻孔灌注桩683根，2.0m陆上桩3根，承台114个，墩台身91个。\n存在的困难:1、全线拆迁基本无进展，造成辅路拓宽多处无法进行，已严重制约工程推进，需督促经开区加快落实拆迁；\n2、杆管线尤其油气管线一直制约工程全面展开，需督促产权单位加快自来水、油气管线、电力迁改工作；\n3、主线桥梁施工需全封闭交通，需继续协调争取交管及地方政府对交通分流支","531760190000002142470E176A03162D"]
["73514970BECCB7A7248912DD5A0D2DFC",0,null,"2016Y0011",-1,{"$nulls":75},"本月累计完成疏浚2570万方","4ED76E5EA0000021C2FF39A1BE0258B9"]
["B86F5C60429DF033E428EE745F15F864",0,null,"2016Y0012",-1,{"$nulls":75},"目前已经建成22.8公里，纵三至纵五段路基抛填基本结束，小丁港河桥主体完工。","452C38DA80000041BB1AF46EF3FAECC2"]
["2880E9B00A0EDCD89AC0ADEA7EEBCEED",0,null,"2016Y0005",-1,{"$nulls":75},"正在进行上部结构、堆场和球形仓施工。","452C38DC80000001ADB05FB1C69E6A31"]
["4B298667348D389F9161103F25479E30",0,null,"2016Y0005",-1,{"$nulls":75},"正在进行桩基施工。","51E882EC80000021B9C40721EDEC0F47"]
["D1A66698B79076D97F7831BA8FA1BFBB",0,null,"2016Y0005",-1,{"$nulls":75},"   地质勘测、可研和初步设计完成；临时道路完工；给排水工程和路灯基础施工等\n","550039AE60000021602B74992B9B08AE"]
["8B12D0ED03E852B623F3F9B256AD3BF4",0,null,"2015Y0005",-1,{"$nulls":75},"沭阳百盟物流产业园项目位于沭阳县南部新城宿沭一级路与上海路交汇处，项目规划总占地面积605.05亩。其中一期占地264亩，于2012年5月8日正式开工建设，规划新建一栋2层的汽修中心5706平方米，两栋6层的司机之家16898平方米，信心交易中心40370平方米、专线物流配送中心12312平方米、零担中心25644平方米、总部经济楼及招商楼11984平方米，仓储中心15700平方米，地下水泵房340平方米等共计13.02万平方米。截止到2015年5月底，项目零担快运中心、信息交易中心、专线物流区、招商楼、总部经济楼已全部建成投入运营。8栋钢结构附属配套仓储中心已竣工。项目北侧65亩门卫室正在进行装修及通讯、监控、信息设备安装。联系消防、环保、物业、规划等各单位进行单项验收。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n","57459BD0E0000021461905DF0BA4CD1E"]
["31C244B4376658C2786FA3C4AAFEFF63",0,null,"2016Y0011",-1,{"$nulls":75},"已立项，后方场地部分正在施工，试桩已完成","544C473EA00000213222A4C463CC9061"]
["6D6A35F26DCE0EE160B27D35F75E8DE5",0,null,"2016Y0011",-1,{"$nulls":75},"   疏浚、水工、陆域形成地基处理工程完工；装卸设备、供电设备购置安装\n","46D12095E00000210EEE5BA374F2A089"]
["E23C3C5DC7AD273CA7F8C397F09809E6",0,null,"2016Y0011",-1,{"$nulls":75},"该项目正在进行PPP招标，计划启动征地拆迁。","53ACB85FC00000013E93FD3AD08F08F0"]
["0AB3CF083C17039EF2D638EDCB89F16D",0,null,"2016Y0011",-1,{"$nulls":75},"已完工","5775684A600000212C2E7D77F2FF6A6E"]
["83376B692C583EE4607C0464125534F4",0,null,"2016Y0011",-1,{"$nulls":75},"建成桥梁主体工程，正在施工接线。","5770F9C3C000000173423052150A38E1"]
["620506C1B165F14986E526052F0B5421",0,null,"2016Y0008",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,{"$nulls":3},21580,5,329,5,105964,111070,113964,1,null,70,null,66,{"$nulls":3},11100,null,200,null,342098,684197,314172,null,50,50,9,40,{"$nulls":3},8000,null,129,null,950,{"$nulls":4},20,null,20,{"$nulls":3},3600,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）路基清表、河塘清淤、软基处理、路基填挖方、非矛盾段小型结构物以及桥梁桩基础和梁板预制施工等工作。路基100.8688万方（42.02%），填方140.3815万方（43.85%）；路面底基层12%灰土2.195万方（10.45%）；基层水泥稳定碎石11.304万平方米（5.38%）；沥青面层21.6831万平方米（11.24%）；桥梁完成3109.3万（17.67%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。\n二、存在问题：1、横溪段剩余9户民房尚未拆除，其中红旗社区8户，严重影响工程整体推进；江宁禄口彭福剩余一处养殖场横穿340省道红线，造成便道不能贯通，桥梁无法进场施工。2、溧水段部分路段杆管线迁移进度缓慢，影响部分路段路基贯。","452C38DB00000021D4253F83097D6579"]
["755569CFEC43FAF79D5BDF2DFEEDFA68",0,null,"2016Y0008",-1,2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":4},2,32,null,61824,52308,146983,9,100,100,null,1,{"$nulls":50},"4640A568A0000021A2BC879912C9A53C"]
["EC6F12E07002091CEB58F4CEBE0941C0",0,null,"2016Y0008",-1,{"$nulls":75},"全线除盐河三桥外已建成，盐河三桥正在积极推进征地拆迁工作。","4D74230D8000002178E3CF444AE9AE57"]
["E6B7F2CA617A205F7B0CD84B4A03497B",0,null,"2016Y0008",-1,{"$nulls":15},0,129,0,null,null,0,0,{"$nulls":3},38,{"$nulls":49},"公路段已完成，市政段正在进行路基施工、征地拆迁工作。","45A630DD40000021758080AC865FC45B"]
["41861CEF8C56C80F7C0B153915C7A58D",0,null,"2016Y0008",-1,{"$nulls":75},"征地拆迁已完成，正在进行项目部建设和钢便桥施工。","51E89D06C0000021C5C64F5378EC545C"]
["1AD4375E89FFAA144B0D269B57D53B09",0,null,"2016Y0008",-1,{"$nulls":75},"项目占地250亩，已取得213亩土地，前期土建、钢结构安装已完成，水电安装完成90%工程量，自动化输送线设备安装完成42%工程量。","528B366AC0000021D4B356996DCCFFA8"]
["5517016C5B5E1FF1FDD96C63205ABA78",0,null,"2016Y0008",-1,{"$nulls":75},"完成施工图设计审查","44F92AE7400000013A0A1F9A656A1EA4"]
["F6156387DA08892F36322C517B6682B1",0,null,"2016Y0008",-1,{"$nulls":75},"项目完工，投入运行。","48AC14EDE0000021742CF36A7A1280AB"]
["E04327BCB58D1A12A3AF888158478151",0,null,"2016Y0008",-1,{"$nulls":75},"一期工程G204以西段25.96公里建成通车。二期工程G204以东段已完成施工图审查，今年实施新204国道至老204国道段6.027公里，当前已完成监理招标和征地拆迁调查工作，正在进行青苗补偿工作，项目部及监理组的组建工作已经完成。","45930AC0A00000013A88F40431F8C61A"]
["ABCC4240DCB2A46BFDE53114BF246F14",0,null,"2016Y0008",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6489,6,144,2,268220,300305,282439,null,100,100,4,11,{"$nulls":3},6489,2,10,6,76634,93428,200846,1,10,0,2,0,{"$nulls":3},5848,null,7,null,71160,60061,169464,null,10,0,2,0,{"$nulls":3},5839,{"$nulls":15},"1-5标已完成。","464AEA1FC0000021B52E367C631B2D38"]
["00DD3B38079369B87A0D0EDC2B68E458",0,null,"2016Y0008",-1,{"$nulls":75},"进行疏浚工作，完成疏浚1950万方","452C38DBA00000A1D9FAC753CD299992"]
["7D80F5EC7D6B7EF7478F798E54F1EBD1",0,null,"2016Y0008",-1,{"$nulls":75},"航道已疏浚土方量785万方；导堤工程仅剩余3500件扭王块未安装。","4A85A54EA000002149498783DFAF6BB9"]
["0D6469006FBDA2A01A8E1C7F804D5936",0,null,"2016Y0008",-1,{"$nulls":75},"已建成通车。","4583086800000021610D57307F655C40"]
["97C18565E7D1522E729BA675FEBF16FC",0,null,"2016Y0008",-1,{"$nulls":75},"项目建成完工投入使用。","531CA9B120000021BEA7261286438186"]
["E6AFD15A4A81394925091F37739DBD67",0,null,"2016Y0010",-1,{"$nulls":75},"初步设计变更审查会已通过，正在开展施工图设计变更编制工作。","4C2FAFDCA0000021C4BD69F74D4CF3C4"]
["42937C4311DEEFE03E3C9394AB472B01",0,null,"2016Y0010",-1,{"$nulls":75},"建成通车，进行扫尾工作","46EA9C3D40000021E09CDF7BE3DADF50"]
["A465F8414725D080C6149C0E3A14114C",0,null,"2016Y0010",-1,13,null,13,{"$nulls":12},13,null,10,{"$nulls":12},13,null,13,{"$nulls":12},12,null,10,{"$nulls":28},"5290FF2D800000218EE2D98EEC67211F"]
["27B44991B070BC4116ED2CA0D11A611F",0,null,"2016Y0006",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["9FA6AB0D63795BC1F5BCB9053DCF44A2",0,null,"2016Y0008",-1,{"$nulls":75},"疏浚已开工","56DF7C02A00000214F3976CFEAB3E5C7"]
["904B955CF2DB28B843AAD65B328C169B",0,null,"2015Y0007",-1,{"$nulls":75},"沭阳百盟物流产业园项目位于沭阳县南部新城宿沭一级路与上海路交汇处，项目规划总占地面积605.05亩。其中一期占地264亩，于2012年5月8日正式开工建设，规划新建一栋2层的汽修中心5706平方米，两栋6层的司机之家16898平方米，信心交易中心40370平方米、专线物流配送中心12312平方米、零担中心25644平方米、总部经济楼及招商楼11984平方米，仓储中心15700平方米，地下水泵房340平方米等共计13.02万平方米。截止到2015年7月底，项目零担快运中心、信息交易中心、专线物流区、招商楼、总部经济楼已全部建成投入运营。8栋钢结构附属配套仓储中心已封顶，正在进行设备安装，同步进行招商工作。项目北侧停车场门卫室基础建设工作已完成，正在进行装修和监控、信息化等设备安装，配送中心(即：原零担7、8号楼补齐相关证件），同步消防、环保、规划等部门进行各分项验收及综合验收。","57417879400000214FD767D51772E78A"]
["1A067671B06C91DF934436CC8753D48F",0,null,"2016Y0009",-1,{"$nulls":75},"码头桩基础试桩施工基本完成，港池降水、港池开挖、土方转运、后方陆域回填、陆域强夯试夯等施工。","513D48A080000021F6ECE2A883127397"]
["D364B74596AD18B2FC976E8DF0B9B98E",0,null,"2016Y0010",-1,{"$nulls":75},"亭湖段已完成征地拆迁工作，全线便道已打通，累计完成土方开挖100%、路及回填31.3%、涵洞100%、桥梁工程20%。大丰段基本完成征拆工作，完成土方开挖99%，路基回填58%，涵洞78%，桥梁工程31%。","53A68FC1C0000021651B0CEA5D438D57"]
["46F8D73AA97C9D175E7A6BD43F8495D1",0,null,"2016Y0007",-1,25,190,25,{"$nulls":3},8,null,null,9,73,{"$nulls":3},22233,25,190,{"$nulls":4},8,80,100,9,73,{"$nulls":3},10000,null,1,25,{"$nulls":3},1,{"$nulls":3},1,{"$nulls":3},22233,null,1,{"$nulls":4},1,{"$nulls":3},1,{"$nulls":3},10000,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["ECB7F5C38CE870E943B2B1A000ED685D",0,null,"2016Y0007",-1,{"$nulls":75},"完成路基清表和河塘处理，正开展路基填筑","4D08381440000021025FCF5FDA219DA7"]
["B312ECD3C15F6541193B9B3DE66A366C",0,null,"2016Y0007",-1,{"$nulls":75},"码头水工主体已完工","44F92AE8C0000061CA99E73B5A18BBB6"]
["EA3ECCA7C7318BA4A68156968759FA64",0,null,"2016Y0007",-1,{"$nulls":75},"准备交工验收","5460F4DA20000021E6011AA2335B9033"]
["20CE38146A1B5BED2601FE4DEDB4AE62",0,null,"2016Y0007",-1,{"$nulls":75},"已基本完成全线桥涵构造物施工；已完成路基填方80.4万方，占总量86%，已完成全部挖方24万；路面底基层已完成32.2万平方，占总量64%，完成基层30.2万平方，占总量64%。开始进行面层试验段施工。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t","53ACA437E00000213FD16E4DA5646D14"]
["3994859FA2211BE82E602A3FC57DAD5C",0,null,"2016Y0007",-1,{"$nulls":75},"方案设计已完成，项目优化方案已通过上海铁路局审核。\n","4596CE63A0000021B9EF1E5E417B9CA3"]
["9C4931EC7362E08AE958AA8A0D5AFFEF",0,null,"2016Y0007",-1,{"$nulls":75},"西斜坡堤工程6217米主体结构已基本完成，目前开展挡浪墙施工等；西直立堤工程本月折合进尺399米，累计进尺2541米；西防波堤工程累计折合进尺8758米，占西防波堤总长9804米的89%。","46D12756A00000212A79E7CE74664FD9"]
["E7A0454D291F04DA6E65F1560BD37550",0,null,"2016Y0007",-1,{"$nulls":75},"   路基工程基本完成，本完成费用含土地190亩7942万元","54FF8480C0000021DE12D878DF626FB5"]
["0AD5327A4E9EC328324B9C6D2C2CF4A1",0,null,"2016Y0010",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,{"$nulls":3},21580,5,352,5,122314,111070,113964,1,null,77,null,72,{"$nulls":3},11200,null,200,null,342098,684197,314172,null,50,50,9,40,{"$nulls":3},8000,null,152,null,17300,{"$nulls":4},27,null,26,{"$nulls":3},3700,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）路基清表、河塘清淤、软基处理、路基填挖方、非矛盾段小型结构物以及桥梁桩基础和梁板预制施工等工作。路基挖方106.2027万方（44.24%），填方151.5527万方（47.34%）；路面底基层12%灰土2.98万方（14.18%）；基层水泥稳定碎石11.304万平方米（5.38%）；沥青面层21.6831万平方米（11.24%）；桥梁完成4197.3万（23.85%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。\n二、存在问题：1、江宁横溪段剩余2户民房尚未拆除，严重影响工程整体推进；石塘社区零星点状问题约200米征地问题尚未解决。2、溧水段剩余两道部队光缆、3道横穿340省道高压线、一处纵向900米高压线尚未拆除。","452C38DB00000021D4253F83097D6579"]
["1670CF0F94FAF258534D01C0B5D37761",0,null,"2016Y0010",-1,{"$nulls":75},"正在开展陆域设计变更","4B96568F00000021E184EC6C9CE9F9DC"]
["EA9E30B2276B44AE3A322CA2A32C2172",0,null,"2016Y0010",-1,{"$nulls":75},"完成码头水工部分主体施工，大批环建完成近90%；继续进行码头前沿硬化和附属设施建设。","54DC423000000021276B64BA6711F2E4"]
["441C165107177291CA7576FE4F995F2B",0,null,"2016Y0010",-1,{"$nulls":75},"337湖熟集镇段正在进行雨水和污水管道施工，正在进行部分路段路基施工和湿喷桩施工","44F92AE9800000A15AC5660EDAD7D017"]
["46B2B434A2E4C00CD6BA9694DD0C1D91",0,null,"2016Y0010",-1,{"$nulls":75},"初步设计已批复，施工图已通过省公路局审查，正在进行第三次招标（前两次均流标）。","57551EAC40000021F51AC305BFD1948C"]
["2B95CD5E56078BFBE1002865811F13AA",0,null,"2016Y0010",-1,{"$nulls":75},"路基已完成，正在进行路面施工。","545A9D02E0000021DDCE427712FDA0AC"]
["5B60D0C9A8936C5F0EB2961FDDF57C36",0,null,"2016Y0010",-1,{"$nulls":75},"配电房等构建筑物单体施工、地基处理II标段工程施工","452C38D960000061A773E74DF5A30C52"]
["A45F42F061E55298A4A5D871043914E1",0,null,"2016Y0010",-1,{"$nulls":75},"华元路到朝阳河桥南主车道贯通，目前慢车道水稳完成，正进行平侧石铺设，其余段落完工。","4A04D699C0000021960B6C19775B7500"]
["4E36FA81CAC0F8CC558AD200B89D7215",0,null,"2016Y0006",-1,{"$nulls":75},"项目建议书已批复，规划选址、环评等已批复，正在进行洪评报批工作，方案设计已报省厅待审。","51E8967480000021790847B05E2E0A04"]
["980997E756FDDC618CA25CDCCAFC69DB",0,null,"2016Y0006",-1,{"$nulls":75},"正在进行桩基施工。","51E8A48140000021EF9FCE54477087FB"]
["D96872BB2D5A62BE80122C13ABFAA1CF",0,null,"2016Y0007",-1,{"$nulls":75},"正在进行上部结构、堆场和球形仓施工","52A51FB6400000217BBD3E37D9F8ED17"]
["010C0CB942503D359039BBCDC023682E",0,null,"2016Y0007",-1,{"$nulls":75},"建成通车。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["4062C2BDA0C964438BB4C75597B3EA59",0,null,"2016Y0007",-1,{"$nulls":75},"工程目前正在进行水工土方工程和大堤土方工程，开展港池基础施工","54DC423000000021276B64BA6711F2E4"]
["EF5DD418C82D1703B178D8CA109FC684",0,null,"2016Y0007",-1,22,501,{"$nulls":4},14,100,100,20,116,{"$nulls":5},111,{"$nulls":5},8,21,null,17,{"$nulls":5},384,{"$nulls":5},93,96,null,105,{"$nulls":5},48,{"$nulls":6},17,null,6,{"$nulls":20},"49E0DFA940000021DE73460C8BA04095"]
["3424D3DC4CCF0E6445E788B0296F96E0",0,null,"2016Y0007",-1,{"$nulls":75},"目前使用岸线申请在国家发改委会签，近期将批复，我局正在同步开展项目初步设计审查。","4B2FF7D380000021FF48FF8FCEED99B8"]
["70A4F76FBE507388ACEB312919C02A25",0,null,"2016Y0007",-1,{"$nulls":75},"宁连路至月季路段2.5公里已完成，月季路至飞耀路段已建成。","545A7B4F20000021344738A715E00356"]
["2E9713095B39BE24F9E3ECA79E8AD96E",0,null,"2016Y0007",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["33F582FB1D14D884832484068FBCC528",0,null,"2016Y0011",-1,{"$nulls":75},"建湖G204至建宝线段19.64km建成通车。建湖234省道至331省道段21.2km全线各标段征地拆迁已全部完成，土方开挖100%，路基回填94%，涵洞100%，桥梁94%。建湖G204以东段征地拆迁基本完成。射阳段8.881km已基本完成征地工作，路基完成96%，中小桥全部完成，大桥完成97%。","459307CF60000021FC7F08A5CEC30386"]
["5709BC4FEBE71138FF86A4BE8185B29A",0,null,"2016Y0012",-1,26,null,26,null,693411,488413,3,null,null,25,78,{"$nulls":4},26,null,26,null,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC",223,72,223,72]
["C3E797A86AB0C7AC2810B51AB98F0B6F",0,null,"2016Y0012",-1,{"$nulls":75},"全线路基工程已完成；已完成全部614根钻孔桩；除邳城河桥梁板在预制安装，其余中小桥已基本完成，邳苍分洪道特大桥正在桥面系施工；路面水稳基层除少数路口已基本完成。下面层完成12.6万平方，占总量20%。","4D93664AE00000210AF21F9AA5BF0167"]
["A3E4462ABD868F5160FB3C456A438FB6",0,null,"2016Y0012",-1,13,{"$nulls":5},2,null,null,1,{"$nulls":65},"工程形象进度：本月实际完成：1.完成19#-20#、24#-27#墩6排立柱,累计完成12排立柱；2完成17#主墩承台、16#主墩墩身第一次浇筑；3.完成2#-5#、21#-22#墩盖梁，累计完成5排盖梁；4.完成18#过渡墩承台；5.完成14#墩桩基2根，累计完成54根（其中主墩桩基8根、过渡墩桩基4根、防撞墩桩基6根、引桥桩基36根）。主要存在问题：1.由于0#台、1#墩以及两处桥台路基连接线处均涉及蟹苗塘的原因，未能交付，软基处理无法进场施工，同时考虑到箱梁存放时间不能过长，间接制约25米小箱梁预制时间，计划延后。2.目前征地工作就全线（13.334公里）区政府派遣8个工作组至各个村部，据现场了解，由于历史遗留问题，本次工程征地属于第三次征地，前两次征地只赔付了青苗费，未对土地费等进行赔偿，因涉及进保问题，引桥部分尚有二分之一红线用地未交付，征迁进度正在推进中。","54E1D086000000211998911745B1249D"]
["038041785FB1AB4386B12CF50A1B38AA",0,null,"2016Y0012",-1,24,null,24,null,326350,280060,3,null,null,18,98,{"$nulls":3},22036,12,{"$nulls":3},9790,0,{"$nulls":3},12,96,{"$nulls":3},22,24,null,12,null,195810,154030,3,null,null,12,75,{"$nulls":3},11000,12,{"$nulls":3},9790,0,{"$nulls":3},12,96,{"$nulls":3},22,{"$nulls":15},"先导段累计完成路基土方填筑95%，底基层39%，基层6%，箱梁预制68%，盖梁台帽71%；盐邵河大桥主桥已完成。二期工程累计完成路基土方填筑18%，涵洞52%。","53AB6008E0000021100DBB3E8C074665",98,14,58,6,58,6,58,6]
["A8ABC38CF3C05604D1DE0978150CA2BE",0,null,"2016Y0012",-1,{"$nulls":75},"已建成","557C8DD6E00000217D3AADACA80D7899"]
["B4E1C2567B27E24BC98BB4F10B2E1A3C",0,null,"2016Y0012",-1,{"$nulls":75},"桩基全部完成，上部结构完成40%。","559646DC40000021D91FE0C7D4A2FAFC"]
["15EB2546C606493839F34F2DAD6AC3C7",0,null,"2016Y0012",-1,{"$nulls":75},"计划2017年开工，实际完成前期施工图设计","557C7C64200000214C8E399FBEB0A0F2"]
["C16F451EDFDBA511C2F839E146BB316E",0,null,"2016Y0012",-1,{"$nulls":75},"湖熟段7公里建成通车，上峰段进场施工","44F92AE9800000A15AC5660EDAD7D017"]
["810A1B23B021FF3AD8A472B289EC81DF",0,null,"2016Y0011",-1,{"$nulls":15},17,400,16,923000,490000,1274000,{"$nulls":4},95,{"$nulls":49},"该项目晶桥、白马段完成；晶桥至明觉段部分段落进行路面施工，桥梁进行上部结构施工，完成交安绿化招投标工作。","44F92AE780000001F6AE7427CA69104E"]
["D22241C960798DCC99A44644A7F38649",0,null,"2016Y0011",-1,{"$nulls":75},"路基土方已完成，桥梁桩基完成90%。","46A37B7E80000021FCCC83E6275E4C98"]
["8F8FC4D2341F5DE4AC978064E531B3FB",0,null,"2016Y0012",-1,{"$nulls":4},97300,97300,{"$nulls":13},97300,97300,{"$nulls":13},97300,97300,{"$nulls":13},97300,97300,{"$nulls":24},"计划内13.9公里县道已建成通车","59205C8DC00000217B31200C27110681",6,6,6,6,6,6,6,6]
["DC4CC4476293E142DF8F2116C2E45966",0,null,"2016Y0012",-1,{"$nulls":9},3,{"$nulls":14},3,{"$nulls":14},3,{"$nulls":14},3,{"$nulls":14},3,{"$nulls":5},"已完工","59206F98E0000001737FC531048C3591"]
["5D84030FCF742384EE6DFE074430F4D3",0,null,"2016Y0012",-1,19,null,19,null,34145,34145,{"$nulls":9},19,null,19,null,34145,34145,{"$nulls":9},19,null,19,null,34145,34145,{"$nulls":9},19,null,19,null,34145,34145,{"$nulls":24},"全部建成通车","5920762CA00000213BBF8D9CED8A5F5C",34145,34145,34145,34145,34145,34145,34145,34145]
["FE8A06F3F7DC02BC82F457632A270015",0,null,"2016Y0012",-1,{"$nulls":75},"全线基本完成路基工程及路面水稳结构层，沥青下面层、路缘石工程完成30%，桥梁工程基本完成合拢施工，下部结构基本完成、上部结构完成90%。","4D742EF9800000214C6FE56D1F577720"]
["12AAA4BF4D6813ABC2F7C46D525B86BC",0,null,"2016Y0012",-1,789,null,760,{"$nulls":12},789,null,760,{"$nulls":12},789,null,760,{"$nulls":12},789,null,760,{"$nulls":28},"59432ABE600000816087549245679FFF"]
["150CE3411E4CD5661C8F04BD2519F2AD",0,null,"2016Y0009",-1,{"$nulls":75},"已建成通车。","545AA9A8E00000014DC918C5BA78E533"]
["77DFFC5E1943783565B58842F55AD229",0,null,"2016Y0009",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成通车","44F92AE720000041FD47DFFCE454F006"]
["B29D9F1A58DC5F9968F96D304CA0C235",0,null,"2016Y0009",-1,{"$nulls":75},"尚未复工","53A7EFB8200000211B7FB59EEE89712A"]
["DD6F81451FCAAD8291A0AB0F71DDECC3",0,null,"2016Y0009",-1,null,16,null,59015,57067,55493,1,{"$nulls":3},7,{"$nulls":5},12,null,44261,42800,41619,1,{"$nulls":3},7,{"$nulls":49},"全长2.24公里，已完工1.67公里。","48110BD0800000016999F8D7C247DD09"]
["A1607675F5574B8329000E6406BC9BBC",0,null,"2016Y0009",-1,{"$nulls":75},"全线路基工程已完成；已完成全部614根钻孔桩；除邳城河桥梁板在预制安装，其余中小桥已基本完成，邳苍分洪道特大桥正在桥面系施工；路面水稳基层除少数路口已基本完成。下面层完成12.6万平方，占总量20%。","4D93664AE00000210AF21F9AA5BF0167"]
["312C66370AFA0B0104DC5D397E03107C",0,null,"2016Y0012",-1,{"$nulls":75},"完成桥梁下部结构95%。","494F9423E0000021971B8B67E472FD4B"]
["1D976D25818D71964B2419A7754F0EB8",0,null,"2016Y0012",-1,{"$nulls":75},"已完工","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["3F9EBE9039889364AD56D7F0227056DE",0,null,"2016Y0012",-1,{"$nulls":75},"PHC灌装沉桩累计完成1920根，盖梁累计完成130榀，钻孔灌注桩全部完成。1#、2#引桥空心板安装完成，3#引桥空心板累计完成410榀，引桥异形板全部完成安装。","5596C27040000021669AC2B2FA70EB78"]
["546350D1040C6950C4590852CB458672",0,null,"2016Y0012",-1,{"$nulls":75},"完工","57754DF5A0000021BE7E0BE71BC31123"]
["49D1FDBF1655D73C2912A875FEFFA581",0,null,"2016Y0005",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["09E1E9748EA6B79F55309747CAEF0B0F",0,null,"2016Y0005",-1,{"$nulls":75},"完成路面基层85%、面层80%。","48173F21C00000213849C18090E227D5"]
["508E56453833AC6299CFC123197C2FD7",0,null,"2016Y0005",-1,{"$nulls":75},"主体已完成，正在附属设施施工。","468F5198A0000021390EE49ABE0B2CD5"]
["8EF6CD918282C55C26E0FD2CAFF9E0F5",0,null,"2016Y0005",-1,{"$nulls":75},"目前省厅港口局已将使用岸线申请上报交通运输部审批。我局正在同步开展项目初步设计审查。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["875AA76CDC2536AAD029D931FC451132",0,null,"2016Y0005",-1,{"$nulls":75},"完成通道工程800米，为年度计划的67%","5460F4DA20000021E6011AA2335B9033"]
["0D093079061F538FFF2F2722436913E2",0,null,"2016Y0006",-1,96,null,96,{"$nulls":12},60,null,60,{"$nulls":12},17,null,17,{"$nulls":12},17,null,10,{"$nulls":27},"已建成通车50公里。","45AB8817400000218E63FD22BDA91CE1"]
["B02A0FC5DF66358522D0FA22BF336F16",0,null,"2016Y0006",-1,11,65,11,{"$nulls":3},2,{"$nulls":7},10640,6,43,6,192161,528105,629651,1,40,57,2,7,{"$nulls":3},-2119,null,13,{"$nulls":12},10640,{"$nulls":7},0,17,{"$nulls":22},"4D897AEAA00000212EF01FB341272DCF"]
["23B2F5FEF603A04713442D2330159D0C",0,null,"2016Y0006",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":4},26,30,26,137962,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC"]
["F4BD176E7444DEADFD4C34E9BABB9C57",0,null,"2016Y0006",-1,{"$nulls":75},"全线路基工程已完成；已完成全部614根钻孔桩；除邳城河桥梁板在预制安装，其余中小桥已基本完成，邳苍分洪道特大桥正在桥面系施工；路面水稳基层除少数路口已基本完成。下面层完成12.6万平方，占总量20%。","4D93664AE00000210AF21F9AA5BF0167"]
["5475906D2C470B68136D97B8DB2A5318",0,null,"2016Y0006",-1,{"$nulls":75},"项目占地250亩，已取得213亩土地，前期土建、钢结构安装已完成，水电安装完成55%工程量，自动化输送线设备安装完成37%工程量。","528B366AC0000021D4B356996DCCFFA8"]
["00F2DDAEC846A281172D10879699472C",0,null,"2016Y0006",-1,{"$nulls":75},"西斜坡堤工程6217米主体结构已基本完成，目前开展护面、挡浪墙施工等；西直立堤工程本月折合进尺294米，累计进尺1029米；西防波堤工程累计折合进尺7246米，占西防波堤总长9804米的74%。","46D12756A00000212A79E7CE74664FD9"]
["2BBE75413B644984E606A8CF5E92060C",0,null,"2016Y0006",-1,{"$nulls":75},"1#钢结构钢柱基本完成\n2#钢结构基本封顶","4FF7CAEF60000001B886392D3D7B79BC"]
["E6501A2E7465DCCC424C354AE562DE13",0,null,"2016Y0006",-1,{"$nulls":75},"已取得建设项目规划许可证，已完成施工图审查。招标公告已发，预计7月8日开标。","557C62C7E00000216B026DFC0627A4CE"]
["E3BB8FD8F71D557D8FF0CFE951D6F7D3",0,null,"2016Y0009",-1,{"$nulls":75},"工程完成了原大堤挖除和港池开挖，码头主体工程完成约80%，新大堤填筑完成约50%","54DC423000000021276B64BA6711F2E4"]
["8DCB17B7D43400466EE2A49E6B3C1C2D",0,null,"2016Y0010",-1,17,null,17,{"$nulls":12},0,null,0,{"$nulls":12},17,null,0,{"$nulls":12},0,null,0,{"$nulls":27},"B标段完成部分路基、涵洞工程。","45C531BE200000219CD9EF28C8D31E82"]
["9F9CBBE21CCAA9AC6FB8604359404195",0,null,"2016Y0010",-1,{"$nulls":75},"全线已通车。","4D7071D66000002165416ADF246EF2BE"]
["BDE5073C7656EC754BEC60ABD33B2777",0,null,"2016Y0012",-1,20,null,20,null,875827,2050000,13,null,null,5,82,2,{"$nulls":3},20,null,20,null,875827,2050000,13,null,null,5,82,2,{"$nulls":49},"463C0CE7E000002109BF6B9E92B4A55D"]
["54419703DA06865258EFECCE2B6D55D8",0,null,"2016Y0007",-1,{"$nulls":75},"水工主体结构完工","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["E7E85AABCD330B9F9E80A118A14CE3C0",0,null,"2016Y0007",-1,27,30,27,122766,613829,613829,2,null,null,22,{"$nulls":6},30,22,122766,521753,509478,2,null,null,22,{"$nulls":21},5,null,18415,52076,{"$nulls":26},"53A229B3C0000001BA18BC5DA5F2D176"]
["98E245DF10AFAEF1040CD946DFFF6D6A",0,null,"2016Y0007",-1,{"$nulls":75},"全线路基基本贯通，山场碎石土、小型构造物工程基本完成，完成石灰土填筑25%，级配碎石完成40%，桥梁下部结构90%，上部结构完成20%。","4D742EF9800000214C6FE56D1F577720"]
["218EE706173FA284940CEA3112176970",0,null,"2016Y0007",-1,{"$nulls":75},"2个泊位水工主体建成","4C2FCA8B60000021201D5B07BBD59C1F"]
["26373E0BAC6E0E1301CF4814B7B945D9",0,null,"2016Y0007",-1,{"$nulls":75},"中港大道以北段完成快慢车道沥青面层600米、水稳基层2公里，海堤公路桥完成桥梁下部结构100%、箱梁预制84%。","5451C27DE0000021B0ADD733CA89E359"]
["EAB74AFBDEE90AC7C13A4D2FF973CAF6",0,null,"2016Y0007",-1,{"$nulls":75},"桩基施工基本完成，正在进行桥梁下部结构施工。","51E88CC1C000000135D9837102FD2D41"]
["A3B9946715EAC222FE627AA567D18E5A",0,null,"2016Y0007",-1,{"$nulls":75},"项目建议书已批复，规划选址、环评等已批复，正在进行洪评报批工作，方案设计已报省厅待审。","51E8967480000021790847B05E2E0A04"]
["97E59E7AD0A45E157214F223313115A4",0,null,"2016Y0007",-1,null,16,null,59015,57067,55493,1,{"$nulls":3},7,{"$nulls":5},12,null,44261,42800,41619,1,{"$nulls":3},7,{"$nulls":49},"全长2.24公里，已完工1.67公里。","48110BD0800000016999F8D7C247DD09"]
["32C86DAA5E03351029CA2161727501AA",0,null,"2016Y0009",-1,{"$nulls":75},"工程复工，加快水工主体施工","46D11F4F40000021C374A969A3743C9A"]
["18CCC367393DECDB368E679C5234F128",0,null,"2016Y0008",-1,{"$nulls":15},15,225,null,500100,null,null,9,100,100,5,60,{"$nulls":3},13828,{"$nulls":46},"452C38D5A00000A1C369596A7753C333"]
["7EA8E2DBE79F95CF7F7DD97DDC7DD1CC",0,null,"2016Y0008",-1,17,null,17,{"$nulls":12},0,null,0,{"$nulls":12},17,null,0,{"$nulls":12},0,null,0,{"$nulls":27},"B标段已招标，施工单位已进场施工。","45C531BE200000219CD9EF28C8D31E82"]
["DEE7277CE62DA56D6C001791A7726D54",0,null,"2016Y0008",-1,25,190,25,{"$nulls":3},8,null,null,9,73,{"$nulls":3},22233,25,190,{"$nulls":4},8,100,100,9,73,{"$nulls":3},10000,null,1,25,{"$nulls":3},1,{"$nulls":3},1,{"$nulls":3},22233,null,1,{"$nulls":4},1,{"$nulls":3},1,{"$nulls":3},10000,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["3CEBD3ABAB5349BBEF4DFC2A13155F00",0,null,"2016Y0008",-1,{"$nulls":75},"全线路面已实现贯通，跨连徐高速主线桥主体工程已完成。","44F92AE7E000004126A44C796491035A"]
["4BA7862168962A4F7B8BFD8E3BA92D4F",0,null,"2016Y0008",-1,{"$nulls":75},"正在进行上部结构、堆场和球形仓施工","452C38DC80000001ADB05FB1C69E6A31"]
["537649B177DD6F07FD67AC31677BFA54",0,null,"2016Y0008",-1,{"$nulls":75},"开始后期导堤施工","46412B4EE000002160BA115A2334239C"]
["558506258815FE18875C11D5ABB9C7FF",0,null,"2016Y0008",-1,{"$nulls":75},"已建成通车","452C38D8A0000041215774BA7CEB1CEE"]
["1839691E09894C5ECAB9E3E3A0120FCF",0,null,"2016Y0008",-1,{"$nulls":75},"完成辅建区工程建设并完成交工验收，物流园南停车场智能化安装并投入运营，完成物流园北停车场工程建设。","468F5198A0000021390EE49ABE0B2CD5"]
["581BA59F6ED6342B6429D2223A6263A1",0,null,"2016Y0005",-1,{"$nulls":75},"淮阴区段已建成；涟水段路基已完成，正在进行路面底基层施工。","4D989A7680000021CAE7FBD451FCC003"]
["D2EF0C9E2B38AF88C25AF292429A348E",0,null,"2016Y0005",-1,{"$nulls":75},"路基施工已完成.","545A9D02E0000021DDCE427712FDA0AC"]
["E35C2BAC1BF9A283A47D438EEFDE7F4D",0,null,"2016Y0005",-1,{"$nulls":75},"S337湖熟段目前全线清表已完成，正在进行部分路段路基平铺工程。","44F92AE9800000A15AC5660EDAD7D017"]
["A3AA3BC32A22E1D1B9C094D91278A152",0,null,"2016Y0008",-1,{"$nulls":75},"亭湖段基本完成项目部及监理部的组建工作，完成房屋拆除工作、征地工作。大丰段基本完成征拆工作，完成土方开挖85%，路基回填12%，涵洞16%。","53A68FC1C0000021651B0CEA5D438D57"]
["324CDA45174BF68EE6C29AF6766557E5",0,null,"2016Y0008",-1,{"$nulls":75},"草庙以东段13km已完成路基挖方100%，路基回填99.06%，混凝土挡墙100%，箱涵100%，桥梁99.18%；草庙至沿海高速段已完成项目部组建工作，征地拆迁基本结束。","53A6915A00000021AD1AD66B463B498A"]
["216B69DD1F8426F40080CC08497AE633",0,null,"2016Y0008",-1,25,140,27,1336352,836248,1317741,23,null,null,28,21,{"$nulls":3},22684,25,140,27,1336352,836248,1317741,23,100,100,28,21,2,null,510,22684,0,5,2,null,null,300118,{"$nulls":10},5,2,null,null,300118,{"$nulls":25},"45886E536000002100B27DDCDF662D01"]
["E6743BA0D09A59955AD5C5AA5D3E1250",0,null,"2016Y0008",-1,{"$nulls":75},"路基施工，黄南小桥两侧沥青路面摊铺。8月完成投资200万元，累计完成投资1492万元。","50A30D9880000021822D064F6E714B8D"]
["C500DE5D04B7F1649A4C09B7D83ACEA7",0,null,"2016Y0008",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":4},26,30,26,137962,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC"]
["99CD6E5A057ADEC673803E9FF87FE7B4",0,null,"2016Y0008",-1,27,30,27,122766,613829,613829,2,null,null,22,{"$nulls":6},30,22,122766,521753,509478,2,null,null,22,{"$nulls":21},5,null,18415,52076,{"$nulls":26},"53A229B3C0000001BA18BC5DA5F2D176"]
["DAC6A72C76446E635118B53F9EA5088E",0,null,"2016Y0008",-1,{"$nulls":75},"码头沉桩48根；17根灌注桩全部浇筑完成；预制纵梁459件；预制面板81件；现浇下横梁4榀；后方堆场开沟降水。6台门机抓紧制造中。","52A51020400000219F26349145A4F022"]
["75AA4A3F55CCE248C752216069FA02D6",0,null,"2016Y0008",-1,{"$nulls":75},"正在进行上部结构、堆场和球形仓施工","52A51FB6400000217BBD3E37D9F8ED17"]
["627B96AEEDF8FADA9EF06376F51C74C1",0,null,"2016Y0007",-1,{"$nulls":75},"无","56BF67C9E0000021BC1B2AEA0891915D"]
["557E9796451316BD1ABBECA1DBBA1689",0,null,"2016Y0008",-1,{"$nulls":75},"无","56BF67C9E0000021BC1B2AEA0891915D"]
["EE1149FE264AC48692B99E285D95E43C",0,null,"2016Y0008",-1,{"$nulls":75},"除LM1标高架下地面道路沥青延期施工， A7标黄巢浜、西八荡尾留段外，其余部分完工","46EA9C3D40000021E09CDF7BE3DADF50"]
["155D5F9795077C20D9B7322F816B421F",0,null,"2016Y0005",-1,13,null,13,{"$nulls":12},8,null,0,{"$nulls":12},13,null,13,{"$nulls":12},7,null,0,{"$nulls":28},"5290FF2D800000218EE2D98EEC67211F"]
["DBEF9F23A8A90DD70EF46738577366B2",0,null,"2016Y0008",-1,{"$nulls":15},22,313,14,587181,531255,338661,2,100,100,11,79,{"$nulls":49},"20.6公里下面层结束，已完成上面层约20%；交安及附属工程完工；绿化完成90%。","45A64AD8E000002115357ED0397AE2AC"]
["8D31118DFCAB7BEA79A173341174BA63",0,null,"2016Y0008",-1,{"$nulls":75},"实施项目灰土水稳施工、沥青砼铺设及绿化栽植。","4A7F4412C0000001B5349862C0B620EE"]
["1BFEC75BE25C60319EC655C7ADC37CE9",0,null,"2016Y0008",-1,{"$nulls":75},"全线路基基本贯通，山场碎石土、小型构造物工程基本完成，完成石灰土填筑、级配碎石40%，桥梁下部结构基本完成，上部结构完成35%。","4D742EF9800000214C6FE56D1F577720"]
["3403B8A88002ADB813E34143E71CA1DC",0,null,"2016Y0008",-1,{"$nulls":75},"全线征地拆迁基本完成，路基工程完成95%，中小桥涵完成70%，大桥完成下部结构，路面底基层、基层完成8公里，沥青路面完成3.5公里。","4D743B53C0000021D528DB4DEF96D439"]
["3817D3B8C9B062DC8C94551A181C3D75",0,null,"2016Y0008",-1,{"$nulls":75},"尚未复工","53A7EFB8200000211B7FB59EEE89712A"]
["0634DF56D547D38AB04DAAB618645B55",0,null,"2016Y0008",-1,{"$nulls":75},"桩基施工完成80%。","51D1D49260000021FCEEDB7A127D7731"]
["84D29D05314136688DFFE964CCE426C0",0,null,"2016Y0008",-1,{"$nulls":75},"桩基施工已完成，正在进行桥梁下部构造和接线路基施工。","51E882EC80000021B9C40721EDEC0F47"]
["A838C801AA1338FC0BA85FC034D188C8",0,null,"2016Y0008",-1,{"$nulls":75},"宁连路至月季路段2.5公里已完成，月季路至飞耀路段已建成。","545A7B4F20000021344738A715E00356"]
["E02C932CD4641C27D2A47A58A58CFD48",0,null,"2016Y0008",-1,{"$nulls":75},"已建成通车。","545AA9A8E00000014DC918C5BA78E533"]
["27C8168E81EB28C61DD2517A2F948631",0,null,"2016Y0008",-1,{"$nulls":75},"亭湖西城桥桥梁施工已完成，正进行接线施工。","458CAF86E00000216E3944578E65ACF2"]
["FD3CFA70866834B404C112D053CC9FAE",0,null,"2016Y0006",-1,13,null,13,{"$nulls":12},9,null,0,{"$nulls":12},13,null,13,{"$nulls":12},8,null,0,{"$nulls":28},"5290FF2D800000218EE2D98EEC67211F"]
["91258A15DAAB6E75F6D11DBC409B938D",0,null,"2016Y0008",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["E73B38C02ACB18B2B3F87093D4428182",0,null,"2016Y0008",-1,{"$nulls":75},"完成小箱梁湿接缝；完成小箱梁中、端横梁；完成小箱梁护栏；完成60m护栏；完成拼宽段8%灰土1000方,累计完成94%。\n","4B2547D8C0000021EA2F1D310FA63F35"]
["E4528197234C1B876951B288C54AD4BD",0,null,"2016Y0008",-1,{"$nulls":75},"    建元路至太东公路完工，太东公路至朗力福大道前期工作。","4A0435E7A0000021E23AE18A8582F231"]
["DBE33144B53C877DF387FB47581DB830",0,null,"2016Y0008",-1,{"$nulls":75},"施工、监理单位已进场，结合围填开展疏浚。","452C38DAC0000021F1078262468FCCED"]
["5D87BB5D46E7FD50ED8AEE194EFDDE58",0,null,"2016Y0008",-1,{"$nulls":75},"完成设备安装","4B96568F00000021E184EC6C9CE9F9DC"]
["823E384C470F278979FFBCD65B9E1461",0,null,"2016Y0008",-1,{"$nulls":75},"本月累计完成疏浚1960万方","4ED76E5EA0000021C2FF39A1BE0258B9"]
["554C18E5AE09E6FAAE728BDD9EDAB3A7",0,null,"2016Y0008",-1,{"$nulls":75},"已完成安评、环评、用海、通航、工可报告，获安全审查意见、通航批文、岸线批文，环评已召开专家评审会，用海申请正在办理。勘察和初步设计已完成招标，正在编制初步设计文件。","5596AF04200000010063731208F43EE3"]
["8950754C6814EE29A08B1BAD4D45FA02",0,null,"2016Y0011",-1,{"$nulls":75},"已建成通车。","50A749104000002111B1BD6A84FDACB7"]
["2452E481206C71D2A9EE6C936FB68AEA",0,null,"2016Y0012",-1,{"$nulls":4},168775,323272,{"$nulls":4},38,{"$nulls":64},"完成征地拆迁，正在进行驻地建设和临时工程。","45A780AFA00000214071DBBE24F820C4",51]
["1528189D7E5FDE57B023B3C625A338A9",0,null,"2016Y0011",-1,{"$nulls":75},"桩基、下部结构、箱梁预制已完成。","51D1B60C60000021547E4A7724FD4535"]
["1DC2F033CF9A640F2C8BBD6A82706A8F",0,null,"2016Y0012",-1,{"$nulls":75},"具备施工条件段落大部已进入96-3施工，开始96顶及路面基层施工准备以及进行老路便道施工；已完成苗成河大桥48根桩基施工；已完成丰徐河中桥及复新河大桥桥面施工。","4D935F2340000021767F74AFEF8958B9"]
["9552C779AB38410CCC9116F782ABFEFD",0,null,"2016Y0012",-1,{"$nulls":75},"主体建成。","45830701A00000018662A81FE3FB2B60"]
["0BFBF9E9CFF57B8A921F9DB13EC94EC1",0,null,"2016Y0012",-1,{"$nulls":19},136000,{"$nulls":55},"该项目睢宁段已完成路基挖方160万方，占总量的100%，已完成路基填方158万方，占总量的70%；桥涵构造物施工已完成全部桩基216根，预制梁板199片，徐洪河大桥开始0号台帽施工。西段完成底基层7.4万方，路面基层6.2万方。","53ACAFBC8000002136D28ECA19D46BF2",null,null,158,160]
["C6ABC78C597DEE4948DDC49DBE8B4211",0,null,"2016Y0012",-1,{"$nulls":75},"正在进行桥梁上部结构施工。","51E88CC1C000000135D9837102FD2D41"]
["22C15E15EED4E5975E41C0A61FD3A529",0,null,"2016Y0012",-1,{"$nulls":75},"完成部分桩基施工。","51E89D06C0000021C5C64F5378EC545C"]
["CEA13AA19DA7A61E8A81A36D285F2B06",0,null,"2016Y0012",-1,9,null,14,null,100545,154638,1,{"$nulls":3},40,{"$nulls":3},1622,2,null,6,null,null,24271,{"$nulls":4},13,{"$nulls":6},4,null,null,1836,{"$nulls":11},4,null,null,1836,{"$nulls":24},"盱张线改造段进场施工。","4582F984A00000210B371656660E7377",28,4,5,2]
["C116E57ABC7CF200596B3B5297FCBB05",0,null,"2016Y0012",-1,{"$nulls":75},"已开工建设。","57551EAC40000021F51AC305BFD1948C"]
["72F890C1A76BEF9AD57FB3D38CAF8844",0,null,"2016Y0012",-1,16,null,19,null,104,153,4,null,null,6,31,0,0,null,2142,16,null,19,null,72,145,4,null,null,6,29,0,0,null,2142,6,{"$nulls":4},145,3,null,null,2,8,{"$nulls":4},6,{"$nulls":4},145,3,null,null,2,8,{"$nulls":19},"全部结束。","45835A3940000021498FFD174D21DCE8",null,133,null,127]
["F07FD448D75986D2BD0F14747E765A13",0,null,"2016Y0012",-1,11,null,11,null,528105,629651,2,null,null,4,11,{"$nulls":3},10640,6,null,6,null,528105,629651,1,null,null,3,8,{"$nulls":3},-2119,{"$nulls":9},1,1,{"$nulls":13},1,1,{"$nulls":20},"4D897AEAA00000212EF01FB341272DCF",65,null,45,null,13,null,13]
["C1C5AF72E562E0DE1F71A4FF2D4C952F",0,null,"2016Y0012",-1,{"$nulls":75},"  件杂区1#仓库和2#仓库完工","46D11E59C00000215FEEE684519DC4AA"]
["F589670B9AC76B414E756504A96D87BE",0,null,"2016Y0012",-1,{"$nulls":75},"年内未开工","46D11F4F40000021C374A969A3743C9A"]
["A4CA402746D4C696105BBDDD297CBA54",0,null,"2016Y0012",-1,{"$nulls":75},"   一期（起步）工程（不含液化泊位和陆域罐区）于8月17日通过市港口局组织的竣工验收；消防泵房成套设备采购与安装工程于9月2日通过交工验收","46D12095E00000210EEE5BA374F2A089"]
["C78A8AFD9A82D583F900DE9F4A8D6C70",0,null,"2016Y0012",-1,{"$nulls":75},"本年度补报从9月份开始，总计1.2个亿的陆域建设工程投资","591F72AA000000219A8E690F13B0B4C3"]
["AB107366951DE935DB36517F11A0BF9B",0,null,"2016Y0012",-1,13,null,14,null,417476,397189,340724,{"$nulls":8},11,null,11,null,347476,300120,279393,{"$nulls":3},95,{"$nulls":4},3,null,14,null,90000,117069,81331,{"$nulls":8},1,null,11,null,20000,20000,20000,{"$nulls":23},"省道341主体工程已完成","44F92AE780000001F6AE7427CA69104E",138,52,128,52,3,null,20]
["89889496D1B131D51A6D4B7BB70F1713",0,null,"2016Y0012",-1,{"$nulls":75},"建成通车","46EA9C3D40000021E09CDF7BE3DADF50"]
["9DE7C143107CF24C7D3D471D5F09B33F",0,null,"2016Y0012",-1,{"$nulls":75},"已建成","557C90AF00000021D97DFED87AEB9B2C"]
["3DF3669C20FE6CB76D6245157DB82081",0,null,"2016Y0012",-1,{"$nulls":5},28860,{"$nulls":14},28860,{"$nulls":14},28860,{"$nulls":14},28860,{"$nulls":25},"5920BDC200000021CF0823D9EACD5463"]
["3181190D8421AC3F02E739E7F408888F",0,null,"2016Y0012",-1,{"$nulls":75},"完成二桥以南31+919~35+575段三层底基层灰土压实及水稳摊铺\n完成二桥以北17+550~30+000段两层6%灰土压实，及第三层素土翻耕。","559630E8000000218266B78BE3987C8D"]
["095CC0B0C387C68D03B2AD5519333EF8",0,null,"2016Y0012",-1,14,null,14,null,82913,82913,{"$nulls":9},14,null,14,null,82913,82913,{"$nulls":9},14,null,14,null,82913,82913,{"$nulls":9},14,null,14,null,82913,82913,{"$nulls":24},"2016农村公路提档升级乡道13.728公里，已全部完工。","59203D84C00000216A14D8224AEDDBAF",6,6,6,6,6,6,6,6]
["BCBD63BF822BB429F4CD2B42B477F9CD",0,null,"2016Y0012",-1,{"$nulls":75},"2016年开工，实是际完成站务用房主体结构，场地是路面水泥稳定碎石","557C7951A00000215F589848C0B544F0"]
["08A97F97F5BC8D4E0C939C19A7FDD0CE",0,null,"2016Y0012",-1,9,null,9,null,20881,20881,{"$nulls":9},9,null,9,null,20881,20881,{"$nulls":9},9,null,9,null,20881,20881,{"$nulls":9},9,null,9,null,20881,20881,{"$nulls":24},"已完农村公路9公里","592080D0C00000218EC7DBD8A6CB61C3",2,2,2,2,2,2,2,2]
["D8AAB8CCD000D3BD3AADE81E7DCF8737",0,null,"2016Y0012",-1,{"$nulls":75},"计划2017年开工，实际完成规划选址意见，项目建议书批复，无前期费用","557C7F6F00000021B837F5D0A7918B1C"]
["61803D80F0AF0BEBDFA56C3745A7F2C2",0,null,"2016Y0012",-1,87,null,87,null,522000,522000,{"$nulls":9},87,null,87,null,522000,522000,{"$nulls":9},87,null,87,null,522000,522000,{"$nulls":9},87,null,87,null,522000,522000,{"$nulls":24},"已完工建成通车","5920B8E0400000214F3328589853B90F",10,null,10,null,10,null,10]
["1E0C993B4059C91A10353AB8653C7861",0,null,"2016Y0012",-1,27,null,27,null,104066,193846,{"$nulls":9},23,null,16,null,77587,131718,{"$nulls":9},27,null,27,null,104066,191392,{"$nulls":9},23,null,16,null,77587,131718,{"$nulls":24},"已完工","59206D80C0000021049D727E4586E441",22,17,20,17,22,17,20,17]
["BDCD1AFE28EA64CB8BD67C3F404DE3E9",0,null,"2016Y0008",-1,13,null,13,{"$nulls":12},13,null,0,{"$nulls":12},13,null,13,{"$nulls":12},12,null,0,{"$nulls":28},"5290FF2D800000218EE2D98EEC67211F"]
["62D3A4C2D2F771A469E6B651FDDA9184",0,null,"2016Y0008",-1,{"$nulls":75},"目前已经建成22.8公里，纵三至纵五段正在推进前期工作。","452C38DA80000041BB1AF46EF3FAECC2"]
["AE6274C0736C2171ECACF3C2A1324C36",0,null,"2016Y0008",-1,{"$nulls":75},"主体建成，投入运营。","452C38D9200000A160383FB696401BD8"]
["70B530C5D63A0B423EFF2C631725A090",0,null,"2016Y0008",-1,{"$nulls":75},"    华元路到朝阳河桥南主车道贯通进入慢车道施工，其余段落完工。","4A04D699C0000021960B6C19775B7500"]
["A377E7684640AE7F073B026BCCDEEFFB",0,null,"2016Y0008",-1,{"$nulls":75},"完成丰黄路以东管线迁改及征迁工作，已完成填挖土方36万方，占总量24%；苗成河大桥因汛期上游放水停工；已完成丰徐河中桥及复新河大桥桥面施工。","4D935F2340000021767F74AFEF8958B9"]
["96B03E0BC55AC97F03B4A1DF537EC79B",0,null,"2016Y0008",-1,{"$nulls":75},"该项目已缴纳剩余土地款并进行招投标程序，预计8月底开工建设。","4D93720CA0000021255B319F74F769D3"]
["7F5587061EED4BF45F4812EAEBB9CA11",0,null,"2016Y0008",-1,{"$nulls":75},"开展港池疏浚","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["AA1AAEE13C851E87753A8189B9553302",0,null,"2016Y0008",-1,{"$nulls":75},"该项目正在进行前期工作。","53ACBF2A800000214F643D4640E1B023"]
["2598FB7FF088D1163A56E722E37E7903",0,null,"2016Y0008",-1,{"$nulls":75},"码头水工主体已完工","44F92AE8C0000061CA99E73B5A18BBB6"]
["7F7639041AA7B343893AF4283C474D5A",0,null,"2016Y0008",-1,{"$nulls":75},"已完工","5460F4DA20000021E6011AA2335B9033"]
["CAFA2F8487416C8E4BBABE2C5DF66DD8",0,null,"2016Y0008",-1,{"$nulls":75},"DZL-SG2标段主体工程4100米已基本完成，东八字口门本月完成进尺336米，东直立堤累计完成进尺4436米，占东直立堤总长4674米的95%。","452C38D9600000015B091B22A009EB3A"]
["0938297E1BA5150791BF81EDD8D46EEF",0,null,"2016Y0008",-1,{"$nulls":75},"水工主体建成","4C2FB609C0000021E347BA6BB8D8C1EF"]
["5EB023F45DB0F12CCE1662746DD242E7",0,null,"2016Y0007",-1,{"$nulls":76},"4C72C2C7E000002123C959BEE8D1748B"]
["BD95FD09AFEE2E90D2723F7AA9BAD1E7",0,null,"2016Y0009",-1,{"$nulls":15},22,313,14,587181,531255,338661,2,100,100,11,79,{"$nulls":49},"20.6公里下面层结束，已完成上面层约20%；交安及附属工程完工；绿化完成90%。","45A64AD8E000002115357ED0397AE2AC"]
["FBB59D64A46EE5E938ACB7D09C803E06",0,null,"2016Y0009",-1,{"$nulls":15},15,225,null,500100,null,null,9,100,100,5,60,{"$nulls":3},13828,{"$nulls":46},"452C38D5A00000A1C369596A7753C333"]
["8212F2E46C29F78C5F1044BDD83E754F",0,null,"2015Y0002",-1,{"$nulls":75},"沭阳百盟物流产业园项目位于沭阳县南部新城宿沭一级路与上海路交汇处，项目规划总占地面积605.05亩。其中一期占地264亩，于2012年5月8日正式开工建设，规划新建一栋2层的汽修中心5706平方米，两栋6层的司机之家16898平方米，信心交易中心40370平方米、专线物流配送中心12312平方米、零担中心25644平方米、总部经济楼及招商楼11984平方米，仓储中心15700平方米，地下水泵房340平方米等共计13.02万平方米。截止到2015年2月底，项目零担快运中心、信息交易中心、专线物流区、招商楼、总部经济楼已全部建成投入运营。8栋钢结构附属配套仓储中心已竣工，全面招商。项目北侧65亩停车场场地正在进行场地平整工作，同步建设门卫及维护工程。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t","57459BD0E0000021461905DF0BA4CD1E"]
["FC71132A1F744321B3EE24A75F04D869",0,null,"2016Y0010",-1,{"$nulls":75},"建成通车。","4756E0D780000021BD984AD195D60C8A"]
["9CEAD64C96FA2B3396C0E58BDCDEC8B0",0,null,"2016Y0010",-1,{"$nulls":75},"建湖G204至建宝线段19.64km建成通车。建湖234省道至331省道段21.2km全线各标段征地拆迁已全部完成，土方开挖100%，路基回填94%，涵洞100%，桥梁90%。建湖G204以东段征地拆迁基本完成。射阳段8.881km已基本完成征地工作，路基完成92%，桥梁完成94%,中小桥全部完成，大桥完成95.7%。","459307CF60000021FC7F08A5CEC30386"]
["9B40834BCCF77016B54054AD25B0A421",0,null,"2016Y0010",-1,{"$nulls":75},"已于2013年建成通车","4D75CB95E0000021F0C08F4C2B0DAD01"]
["033A8917F2167B2022C367CA365C0046",0,null,"2016Y0010",-1,{"$nulls":75},"一期工程G204以西段25.96公里建成通车。二期工程G204以东段已完成施工图审查，今年实施新204国道至老204国道段6.027公里，当前已完成监理招标和征地拆迁调查工作，正在进行青苗补偿工作，项目部及监理组的组建工作已经完成。","45930AC0A00000013A88F40431F8C61A"]
["2ABF32520CDBA06AD23A84E4C7B89408",0,null,"2016Y0010",-1,null,16,null,59015,57067,55493,1,{"$nulls":3},7,{"$nulls":5},12,null,44261,42800,41619,1,{"$nulls":3},7,{"$nulls":49},"全长2.24公里，已完工1.67公里，剩余路段正在进行打桩。","48110BD0800000016999F8D7C247DD09"]
["68E4295BCF8F501E126B4E473EB6A960",0,null,"2016Y0010",-1,{"$nulls":75},"编制招标文件，准备招标","44F92AE7400000013A0A1F9A656A1EA4"]
["41FAD5BF09B21DE03EFFBA8D4738227F",0,null,"2016Y0010",-1,{"$nulls":75},"已完成安评、环评、用海、通航、工可报告，获安全审查意见、通航批文、岸线批文，环评已召开专家评审会，用海申请正在办理。勘察和初步设计已完成招标，正在编制初步设计文件。","5596AF04200000010063731208F43EE3"]
["8D757FF12214A6E7E4366C5A2D51C1A5",0,null,"2016Y0010",-1,{"$nulls":75},"水上沉桩PHC管桩累计完成1095根,抛填袋装砂已全部完成，盖梁累计完成116榀，钻孔灌注桩累计完成45根，1#引桥空心板安装495榀，引桥异形板累计完成75榀，内档码头靠船构建累计完成14榀。","5596C27040000021669AC2B2FA70EB78"]
["F6A2F5243A958A304597E165E4058005",0,null,"2016Y0010",-1,{"$nulls":75},"项目已建成完工。","531CA9B120000021BEA7261286438186"]
["73845CE55E28A2F4270285461D7383B6",0,null,"2016Y0010",-1,{"$nulls":75},"项目占地250亩，已取得213亩土地，前期土建、钢结构安装已完成，水电安装已完成，自动化输送线设备安装完成75%工程量。","528B366AC0000021D4B356996DCCFFA8"]
["8515FD354140889C9DC89C0886F2F147",0,null,"2016Y0010",-1,{"$nulls":15},17,400,16,923000,490000,1274000,{"$nulls":4},95,{"$nulls":49},"该项目晶桥、白马段完成；晶桥至明觉段部分段落进行路面施工，桥梁进行上部结构施工，完成交安绿化招投标工作。","44F92AE780000001F6AE7427CA69104E"]
["A79C8D2FB4157E1506228685A960E9A8",0,null,"2016Y0010",-1,{"$nulls":15},0,129,0,null,null,0,0,{"$nulls":3},38,{"$nulls":49},"公路段已完成，市政段正在进行路基施工、征地拆迁工作。","45A630DD40000021758080AC865FC45B"]
["56CBB2A25873F67DE7EDDDD675C85B78",0,null,"2016Y0010",-1,{"$nulls":75},"项目完成主体工程95%","557C8096A0000021B39AE5B8E89B9A84"]
["1DAED203D04AE1561028E032E9F54C9C",0,null,"2016Y0010",-1,6,30,3,153018,143500,670147,1,100,100,1,23,{"$nulls":5},5,{"$nulls":14},30,{"$nulls":5},30,60,null,13,{"$nulls":5},5,{"$nulls":29},"4640B199A0000021EB976A9433EF07F4"]
["DEBE2C9179261B1061EA5B2D4C9F5559",0,null,"2016Y0006",-1,66,null,66,{"$nulls":12},30,null,20,{"$nulls":12},0,null,16,{"$nulls":12},0,null,6,{"$nulls":27},"已交工验收20.6公里。","45C5231CE0000021BC17A82CFFD70F54"]
["11C6EA7939E645EC11FE3A7069A37266",0,null,"2016Y0006",-1,43,560,43,1050730,2101463,1929915,3,100,100,9,115,{"$nulls":3},21580,5,292,5,105014,111070,113964,1,null,60,null,66,{"$nulls":3},10700,null,200,null,342098,684197,314172,null,50,50,9,40,{"$nulls":3},8000,null,92,{"$nulls":6},10,null,20,{"$nulls":3},3200,{"$nulls":15},"一、工程形象进度：先导段（4.6公里）于2013年9月建成通车。现正进行江宁段(16.534公里）和溧水段（8.135公里）路基清表、河塘清淤、软基处理、路基填挖方、非矛盾段小型结构物以及桥梁桩基础和梁板预制施工等工作。路基挖方88.8665万方（37.02%），填方116.0514万方（36.25%）；路面底基层12%灰土2.1万方（9.99%）；基层水泥稳定碎石11.304万平方米（5.38%）；沥青面层21.6831万平方米（11.24%）；桥梁完成投资2443.3万（13.88%）；绿化完成投资300万（11.96%）；交安完成投资281万（6.58%）。\n二、存在问题：1、横溪段剩余15户房屋未拆迁，670米土地未交付，杆线迁移进度特别缓慢；2、溧水段联民社区东满园林150米苗圃，红星社区苗圃3.5亩、土地1.8亩尚未交付，影响长度约120米，路基无法贯通。","452C38DB00000021D4253F83097D6579"]
["1AAF2576A86F5C1ACD74E790DEED0528",0,null,"2016Y0006",-1,25,140,27,1336352,836248,1317741,23,null,null,28,21,{"$nulls":3},22684,25,140,25,1336352,836248,1317741,23,100,100,28,21,2,null,510,22684,0,5,2,null,null,300118,{"$nulls":10},5,{"$nulls":3},300118,{"$nulls":25},"45886E536000002100B27DDCDF662D01"]
["18ABA65AA0A29CFE6DE943B7D5FAFBC3",0,null,"2016Y0006",-1,{"$nulls":15},3,46,4,150320,209847,568814,2,100,100,2,14,{"$nulls":3},13150,{"$nulls":45},"全线已通车。","4D70707C00000001E077DAB59B768AFF"]
["D5309F55A7C8403B4784AC83480E323D",0,null,"2016Y0006",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6489,6,144,2,268220,300305,282439,null,92,100,3,11,{"$nulls":3},6489,2,10,6,76634,93428,200846,1,10,0,2,0,{"$nulls":3},5848,null,7,null,71160,60061,169464,null,2,0,1,0,{"$nulls":3},5839,{"$nulls":15},"1-5标已完成。","464AEA1FC0000021B52E367C631B2D38"]
["072654A68FD569AD2AA7E5466E0B427F",0,null,"2016Y0006",-1,47,38,47,218574,1036343,1003990,3,null,null,50,151,{"$nulls":65},"53A2269420000021B4EDBBA7A0728BF8"]
["5A3AB62A092CC2AE5F9F4FBBFBE9BB88",0,null,"2016Y0006",-1,{"$nulls":75},"进行路基施工，黄南小桥桥面铺装及护栏施工。本月完成投资90万元，共完成投资1092万元。","50A30D9880000021822D064F6E714B8D"]
["ACFF7582B0CF9B6CDFBD110CCCD4C93B",0,null,"2016Y0006",-1,6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":4},6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":50},"4D6F1C538000000151F6EA761DDE2303"]
["0BBE5202B4A1CBF61A23992A87672C30",0,null,"2016Y0006",-1,{"$nulls":75},"完成丰黄路以东管线迁改及征迁工作，已完成填挖土方27万方，占总量20%；苗成河大桥正在进行桩基施工，已完成43根，剩余5根；已完成丰徐河中桥及复新河大桥桥面施工。","4D935F2340000021767F74AFEF8958B9"]
["F89B8E9B0F343831154E847B3234BD50",0,null,"2016Y0006",-1,{"$nulls":75},"已基本完成全线桥涵构造物施工；已完成路基填方80.4万方，占总量86%，已完成全部挖方24万；路面底基层已完成32.2万平方，占总量64%，完成基层30.2万平方，占总量64%。开始进行面层试验段施工。\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t\n\t\t\t\t\t\t\t","53ACA437E00000213FD16E4DA5646D14"]
["865C507FA03E34F810ADD0648DE87052",0,null,"2016Y0006",-1,{"$nulls":75},"草庙以东段13km已完成路基挖方100%，路基回填78.08%，混凝土挡墙100%，箱涵100%，桥梁98.62%；草庙至沿海高速段已完成招标工作，确定施工单位，开始启动征地拆迁。","53A6915A00000021AD1AD66B463B498A"]
["F3F2F9245BACEDD0DD8A997BCA1A75D4",0,null,"2016Y0006",-1,{"$nulls":75},"建湖G204至建宝线段19.64km建成通车。建湖234省道至331省道段21.2km全线各标段征地拆迁已全部完成，土方开挖100%，路基回填46%，涵洞100%，桥梁66%。建湖G204以东段正在进行征地拆迁，已完成工作量的60%；正在进行项目部组件工作。射阳段8.881km已基本完成征地工作，土方开挖全部完成；PC管桩已完成76%，涵洞完成97%，路基完成68%，桥梁完成81.6%。","459307CF60000021FC7F08A5CEC30386"]
["D54EAF48646CF3160B540FA44B4DFA86",0,null,"2016Y0006",-1,{"$nulls":75},"该项目正在进行前期工作。","53ACB85FC00000013E93FD3AD08F08F0"]
["6B481E93617F6466712973A9A007A021",0,null,"2016Y0004",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"墟沟互通全面建成通车，隧道右线建成通车，隧道左线全线贯通。","44F92AE720000041FD47DFFCE454F006"]
["E395EA30B4B1DAB240CFD4383C98E947",0,null,"2016Y0006",-1,{"$nulls":75},"建成通榆河大桥、射阳河大桥和先导段3.1公里，其余路段完成路基填筑80%、路面基层30%、面层18%、桥梁工程70%。","4E39B2EA40000021C40EAD1C3B2CA5F0"]
["758E597B3D690D81574A56EA1C9EC8E5",0,null,"2016Y0006",-1,{"$nulls":75},"南环段已建成，上跨长深高速公路大桥已完成，西延段招标工作已结束，正在落实征地拆迁工作。","4D746069A0000021424848A8623D4A12"]
["8F27F78937AC26248035329A1FF17608",0,null,"2016Y0006",-1,{"$nulls":75},"中港大道以北段完成路面基层100%、面层25%，海堤公路桥完成桥梁下部结构60%、箱梁预制80%。","5451C27DE0000021B0ADD733CA89E359"]
["E08686A9AE1ED61A0361770D6D3807B0",0,null,"2016Y0006",-1,{"$nulls":75},"目前省厅港口局已将使用岸线申请上报交通运输部审批。我局正在同步开展项目初步设计审查。","4A892EFBA0000021A9C1E3A8E36ABAA5"]
["E1DBC0FCAA663A35F61FB11B64C5F0EC",0,null,"2016Y0006",-1,{"$nulls":75},"目前岸线已获得交通部审批，正在进行初步设计审查。","4B2FF7D380000021FF48FF8FCEED99B8"]
["B04636BA04931EBB0B1CDF009D03FD83",0,null,"2016Y0006",-1,{"$nulls":75},"连申线灌河西段航道整治工程工可已批复，初步设计通过省发改委会审。市交通运输局已成立连申线灌河西段航道整治工程建设管理办公室，人员、办公场所等已到位。","537D60FE00000021BC8658DA66B79814"]
["1D5281642B7E4539B43242E47B4A1DD7",0,null,"2016Y0006",-1,{"$nulls":75},"   疏浚、水工、陆域形成地基处理工程完工；装卸设备、供电设备购置安装\n","46D12095E00000210EEE5BA374F2A089"]
["1EC6240903E4349DE80F932CC18848F3",0,null,"2016Y0006",-1,{"$nulls":75},"完成接岸段4km抛填，加快延伸段施工，赣榆港区初步形成了双堤环抱雏形。\n","4C2FAFDCA0000021C4BD69F74D4CF3C4"]
["B9E0AF9C7955601790516C6024FB1962",0,null,"2016Y0006",-1,{"$nulls":75},"4100米DZL-SG2标段主体工程已基本完成，占东直立堤总长4674米的88%，目前开展挡浪墙施工等。","452C38D9600000015B091B22A009EB3A"]
["E9D723F93557CE1AB86F100550752B3B",0,null,"2016Y0006",-1,{"$nulls":75},"水工主体建成","4C2FBB62400000215AFA7F2E2F3C2A28"]
["9DC76843A23B45C302AEFDF1810547C4",0,null,"2016Y0006",-1,{"$nulls":75},"2个泊位水工主体建成","4C2FCA8B60000021201D5B07BBD59C1F"]
["F86DA4924B666410018F051A05A40795",0,null,"2016Y0006",-1,{"$nulls":75},"目前完成承台16个，桥墩11个，钻孔灌注桩209根，道路路基完成2000米，水泥搅拌桩1100根，其中前期及拆迁费用1.072亿元","557C6B7F4000002118C12746D919A3A0"]
["3B5DFF76E4D4B3951814F8E61F746F75",0,null,"2016Y0005",-1,{"$nulls":75},"一期工程G204以西段25.96公里建成通车。二期工程G204以东段已完成施工图审查，今年实施新204国道至老204国道段6.027公里，当前已完成监理招标和征地拆迁调查工作，正在进行青苗补偿工作，施工单位近期开标。","45930AC0A00000013A88F40431F8C61A"]
["C92DAF0ECBF3D08B486DBBF1AE412839",0,null,"2016Y0005",-1,{"$nulls":75},"草庙以东段13km已完成路基挖方100%，路基回填78.08%，混凝土挡墙100%，箱涵100%，桥梁98.62%；草庙至沿海高速段已完成招标工作，确定施工单位，开始启动征地拆迁。","53A6915A00000021AD1AD66B463B498A"]
["2A3371CD2169F9170458E95310BA28B8",0,null,"2016Y0005",-1,{"$nulls":75},"已完成沈海高速以西段施工图审查，完成东台北绕城段12.64公里、高兴东段9.33公里和机械产业园段0.9公里。本年开工建设串场河大桥及其引桥3公里，当前已完成该段征地拆迁调查工作，施工单位近期开标。","53A69343800000016330E2AAE727C4C0"]
["392137AB528BBE972B954FC47736083F",0,null,"2016Y0005",-1,7,72,8,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,null,72,null,295475,268617,244197,1,100,100,1,12,{"$nulls":3},7276,7,72,8,29547,120879,195358,1,50,10,1,0,{"$nulls":3},7276,{"$nulls":3},29547,120879,195358,1,50,10,1,{"$nulls":4},7276,{"$nulls":15},"主体工程已建成通车。","4D70741A20000021FFF8CC821D5CE7DB"]
["1F96D76E797FFE01ABF8CDAD613BFA08",0,null,"2016Y0005",-1,{"$nulls":75},"建成通车。","4756E0D780000021BD984AD195D60C8A"]
["2B06EC048AE72B82D28AF79F472FF0EA",0,null,"2016Y0005",-1,26,30,26,137962,693411,488413,3,null,null,25,78,{"$nulls":4},26,30,26,137962,693411,488413,3,null,null,25,76,{"$nulls":50},"53A2283040000021AD7C1F073733A9EC"]
["289E9668BCDCE74B6DFADE0963B81011",0,null,"2016Y0005",-1,27,30,27,122766,613829,613829,2,null,null,22,{"$nulls":66},"53A229B3C0000001BA18BC5DA5F2D176"]
["7DD86DD5C2B728D8D0667D896D922C24",0,null,"2016Y0005",-1,{"$nulls":15},15,225,null,500100,null,null,9,100,100,5,60,{"$nulls":3},13828,{"$nulls":46},"452C38D5A00000A1C369596A7753C333"]
["70AD4BB27802000501C313728CF4F2A1",0,null,"2016Y0005",-1,5,112,5,208954,196309,573301,4,100,100,5,30,{"$nulls":3},3381,4,88,{"$nulls":5},70,30,5,30,{"$nulls":3},1176,1,31,null,208954,196309,573301,null,69.6,30,{"$nulls":5},2204,1,7,{"$nulls":12},1102,{"$nulls":16},"452C38DBA0000101EE35873CD541EA02"]
["D990DC14F15FDFB416FE293F30A2F9E0",0,null,"2016Y0005",-1,{"$nulls":75},"开展路基和雨污水管施工","4EDD9C40A0000021AB18D369C57D514A"]
["A08FFA17348D4179C3942D86D3C489D3",0,null,"2016Y0005",-1,{"$nulls":75},"尚未复工","53A7EFB8200000211B7FB59EEE89712A"]
["DFB6D222F630FF937C777BF944F07EF4",0,null,"2016Y0005",-1,{"$nulls":75},"该项目已完成新城区新元大道与经济技术开发区昆仑大道间6公里的路面及附属设施施工。","4D93720CA0000021255B319F74F769D3"]
["19513FC1CD11CD3FD0C7D9E3FF6A4B69",0,null,"2016Y0005",-1,{"$nulls":75},"建成通车。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["E13D38B59704473D77E31194DF8AE950",0,null,"2016Y0005",-1,{"$nulls":75},"主体已完成，铁路专用线开通，综合办公楼施工。","452C38D9200000A160383FB696401BD8"]
["9F7DA99C3DBEBCE67692746C8F256933",0,null,"2016Y0005",-1,{"$nulls":75},"已交工验收","4B96568F00000021E184EC6C9CE9F9DC"]
["AF2BFF19A4638492DCE75E204F7B7602",0,null,"2016Y0010",-1,10,393,null,614740,483910,766766,13,100,100,5,78,{"$nulls":3},25680,null,393,null,614740,482500,null,13,100,100,5,78,{"$nulls":3},25680,{"$nulls":3},60550,68910,766766,{"$nulls":12},60550,67500,{"$nulls":26},"452C38D900000041E569F21C93091E69"]
["F5DA255F11C75674751252B193E25F0E",0,null,"2016Y0010",-1,500,27,500,3568219,3568219,3026273,{"$nulls":9},500,27,500,3568219,3568219,3026273,{"$nulls":9},500,27,500,3568219,3568219,3026273,{"$nulls":9},500,27,426,3568219,3568219,2578385,{"$nulls":25},"5774DA90E0000021955F838DE13DD727"]
["E66BF24956953BA161A5F468D2BC18D8",0,null,"2016Y0010",-1,{"$nulls":75},"已建成通车","452C38D8E00000016E11E8A797F21D0A"]
["64F01B117228B450AE2644999F4623E7",0,null,"2016Y0010",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6489,6,144,2,268220,300305,282439,null,100,100,4,11,{"$nulls":3},6489,2,10,6,76634,93428,200846,1,10,0,2,0,{"$nulls":3},5848,null,7,null,71160,60061,169464,null,10,0,2,0,{"$nulls":3},5839,{"$nulls":15},"1-5标已完成。","464AEA1FC0000021B52E367C631B2D38"]
["25C5A012D4DDA1D2B3C3240583C165DB",0,null,"2016Y0010",-1,35,214,null,901675,814568,1313351,4,100,100,21,123,{"$nulls":3},32535,2,102,null,207385,162914,13133,null,60,80,8,77,{"$nulls":3},325,35,214,null,631172,488740,656675,1,50,100,15,123,{"$nulls":3},15000,2,102,null,207385,162914,13133,null,60,80,8,77,{"$nulls":3},325,{"$nulls":15},"高邮先导段已交工，二期工程底基层已完成，水稳基层完成75%施工。向阳河特大桥全桥主体工程基本完成。邗江段路基完成40%，软基处理完成50%，涵洞完成70%，桩基完成78%，预制箱梁完成20%。","53AB5E72800000219F8F0ED14F139BBE"]
["E1FF5F21E5A27079C41C8AB26F711C50",0,null,"2016Y0010",-1,6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":4},6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":50},"4D6F1C538000000151F6EA761DDE2303"]
["0C0E2D6E50D73C127F8F54D5AB3DC81E",0,null,"2016Y0010",-1,244,null,244,{"$nulls":3},9,null,null,76,{"$nulls":5},212,null,212,{"$nulls":6},76,{"$nulls":5},244,null,244,{"$nulls":3},9,null,null,76,{"$nulls":5},212,null,212,{"$nulls":6},76,{"$nulls":21},"531C0B09800000213AEF0095AEB1C8E4"]
["2AA8E325E727CAE657E5389858485AE8",0,null,"2016Y0010",-1,{"$nulls":75},"水稳施工。本月完成投资100万元，累计完成投资2200万元。","50A2E87680000021494BCC0A662835C1"]
["CFD205257D999B16B92944C48FAEB83C",0,null,"2016Y0010",-1,{"$nulls":75},"进行疏浚工作，完成疏浚1950万方","452C38DBA00000A1D9FAC753CD299992"]
["7814CF5F3A5E344770F36DB61D7C7BF1",0,null,"2016Y0010",-1,{"$nulls":75},"正在进行锚碇墙导梁的施工","50ACF3B5C000002140A49A608B6CF75F"]
["0D48BF45071810BA33854A274A7EE08A",0,null,"2016Y0010",-1,{"$nulls":75},"工可编制已完成，岸线申请已报至省交通运输厅。招投标已完成，进行施工前期准备工作，近期初步设计预审。","544C473EA00000213222A4C463CC9061"]
["62663BA3E91CDE149515B9105FDB151A",0,null,"2016Y0010",-1,{"$nulls":75},"正在进行桥面系施工和接线路基施工。","45830701A00000018662A81FE3FB2B60"]
["52ABEBD7AB67890CB77CF3B853F3E3D1",0,null,"2016Y0010",-1,{"$nulls":75},"全线除盐河三桥外已建成，盐河三桥正在积极推进征地拆迁工作。","4D74230D8000002178E3CF444AE9AE57"]
["C1DDC8E02A59314613A0CFFC415E0859",0,null,"2016Y0010",-1,{"$nulls":75},"主体建成。","50A749104000002111B1BD6A84FDACB7"]
["1D8715805EA37935E11F75D53BA4696E",0,null,"2016Y0010",-1,{"$nulls":75},"桥梁下部构造基本完成，正在进行接线路基施工。","51E882EC80000021B9C40721EDEC0F47"]
["1918AB9996D0020A102E2D08744390D8",0,null,"2016Y0010",-1,{"$nulls":75},"桩基施工已完成，正在进行桥梁下部构造和接线路基施工。","51E88CC1C000000135D9837102FD2D41"]
["1B5A20BC30366E65420B4581C170E958",0,null,"2016Y0010",-1,{"$nulls":75},"已建成投入使用。","5364A5A2C00000011BDE5991814C61E3"]
["30490800016D8E60F544C9B301FDE333",0,null,"2016Y0010",-1,{"$nulls":75},"三通一平已完成，管线迁移及临时道路建设已完成，基坑支护完成50%。","4B2FE5AB600000211F6D440BC42C931E"]
["6D3D8DC1ADB90322D165FBF88E2B38A3",0,null,"2016Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"建成通车","44F92AE720000041FD47DFFCE454F006"]
["7D86346CFB241BC64BCAD4EB5EC98C7E",0,null,"2016Y0006",-1,{"$nulls":75},"雨污水管完成80%，现在转换至另半幅施工","4EDD9C40A0000021AB18D369C57D514A"]
["3492E8866B6D78EE03557966DBFAF780",0,null,"2016Y0006",-1,{"$nulls":75},"正在推进前期工作。","4596CE63A0000021B9EF1E5E417B9CA3"]
["59E6E12008D52DEC7A193A74F9485F90",0,null,"2016Y0006",-1,{"$nulls":75},"完成路面基层90%、面层85%。","48173F21C00000213849C18090E227D5"]
["8E07147CB631FA9AD86B63AD71362184",0,null,"2016Y0006",-1,{"$nulls":75},"尚未复工","53A7EFB8200000211B7FB59EEE89712A"]
["2100F075887F056DC90104EDD1CBDFE6",0,null,"2016Y0006",-1,{"$nulls":75},"主体已完成并投入运营，铁路专用线开通，综合办公楼施工。","452C38D9200000A160383FB696401BD8"]
["22FF2C5DE694DE95DD53F3EB398836DE",0,null,"2016Y0006",-1,{"$nulls":75},"目前已经建成22.8公里，纵三至纵五段正在推进前期工作。","452C38DA80000041BB1AF46EF3FAECC2"]
["3679E549CBE05B71F20AAC09D010861B",0,null,"2016Y0006",-1,{"$nulls":75},"完成桥梁灌注桩100%，系梁50%、墩柱12%。","494F9423E0000021971B8B67E472FD4B"]
["6E362865A13F321E98155C6CB372B250",0,null,"2016Y0006",-1,{"$nulls":75},"水工主体建成","4C2FB609C0000021E347BA6BB8D8C1EF"]
["583C38DBD41FD05B6C375C8932D2C938",0,null,"2016Y0006",-1,{"$nulls":75},"加快一突堤抛填","54FF6D5820000021298A28081FBDF9AC"]
["410BE690335CA9336CFD81EBAD269A9C",0,null,"2016Y0006",-1,10,393,null,614740,483910,766766,13,100,100,5,78,{"$nulls":3},25680,null,393,null,614740,482500,null,13,100,100,5,78,{"$nulls":3},25680,{"$nulls":3},60550,68910,766766,{"$nulls":12},60550,67500,{"$nulls":26},"452C38D900000041E569F21C93091E69"]
["1E913E13447EA3E1C963CA5581E48B69",0,null,"2016Y0006",-1,5,112,5,208954,196309,573301,4,100,100,5,30,{"$nulls":3},3381,4,88,{"$nulls":5},70,30,5,30,{"$nulls":3},1176,1,31,null,208954,196309,573301,null,69.6,30,{"$nulls":5},2204,1,7,{"$nulls":12},1102,{"$nulls":16},"452C38DBA0000101EE35873CD541EA02"]
["20082D041C4C2035E0A76948C81F59D6",0,null,"2016Y0006",-1,34,490,34,1100000,900000,2480000,3,{"$nulls":3},102,{"$nulls":4},34,420,16,953000,590000,1274000,0,{"$nulls":3},99,{"$nulls":4},17,90,18,177000,410000,1206,0,{"$nulls":3},7,{"$nulls":4},17,20,0,30000,100000,0,0,{"$nulls":3},4,{"$nulls":4},"\n","\n","\n","\n","\n","\n","\n","\n","\n","\n","\n",{"$nulls":4},"办理土地相关手续，晶桥至白马段16公里完成，晶桥至明觉段进行路基路面施工，桥梁上部结构施工","44F92AE780000001F6AE7427CA69104E"]
["990DD803EB8AF31AE545854CECC6C0C8",0,null,"2016Y0006",-1,{"$nulls":75},"S337先导段、湖熟非集镇段、禄口段沥青上面层施工全部结束。S337湖熟段目前全线清表已基本完成，正在进行部分路段路基施工和湿喷桩施工。","44F92AE9800000A15AC5660EDAD7D017"]
["74B6602F9A2B29D17879ADFE3853A307",0,null,"2016Y0006",-1,{"$nulls":75},"完成施工图工前测量，完成施工图设计。","44F92AE7400000013A0A1F9A656A1EA4"]
["1A0215E775FB7B096CF84BB6F402B313",0,null,"2016Y0006",-1,{"$nulls":75},"码头水工主体已完工","44F92AE8C0000061CA99E73B5A18BBB6"]
["4B80010B217DA04FDF0E33FF01771517",0,null,"2016Y0006",-1,{"$nulls":75},"水工主体结构已交工验收，已完成门机招投标，准备安装，正在进行陆域地基处理。","4B96568F00000021E184EC6C9CE9F9DC"]
["7450002D96237A1934DD2AE19484723C",0,null,"2016Y0006",-1,{"$nulls":75},"已取得概算批复；招标公告已发，预计7月11日开标。","557C8B70E00000212D51668A2818D6A7"]
["93EAFFD508C5659BE1280EC55463EE7B",0,null,"2016Y0006",-1,{"$nulls":75},"已取得概算批复；招标公告已发，预计7月11日开标。","557C8DD6E00000217D3AADACA80D7899"]
["90525A507E4FBEC767E01539276BB11B",0,null,"2016Y0006",-1,{"$nulls":75},"已取得概算批复；招标公告已发，预计7月11日开标。","557C8F2540000021AD96D705F8B81957"]
["8E8A71D8FE711014CC98C1CE8DC48C99",0,null,"2016Y0006",-1,{"$nulls":75},"已建成通车","452C38D8A0000041215774BA7CEB1CEE"]
["8BAD65403EF4181E2C62535F1B98B292",0,null,"2016Y0006",-1,null,16,null,59015,57067,55493,1,{"$nulls":3},7,{"$nulls":5},12,null,44261,42800,41619,1,{"$nulls":3},7,{"$nulls":49},"全长2.24公里，已完工1.67公里。","48110BD0800000016999F8D7C247DD09"]
["CB510B128CD016AFD2C8C59DA45D32D9",0,null,"2016Y0006",-1,{"$nulls":75},"一期全部完成，目前二期征地拆迁款4235万已拨付到位，施工单位即将进场施工。","46A37B7E80000021FCCC83E6275E4C98"]
["043971C686E61B2D62E7EB4640D77DE0",0,null,"2016Y0006",-1,{"$nulls":75},"桩基施工完成80%。","51D1D49260000021FCEEDB7A127D7731"]
["31D3CFB486E32539B43607CFD070EDDB",0,null,"2016Y0006",-1,{"$nulls":75},"宁连路至月季路段2.5公里已完成，月季路至飞耀路段已建成。","545A7B4F20000021344738A715E00356"]
["B03880102A0256324CDAE89A73D3207E",0,null,"2016Y0006",-1,{"$nulls":75},"已建成通车。","545AA9A8E00000014DC918C5BA78E533"]
["3BEC83C56E46B6EFF4E19947DA4BB58F",0,null,"2016Y0006",-1,{"$nulls":75},"    华元路到朝阳河桥南主车道进入基层施工，其余主车道贯通，慢车道平侧石施工结束，准备铺设沥青；朝阳河桥东侧完成架梁，开始桥面系施工。","4A04D699C0000021960B6C19775B7500"]
["8CEA24652E0A22FF1F69A4C098AC9321",0,null,"2016Y0006",-1,{"$nulls":75},"完成小箱梁湿接缝；完成小箱梁中、端横梁；完成小箱梁护栏；完成60m护栏；完成拼宽段8%灰土1000方,累计完成94%。","4B2547D8C0000021EA2F1D310FA63F35"]
["8DF2AD7B10EDD40C64E51F6E07E3E3A6",0,null,"2016Y0010",-1,{"$nulls":75},"项目完工，投入运行。","48AC14EDE0000021742CF36A7A1280AB"]
["ACFD1142A6FF5F22B803165B95A41FBE",0,null,"2016Y0010",-1,24,98,24,334460,326350,280060,3,100,100,18,98,{"$nulls":3},22036,null,51,null,6689,0,0,null,30,65,4,91,{"$nulls":3},22,24,98,12,234122,195810,154030,3,100,100,12,75,{"$nulls":3},11000,null,51,null,6689,0,0,null,30,65,4,91,{"$nulls":3},22,{"$nulls":15},"先导段累计完成路基土方填筑86%，箱梁54%，盖梁台帽65%；盐邵河大桥主桥悬浇施工完成50%。二期工程累计完成路基土方填筑10%，涵洞48%。","53AB6008E0000021100DBB3E8C074665"]
["C2E842E25BEC72600C211A11B891C6DD",0,null,"2016Y0010",-1,25,140,27,1336352,836248,1317741,23,null,null,28,21,{"$nulls":3},22684,25,140,27,1336352,836248,1317741,23,100,100,28,21,2,null,510,22684,0,5,2,null,null,300118,{"$nulls":10},5,2,null,null,300118,{"$nulls":25},"45886E536000002100B27DDCDF662D01"]
["89060C3DD7754964D1E6DB4844D38AA8",0,null,"2016Y0010",-1,25,190,25,{"$nulls":3},8,null,null,9,73,{"$nulls":3},22233,25,190,{"$nulls":4},8,100,100,9,73,{"$nulls":3},10000,null,1,25,{"$nulls":3},1,{"$nulls":3},1,{"$nulls":3},22233,null,1,{"$nulls":4},1,{"$nulls":3},1,{"$nulls":3},10000,{"$nulls":16},"458887AF00000021883DEACA51071D92"]
["DF18296F79A17BDEED59A3F6D0A6CEAE",0,null,"2016Y0011",-1,{"$nulls":75},"竣工通车","4E42F599E0000021BA83650E545E4DA9"]
["A82944B12F090777A4101F76E15B3C64",0,null,"2016Y0011",-1,{"$nulls":75},"建成通车。","4A98ADB6E00000213FE2CCEEAEE0EE7E"]
["76AAD3BEC2704AA674503E09AFAAED7E",0,null,"2016Y0011",-1,13,null,13,{"$nulls":12},13,null,12,{"$nulls":12},13,null,13,{"$nulls":12},12,null,12,{"$nulls":28},"5290FF2D800000218EE2D98EEC67211F"]
["D965F0C326683B9D2125885570D5951B",0,null,"2016Y0012",-1,24,null,24,null,590283,564435,{"$nulls":9},24,null,24,null,590283,564435,2,null,null,11,79,{"$nulls":4},2,null,10,null,59028,225774,{"$nulls":9},2,null,10,null,59028,225774,{"$nulls":24},"已完工验收","45A64AD8E000002115357ED0397AE2AC",238,101,238,101,19,8,19,8]
["85B2A4B857EEDAF4810333E603A057F8",0,null,"2016Y0012",-1,24,null,24,{"$nulls":12},24,null,24,{"$nulls":12},24,null,24,{"$nulls":12},24,null,24,{"$nulls":27},"已交工","5920707BA0000021098BFE2FF97B8717"]
["258C01722205C647548DF0812E0151CC",0,null,"2016Y0010",-1,66,null,66,{"$nulls":12},30,null,20,{"$nulls":12},0,null,16,{"$nulls":12},0,null,6,{"$nulls":27},"已交工验收20.6公里。","45C5231CE0000021BC17A82CFFD70F54"]
["717788A13E3CDAA128AE7CBB7239934B",0,null,"2016Y0010",-1,96,null,96,{"$nulls":12},60,null,60,{"$nulls":12},17,null,17,{"$nulls":12},17,null,10,{"$nulls":27},"已建成通车50公里。泗阳段1.2标开展路基、桥涵施工。","45AB8817400000218E63FD22BDA91CE1"]
["C25569BC46094D6F7D334FE8C0721C13",0,null,"2016Y0010",-1,{"$nulls":75},"目前完成全线沥青及标线施工，完成分隔带绿化填土，正在进行人行道、路灯及交安附属设施施工，完成进度的99%。","476C4BC84000002168C8EFB59D88315C"]
["03D74F030E94AD129CCDC973740D601D",0,null,"2016Y0010",-1,11,65,11,192161,528105,629651,2,100,100,4,11,{"$nulls":3},10640,6,43,6,192161,528105,629651,1,60,100,2,7,{"$nulls":3},-2119,null,13,null,10530,0,0,null,40,50,1,1,{"$nulls":3},10640,{"$nulls":7},24,50,{"$nulls":22},"4D897AEAA00000212EF01FB341272DCF"]
["E09800E97A0B28979308CA5548D47067",0,null,"2016Y0010",-1,{"$nulls":75},"盐都段已分期建成229省道至大纵湖风景区段25.392km，大纵湖风景区至兴化交界段8.5km暂无实施计划，当前正在新建229省道至204国道段8.7km当前土方开挖完成100%，路基回填完成100%，涵洞完成76%，桥梁完成98%。","452C38D5E0000101955840B450CF8800"]
["8360D6A0D4E0108B0FC2485B93AC3726",0,null,"2016Y0010",-1,{"$nulls":75},"目前全线征地拆迁结束，高新区（原新海新区）段长0.8公里，按城市主干道标准全面建成，其余全线路基施工结束，桥梁施工结束，软基、涵施工洞结束，马涧路基爆破施工结束，沥青路面完成93%，交安设施施工完成95%，绿化施工完成70%。","44F92AE7E000004126A44C796491035A"]
["EA4591311AD6CF4D84BBC44C254FD8BC",0,null,"2016Y0010",-1,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$nulls":15},"正在进行码头水工的建设","452C38D680000061945BBA12FA20CE28"]
["7A8B0A6C8694C8F5226651B8E1A6AF16",0,null,"2016Y0010",-1,{"$nulls":75},"工程完工，准备验收","4B8C51DCE00000217D7EDDE1F74ABEDD"]
["BB240D69AB8A31278146F30A05E383BA",0,null,"2016Y0010",-1,{"$nulls":75},"项目已完工，正在试运行","529BC5F4A0000001199EEF6E770F959B"]
["B562926AC189707CECC1E7DF642555F0",0,null,"2016Y0010",-1,{"$nulls":75},"已完工","5460F4DA20000021E6011AA2335B9033"]
["3DBE5FCF22F592FFE106DDF75AC1CD5E",0,null,"2016Y0010",-1,{"$nulls":75},"雨污管道完成80%,镇区段完成半幅沥青下面层，正开展另半幅灰土施工，野外段完成全幅下面层施工和部分上面层的施工","4EDD9C40A0000021AB18D369C57D514A"]
["ABA3E58ED123155ABD8C2CB2E1AC53C2",0,null,"2016Y0010",-1,{"$nulls":75},"完成部分项目审批、土建部分招标","53F3A14460000001877A1E501EA56D99"]
["E080A8F033BA0A9D05CC82D980EDEEAB",0,null,"2016Y0010",-1,{"$nulls":75},"方案设计已完成，项目优化方案已通过上海铁路局审核，施工图已完成，征地线已放完。","4596CE63A0000021B9EF1E5E417B9CA3"]
["4F43D0456E307373FFBC261964506FA8",0,null,"2016Y0010",-1,{"$nulls":75},"进行路基、基层施工及部分附属设施施工。本月完成投资1200万元，累计完成投资4200万元。","561FD31F6000002168E325F739950BAC"]
["DD555FADCFF5AB5A33EF810760DD647F",0,null,"2016Y0010",-1,{"$nulls":75},"航道已疏浚土方量785万方；导堤工程仅剩余3500件扭王块未安装。","4A85A54EA000002149498783DFAF6BB9"]
["13808517515B997738451DB6B1029D66",0,null,"2016Y0010",-1,{"$nulls":75},"宁连路至月季路段2.5公里已完成，月季路至飞耀路段已建成。","545A7B4F20000021344738A715E00356"]
["0AAEF0D2CCA96CB20FF09559FA24E6E9",0,null,"2016Y0010",-1,{"$nulls":75},"已建成通车。","4E0AAEDB80000001A21A3E3285F69BC1"]
["984023B60FE3DB05B57ABF6A4B033B99",0,null,"2016Y0010",-1,{"$nulls":75},"无","56BF67C9E0000021BC1B2AEA0891915D"]
["039E6465BDC1B52D76A11C13D51C5391",0,null,"2016Y0010",-1,{"$nulls":75},"物流园南、北停车场投入试运营。","468F5198A0000021390EE49ABE0B2CD5"]
["82744D1A9DEE50F7407605D7793A2FB3",0,null,"2016Y0010",-1,{"$nulls":75},"目前工程工可已批复，初步设计通过省厅内审，还未得到省发改委批复。市政府成立了由分管市长任组长的工程建设领导小组，市交通运输局和灌南县政府也分别成立工程建设管理办公室和征地保障管理办公室，人员到位并开展相关准备工作。为推进灌河航道整治工程初步设计早日批复，灌南县人民政府、连云港市水利局、连云港市交通运输局三方签订《灌河航道放水冲淤保通航调度方案》，完成灌河航道放水冲淤保通航调度方案论证报告，并通过市水利局批复。","537D60FE00000021BC8658DA66B79814"]
["77A006352AAEBADCA19B3065BA30897B",0,null,"2016Y0012",-1,{"$nulls":75},"开展路基和桥梁施工","4D08381440000021025FCF5FDA219DA7"]
["F400B4BD9D447F8CBD47CB546F242E31",0,null,"2016Y0012",-1,{"$nulls":75},"完工","5775684A600000212C2E7D77F2FF6A6E"]
["2BCE523D42780B59ACE315279DFB99F7",0,null,"2016Y0012",-1,{"$nulls":75},"建成通车","44F92AE720000041FD47DFFCE454F006"]
["C04C2B15FA2BD9B2975EEE60FF646C41",0,null,"2016Y0012",-1,{"$nulls":75},"已建成投入使用。","5364A5A2C00000011BDE5991814C61E3"]
["50A3A3D2AE50FEBAF3B4CA575E851AC8",0,null,"2016Y0012",-1,{"$nulls":75},"征地拆迁基本完成，施工单位已进场开工建设。\n","4596CE63A0000021B9EF1E5E417B9CA3"]
["CCEF39C0AD7B5859D9EF125B5A71CEF2",0,null,"2016Y0005",-1,6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":4},6,42,6,224912,371494,489057,1,100,100,null,9,{"$nulls":50},"4D6F1C538000000151F6EA761DDE2303"]
["2AED9EED43A9BFA5576DA6F800796C7E",0,null,"2016Y0005",-1,8,147,8,273694,333672,313821,1,100,100,4,11,{"$nulls":3},6489,6,144,2,268220,283621,266748,null,92,100,3,11,{"$nulls":3},6489,2,10,6,76634,93428,200846,1,10,0,2,0,{"$nulls":3},5848,null,7,null,71160,43377,153773,null,2,0,1,0,{"$nulls":3},5839,{"$nulls":15},"1-5标已完成。","464AEA1FC0000021B52E367C631B2D38"]
["5BFD5DBEE788761A8A80B04BCD89A54D",0,null,"2016Y0009",-1,{"$nulls":16},466,{"$nulls":5},72,77,null,164,{"$nulls":50},"452C38D720000081C14CEFA6969A8D06"]
["2A207490773361339CF1A954C68C55EC",0,null,"2016Y0009",-1,{"$nulls":75},"全线已通车。","4D7071D66000002165416ADF246EF2BE"]
["408D96FB63A185AAD7ED0E0DF02709E9",0,null,"2016Y0009",-1,21,655,21,1131535,1131537,2380000,9,0,0,17,47,0,0,0,81343,11,629,19,1072800,1015900,2154700,9,0,0,17,47,0,0,0,70000,10,26,2,59035,116037,225700,0,0,0,0,0,0,0,0,11343,0,1,0,800,900,900,0,0,0,0,0,0,0,0,200,{"$nulls":15},"工程全长20.976公里，分为前半段“起点—坟头”10.176公里和后半段“坟头—终点”10.8公里两个段落。如今后半段10.8公里已于2013年9月完成交工验收；绕城高速至坟头段（含S122NJ-QL2标段）于2016年5月26日完成交工验收。主线2015年底已全部贯通。剩余西村战术场等3处部队矛盾段落，将在矛盾处理完后才能施工。","44F92AE840000101423CCFA36BCE2089"]
["4F45C9C96E0AFB59AAD0D5495811FE61",0,null,"2016Y0009",-1,42,null,42,{"$nulls":12},42,null,42,{"$nulls":12},0,null,27,{"$nulls":12},0,null,27,{"$nulls":27},"全线建成已交工通车。","45C546C200000021547764ADF0037399"]
["639C3283F7C24CB5C6C0BD3D639F90A5",0,null,"2016Y0009",-1,17,null,17,{"$nulls":12},0,null,0,{"$nulls":12},17,null,0,{"$nulls":12},0,null,0,{"$nulls":27},"B标段完成部分路基、涵洞工程。","45C531BE200000219CD9EF28C8D31E82"]
["0644CEDE09933140A813CD72858DF161",0,null,"2016Y0009",-1,66,null,66,{"$nulls":12},30,null,20,{"$nulls":12},0,null,16,{"$nulls":12},0,null,6,{"$nulls":27},"已交工验收20.6公里。","45C5231CE0000021BC17A82CFFD70F54"]
["590649BAFBAAD5FF2F7CF430542D8AB1",0,null,"2016Y0009",-1,96,null,96,{"$nulls":12},60,null,60,{"$nulls":12},17,null,17,{"$nulls":12},17,null,10,{"$nulls":27},"已建成通车50公里。泗洪段1.2标开展路基、桥涵施工。","45AB8817400000218E63FD22BDA91CE1"]
["89A74138B0D2ECE6CEC4BFFDD9EEA8E7",0,null,"2016Y0009",-1,{"$nulls":75},"建成通车。","4756E0D780000021BD984AD195D60C8A"]
["0911663AB64782C70930A7B84C9F3C8C",0,null,"2016Y0009",-1,{"$nulls":75},"淮阴区段已建成；涟水段主体建成。","4D989A7680000021CAE7FBD451FCC003"]
["716830AAFC3740C49932436604765171",0,null,"2016Y0009",-1,{"$nulls":75},"主体建成。","50A749104000002111B1BD6A84FDACB7"]
["C6F33899D063865C61640899EED7D3C6",0,null,"2016Y0009",-1,{"$nulls":75},"桩基已完成，正在进行下部结构和接线路面底基层施工。","51D1B60C60000021547E4A7724FD4535"]
["B2D1195E73FDD47D4EFF1AC636256695",0,null,"2016Y0009",-1,{"$nulls":75},"桩基施工基本完成，正在进行桥梁下部结构施工。","51D1D49260000021FCEEDB7A127D7731"]
["0D9587D8F6E04A13A0BBB853906C6AAB",0,null,"2016Y0009",-1,{"$nulls":75},"桩基施工已完成，正在进行桥梁下部构造和接线路基施工。","51E882EC80000021B9C40721EDEC0F47"]
["C9684CD1B5C0F906918D849FD9AF282D",0,null,"2016Y0009",-1,{"$nulls":75},"桩基施工已完成，正在进行桥梁下部构造和接线路基施工。","51E88CC1C000000135D9837102FD2D41"]
["E61F574CBAAA41CDB2DC443CAF55C2A9",0,null,"2016Y0012",-1,{"$nulls":9},10,{"$nulls":14},10,{"$nulls":14},10,{"$nulls":14},10,{"$nulls":20},"完成危桥改造10座","5920617B40000021B9FFDE1C25433173"]
["DC3E892D798054A5B2E6CB6B43D5B9E5",0,null,"2016Y0012",-1,174,null,174,null,284,284,{"$nulls":9},174,null,174,null,284,284,{"$nulls":9},174,null,174,null,284,284,{"$nulls":9},174,null,174,null,284,284,{"$nulls":24},"全部建成通车","5920779FA0000021AC5B2E1853EA170C",284,284,284,284,284,284,284,284]
["DEEF83CF862D0567A005354D00DA0C51",0,null,"2016Y0012",-1,{"$nulls":75},"疏浚维护","46412B4EE000002160BA115A2334239C"]
["A7D13E60B4F0EE1C8A0A7BC8B5A16A14",0,null,"2016Y0012",-1,{"$nulls":75},"项目已完成","557C880820000021E6B80B97DEA5406F"]
["EAB2AC379DAE92D9B416D023BE03B8CF",0,null,"2016Y0012",-1,{"$nulls":75},"水工结构完成70%左右","50ACF3B5C000002140A49A608B6CF75F"]
["5F1FCD9A757D3D41AB3A76AA0F8C9BFC",0,null,"2016Y0012",-1,{"$nulls":75},"沉桩、预制工作、现浇下横梁均已完成；累计安装纵梁549件,安装面板754件；现浇上横梁48榀；同时抓紧浇筑面层。后方堆场降水、强夯。6台门机全部上岸","52A51020400000219F26349145A4F022"]
["B84513379FE219A06A92990ECFDBEF1F",0,null,"2016Y0012",-1,{"$nulls":75},"已建成","557C83D00000002130E051638A8AA34A"]
["66B6C50F402622A749B407E76230ABFF",0,null,"2016Y0012",-1,{"$nulls":75},"已建成","557C8502A0000021E995662E3519484C"]
["B82A7E258BC5C6487C20BF7BE1AA44CE",0,null,"2016Y0012",-1,{"$nulls":75},"桥梁主体建成，接线完成90%。","458CAF86E00000216E3944578E65ACF2"]
["49FC6D8976808D1B98DF70BA9077B127",0,null,"2016Y0012",-1,{"$nulls":4},259860,259860,{"$nulls":13},259860,259860,{"$nulls":13},259860,259860,{"$nulls":13},259860,259860,{"$nulls":24},"已建成","59207C8F000000211BFF0D64F6999D8A",13,13,13,13,13,13,13,13]
["F8A7716B568EAAD155D3BC273313FF1B",0,null,"2016Y0012",-1,{"$nulls":75},"完成桥梁下部结构和梁板预制。","5156819540000001E42DD4EFA2CA58A7"]
["2FD9A59F401F00A84465E18B8B3C7EAC",0,null,"2016Y0012",-1,{"$nulls":75},"进行，基层。面层及附属设施施工。本月完成投资300万元。","561FD31F6000002168E325F739950BAC"]
["B9A29B75D13A259C7437F8A6D8B7B9E3",0,null,"2016Y0012",-1,{"$nulls":75},"水工结构已完成，陆域部分正在施工","4B294D3A40000021302C1EB5290B273A"]
["F19A1CAC96BE96062B7186806FD18668",0,null,"2016Y0012",-1,{"$nulls":75},"完工","4ED76E5EA0000021C2FF39A1BE0258B9"]
["501463D47DD3BBA93D920C43A5CEEF60",0,null,"2016Y0012",-1,{"$nulls":75},"主体建成，投产运营。","452C38D9200000A160383FB696401BD8"]
["AB23C858C529A8204413ED00463B6BCB",0,null,"2016Y0012",-1,{"$nulls":75},"柘汪物流中心一期投入常态化运营；物流园南、北停车场投入试运营。","468F5198A0000021390EE49ABE0B2CD5"]
["D3129ADB9D393BCB2E38DC8F368DE9AB",0,null,"2016Y0012",-1,{"$nulls":75},"全线除盐河三桥外已建成，盐河三桥已启动征地拆迁工作。","4D74230D8000002178E3CF444AE9AE57"]
["3261862F3507A424505E505E7817440C",0,null,"2016Y0012",-1,{"$nulls":75},"全线（其中赣马段11公里已建成通车）征地拆迁基本完成，路基、大桥及中小桥涵基本完成，路面底基层完成80%，基层完成55%、沥青路面完成38%，交安工程完成35%。 ","4D743B53C0000021D528DB4DEF96D439"]
["8539C410041EEE8A0F965D578E44CD39",0,null,"2016Y0012",-1,9,null,9,null,34688,64615,{"$nulls":9},9,null,9,null,34688,64615,{"$nulls":9},9,null,9,null,34688,64615,{"$nulls":9},9,null,9,null,34688,64615,{"$nulls":24},"已交工","592072A220000021A5DF1F867997115B",8,5,8,5,8,5,8,5]
["469B61949FCAB07B96C64983B6AF9EE8",0,null,"2016Y0012",-1,1,null,1,null,9742,9455,1,{"$nulls":3},5,{"$nulls":4},1,null,1,null,9742,9455,1,{"$nulls":3},5,{"$nulls":4},1,null,1,null,9742,9455,1,{"$nulls":3},5,{"$nulls":4},1,null,1,null,9742,9455,1,{"$nulls":3},5,{"$nulls":19},"一期工程建成","5590B4BB8000002188F1A01A528A64EB",2,1,2,1,2,1,2,1]
["12AFE65650174A1B1980374CCFC13F75",0,null,"2016Y0012",-1,{"$nulls":75},"水工结构已完成，陆域部分已完成50%","501D2168E0000001009E18AEB704D996"]
["1FE5BEE0C26B5872547C399AD4B1B122",0,null,"2016Y0012",-1,{"$nulls":75},"水工结构已完成50%，陆域部分正在施工","532B1F97A0000021916D6A45C69794D0"]
["173F72F4F2A6D961A2337A87C4A69237",0,null,"2016Y0012",-1,{"$nulls":75},"建成通车。","452C38DBE00000616AD445E437E62A7E"]
["69D7BCBBCFEFDA040345D2F4C6EE2228",0,null,"2016Y0012",-1,{"$nulls":75},"累计完成98%的路基填筑、98%的小型构造物；完成85%的桥梁上部现浇砼、76%的桥面铺装；完成75%的底基层、57%的基层施工。","49E0F21C200000214178341411919FAB"]
["27033BBD0475348A878B4C4E2AE8652E",0,null,"2016Y0012",-1,{"$nulls":76},"51321CCD6000002166FFE3002ACD9EF3"]

{"sheet":"Sheet1","index":1,"n_rows":97,"n_cols":5,"rows_kept":97,"flags":["formulas_cached_only"]}
["指标标识","指标标题","指标类型","精度","小数位"]
["UNITID","单位","唯一标识型",0,0]
["DATATIME","数据时期","字符型",10,0]
["FLOATORDER","浮动行顺序号","数值型",23,5]
["TZXM","投资项目","唯一标识型",0,0]
["TZ05010001001","设计总工程量-路基","数值型",18,0]
["TZ05010001002","设计总工程量-土石方","数值型",18,0]
["TZ05010001003","设计总工程量-路面","数值型",18,0]
["TZ05010001004","设计总工程量-路面底基层","数值型",18,0]
["TZ05010001005","设计总工程量-路面基层","数值型",18,0]
["TZ05010001006","设计总工程量-路面面层","数值型",18,0]
["TZ05010001007","设计总工程量-特大桥、大桥","数值型",18,0]
["TZ05010001008","设计总工程量-上部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010001009","设计总工程量-下部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010001010","设计总工程量-中桥、小桥","数值型",18,0]
["TZ05010001011","设计总工程量-涵洞、通道","数值型",18,0]
["TZ05010001012","设计总工程量-隧道","数值型",18,0]
["TZ05010001013","设计总工程量-掘进","数值型",18,0]
["TZ05010001014","设计总工程量-衬砌","数值型",18,0]
["TZ05010001015","设计总工程量-防护工程","数值型",18,0]
["TZ05010002001","自开始建设累计完成工程量-路基","数值型",18,0]
["TZ05010002002","自开始建设累计完成工程量-土石方","数值型",18,0]
["TZ05010002003","自开始建设累计完成工程量-路面","数值型",18,0]
["TZ05010002004","自开始建设累计完成工程量-路面底基层","数值型",18,0]
["TZ05010002005","自开始建设累计完成工程量-路面基层","数值型",18,0]
["TZ05010002006","自开始建设累计完成工程量-路面面层","数值型",18,0]
["TZ05010002007","自开始建设累计完成工程量-特大桥、大桥","数值型",18,0]
["TZ05010002008","自开始建设累计完成工程量-上部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010002009","自开始建设累计完成工程量-下部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010002010","自开始建设累计完成工程量-中桥、小桥","数值型",18,0]
["TZ05010002011","自开始建设累计完成工程量-涵洞、通道","数值型",18,0]
["TZ05010002012","自开始建设累计完成工程量-隧道","数值型",18,0]
["TZ05010002013","自开始建设累计完成工程量-掘进","数值型",18,0]
["TZ05010002014","自开始建设累计完成工程量-衬砌","数值型",18,0]
["TZ05010002015","自开始建设累计完成工程量-防护工程","数值型",18,0]
["TZ05010003001","本年计划完成工程量-路基","数值型",18,0]
["TZ05010003002","本年计划完成工程量-土石方","数值型",18,0]
["TZ05010003003","本年计划完成工程量-路面","数值型",18,0]
["TZ05010003004","本年计划完成工程量-路面底基层","数值型",18,0]
["TZ05010003005","本年计划完成工程量-路面基层","数值型",18,0]
["TZ05010003006","本年计划完成工程量-路面面层","数值型",18,0]
["TZ05010003007","本年计划完成工程量-特大桥、大桥","数值型",18,0]
["TZ05010003008","本年计划完成工程量-上部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010003009","本年计划完成工程量-下部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010003010","本年计划完成工程量-中桥、小桥","数值型",18,0]
["TZ05010003011","本年计划完成工程量-涵洞、通道","数值型",18,0]
["TZ05010003012","本年计划完成工程量-隧道","数值型",18,0]
["TZ05010003013","本年计划完成工程量-掘进","数值型",18,0]
["TZ05010003014","本年计划完成工程量-衬砌","数值型",18,0]
["TZ05010003015","本年计划完成工程量-防护工程","数值型",18,0]
["TZ05010004001","自年初至本月底累计完成工程量-路基","数值型",18,0]
["TZ05010004002","自年初至本月底累计完成工程量-土石方","数值型",18,0]
["TZ05010004003","自年初至本月底累计完成工程量-路面","数值型",18,0]
["TZ05010004004","自年初至本月底累计完成工程量-路面底基层","数值型",18,0]
["TZ05010004005","自年初至本月底累计完成工程量-路面基层","数值型",18,0]
["TZ05010004006","自年初至本月底累计完成工程量-路面面层","数值型",18,0]
["TZ05010004007","自年初至本月底累计完成工程量-特大桥、大桥","数值型",18,0]
["TZ05010004008","自年初至本月底累计完成工程量-上部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010004009","自年初至本月底累计完成工程量-下部结构（特大桥、大桥）占比重","数值型",18,2]
["TZ05010004010","自年初至本月底累计完成工程量-中桥、小桥","数值型",18,0]
["TZ05010004011","自年初至本月底累计完成工程量-涵洞、通道","数值型",18,0]
["TZ05010004012","自年初至本月底累计完成工程量-隧道","数值型",18,0]
["TZ05010004013","自年初至本月底累计完成工程量-掘进","数值型",18,0]
["TZ05010004014","自年初至本月底累计完成工程量-衬砌","数值型",18,0]
["TZ05010004015","自年初至本月底累计完成工程量-防护工程","数值型",18,0]
["TZ05010005001","备注-路基","字符型",200,0]
["TZ05010005002","备注-土石方","字符型",200,0]
["TZ05010005003","备注-路面","字符型",200,0]
["TZ05010005004","备注-路面底基层","字符型",200,0]
["TZ05010005005","备注-路面基层","字符型",200,0]
["TZ05010005006","备注-路面面层","字符型",200,0]
["TZ05010005007","备注-特大桥、大桥","字符型",200,0]
["TZ05010005008","备注-上部结构（特大桥、大桥）占比重","字符型",200,0]
["TZ05010005009","备注-下部结构（特大桥、大桥）占比重","字符型",200,0]
["TZ05010005010","备注-中桥、小桥","字符型",200,0]
["TZ05010005011","备注-涵洞、通道","字符型",200,0]
["TZ05010005012","备注-隧道","字符型",200,0]
["TZ05010005013","备注-掘进","字符型",200,0]
["TZ05010005014","备注-衬砌","字符型",200,0]
["TZ05010005015","备注-防护工程","字符型",200,0]
["TZ05010000000","形象进度存在问题说明","字符型",400,0]
["TZ05010001016","设计总工程量-填方","数值型",18,0]
["TZ05010001017","设计总工程量-挖方","数值型",18,0]
["TZ05010002016","自开始建设累计完成工程量-填方","数值型",18,0]
["TZ05010002017","自开始建设累计完成工程量-挖方","数值型",18,0]
["TZ05010003016","本年计划完成工程量-填方","数值型",18,0]
["TZ05010003017","本年计划完成工程量-挖方","数值型",18,0]
["TZ05010004016","自年初至本月底累计完成工程量-填方","数值型",18,0]
["TZ05010004017","自年初至本月底累计完成工程量-挖方","数值型",18,0]
["TZ05010005016","备注-填方","字符型",200,0]
["TZ05010005017","备注-挖方","字符型",200,0]
["TZ05010005018","自开始建设累计完成进度-桥梁","数值型",18,0]
["TZ05010005019","自开始建设累计完成进度-涵洞","数值型",18,0]
["TZ05010005020","自开始建设累计完成进度-隧道","数值型",18,0]
["TZ05010005021","自年初至本月底累计完成进度-桥梁","数值型",18,0]
["TZ05010005022","自年初至本月底累计完成进度-涵洞","数值型",18,0]
["TZ05010005023","自年初至本月底累计完成进度-隧道","数值型",18,0]