{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["项目工作量估算","项目计划","方案说明"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"项目工作量估算","index":0,"n_rows":87,"n_cols":4,"rows_kept":87,"cut":false,"hidden":false,"merged":[[0,0,0,3],[1,1,1,3],[79,0,79,3],[3,1,18,1],[19,1,40,1],[41,1,49,1],[50,1,57,1],[58,1,60,1],[61,1,65,1],[66,1,74,1],[75,1,78,1],[3,2,4,2],[5,2,6,2],[7,2,16,2],[19,2,20,2],[21,2,22,2],[23,2,24,2],[25,2,26,2],[27,2,28,2],[29,2,30,2],[31,2,32,2],[33,2,34,2],[35,2,36,2],[37,2,38,2],[39,2,40,2],[41,2,42,2],[43,2,47,2],[48,2,49,2],[50,2,51,2],[52,2,53,2],[54,2,55,2],[56,2,57,2],[58,2,60,2],[61,2,63,2],[64,2,65,2],[69,2,71,2],[72,2,73,2]]}
["项目工作量估算"]
["项目名称","建设经营系统webservice接口开发"]
["序号","功能模块","子模块","功能"]
[{"$f":"ROW()-3","v":1},"基础功能","字典信息","通过字典主键查询字典值"]
[2,null,null,"通过字典父ID查询全部子数据"]
[3,null,"附件","通过附件主键，返回附件信息"]
[4,null,null,"通过附件主键，返回附件信息及附件数据流"]
[5,null,"港口基础信息查询","行政单位信息查询"]
[6,null,null,"行政单位人员信息查询"]
[7,null,null,"港口信息查询"]
[8,null,null,"港区信息查询"]
[9,null,null,"作业区信息查询"]
[10,null,null,"锚地信息查询"]
[11,null,null,"岸线信息查询"]
[12,null,null,"防波堤信息查询"]
[13,null,null,"进港航道信息查询"]
[14,null,null,"船舶信息查询"]
[15,null,"用户登录鉴权","用户登录鉴权，返回用户信息(用户、角色、所属管理人员或所属经营人)"]
[16,null,"待办列表"]
[17,"经营人信息管理","经营人基本信息","列表"]
[18,null,null,"详细"]
[19,null,"码头信息","列表"]
[20,null,null,"详细"]
[21,null,"泊位信息","列表"]
[22,null,null,"详细"]
[23,null,"仓库信息","列表"]
[24,null,null,"详细"]
[25,null,"储罐信息","列表"]
[26,null,null,"详细"]
[27,null,"堆场信息","列表"]
[28,null,null,"详细"]
[29,null,"人员信息","人员列表"]
[30,null,null,"人员详细"]
[31,null,"持证信息","证书列表"]
[32,null,null,"证书详细"]
[33,null,"设施设备信息","列表"]
[34,null,null,"详细"]
[35,null,"企业投资信息","列表"]
[36,null,null,"详细"]
[37,null,"装卸机械信息","列表"]
[38,null,null,"详细"]
[{"$f":"ROW()-3","v":39},"项目信息管理","项目信息","项目信息列表"]
[40,null,null,"根据id获取项目详细信息"]
[41,null,"建设进度管理","建设进度列表"]
[42,null,null,"根据id获取项目进度详细信息"]
[43,null,null,"根据id获取进度进度审批历史流程"]
[44,null,null,"根据id获取项目实施过程信息列表"]
[45,null,null,"根据id获取项目实施过程详细信息"]
[46,null,"投资计划","投资计划列表"]
[47,null,null,"根据id获取项目投资计划详细信息"]
[48,"港口经营许可管理","港口经营许可申请","港口经营许可申请列表"]
[49,null,null,"根据id获取港口经营许可申请详细信息"]
[50,null,"港口经营许可变更","港口经营许可变更列表"]
[51,null,null,"根据id获取港口经营许可变更详细信息"]
[52,null,"港口经营许可延续","港口经营许可延续列表"]
[53,null,null,"根据id获取港口经营许可延续详细信息"]
[54,null,"港口经营许可注销","港口经营许可注销列表"]
[55,null,null,"根据id获取港口经营许可注销详细信息"]
[56,"船港货信息管理","港口单船作业申报","港口单船作业申报申请"]
[57,null,null,"港口单船作业申报流程审核(同意，退回)"]
[58,null,null,"港口单船作业申报查看"]
[59,"港口公共信息服务","集装箱航线航班管理","集装箱航线航班列表"]
[60,null,null,"根据id获取集装箱航线航班详细信息(月信息，列表)"]
[61,null,null,"根据id获取集装箱航线航班详细信息(月信息，详细信息)"]
[62,null,"通知公告","通知公告列表"]
[63,null,null,"根据id获取通知公告详细信息"]
[64,"数据统计分析","单船吞吐量统计","单船吞吐量统计"]
[65,null,"港口吞吐量统计分析","港口吞吐量统计分析"]
[66,null,"港口基础设施建设分析","港口基础设施建设分析"]
[67,null,"港口岸线资源和码头利用率分析","区域同类型码头量能比"]
[68,null,null,"单位岸线泊位吞吐量"]
[69,null,null,"港口岸线有效利用率"]
[70,null,"港口作业申报月报表","港口作业申报月报表列表"]
[71,null,null,"根据id获取港口作业申报月报表详细信息"]
[72,null,"航线航班统计","航线航班月度统计表"]
[73,"其他任务","WS框架封装"]
[74,null,"接口API手册"]
[75,null,"上线部署"]
[76,null,"接口联调"]
["合计"]
[]
["说明："]
["1、此报价含6个点的增值税"]
["2、此报价不含差旅费及出差补贴"]
["3、此报价不含需求变更及需求新增"]
["4、单船作业申报的接口直接调用微信端接口"]
["5、此报价含接口开发、接口联调、上线部署、系统测试等阶段"]

{"sheet":"项目计划","index":1,"n_rows":37,"n_cols":5,"rows_kept":37,"cut":false,"hidden":false,"merged":[[0,0,0,4],[2,1,6,1],[7,1,18,1],[19,1,21,1],[22,1,26,1],[28,1,29,1],[30,1,36,1],[2,3,17,3],[19,3,25,3],[27,3,35,3],[2,4,17,4],[19,4,25,4],[27,4,35,4]]}
["项目工作计划"]
["序号","功能模块","子模块","开始时间","结束时间"]
[{"$f":"ROW()-2","v":1},"基础功能","字典信息","2016-11-14","2016-11-23"]
[{"$f":"ROW()-2","v":2},null,"附件"]
[3,null,"港口基础信息查询"]
[4,null,"用户登录鉴权"]
[5,null,"待办列表"]
[6,"经营人信息管理","经营人基本信息"]
[7,null,"码头信息"]
[8,null,"泊位信息"]
[9,null,"仓库信息"]
[10,null,"储罐信息"]
[11,null,"堆场信息"]
[12,null,"人员信息"]
[13,null,"持证信息"]
[14,null,"设施设备信息"]
[15,null,"企业投资信息"]
[16,null,"装卸机械信息"]
[17,null,"接口联调","2016-11-24","2016-11-25"]
[18,"项目信息管理","项目信息","2016-11-28","2016-12-06"]
[19,null,"建设进度管理"]
[20,null,"投资计划"]
[21,"港口经营许可管理","港口经营许可申请"]
[22,null,"港口经营许可变更"]
[23,null,"港口经营许可延续"]
[24,null,"港口经营许可注销"]
[25,null,"接口联调","2016-12-07","2016-12-09"]
[26,"船港货信息管理","港口单船作业申报","2016-12-12","2016-12-16"]
[27,"港口公共信息服务","集装箱航线航班管理"]
[28,null,"通知公告"]
[29,"数据统计分析","单船吞吐量统计"]
[30,null,"港口吞吐量统计分析"]
[{"$f":"ROW()-2","v":31},null,"港口基础设施建设分析"]
[32,null,"港口岸线资源和码头利用率分析"]
[33,null,"港口作业申报月报表"]
[34,null,"航线航班统计"]
[35,null,"接口联调","2016-12-19","2016-12-20"]

{"sheet":"方案说明","index":2,"n_rows":6,"n_cols":1,"rows_kept":6,"cut":false,"hidden":false,"merged":[]}
["接口方案说明："]
["1、不采用直接访问数据库表的方式做数据对接"]
["2、所有的数据均通过webservice接口的方式流转"]
["3、经营人信息管理中的11类基础信息不提供增删改的接口，只提供查询接口"]
["4、项目信息管理模块与港口经营许可管理模块提供工作流程的审批接口"]
["5、提供接口的API开发手册"]