{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":19,"n_cols":12,"rows_kept":19,"cut":false,"hidden":false,"merged":[]}
[null,"序号","所在地","状态","联系人1","联系电话","联系人2","联系电话","备注"]
[null,1,"省局","已部署","杨正",null,null,null,"省厅信息中心"]
["已培训",2,"镇江","已部署，已培训","陈俊",15051143886,"陈海浪",15262904156,"镇江市口岸门户"]
["已培训",3,"南京","已部署，已培训，试运行完善中","殷科",null,null,null,"http://221.226.102.115:8080/yjpt/Main.html "]
["和刘局沟通，周三培训",4,"南通港","已部署","陈处","QQ：250285346",null,null,"已向政务网申请发布外网链接"]
["已培训",5,"常州","已部署","常州市交通局邓处",348872230]
["已培训",6,"淮安","已部署，已培训","漆伟","qq:568358608 手机：15152362307"]
["采购计划已报财政",7,"南通内河港","交通局在搬到新大楼，但是尚未通电，因此耽搁了部署进度，10月中旬完成","程峰","QQ：651552848，手机：13813745446","纪林 1750407863",13606298999]
["缺少外网IP映射，需要省局发文",8,"扬州","局里统筹安排软硬件，周六上午给IP地址进行系统部署","扬州港口管理局何局",13605272130,"钱科","15298461008，QQ：19783617","赵处 15995122002"]
["杨科反馈硬件已采购完毕，尚未安装",9,"泰州","设备正在采购中，大约10月中旬能够部署好","杨科","QQ:475934690，手机：18952611219","戚处","办公室：86881800手机：13337792999","唐科 052386881790"]
[null,10,"盐城港","9月29日招标结束，设备已进场，正在安装部署","胡主任","QQ：369116968，手机：13805103833"]
[null,11,"盐城内河港","分管领导开组织会时进行研究，部署工作","单科","QQ：550188531，手机：18961996506"]
["已部署",12,"镇江内河港","已部署","沈科","QQ：191119212，手机：18912803979","查主任",18912809211,"吕 18912803882","工程师 18912803911",null,"欧主任 80828399 912533016"]
["正在政府采购",13,"连云港","如果一切顺利的情况，从省局发文到部署完成，大约需要1个月的时间","王处","邮箱：LYGKAW@126.com，手机：13775584597"]
["已部署未培训，市县分级功能需要确认",14,"无锡港","已部署","孙科","QQ：3241902，手机：13585072886","钱主任","QQ：472979272，手机：13915350058"]
["杨处反馈还需要几天",15,"苏州港","正在做系统迁移，10月中旬能完成部署","张处","办公室：051268125860","杨处","手机：15950063113\n邮箱：yanghoude@szjt.gov.cn\n     yanghoude@163.com\nQQ: 1248970034"]
["已培训",16,"徐州港","已部署","许处","QQ：812365636，手机：13952169499"]
[null,17,"宿迁","设备已满足条件，但是搬到新楼里基建施工影响了部署进度","宿迁港口局朱科","QQ：250947419，13951194228","钱主任","0527-84381105","张杨科长：qq14244286"]
[null,18,"连云港内河港","情况比较复杂特殊，现由港口办管理港口事务，且两名管理人员都为借调人员，需要时会同业务和信息处室进行处理，业务方面没有危化品企业，没有吞吐量较大的码头，（曾经有过，已被连云港港接管）","港口办"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}