{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["项目体制图","项目整体计划20151030","项目整体计划20151118"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"项目体制图","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"项目整体计划20151030","index":1,"n_rows":73,"n_cols":17,"rows_kept":73,"cut":false,"hidden":false,"merged":[[2,1,2,3],[2,4,2,7],[2,8,2,12],[2,13,2,16],[4,1,40,1],[41,1,54,1],[55,1,57,1],[58,1,60,1],[4,2,13,2],[14,2,21,2],[22,2,27,2],[28,2,35,2],[36,2,39,2],[41,2,47,2],[48,2,49,2],[50,2,51,2],[52,2,53,2],[4,4,13,4],[14,4,21,4],[22,4,27,4],[28,4,35,4],[36,4,39,4],[41,4,47,4],[48,4,49,4],[50,4,51,4],[52,4,53,4],[55,4,57,4],[58,4,60,4],[4,5,13,5],[14,5,21,5],[22,5,27,5],[28,5,35,5],[36,5,39,5],[41,5,47,5],[48,5,49,5],[50,5,51,5],[52,5,53,5],[55,5,57,5],[58,5,60,5],[4,6,13,6],[14,6,21,6],[22,6,27,6],[28,6,35,6],[36,6,39,6],[41,6,47,6],[48,6,49,6],[50,6,51,6],[52,6,53,6],[55,6,57,6],[58,6,60,6],[4,7,13,7],[14,7,21,7],[22,7,27,7],[28,7,35,7],[36,7,39,7],[41,7,47,7],[48,7,49,7],[50,7,51,7],[52,7,53,7],[55,7,57,7],[58,7,60,7],[6,13,9,13],[10,13,13,13],[14,13,20,13],[22,13,23,13],[24,13,27,13],[28,13,35,13],[36,13,39,13],[48,13,49,13],[50,13,51,13],[52,13,53,13],[55,13,57,13],[58,13,60,13],[6,14,9,14],[10,14,13,14],[14,14,20,14],[22,14,23,14],[24,14,27,14],[28,14,35,14],[36,14,39,14],[48,14,49,14],[50,14,51,14],[52,14,53,14],[55,14,57,14],[58,14,60,14],[6,15,9,15],[10,15,13,15],[14,15,20,15],[22,15,23,15],[24,15,27,15],[28,15,35,15],[36,15,39,15],[48,15,49,15],[50,15,51,15],[52,15,53,15],[55,15,57,15],[58,15,60,15],[6,16,9,16],[10,16,13,16],[14,16,20,16],[22,16,23,16],[24,16,27,16],[28,16,35,16],[36,16,39,16],[48,16,49,16],[50,16,51,16],[52,16,53,16],[55,16,57,16],[58,16,60,16],[0,1,1,16]]}
[null,"项目整体实施计划"]
[]
[null,"功能模块",null,null,"详细设计阶段",null,null,null,"开发阶段",{"$nulls":4},"测试阶段"]
[null,"一级任务","二级任务","三级任务","开始时间","完成时间","担当者","状态","开始时间","完成时间","担当者","NEW","状态","开始时间","完成时间","担当者","状态"]
[null,"建设与经营管理子系统","港口建设管理模块","投资计划管理","2015-11-02","2015-11-04","徐惠香","未进行","2015-11-03","2015-11-12","聂文轩","聂文轩","未进行","2015-11-16","2015-11-17","A","未进行"]
[null,null,null,"项目建设进度管理",{"$nulls":4},"2015-11-12","2015-11-20","聂文轩","聂文轩","未进行","2015-11-25","2015-11-26","A","未进行"]
[null,null,null,"港口岸线利用审批",{"$nulls":4},"2015-11-04","2015-11-07","尹允彤","尹允彤","未进行","2015-11-18","2015-11-19","A","未进行"]
[null,null,null,"项目审批、核准、备案",{"$nulls":4},"2015-11-09","2015-11-10","尹允彤","尹允彤","未进行"]
[null,null,null,"初步设计审批管理",{"$nulls":4},"2015-11-11","2015-11-12","尹允彤","尹允彤","未进行"]
[null,null,null,"施工图设计审批管理",{"$nulls":4},"2015-11-13","2015-11-14","尹允彤","尹允彤","未进行"]
[null,null,null,"开工备案管理",{"$nulls":4},"2015-11-16","2015-11-17","尹允彤","尹允彤","未进行","2015-11-21","2015-11-21","A","未进行"]
[null,null,null,"交工验收备案管理",{"$nulls":4},"2015-11-18","2015-11-18","尹允彤","尹允彤","未进行"]
[null,null,null,"试运行备案管理",{"$nulls":4},"2015-11-19","2015-11-19","尹允彤","尹允彤","未进行"]
[null,null,null,"竣工验收管理",{"$nulls":4},"2015-11-20","2015-11-21","尹允彤","尹允彤","未进行"]
[null,null,"港口经营管理","港口经营人相关信息管理","2015-11-02","2015-11-04","李前锟","未进行","2015-11-02","2015-11-06","徐惠香、赵和章","徐惠香、赵和章","未进行","2015-11-23","2015-11-24","A","未进行"]
[null,null,null,"港口经营许可申请",{"$nulls":4},"2015-11-07","2015-11-09","徐惠香、 赵和章","徐惠香、蒋碧瑜","未进行"]
[null,null,null,"港口经营许可变更",{"$nulls":4},"2015-11-10","2015-11-11","徐惠香、 赵和章","徐惠香、蒋碧瑜","未进行"]
[null,null,null,"港口经营许可延续",{"$nulls":4},"2015-11-12","2015-11-13","徐惠香、 赵和章","徐惠香、蒋碧瑜","未进行"]
[null,null,null,"港口经营注销管理",{"$nulls":4},"2015-11-14","2015-11-16","徐惠香、 赵和章","徐惠香、蒋碧瑜","未进行"]
[null,null,null,"港口理货许可管理",{"$nulls":4},"2015-11-17","2015-11-19","徐惠香、 赵和章","徐惠香、蒋碧瑜","未进行"]
[null,null,null,"港口经营监督检查",{"$nulls":4},"2015-11-20","2015-11-21","徐惠香、 赵和章","徐惠香、蒋碧瑜","未进行"]
[null,null,null,"船港货作业信息管理",{"$nulls":4},"2015-11-09","2015-11-14","赵航","赵航","未进行","2015-11-16","2015-11-16","A","未进行"]
[null,null,"港口统计与运行分析","单船吞吐量统计","2015-11-07","2015-11-12","李前锟","未进行","2015-11-13","2015-11-14","宋涛","宋涛","未进行","2015-11-20","2015-11-20","A","未进行"]
[null,null,null,"港口吞吐量分析",{"$nulls":4},"2015-11-16","2015-11-17","宋涛","宋涛","未进行"]
[null,null,null,"港口基础设施建设分析",{"$nulls":4},"2015-11-18","2015-11-20","宋涛","宋涛","未进行","2015-11-27","2015-11-28","A","未进行"]
[null,null,null,"港口岸线资源和码头设施利用效率分析",{"$nulls":4},"2015-11-09","2015-11-12","马尚妮","马尚妮","未进行"]
[null,null,null,"港口能源消耗及经营财务分析",{"$nulls":4},"2015-11-13","2015-11-16","马尚妮","马尚妮","未进行"]
[null,null,null,"港口与经济关联分析",{"$nulls":4},"2015-11-17","2015-11-20","马尚妮","马尚妮","未进行"]
[null,null,"港口基础信息管理","行政管理部门信息管理","2015-11-02","2015-11-04","马尚妮","未进行","2015-11-02","2015-11-05","赵航","赵航","未进行","2015-11-13","2015-11-14","A","未进行"]
[null,null,null,"行政管理人员信息管理",{"$nulls":4},"2015-11-06","2015-11-07","赵航","赵航","未进行"]
[null,null,null,"港口、港区、作业区管理",{"$nulls":4},"2015-11-02","2015-11-09","孙正","孙正","未进行"]
[null,null,null,"锚地",{"$nulls":4},"2015-11-10","2015-11-12","孙正","孙正","未进行"]
[null,null,null,"岸线",{"$nulls":4},"2015-11-02","2015-11-05","蒋碧瑜","孙正","未进行"]
[null,null,null,"防波堤",{"$nulls":4},"2015-11-06","2015-11-07","蒋碧瑜","孙正","未进行"]
[null,null,null,"进港航道",{"$nulls":4},"2015-11-09","2015-11-10","蒋碧瑜","孙正","未进行"]
[null,null,null,"船舶信息",{"$nulls":4},"2015-11-11","2015-11-12","蒋碧瑜","孙正","未进行"]
[null,null,"公共服务信息管理","企业诚信管理","2015-11-05","2015-11-07","徐惠香","未进行","2015-11-12","2015-11-14","梁赞","梁赞","未进行","2015-11-30","2015-11-30","A","未进行"]
[null,null,null,"集装箱航线航班管理",{"$nulls":4},"2015-11-13","2015-11-17","孙正","孙正","未进行"]
[null,null,null,"货种监督及公示",{"$nulls":4},"2015-11-18","2015-11-21","孙正","孙正","未进行"]
[null,null,null,"通知公告",{"$nulls":4},"2015-11-13","2015-11-21","蒋碧瑜","徐惠香、蒋碧瑜","未进行"]
[null,null,"系统管理","用户、角色、权限",{"$nulls":4},"2015-11-02","2015-11-02","梁赞","梁赞","未进行",null,null,null,"未进行"]
[null,"港口综合智能监控子系统","资源管理模块","通用专题图","2015-11-03","2015-11-07","宋涛","未进行","2015-11-03","2015-11-05","沈瞳周、蒋筱凡","沈瞳周、蒋筱凡","未进行","2015-11-18","2015-11-18","B","未进行"]
[null,null,null,"船舶动态专题图",{"$nulls":4},"2015-11-06","2015-11-09","沈瞳周、蒋筱凡","沈瞳周、蒋筱凡","未进行","2015-11-19","2015-11-19","B","未进行"]
[null,null,null,"安全监管专题图",{"$nulls":4},"2015-11-10","2015-11-12","沈瞳周、蒋筱凡","沈瞳周、蒋筱凡","未进行","2015-11-20","2015-11-20","B","未进行"]
[null,null,null,"项目建设专题图",{"$nulls":4},"2015-11-13","2015-11-16","沈瞳周、蒋筱凡","沈瞳周、蒋筱凡","未进行","2015-11-21","2015-11-21","B","未进行"]
[null,null,null,"港口经营专题图",{"$nulls":4},"2015-11-17","2015-11-19","沈瞳周、蒋筱凡","沈瞳周、蒋筱凡","未进行","2015-11-25","2015-11-25","B","未进行"]
[null,null,null,"港口规划专题图",{"$nulls":4},"2015-11-20","2015-11-21","沈瞳周、蒋筱凡","沈瞳周、蒋筱凡","未进行","2015-11-26","2015-11-26","B","未进行"]
[null,null,null,"锚地动态监管专题图",{"$nulls":8},"未进行"]
[null,null,"安全监管模块","危货作业统计","2015-11-05","2015-11-07","马尚妮","未进行","2015-11-09","2015-11-10","宋涛","宋涛","未进行","2015-11-27","2015-11-27","B","未进行"]
[null,null,null,"危货作业查询",{"$nulls":4},"2015-11-11","2015-11-12","宋涛","宋涛","未进行"]
[null,null,"建设经营模块","单船吞吐量统计","2015-11-05","2015-11-05","李前锟","未进行","2015-11-16","2015-11-18","赵航","赵航","未进行","2015-11-28","2015-11-28","B","未进行"]
[null,null,null,"单船吞吐量查询",{"$nulls":4},"2015-11-19","2015-11-21","赵航","赵航","未进行"]
[null,null,"锚地调度模块","锚地动态",{"$nulls":8},"未进行"]
[null,null,null,"锚地计划",{"$nulls":8},"未进行"]
[null,null,"办公自动化","待办收发文","2015-11-02","2015-11-02","李前锟","设计完成","2015-11-02","2015-11-03","尹允彤","尹允彤","未进行","2015-11-16","2015-11-16","B","未进行"]
[null,"数据交换与共享平台","省级与所在地系统",null,"2015-11-02","2015-11-05","石勇","未进行","2015-11-16","2015-11-21","石勇、顾许磊","石勇、顾许磊","未进行","2015-11-23","2015-11-24","B","未进行"]
[null,null,"省厅系统之间",{"$nulls":5},"2015-11-09","2015-11-14","石勇、顾许磊","石勇、顾许磊","未进行"]
[null,null,"外部系统",{"$nulls":5},"2015-11-02","2015-11-07","石勇、顾许磊","石勇、顾许磊","未进行"]
[null,"RTX即时通讯子系统","即时通讯",null,"2015-11-02","2015-11-03","梁赞","未进行","2015-11-07","2015-11-09","梁赞","梁赞","未进行","2015-11-13","2015-11-13","B","未进行"]
[null,null,"反向登录",{"$nulls":5},"2015-11-10","2015-11-10","梁赞","梁赞","未进行"]
[null,null,"信息推送",{"$nulls":5},"2015-11-11","2015-11-11","梁赞","梁赞","未进行"]
[null,"微信移动应用","单船申报",null,"2015-11-06","2015-11-06","李前锟","未进行",null,null,"王浩","王浩","未进行","2015-11-14","2015-11-14","B","未进行"]
[]
[]
[null,"个别任务"]
[null,null,"担当者"]
[null,"需求分析","李前锟、马尚妮、徐惠香、宋涛、石勇"]
[null,"数据库设计文档","顾广安"]
[null,"数据库脚本制作","顾广安"]
[null,"开发规约","梁赞"]
[null,"sample画面","梁赞"]
[null,"美术UI风格确定","顾广安"]
[null,"测试人员进场","顾广安"]

{"sheet":"项目整体计划20151118","index":2,"n_rows":58,"n_cols":11,"rows_kept":58,"cut":false,"hidden":false,"merged":[[2,1,2,3],[2,4,2,5],[2,6,2,7],[2,8,2,9],[2,10,2,11],[3,10,3,11],[4,10,4,11],[5,10,5,11],[6,10,6,11],[7,10,7,11],[8,10,8,11],[9,10,9,11],[10,10,10,11],[11,10,11,11],[12,10,12,11],[13,10,13,11],[14,10,14,11],[15,10,15,11],[16,10,16,11],[17,10,17,11],[18,10,18,11],[19,10,19,11],[20,10,20,11],[21,10,21,11],[22,10,22,11],[23,10,23,11],[24,10,24,11],[25,10,25,11],[26,10,26,11],[27,10,27,11],[28,10,28,11],[29,10,29,11],[30,10,30,11],[31,10,31,11],[32,10,32,11],[33,10,33,11],[34,10,34,11],[35,10,35,11],[36,10,36,11],[37,10,37,11],[38,10,38,11],[39,10,39,11],[40,10,40,11],[41,10,41,11],[42,10,42,11],[43,10,43,11],[44,10,44,11],[45,10,45,11],[46,10,46,11],[47,10,47,11],[4,1,29,1],[30,1,40,1],[41,1,43,1],[44,1,46,1],[4,2,6,2],[7,2,13,2],[14,2,17,2],[18,2,26,2],[27,2,28,2],[30,2,35,2],[36,2,37,2],[38,2,39,2],[4,4,6,4],[7,4,13,4],[14,4,17,4],[18,4,26,4],[27,4,28,4],[30,4,35,4],[36,4,37,4],[38,4,39,4],[41,4,43,4],[44,4,46,4],[4,5,6,5],[7,5,13,5],[14,5,17,5],[18,5,26,5],[27,5,28,5],[30,5,35,5],[36,5,37,5],[38,5,39,5],[41,5,43,5],[44,5,46,5],[4,6,6,6],[8,6,13,6],[18,6,26,6],[4,8,6,8],[7,8,12,8],[14,8,15,8],[16,8,17,8],[18,8,26,8],[27,8,28,8],[36,8,37,8],[38,8,39,8],[41,8,43,8],[44,8,46,8],[7,9,12,9],[14,9,15,9],[16,9,17,9],[18,9,26,9],[27,9,28,9],[36,9,37,9],[38,9,39,9],[41,9,43,9],[44,9,46,9],[0,1,1,11]]}
[null,"项目整体实施计划"]
[]
[null,"功能模块",null,null,"详细设计",null,"编码开发",null,"集成测试",null,"备注"]
[null,"一级任务","二级任务","三级任务","担当者","状态","担当者","状态","担当者","状态"]
[null,"建设与经营管理子系统","港口建设管理模块","项目信息管理","徐惠香","用户确认完成","徐惠香","开发中","邓久红","未进行"]
[null,null,null,"建设进度管理",null,null,null,"未进行",null,"未进行"]
[null,null,null,"投资计划管理",null,null,null,"未进行",null,"未进行"]
[null,null,"港口经营管理","港口经营人相关信息管理","李前锟","用户确认完成","梁赞","开发中","邓久红","未进行"]
[null,null,null,"港口经营许可申请",null,null,"徐惠香","开发中"]
[null,null,null,"港口经营许可变更",null,null,null,"未进行"]
[null,null,null,"港口经营许可延续",null,null,null,"未进行"]
[null,null,null,"港口经营注销管理",null,null,null,"未进行"]
[null,null,null,"港口经营监督检查",null,null,null,"未进行"]
[null,null,null,"船港货作业信息管理",null,null,null,"未进行","邓久红","未进行"]
[null,null,"港口统计与运行分析","单船吞吐量统计","李前锟","未进行",null,"未进行","邓久红","未进行"]
[null,null,null,"港口吞吐量分析",null,null,null,"未进行"]
[null,null,null,"港口岸线资源和码头设施利用效率分析",null,null,null,"未进行","邓久红","未进行"]
[null,null,null,"港口能源消耗及经营财务分析",null,null,null,"未进行"]
[null,null,"港口基础信息管理","行政单位信息管理","马尚妮","设计完成","梁赞","开发完成","邓久红","未进行"]
[null,null,null,"港口",null,null,null,"开发完成"]
[null,null,null,"港区",null,null,null,"开发完成"]
[null,null,null,"作业区",null,null,null,"开发完成"]
[null,null,null,"锚地",null,null,null,"开发完成"]
[null,null,null,"岸线",null,null,null,"开发完成"]
[null,null,null,"防波堤",null,null,null,"开发完成"]
[null,null,null,"进港航道",null,null,null,"开发完成"]
[null,null,null,"船舶信息",null,null,null,"未进行"]
[null,null,"公共服务","集装箱航线航班管理",null,null,"孙正","未进行","邓久红","未进行"]
[null,null,null,"通知公告",null,null,"梁赞","开发中"]
[null,null,"系统管理","用户、角色、权限",null,"设计完成","梁赞","开发完成","邓久红","未进行"]
[null,"港口综合智能监控子系统","资源管理模块","通用专题图","宋涛","设计完成","沈瞳周","开发中","邓久红","未进行"]
[null,null,null,"船舶动态专题图",null,null,"沈瞳周","未进行","邓久红","未进行"]
[null,null,null,"安全监管专题图",null,null,"沈瞳周","未进行","邓久红","未进行"]
[null,null,null,"项目建设专题图",null,null,"沈瞳周","未进行","邓久红","未进行"]
[null,null,null,"港口经营专题图",null,null,"沈瞳周","未进行","邓久红","未进行"]
[null,null,null,"港口规划专题图",null,null,"沈瞳周","未进行","邓久红","未进行"]
[null,null,"安全监管模块","危货作业统计","马尚妮","设计完成","宋涛","开发完成","邓久红","未进行"]
[null,null,null,"危货作业查询",null,null,"宋涛","未进行"]
[null,null,"建设经营模块","单船吞吐量统计","李前锟","未进行","宋涛","未进行","邓久红","未进行"]
[null,null,null,"单船吞吐量查询",null,null,"宋涛","未进行"]
[null,null,"办公自动化","待办收发文","李前锟","设计完成","宋涛","开发中","邓久红","未进行"]
[null,"数据交换与共享平台","省级与所在地系统",null,"石勇","设计中","石勇","未进行","邓久红","未进行"]
[null,null,"省厅系统之间",null,null,null,"石勇","未进行"]
[null,null,"外部系统",null,null,null,"石勇","未进行"]
[null,"RTX即时通讯子系统","即时通讯",null,"梁赞","未进行","梁赞","未进行","邓久红","未进行"]
[null,null,"反向登录",null,null,null,"梁赞","未进行"]
[null,null,"信息推送",null,null,null,"梁赞","未进行"]
[null,"微信移动应用","单船申报",null,"李前锟","未进行","王浩","未进行","邓久红","未进行"]
[]
[]
[null,"个别任务"]
[null,null,"担当者"]
[null,"需求分析","李前锟、马尚妮、徐惠香、宋涛、石勇"]
[null,"数据库设计文档","顾广安"]
[null,"数据库脚本制作","顾广安"]
[null,"开发规约","梁赞"]
[null,"sample画面","梁赞"]
[null,"美术UI风格确定","顾广安"]