{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["变更申请单"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"变更申请单","index":0,"n_rows":30,"n_cols":5,"rows_kept":30,"cut":false,"hidden":false,"merged":[[0,0,0,5],[1,1,1,5],[3,0,3,5],[4,0,9,0],[4,1,9,5],[2,1,2,2],[2,4,2,5],[16,0,16,5],[17,1,17,5],[18,1,18,5],[10,0,15,0],[10,1,10,2],[10,3,10,5],[11,1,11,2],[26,1,26,2],[26,4,26,5],[11,3,11,5],[20,0,20,5],[21,0,24,0],[21,1,24,5],[25,1,25,5],[19,1,19,5],[12,1,12,2],[12,3,12,5],[13,1,13,2],[13,3,13,5],[14,1,14,2],[14,3,14,5],[15,1,15,2],[15,3,15,5],[27,0,27,5],[28,1,28,2],[28,4,28,5],[29,1,29,2],[29,4,29,5]]}
["变更申请单"]
["申请单编号","20140508-1"]
["申请人","肖敏",null,"申请时间","2014-05-08"]
["变更说明"]
["变更内容及原因","1.大屏右侧3*2部分的精细化展示图表功能，包括1个收费站，1个服务区，1个枢纽\n变更原因：在设计过程中，项目组认为增加此功能，既可以优化用户体验，又利于公司技术沉淀，因此内部提出的需求增加\n\n"]
[]
[]
[]
[]
[]
["需变更的文档或代码","文件名",null,"变更内容"]
[null,"需求规格说明书-广靖锡澄高速公路营运管理平台",null,"修改M1-F01、M2-F01、M6-F01功能，增加精细化展示图标功能。"]
[null,"项目整体计划-江苏广靖锡澄高速公路营运管理平台",null,"调整人力资源"]
[]
[]
[]
["变更评估"]
["估计工作量","60人天（修改需求文档和已完成的设计文档的工作量，以及后续增加的开发、测试工作量）"]
["估计工期影响","无（增加人手）"]
["估计其他成本","无"]
["审批"]
["审批意见","同意"]
[]
[]
[]
["结论","同意变更"]
["审批人","施展",null,"审批时间","2014-05-08"]
["跟踪"]
["执行人","肖敏",null,"执行时间","2014-05-10"]
["执行确认人","施展",null,"执行确人时间","2014-05-10"]