{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["变更管理表"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"变更管理表","index":0,"n_rows":5,"n_cols":12,"rows_kept":5,"cut":false,"hidden":false,"merged":[[0,0,0,11],[1,0,1,5],[1,6,1,11],[3,4,4,4],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,6,4,6],[3,9,4,9],[3,10,4,10],[3,11,4,11],[3,7,4,7],[3,8,4,8]]}
["变更管理表"]
["变更说明",{"$nulls":5},"变更情况跟踪"]
["变更申请单编号","申请人","申请时间","变更内容","申请结果","需变更的配置项名称","当前状态","变更执行日期","变更执行人","影响基线","变更后版本","备注"]
["20140508-01","肖敏","2014-05-08","需求变更：大屏右侧3*2部分的精细化展示图表功能，包括1个收费站，1个服务区，1个枢纽。\n计划变更：调整后续工作的资源。","同意变更","需求规格说明书-广靖锡澄高速公路营运管理平台","已完成","2014-05-10","肖敏","需求基线","需求基线-20140510"]
[{"$nulls":5},"项目整体计划-江苏广靖锡澄高速公路营运管理平台"]