{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["EPG月度报告"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"EPG月度报告","index":0,"n_rows":34,"n_cols":7,"rows_kept":34,"cut":false,"hidden":false,"merged":[[0,0,0,7],[1,0,1,7],[2,0,2,7],[3,1,3,2],[3,5,3,7],[4,1,4,2],[4,5,4,7],[5,1,5,2],[5,5,5,7],[6,1,6,2],[6,5,6,7],[7,0,7,7],[8,0,8,2],[8,4,8,5],[8,6,8,7],[9,0,9,2],[9,4,9,5],[9,6,9,7],[10,0,10,2],[10,4,10,5],[10,6,10,7],[11,0,11,2],[11,4,11,5],[11,6,11,7],[12,0,12,2],[12,4,12,5],[12,6,12,7],[13,0,13,2],[13,4,13,5],[13,6,13,7],[14,0,14,2],[14,4,14,5],[14,6,14,7],[15,0,15,2],[15,4,15,5],[15,6,15,7],[16,0,16,7],[17,0,17,2],[17,4,17,5],[17,6,17,7],[20,0,20,2],[20,4,20,5],[20,6,20,7],[18,0,18,2],[18,4,18,5],[18,6,18,7],[19,0,19,2],[19,4,19,5],[19,6,19,7],[21,0,21,2],[21,4,21,5],[21,6,21,7],[22,0,22,2],[22,4,22,5],[22,6,22,7],[23,0,23,2],[23,4,23,5],[23,6,23,7],[24,0,24,7],[25,0,32,7],[33,1,33,3],[33,5,33,7]]}
["EPG月度报告"]
["2014年6月"]
["本月完成或仍在进行中的改进课题"]
["编号","课题专项",null,"负责人","计划完成\n时间","当前状态"]
[1,"建立管理体系",null,"施展","2015-05-30","试点运行中"]
[2,"建立与维护资产库",null,"袁晓冬","2014-07-18","已完成资产库的初始化并首次正式发布"]
[]
["本月工作情况"]
["任务",null,null,"责任人","参与人",null,"状态"]
["筛选组织资产入库","筛选组织资产入库","筛选组织资产入库","纪蓉","EPG全体成员","EPG全体成员","按时完成"]
["收集历史项目度量数据，建立度量库","收集历史项目度量数据，建立度量库","收集历史项目度量数据，建立度量库","纪蓉","EPG全体成员","EPG全体成员","按时完成"]
["发布组织资产库","发布组织资产库","发布组织资产库","袁晓冬",null,null,"按时完成"]
["编写并提交5月份《EPG月度报告》",null,null,"纪蓉",null,null,"按时完成"]
[]
[]
[]
["下月工作计划"]
["任务",null,null,"责任人","参与人",null,"计划完成时间"]
["收集反馈意见，完善资产库",null,null,"袁晓冬",null,null,"2014-07-18"]
["编写并提交6月份《EPG月度报告》",null,null,"纪蓉",null,null,"2014-07-02"]
[]
[]
[]
[]
["问题及解决情况"]
["无"]
{"$rows_empty":7}
["汇报人","纪蓉",null,null,"汇报日期","2014-07-02"]