{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["0904"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"0904","index":0,"n_rows":199,"n_cols":31,"rows_kept":199,"flags":["formulas_cached_only"]}
["Bug编号","所属产品","所属模块","所属项目","相关需求","相关任务","Bug标题","关键词","严重程度","Bug类型","操作系统","浏览器","重现步骤","Bug状态","是否确认","由谁创建","创建日期","影响版本","指派给","解决者","解决方案","解决版本","解决日期","由谁关闭","关闭日期","重复ID","相关Bug","相关用例","最后修改者","最后修改日期","附件"]
[1,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"待办事项、事件调度点击进入事件编辑界面，界面标题统一为事件处置",null,3,"代码错误",null,null,"点击待办事项进入事件列表页面，页面抬头显示的是待办事项，修改为事件处置\r\n\r\n \r\n\r\n\n\r\n\r\n指挥调度>事件填报，点击确定进入下面的页面，上方的处置预案也修改为事件处置\r\n\r\n ","已解决","已确认","朱玲","2014-06-16","演示版本(#2)","朱玲","潘彩侠","已解决","演示版本(#2)","2014-06-16",null,"0000-00-00",0,null,0,"潘彩侠","2014-06-16"]
[2,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0," 方向从上行、下行该成：北京方向、上海方向，客户比较习惯这种输入方式。【细化需求】",null,4,"其他",null,null,"[步骤]\r\n事件快速填报页面，方向从上行、下行该成：北京方向、上海方向\r\n[结果]\r\n[期望]","已解决","已确认","朱玲","2014-06-16","演示版本(#2)","朱玲","曹碧蓉","已解决","演示版本(#2)","2014-06-16",null,"0000-00-00",0,null,0,"朱玲","2014-06-16"]
[3,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,"用户分配按钮权限功能(1)","发布信息的按钮",null,4,"界面优化","win7","other","\r\n为了保证他们业务人员不要发生误操作，请将其中一个工作优先做一下，就是把这个按钮换成“上报联网中心”，点击后在弹出一个提示“将上报联网中心，是否确认”，确认后就将数据推给前置机了。\r\n\r\n\n\r\n\r\n","已解决","已确认","王晖","2014-06-16","演示版本(#2)","朱玲","曹碧蓉","已解决","演示版本(#2)","2014-06-16",null,"0000-00-00",0,null,0,"朱玲","2014-06-12","按钮修改问题\n"]
[4,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"出现无法保存问题",null,3,"代码错误","win7","maxthon","当我的输入不存在问题的时候，我点击保存按钮，出现无法保存的情况，不知道是什么原因，求解答\r\n\r\n ","已解决","已确认","肖敏","2014-06-16","演示版本(#2)","朱玲","潘彩侠","已解决","演示版本(#2)","2014-06-16",null,"0000-00-00",0,null,0,"朱玲","2014-06-16"]
[5,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"输入字符与提示字符存在不一致情况",null,3,"代码错误","win7","maxthon","\r\n \r\n\r\n\n\r\n","已解决","已确认","肖敏","2014-06-16","Trunk(#trunk)","朱玲","潘彩侠","已解决","演示版本(#2)","2014-06-16",null,"0000-00-00",0,null,0,"朱玲","2014-06-16"]
[6,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"交通拥堵类型事件，页面的拥堵情况文本框后，添加km单位",null,2,"界面优化",null,null,"\r\n\r\n","已解决","已确认","朱玲","2014-06-16","演示版本(#2)","朱玲","潘彩侠","已解决","演示版本(#2)","2014-06-17",null,"0000-00-00",0,null,0,"潘彩侠","2014-06-17"]
[7,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"事件填报中的事件类型与预案处理的时间类型出现不一致的情况",null,3,"代码错误",null,null,"[步骤]在事件填报中选择了事件类型为“不法行为”（见截图）\r\n\r\n \r\n[结果] 在预案处理中，基本类型中，出现了其他类型（见截图）\r\n\r\n\n\r\n\r\n[ 期望，希望开发人员处理下，谢谢~~ ","已关闭","已确认","秦洁","2014-06-16","演示版本(#2)","Closed","曹碧蓉","设计如此",null,"2014-06-16","朱玲","2014-06-16",0,null,0,"朱玲","2014-06-16"]
[8,"gxjc营运管理项目(#1)","运行监测(#1)","GXJC(#1)",0,0,"关于事件发生的顺序展示问题",null,3,"代码错误","windows","ie11","\r\n\n\r\n\r\n 目前事件如果发生在同一个桩号发生图标会重叠在一起无法查看，请要求开发人员做一下修改，如何让同一桩号先后发生的事件都能被有效查看。\n\r\n\r\n\r\n\n\r\n","已解决","已确认","秦洁","2014-06-16","825版本(#3)","朱玲","陈继伟","延期处理","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-22"]
[9,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"修改事件ID生成规则",null,3,"配置相关",null,null,"事件ID编码方式如下：\n\r\n\n\r\nCCCYYYYMMDDXXXXXXXXXXXXX\n\r\n其中：CCC为路桥公司编码（按照数据约定1.0，请把这个作为可配置的参数）\n\r\n          YYYYMMDD为事件录入时间，如：20140610\n\r\n          XXXXXXXXXXXXX共13位数字，作为事件序号（在各路公司内保证唯一性）\r\n\n\r\n\r\n\r\n\n\r\n","已解决","已确认","朱玲","2014-06-16","演示版本(#2)","徐永刚","徐永刚","已解决","演示版本(#2)","2014-06-16",null,"0000-00-00",0,null,0,"朱玲","2014-06-16"]
[10,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"出现时间发生方向时的错误",null,3,"代码错误",null,null,"步骤： 在指挥调度中，选择平时交通运营管理，方向选择双向\r\n\r\n\r\n\r\n[结果]\r\n\r\n发现方向在处置预算中，没有关联到。","已解决","已确认","秦洁","2014-06-16","演示版本(#2)","秦洁","潘彩侠","已解决","演示版本(#2)","2014-06-17",null,"0000-00-00",0,null,0,"潘彩侠","2014-06-17"]
[11,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"待办事件列表要增加方向列数据显示",null,2,"界面优化",null,null,"\r\n待办事件列表要增加方向列显示\r\n\r\n   \r\n\r\n\r\n\n\r\n\r\n\r\n\n\r\n","已解决","已确认","朱玲","2014-06-16","演示版本(#2)","朱玲","潘彩侠","已解决","演示版本(#2)","2014-06-16",null,"0000-00-00",0,null,0,"潘彩侠","2014-06-16"]
[12,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"修改图标为最新版美工提供图标",null,2,"界面优化",null,null,"这几个图层的图标麻烦换成顾丽珺做的图标\n\r\n\n\r\n \n\r\n\r\n\r\n\n\r\n","激活","已确认","朱玲","2014-06-16","演示版本(#2)","陈继伟","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[13,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"事件处理的事件类型问题",null,3,"代码错误",null,null,"问题描述：\r\n      在点击事件填报中，如果事件类型点击的是”车辆故障“，进入预案处理界面后，发现基本信息中，显示的事件类型是”上海到北京“（详见截图），是否是设计时候的要求，不清楚，麻烦看下，多谢~~\r\n     \r\n    \r\n","已解决","已确认","秦洁","2014-06-17","演示版本(#2)","朱玲","潘彩侠","已解决","演示版本(#2)","2014-06-30",null,"0000-00-00",0,null,0,"潘彩侠","2014-07-08"]
[14,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"关于图片和图片位置的问题",null,3,"代码错误",null,null,"问题描述：\r\n      在情报板中的，情报板信息发布版块中，播放内容设置                                                      如果对于图片是选择无图片的，是否可以将图片位置的选择不可选或者直接隐藏掉？这个亮度方面的，是不是也可以优化下？\r\n麻烦看下问题，谢谢~~","激活","已确认","秦洁","2014-06-17","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"秦洁","2014-06-17"]
[15,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"关于信息发布的播放内容设置的条件选择",null,3,"代码错误",null,null,"问题描述：\r\n       在信息发布的播放内容设置中，输入一段问题，有几个对输入内容的调整按钮，不起作用，\r\n       例如“文字字体”，“显示方式”,\"屏幕类型“，”发布方式“，”字间间距“几个按钮的功能，点击后，对应的字体没有变化。\r\n   麻烦你核实下。","激活","已确认","秦洁","2014-06-17","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[16,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"上报联网中心失败问题",null,3,"代码错误",null,null,"问题描述：\r\n       在警卫任务，抛洒物中，如果点击上报联网中心（前提条件是里面填写的单子内容是正确的），则出现不能上报成功，而同样的问题，在群体事件中，如果点击上报联网中心（里面的内容填写正确的）， 则可以上报成功。\r\n      麻烦看下这个是什么问题，谢谢~~","激活","已确认","秦洁","2014-06-17","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"秦洁","2014-06-17"]
[17,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"关于经度和纬度问题",null,3,"代码错误",null,null,"[步骤]在事件处理中，填写经度和纬度，出现了问题。\r\n[结果]\r\n\r\n问题： 1 经度和纬度是存在负数的，这个不允许存在。\r\n          2 对于经度的提示，让输入正确的纬度信息，纬度的提示，是让输入正确的经度信息。\r\n麻烦核实下信息，谢谢~","激活","已确认","秦洁","2014-06-17","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[18,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC","20140617运行监测问题单(#8)",0,"情报板K1060+445地图上没有。",null,3,"代码错误",null,null," \n","激活","已确认","朱玲","2014-06-18","演示版本(#2)","陈继伟","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[19,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC","20140617运行监测问题单(#8)",0,"K1061-K1056桩号没有经纬度，是否可以计算获得？",null,3,"代码错误",null,null,"\r\n\r\n       K1061-K1056 桩号没有经纬度，是否可以计算获得？   \r\n\r\n  \n","激活","已确认","朱玲","2014-06-18","演示版本(#2)","陈继伟","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[20,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC","20140617运行监测问题单(#8)",0,"摄像机K1053+528的位置应该在情报板K1053+520之后，目前是反的，可将两设备经纬度对调一下",null,3,"代码错误",null,null,"\r\n\r\n摄像机 K1053+528 的位置应该在情报板 K1053+520 之后，目前是反的，可将两设备经纬度对调一下 \r\n\r\n    \n\r\n \r\n\r\n\r\n\r\n\n\r\n\r\n\r\n\n\r\n","激活","已确认","朱玲","2014-06-18","演示版本(#2)","陈继伟","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[21,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC","20140617运行监测问题单(#8)",0,"情报板K1039+600地图上没有。",null,3,"代码错误",null,null,"\r\n\r\n      情报板 K1039+600 地图上没有。   \r\n\r\n  \n","激活","已确认","朱玲","2014-06-18","演示版本(#2)","陈继伟","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[22,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC","20140617运行监测问题单(#8)",0," 摄像机 K1038+685 地图上没有",null,2,"代码错误",null,null,"\r\n\r\n 一、摄像机、情报板、车检器问题：    \r\n\r\n 1、     摄像机 K1038+685 地图上没有。   \r\n\r\n    \n\r\n \r\n\r\n\r\n\r\n\r\n\n\r\n\r\n\r\n\n\r\n","激活","已确认","朱玲","2014-06-18","演示版本(#2)","陈继伟","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[23,"gxjc营运管理项目(#1)","辅助管理(#4)","GXJC(#1)",0,0,"系统管理：系统常量管理页面，点击新增页面中的“有效标志”没有必填的星号，但是保存时却提示为必填",null,3,"代码错误",null,null,"系统管理：系统常量管理页面，点击新增页面中的“有效标志”没有必填的星号，但是保存时却提示为必填\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲"]
[24,"gxjc营运管理项目(#1)","信息发布(#3)","GXJC(#1)",0,0,"在情报板信息发布页面，添加信息完成后，点击“发布”按钮，弹出“程序出错！”的提示。",null,3,"代码错误",null,null,"在情报板信息发布页面，添加信息完成后，点击“发布”按钮，弹出“程序出错！”的提示。\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","不予解决","演示版本(#2)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-09"]
[25,"gxjc营运管理项目(#1)","待办事项","GXJC",0,0,"待办事项：事件处置页面，事件编辑中的起始桩号自动获取，但是编辑其他信息后并保存，需要修改起始桩号",null,3,"代码错误",null,null,"待办事项：事件处置页面，事件编辑中的起始桩号自动获取，但是编辑其他信息后并保存，需要修改起始桩号\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[26,"gxjc营运管理项目(#1)","信息发布(#3)","GXJC(#1)",0,0,"号角广播：信息发布页面，输入内容后，“收听”“发布”功能未实现",null,3,"代码错误",null,null,"好觉广播：信息发布页面，输入内容后，“收听”“发布”功能未实现\r\n\r\n \r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","延期处理","Trunk(#trunk)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-09"]
[27,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案管理：点击进入预案模型，选择一个进行编辑，新增一个任务完成后，对此任务进行编辑，内容展示为空，删除功能未实现",null,3,"代码错误",null,null,"预案管理：点击进入预案模型，选择一个进行编辑，新增一个任务完成后，对此任务进行编辑，内容展示为空，删除功能未实现\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","延期处理","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[28,"gxjc营运管理项目(#1)","运行监测(#1)","GXJC(#1)",0,0,"配置管理：进入设备管理页面，选中某设备类型进行查询，翻到第二页，然后再选择其他类型查询，当前类型查询出的记录，默认进入到之前翻的页数",null,3,"代码错误",null,null,"配置管理：进入设备管理页面，选中某设备类型进行查询，翻到第二页，然后再选择其他类型查询，当前类型查询出的记录，默认进入到之前翻的页数\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[29,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"事件填报：填报完事件自动跳入事件处置页面，左下角的“添加任务”“删除任务”“预案变更”功能未实现",null,3,"代码错误",null,null,"事件填报：填报完事件自动跳入事件处置页面，左下角的“添加任务”“删除任务”“预案变更”功能未实现\r\n\r\n \r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","延期处理","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-21"]
[30,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案管理：【预案模型】窗口最大化后，页面数据显示不全",null,3,"代码错误",null,null,"预案管理：【预案模型】窗口最大化后，页面数据显示不全\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","延期处理","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-21"]
[31,"gxjc营运管理项目(#1)","信息发布(#3)","GXJC(#1)",0,0,"选择“情报板信息查询”，在内容或发布人输入框中输入存在的内容，点击查询按钮，查不到相应内容",null,3,"代码错误",null,null,"选择“情报板信息查询”，在内容或发布人输入框中输入存在的内容，点击查询按钮，查不到相应内容\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[32,"gxjc营运管理项目(#1)","辅助管理(#4)","GXJC(#1)",0,0,"系统管理：角色管理页面，首次点击“综合部”出现相对应的角色名称，但是点过下面的组织架构列表后，再回到“综合部”，页面没有刷新，角色名称仍然是之前点击过的。",null,3,"代码错误",null,null,"系统管理：角色管理页面，首次点击“综合部”出现相对应的角色名称，但是点过下面的组织架构列表后，再回到“综合部”，页面没有刷新，角色名称仍然是之前点击过的。\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲"]
[33,"gxjc营运管理项目(#1)","辅助管理(#4)","GXJC(#1)",0,0,"系统管理：进入角色管理页面，点击没有备注的记录进入编辑，备注显示null",null,3,"代码错误",null,null,"系统管理：进入角色管理页面，点击没有备注的记录进入编辑，备注显示null\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲"]
[34,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案管理：选择预案模型，选择一条记录点击编辑按钮，进入“编辑预案明细”页面，取消按钮没有反应。",null,3,"代码错误",null,null,"预案管理：选择预案模型，选择一条记录点击编辑按钮，进入“编辑预案明细”页面，取消按钮没有反应。\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[35,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案管理：选择预案模型，翻到第二页序号从1开始，但是右下角页数展 示从第11条",null,3,"代码错误",null,null,"预案管理：选择预案模型，翻到第二页序号从1开始，但是右下角页数展 示从第11条\r\n\r\n\r\n\r\n\r\n\n\r\n","已解决","已确认","高宇霆","2014-06-22","演示版本(#2)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[36,"gxjc营运管理项目(#1)","待办事项","GXJC",0,0,"代办事项-进入事件处置页面，选择一条记录进行补填，事件信息自助填报区的“确认摄像机编号”字段的选项显示少个右括号，上海-北京，应改为北京方向",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n代办事项-进入事件处置页面，选择一条记录进行补填，事件信息自助填报区的“确认摄像机编号”字段的选项显示少个右括号，上海-北京，应改为北京方向。\r\n","已解决","已确认","曹碧蓉","2014-06-22","演示版本(#2)","曹碧蓉","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[37,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"代办事项-进入事件处置页面，填报人、核实人可以编辑",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n代办事项-进入事件处置页面，填报人、核实人可以编辑。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[38,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"员管理：选择预案模型，最大化后“操作”一列的数据展示不全",null,3,"代码错误",null,null,"员管理：选择预案模型，最大化后“操作”一列的数据展示不全\r\n\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-22","演示版本(#2)","朱玲","曹碧蓉","已解决",null,"2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[39,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"【信息发布】中的“收藏”和“发布”无入口处能查看到，另外“另存为”按钮没反应。",null,3,"代码错误",null,null,"【信息发布】中的“收藏”和“发布”无入口处能查看到，另外“另存为”按钮没反应。\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-22","演示版本(#2)","朱玲","曹碧蓉","已解决",null,"2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[40,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"代办事项-点击处置按钮，选择调度执行，开始时间段比结束时间段早，也能保存成功，电话按钮没有反应",null,3,"代码错误","win7","chrome","\r\n\r\n代办事项-点击处置按钮，选择调度执行，开始时间段比结束时间段早，也能保存成功，电话按钮没有反应。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[41,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件处置-点击补填按钮，右上方的“添加任务”等功能没有实现",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件处置-点击补填按钮，右上方的“添加任务”等功能没有实现。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[42,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件处置-选择字段名称列，第6个选项没有名称，默认是不选中状态",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件处置-选择字段名称列，第6个选项没有名称，默认是不选中状态。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[43,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件处置-点击补填按钮，进入事件处置页面，选择服务区的时间段，开始时间晚于结束时间，也能保存成功",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件处置-点击补填按钮，进入事件处置页面，选择服务区的时间段，开始时间晚于结束时间，也能保存成功。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[44,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"左侧功能菜单",null,3,"代码错误",null,null,"屏幕刷新后，看不到左侧第一个功能菜单\r\n\r\n\r\n","激活","已确认","高宇霆","2014-06-22","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,"高宇霆","2014-07-08"]
[45,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件处置-点击补填按钮进入页面后，选择过程信息，时间字段没有出现日历选择",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件处置-点击补填按钮进入页面后，选择过程信息，时间字段没有出现日历选择。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[46,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"滚动的时候连带屏幕一起滚动",null,4,"界面优化",null,null,"窗口滚动条：滚动的时候连带屏幕一起滚动\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[47,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件处置-进入页面，选择过程信息，输入时间，内容，点击提交按钮，没有反应",null,3,"代码错误","win7","chrome","\r\n事件处置-进入页面，选择过程信息，输入时间，内容，点击提交按钮，没有反应。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[48,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"【发布列表】中的操作按钮，“编辑”和“删除”无反应",null,3,"代码错误",null,null,"【发布列表】中的操作按钮，“编辑”和“删除”无反应\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[49,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件处置-进入页面，选择调度资源，下面的按钮都没有反应",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件处置-进入页面，选择调度资源，下面的按钮都没有反应。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[50,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件填报-选择桩号后摄像头下拉列表中应关联与桩号位置最邻近的两个方向摄像头，没有提供一个全摄像头查询功能，用来选择全部摄像头进行查看。",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件填报-选择桩号后摄像头下拉列表中应关联与桩号位置最邻近的两个方向摄像头，没有提供一个全摄像头查询功能，\r\n\r\n\r\n用来选择全部摄像头进行查看。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[51,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【事件填报】进入事件处置页面，选择一条记录进行补填，在文本区域输入错误，点击保存按钮后提示错误信息，但是删除掉文本中的错误信息后按回车键，页面跳出500错误",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n\r\n【事件填报】进入事件处置页面，选择一条记录进行补填，在文本区域输入错误，点击保存按钮后提示错误信息，但是删除掉文本中的错误信息后按回车键，页面跳出500错误。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[52,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"情报板：翻页数据，例如翻到下一页时，数据序号还是从第一条开始",null,3,"代码错误",null,null,"\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[53,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"首页-地图上的事发事件，选择情报板发布，左侧没有选中情报板，在右侧的文字内容文本框中刚输入一个字符，就弹出“输入字数过多”的提示",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n\r\n首页-地图上的事发事件，选择情报板发布，左侧没有选中情报板，在右侧的文字内容文本框中刚输入一个字符，就弹出“输入字数过多”的提示。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[54,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"点击右上角的辅助管理，选择“系统管理”进入组织机构页面，右侧信息下方有搜索框压住了页数，不清楚是按什么进行搜索，右上角的最小化框没有反应。",null,3,"代码错误",null,null,"\r\n\n\r\n\r\n\r\n点击右上角的辅助管理，选择“系统管理”进入组织机构页面，右侧信息下方有搜索框压住了页数，不清楚是按什么进行搜索，右上角的最小化框没有反应。\r\n\r\n\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-22","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[55,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"首页-地图上的路段事故，选择排障车调度，点击搜索按钮，“排障车调度”页面消失，弹出“选择调度车”页面，选择按钮没反应",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n首页-地图上的路段事故，选择排障车调度，点击搜索按钮，“排障车调度”页面消失，弹出“选择调度车”页面，选择按钮没反应。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[56,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"配置管理-选择进入设备管理页面，光标在桩号值上时，出现了英文提示，建议改成用户容易理解的中文提示",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n配置管理-选择进入设备管理页面，光标在桩号值上时，出现了英文提示，建议改成用户容易理解的中文提示。","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[57,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"配置管理-选择进入设备管理页面，选择设备类型为“可变信息标识”，但是查询出的数据也包含设备类型为“气象监测器、视频监控设备”等",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n配置管理-选择进入设备管理页面，选择设备类型为“可变信息标识”，但是查询出的数据也包含设备类型为“气象监测器、视频监控设备”等。\r\n","激活","已确认","曹碧蓉","2014-06-22","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[58,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件填报-根据《业主对系统建议》文档中说明“占据车道”为必填项，然而这里未勾选“占据车道”仍然能够联网上报成功",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n\r\n\r\n\r\n事件填报-根据《业主对系统建议》文档中说明“占据车道”为必填项，然而这里未勾选“占据车道”仍然能够联网上报成功。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[59,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"首页：代办事项\t进入代办事项页面，点击每页的最后一条记录，整条记录会向上移动一点",null,3,"代码错误",null,null,"首页：代办事项 进入代办事项页面，点击每页的最后一条记录，整条记录会向上移动一点\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[60,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件填报-根据《业主对系统建议》文档中说明：“路线编号”、“管理路段编号”为只读不可写，然而当前系统是可读可写，并能保存联网上报成功； 另外未找到“目标单位”、“经纬度”",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件填报-根据《业主对系统建议》文档中说明：“路线编号”、“管理路段编号”为只读不可写，然而当前系统是可读可写，\r\n\r\n\r\n并能保存联网上报成功； 另外未找到“目标单位”、“经纬度”。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[61,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件填报-根据《业主对系统建议》文档中说明：需要两个分开的按钮“保存”和“上报”来进行区别，但目前系统是将保存和上报并为一个按钮",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n\r\n\r\n\r\n事件填报-根据《业主对系统建议》文档中说明：需要两个分开的按钮“保存”和“上报”来进行区别，但目前系统是将保存和上报并为一个按钮。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[62,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件填报-根据《业主对系统建议》文档中说明：事件标题要支持根据事件类型自动生成：交通事故1、交通事故2等等。 当前系统的“事件标题”没有随着“事件类型”的改变而改变",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件填报-根据《业主对系统建议》文档中说明：事件标题要支持根据事件类型自动生成：交通事故1、交通事故2等等。\r\n\r\n\r\n 当前系统的“事件标题”没有随着“事件类型”的改变而改变。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[63,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"资源管理：名称标志上只有“服务区”不能点击，其它都可以",null,3,"代码错误",null,null,"资源管理：名称标志上只有“服务区”不能点击，其它都可以\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[64,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"动态资源",null,3,"设计缺陷",null,null,"\r\n\n\r\n\r\n\r\n\r\n\r\n点击进入人员布防页面，添加人员成功后，出现名称，再次点击不展示该人员信息\r\n\r\n\r\n点击进入人员布防页面，添加人员成功后，出现名称，再次点击不展示该人员信息\r\n\r\n\r\n\r\n\r\n\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[65,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"交通事故处置预案-根据《业主对系统建议》文档中说明，未找到相关功能内容",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n交通事故处置预案-根据《业主对系统建议》文档中说明，未找到相关功能内容。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[66,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"交通事故处置预案-根据《业主对系统建议》文档中说明，未找到相关功能内容",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n交通事故处置预案-根据《业主对系统建议》文档中说明，未找到相关功能内容。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[67,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"交通事故处置预案-根据《业主对系统建议》文档中说明，未找到相关功能内容",null,3,"代码错误","win7","chrome","\r\n\r\n交通事故处置预案-根据《业主对系统建议》文档中说明，未找到相关功能内容。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[68,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"短信推送-与《业主对系统建议》文档中说明不符",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n\r\n\r\n\r\n短信推送-与《业主对系统建议》文档中说明不符。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[69,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"预案管理-【预案模型】删除操作无反应",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n预案管理-【预案模型】删除操作无反应。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[70,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"系统管理-进入系统常量管理页面，新增系统常量，保存后，弹出乱码的提示",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n系统管理-进入系统常量管理页面，新增系统常量，保存后，弹出乱码的提示。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[71,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"系统管理-进入系统常量管理页面，选择“协同资源类型”进行查询，数据共2页，点击下翻页按钮，总页数变成了35页，出现了所有记录",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n\r\n系统管理-进入系统常量管理页面，选择“协同资源类型”进行查询，数据共2页，点击下翻页按钮，总页数变成了35页，出现了所有记录。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[72,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"系统管理-进入权限设置页面，在某一权限列表上右击，选择编辑、删除，都没反应",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n进入权限设置页面，在某一权限列表上右击，选择编辑、删除，都没反应。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[73,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"预案管理页面",null,2,"代码错误",null,null,"\r\n\n\r\n\r\n\r\n\r\n\r\n\r\n\n\r\n1、“预案模型”中只有纵向滚动条，没有横向滚动条，故看不清后面的内容。\n\r\n2、新增预案时，为空也能保存成功。并且保存之后，不刷新界面更新数据。\r\n\r\n\r\n\r\n\r\n\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[74,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"预案管理-【预案模型】中添加任务，不能对“任务模板”进行选择",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n\r\n预案管理-【预案模型】中添加任务，不能对“任务模板”进行选择。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","侍凡","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[75,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件填报-【事件处置】【过程信息】： “提交”按钮无反应 “刷新”按钮无反应",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n事件填报-\r\n【事件处置】【过程信息】：\r\n\r\n\r\n    \r\n“提交”按钮无反应。\r\n\r\n\r\n\n\r\n\r\n\r\n    \r\n“刷新”按钮无反应。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[76,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【事件处置】 取消、添加任”、删除任务、预案变更按钮点击无反应 【基本信息】中的发生地点与【事件编辑】中的【事发点点起始桩号”和“事发地点结束桩号”不符",null,3,"代码错误","win7","chrome","\r\n\r\n事件填报-【事件处置】 1、“取消”按钮点击无反应 2、“添加任务”、“删除任务”、“预案变更”按钮点击无反应 3、【基本信息】中的发生地点，与【事件编辑】中的【事发点点起始桩号”和“事发地点结束桩号”不符，并且“事发点点起始桩号”和“事发地点结束桩号”做了校验（只能选择1039～1094之间）\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[77,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"系统管理-进入“组织机构管理”页面，对搜索出的某条数据编辑，修改用户完成后，刷新出所有的用户信息，而不是之前搜索的信息。",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n系统管理-进入“组织机构管理”页面，对搜索出的某条数据编辑，修改用户完成后，刷新出所有的用户信息，而不是之前搜索的信息。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[78,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"系统管理-进入“组织机构管理”页面，在搜索框中只能输入数字与字母进行搜索，中文无法搜索",null,3,"代码错误","win7","chrome"," \r\n\r\n\r\n系统管理-进入“组织机构管理”页面，在搜索框中只能输入数字与字母进行搜索，中文无法搜索。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[79,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"预案管理-预案模型页面，编辑预案明细，添加任务时，任务模板无法添加，输入任务名称，动作选择后，任务名称就相应的变为动作的选项",null,3,"代码错误","win7","chrome"," \r\n\r\n\r\n\r\n预案模型页面，编辑预案明细，添加任务时，任务模板无法添加，输入任务名称，动作选择后，任务名称就相应的变为动作的选项。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[80,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"配置管理-进入“设备管理”页面，选择一个设备类型自动查询出多页数据，翻页后再选择其他设备类型，自动查询出数据，但是点击“查询”按钮，无数据",null,3,"代码错误","win7","chrome"," \r\n\r\n\r\n\r\n进入“设备管理”页面，选择一个设备类型自动查询出多页数据，翻页后再选择其他设备类型，自动查询出数据，但是点击“查询”按钮，无数据\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[81,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"进入“权限管理”页面，在权限设置中选择一个叶子栏目进行编辑，必填项为空",null,3,"代码错误","win7","chrome"," \r\n\r\n\r\n进入“权限管理”页面，在权限设置中选择一个叶子栏目进行编辑，必填项为空。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[82,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"【组织机构管理】树形列表数据与【角色管理】中的树形列表数据不一致，在【组织机构管理】新增的组织机构，在【角色管理】却没有刷新数据库",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n【组织机构管理】树形列表数据与【角色管理】中的树形列表数据不一致，在【组织机构管理】新增的组织机构，在【角色管理】却没有刷新数据库\r\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[83,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"【组织机构管理】中双击树形列表时数据展示没问题，但如果单击，则数据展示有时展示不对",null,3,"代码错误","win7","chrome","\r\n\r\n 【组织机构管理】中双击树形列表时数据展示没问题，但如果单击，则数据展示有时展示不对。\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[84,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"【组织机构管理】【新增组织机构】不能保存成功;&quot;备注&quot;做了校验，为必填项，然后却没有标注&quot;*&quot;",null,3,"代码错误","win7","chrome","\r\n\r\n\r\n\r\n【组织机构管理】【新增组织机构】不能保存成功;\r\n\"备注\"做了校验，为必填项，然后却没有标注\"*\"。\r\n\r\n\r\n\n\r\n","激活","已确认","曹碧蓉","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[85,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"系统常量管理，“新增系统常量”无页面提示语",null,3,"代码错误",null,null,"\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[86,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"系统管理页面中【权限设置】，右击“删除”按钮无反应",null,1,"代码错误",null,null,"\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[87,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"按钮中的字体位置最好居中",null,4,"界面优化",null,null,"\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","潘彩侠","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0]
[88,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"点【信息发布】按钮后，报404错误",null,1,"代码错误",null,null,"\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[89,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"模板管理页面",null,2,"设计缺陷",null,null,"1、“增加模板”，未做限制就能添加成功。\r\n2、“最小化”按钮，无反应。\r\n\r\n\n\r\n\r\n3、“编辑”中的“预览”无反应。\r\n\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[90,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"信息控制页面",null,1,"设计缺陷",null,null,"点击【信息控制】中的“发布”按钮后，提示语显示为“添加成功”。\r\n另外，未点击任何信息，也能发布。\r\n\r\n\n\r\n\r\n【情报板】界面，未显示退出或返回等方式字样。\r\n\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[91,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"发布列表中的“删除”按钮操作无反应",null,2,"设计缺陷",null,null,"\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","Trunk(#trunk)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[92,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"“添加”按钮，不输入内容也能添加成功",null,3,"设计缺陷",null,null,"\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[93,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",0,0,"信息发布最小化按钮没反应",null,3,"代码错误",null,null,"信息发布最小化按钮没反应","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[94,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"有些图标没有功能",null,1,"设计缺陷",null,null,"\r\n[结果] \r\n\r\n    \n\r\n \r\n\r\n有些图标没有功能\r\n\r\n[期望]\r\n功能全部实现","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[95,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"底部功能模块被挡住了",null,3,"代码错误",null,null,"\r\n[结果]\r\n\r\n\r\n\r\n\r\n\r\n\r\n[期望]\r\n底部待办事项等无遮挡","激活","已确认","高宇霆","2014-06-23","Trunk(#trunk)","朱玲","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[96,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"图中选中的选项，点了“首页”后，这些打钩的选项就没有了",null,3,"设计缺陷",null,null,"\r\n\r\n\r\n点击首页后应该保留勾选选项\r\n\r\n\n\r\n","激活","已确认","高宇霆","2014-06-23","演示版本(#2)","朱玲","高宇霆","已解决","825版本(#3)","2014-06-30",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[97,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"同一桩号多个事件时，事件图层全部覆盖在一起",null,3,"界面优化","windows","ie11","建议修改为，1个事件时，鼠标悬停显示事件详细信息，多个事件时，显示多个事件的图标，横向排列，鼠标悬停在哪个事件上，再显示对应的事件详细信息\r\n\n\r\n\r\n\r\n\n\r\n","激活","已确认","朱玲","2014-08-18","825版本(#3)","陈继伟","曹碧蓉","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[98,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"事件图层，鼠标悬停后，显示信息中，时间格式错误",null,2,"界面优化","windows","ie"," \n","激活","已确认","朱玲","2014-08-18","825版本(#3)","陈继伟","曹碧蓉","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[99,"gxjc营运管理项目(#1)","信息发布(#3)","GXJC(#1)",0,0,"号角广播信息发布问题",null,3,"代码错误","windows","ie","[步骤]\r\n1、点击信息发布/号角广播/信息发布菜单，进入号角广播列表页面\r\n[结果]\r\n1、缺少查询条件\r\n2、文本内容过长时，有缩略效果，但无泡泡显示所有内容\r\n3、横向和竖向都出现滚动条\r\n4、点击新增，进入新增界面，字体太大\r\n5、点击新增，进入新增界面，文件名未加长度校验\r\n6、记录无排序\r\n[期望]\r\n1、增加按照文件内容模糊匹配，操作人，操作时间进行查询\r\n2、文本内容过长时，有缩略效果，鼠标悬停在文本上，泡泡显示所有内容\r\n3、没有滚动条\r\n4、点击新增，进入新增界面，字体设置为12\r\n5、文件名加上长度限制\r\n6、记录按照创建时间降序排列\r\n\r\n\n\r\n\r\n\r\n\n\r\n","已解决","已确认","朱玲","2014-08-18","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,"曹碧蓉","2014-07-23"]
[100,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"快速填报页面，选择桩号后，摄像头数据为空时，请处理后台Null Point 的异常",null,3,"代码错误","windows","ie","[步骤]\r\n[结果]\r\n[期望]","已关闭","已确认","朱玲","2014-08-18","825版本(#3)","Closed","曹碧蓉","已解决","825版本(#3)","2014-08-19","朱玲","2014-07-23",0,null,0,"朱玲","2014-07-23"]
[101,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"新增预案时，编辑预案明细页面，增加一列属性，是否默认，因为每一类事件都有不同的事件等级，一种类型对应多等级时，设置加载的默认预案",null,3,"设计缺陷","windows","ie","[步骤]\r\n[结果]\r\n[期望]","已解决","已确认","朱玲","2014-08-18","825版本(#3)","朱玲","高宇霆","延期处理","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,"高宇霆","2014-07-22"]
[102,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"新增预案中新增任务列表，翻页功能有问题",null,3,"代码错误","windows","ie","任务列表增加12个任务，翻页到下一页时，翻页功能未实现\r\n\r\n","已解决","已确认","朱玲","2014-08-18","825版本(#3)","朱玲","高宇霆","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,"高宇霆","2014-07-21"]
[103,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案模型新增任务时，建议直接在打开的任务列表中增加复选框，选中全部保存",null,3,"设计缺陷","windows","ie","新增预案模型页面，点击新增任务，进入任务列表页面\r\n目前是双击的方式，操作不方便，不能确定是否已增加任务，建议修改为复选框方式，勾选保存\r\n\r\n","已解决","已确认","朱玲","2014-08-18","825版本(#3)","朱玲","高宇霆","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,"高宇霆","2014-07-22"]
[104,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案模型新增界面，字体显示不一致",null,1,"界面优化","windows","all"," \r\n\n\r\n\r\n\r\n\n\r\n","已解决","已确认","朱玲","2014-08-18","825版本(#3)","朱玲","高宇霆","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,"朱玲","2014-07-22"]
[105,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案管理列表页面中，经办时间格式不正确，并且内部显示部分为蓝色",null,2,"界面优化","windows","ie","   \n","已解决","已确认","朱玲","2014-08-18","825版本(#3)","朱玲","高宇霆","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,"高宇霆","2014-07-22"]
[106,"gxjc营运管理项目(#1)","指挥调度(#2)","GXJC(#1)",0,0,"预案管理列表页面，请增加查询条件进行筛选",null,3,"代码错误","windows","ie11","[步骤]\r\n点击指挥调度/预案模型，进入预案管理列表页面\r\n[结果]\r\n1、查询条件：事件类型，事件级别\r\n2、列表页面\r\n[期望]\r\n1、查询条件：事件类型，事件级别\r\n2、列表页面\r\n\r\n \r\n\r\n  ","已解决","已确认","朱玲","2014-08-18","825版本(#3)","朱玲","高宇霆","已解决","825版本(#3)","2014-08-19",null,"0000-00-00",0,null,0,"高宇霆","2014-07-22"]
[107,"gxjc营运管理项目(#1)","系统管理(#5)","GJXC",0,0,"删除了对应组织机构下的角色后，人员更换了角色信息",null,3,"代码错误","windows","ie11","1、原来测试1这个组织机构下，新增了测试1这个角色，\r\n2、新增了用户，选择了测试1这个角色\r\n3、删除了测试1角色\r\n4、进入用户列表中，用户存在，但是用户角色变为了52\r\n\r\n\r\n","激活","已确认","朱玲","2014-08-19","825版本(#3)","徐永刚","徐永刚","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[108,"gxjc营运管理项目(#1)","系统管理(#5)","GJXC",0,0,"组织机构下增加了角色，并且增加了对应角色的用户，删除角色时不能进行删除",null,3,"设计缺陷","windows","ie11","[步骤]\r\n1、组织机构下增加了对应角色的人员\r\n\r\n2、进入角色管理中，将角色删除，虽然有提示，但是建议不能进行删除，不然，人员加了没有任何用途\r\n\r\n \r\n[结果]\r\n[期望]","激活","已确认","朱玲","2014-08-19","825版本(#3)","徐永刚","徐永刚","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[109,"gxjc营运管理项目(#1)","系统管理(#5)","GJXC",0,0,"组织机构树如果过长，不能通过滚动鼠标的效果达到下移功能，只能缩起来一些组织机构才能看到下面的组织机构",null,3,"设计缺陷","windows","ie11","\r\n\r\n\r\n\r\n\n\r\n","激活","已确认","朱玲","2014-08-19","825版本(#3)","徐永刚","徐永刚","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,"朱玲","2014-07-23"]
[110,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"左侧菜单不隐藏",null,3,"代码错误","windows","ie11","[步骤]\r\n进入系统，点击运行监测下左侧的运行监测菜单\r\n[结果]\r\n换到指挥调度，或者其他菜单下，二级菜单不隐藏\r\n\r\n\r\n\r\n[期望]","激活","已确认","朱玲","2014-08-19","825版本(#3)","陈继伟","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[111,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件填报时，选择了某一摄像头进行查看，点击保存后，确认的摄像信息不是选择的摄像头信息",null,3,"代码错误","windows","firefox","[步骤]\r\n1、快速填报时，选择了确认的摄像头\r\n\r\n\r\n\r\n2、保存后，确认的摄像头不是选择的这个摄像头\r\n\r\n\r\n","激活","已确认","朱玲","2014-08-19","825版本(#3)","侍凡","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[112,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"选中待办事件图层，勾选广靖和锡澄路段，地图上多了很多不明标签",null,3,"代码错误",null,null,"\r\n\n","激活","已确认","朱玲","2014-08-19","825版本(#3)","陈继伟","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[113,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"情报板图层点击不显示任何内容",null,3,"代码错误",null,null,"\r\n[步骤]\r\n[结果]\r\n[期望]","激活","已确认","朱玲","2014-08-19","825版本(#3)","陈继伟","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[114,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"同时选择车检器和气象监测器，图层报错",null,3,"代码错误","windows","firefox","\r\n\r\n\r\n\n\r\n\r\n\r\n\n\r\n\r\n\r\n\n\r\n\r\n\r\n\n\r\n\r\n\r\n\r\n","激活","已确认","朱玲","2014-08-19","825版本(#3)","陈继伟","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[115,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",0,0,"角色的应用有问题，在收费站（父节点）中增加一个角色，下面增加了收费站（子节点），角色信息，子节点也应该应用到",null,3,"代码错误",null,null,"1、 \r\n2、\r\n\r\n \r\n\r\n\n\r\n\r\n\r\n\n\r\n\r\n3、在璜瑭收费站中新增人员，角色应该能选择到收费站管理员和收费员2种，但是只有1种\r\n     \n\r\n  ","激活","已确认","朱玲","2014-08-20","825版本(#3)","徐永刚","徐永刚","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0]
[116,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"绑定权限页面树形展示的应该是系统的菜单，请修改",null,3,"代码错误",null,null,"\r\n\r\n  \r\n\r\n  ","激活","已确认","朱玲","2014-08-20","825版本(#3)","徐永刚","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,"朱玲","2014-08-05"]
[117,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"调度信息通知修改为调度清障资源",null,3,"代码错误",null,null," \n","激活","已确认","朱玲","2014-08-20","825版本(#3)","高宇霆","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[118,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"事件编辑中，点击编辑任务，功能未达成",null,3,"代码错误",{"$nulls":3},"激活","已确认","朱玲","2014-08-20","825版本(#3)","曹碧蓉","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[119,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"完整填报进入事件编辑页面，点击取消按钮，待办事项列表中还是生成了一条新的纪录",null,3,"代码错误",null,null,"[步骤]\r\n[结果]\r\n[期望]","激活","已确认","朱玲","2014-08-20","825版本(#3)","曹碧蓉","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[120,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"设备名称改为情报板名称",null,3,"代码错误",{"$nulls":3},"激活","已确认","朱玲","2014-08-20","825版本(#3)","曹碧蓉","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[121,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",0,0,"设备管理进入，下拉框选择默认选中车检器，列表显示车检器的信息",null,3,"代码错误",null,null," \n","激活","已确认","朱玲","2014-08-20","825版本(#3)","曹碧蓉","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[122,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【待办事项】点归档按钮，进入事件归档，页面左下角报网页错误",null,2,"代码错误",null,null,"[步骤]1、进入代办事项页面，选择某条记录，点归档按钮\r\n        2、进入事件归档界面\r\n[结果]页面左下角出现网页错误\r\n         \r\n\r\n[期望]准确展示归档界面，网页无错误","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-25",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[123,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【待办事项】点完整处置按钮，选择编辑任务按钮进入界面，点击新增任务，左下角出现网页错误",null,2,"代码错误",null,null,"[步骤]1、进入代办事项页面，选择某条记录，点完整处置按钮进入界面\r\n         2、然后点编辑任务按钮进入界面，点击新增任务\r\n[结果]添加任务界面展示为空，左下角出现网页错误\r\n       \r\n\r\n        \r\n\r\n[期望]准确展示新增任务界面，网页无错误","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-28",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[124,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【快速填报】选择事发起始地点小于结束地点时，摄像头为空，但是如果正常选择则有摄像头显示",null,1,"代码错误",null,null,"[步骤]1、进入快速填报界面，选择事发起始地点为K1039，然后再修改结束地点为K1038\r\n         2、弹出提示框：事件结束地点不能小于事件起始地点，点确认按钮，检查摄像头\r\n[结果]结束地点默认和起始地点一致，摄像头为空\r\n[期望]结束地点默认和起始地点一致时，刷新摄像头","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[125,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【待办事项】点补填按钮，进入补填界面，在车辆设置中输入带有中文字符的车牌号，上报成功后，再次点击进去查看车牌号，中文显示？？",null,2,"代码错误",null,null,"[步骤]2、进入代办事项页面，选择某条记录的补填按钮，进入界面\r\n         2、在车辆设置中输入带有中文字符的车牌号，上报成功后，再次点击进去查看车牌号\r\n[结果]带有中文的车牌号显示？？\r\n        \r\n\r\n[期望]准确显示车牌号","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-28",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[126,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【待办事项】选择第二页的某条数据，点快速处置按钮进入页面，处置完返回列表页面，显示第一页的数据，但是页数仍然是第二页",null,2,"代码错误",null,null,"[步骤]1、进入代办事项页面，选择第二页的某条数据，点快速处置按钮进入页面\r\n         2、处置完返回列表页面，检查数据展示\r\n[结果]数据展示第一页，但是页数显示的是第二页\r\n        \r\n\r\n[期望]返回列表页面，数据展示正确","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-26",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[127,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】基本信息填报区的计划恢复时间与实际恢复时间是灰色的，不能手工输入但是可以选择日期，日期选中后就不能删除",null,2,"代码错误",null,null,"[步骤]1、进入代办事项页面，点完整处置按钮进入界面\r\n         2、事件编辑--基本信息填报区，计划恢复时间与实际恢复时间文本框是灰色的，输入日期\r\n[结果]不能手工输入但是可以选择日期，日期选中后就不能删除\r\n[期望]可以手工输入，也可以日期选择","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[128,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】进入事件编辑界面，事件类型为“交通事故”，选择事故等级时，系统弹出提示：死亡人数与事故等级不符，提示信息不明确",null,1,"代码错误",null,null,"[步骤]1、进入代办事项，选择事故类型为“交通事故”，点完整处置按钮，进入界面\r\n         2、死亡人数为0时，选择事故等级为一般\r\n[结果]页面弹出：死亡人数与事故等级不符，提示信息不明确\r\n[期望]给出合理的数字取值范围","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[129,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】事件编辑界面，修改了信息，点保存并上报，继续上报联网中心，确认后，系统提示：上报失败",null,3,"代码错误",null,null,"[步骤]1、进入代办事项，点完整处置按钮进入页面\r\n         2、在事件编辑页面，补充填写信息，点“保存并上报”按钮\r\n         3、弹出“将上报联网中心，是否确认”，点“继续上报”按钮\r\n[结果]系统提示：上报失败\r\n[期望]弹出：上报成功“的提示，如果失败也应该给出失败的原因","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[130,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【快速填报】在快速填报界面，方向选择为双向，进入待办事项，点补填按钮进入界面，方向为上行，数据不一致",null,2,"代码错误",null,null,"[步骤]1、在快速填报界面，方向选择为双向\r\n         2、进入待办事项，点补填或完整处置按钮进入相应界面，查看方向\r\n[结果]基本信息区域方向为上行\r\n        \r\n\r\n       \r\n\r\n[期望] 方向要保持一致","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[131,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【待办事项】点完整处置按钮，起始、结束不是同一桩号时，显示两次信息发布、短信推送以及其他的处置",null,2,"代码错误",null,null,"[步骤]1、进入待办事项界面，选择起始、结束不是同一桩号的某条记录\r\n         2、点对应的“完整处置”按钮进入界面，查看处置事项\r\n[结果]显示两遍\r\n        \r\n\r\n  \r\n[期望]起始结束桩号一样或不一样，处置事项应该显示一遍","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-26",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[132,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【待办事项】点完整处置按钮，调试执行界面的短信推送内容，点查看推送名单链接，报404错误",null,3,"代码错误",null,null,"[步骤]1、登陆系统首页，点完整处置按钮进入页面\r\n         2、在调试执行界面的短信推送内容中，点“查看推送名单”\r\n         \r\n\r\n[结果]页面报404错误，如下图：\r\n         \r\n\r\n[期望]正常查看推送名单","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-26",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[133,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【快速填报】车辆数输入7位数字或其它字符，点保存按钮，一直为loadding，给用户的错误提示信息不明确",null,2,"代码错误",null,null,"[步骤]1、登陆系统首页，点右下角的“快速填报”进入页面\r\n         2、车辆数文本框中输入7位数字或其它字符，点“保存”按钮\r\n[结果]按钮一直变loadding\r\n[期望]明确给出用户输入错误的提示信息","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,"秦洁","2014-08-13"]
[134,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】进入事件处置页面，操作完调度信息通知、调度公共资源，再次进入页面，调度信息通知顶部相应的任务没有改变状态",null,1,"代码错误",null,null,"[步骤]1、进入代办事项，点完整处置按钮，进入事件处置页面\r\n         2、操作完调度信息通知、调度公共资源，在左侧刷新事件过程，有相应的操作记录\r\n[结果]调度信息通知顶部相应的任务没有改变状态\r\n        \r\n\r\n[期望]操作过的任务，顶部相应的状态也应该更新","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[135,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】进入处置页面，调度信息通知区域填写报警人、报警电话等信息后，点提交后，桩号变为KK1038",null,1,"代码错误",null,null,"[步骤]1、进入代办事项，点完整处置按钮，进入处置页面\r\n         2、调度信息通知区域，填写报警人、报警电话等信息后，点提交按钮\r\n         3、保存成功后，关掉窗口，重新进入事件处置页面\r\n[结果]桩号由原来的K1038变为KK1038\r\n        \r\n\r\n[期望]修改完调度信息通知区域，再次查看桩号显示正确","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[136,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【知识管理】点击知识管理，出现二级菜单，在不消失的情况下，切换右上角的模块，知识管理的二级菜单还存在，无法消失",null,2,"代码错误",null,null,"[步骤]1、在指挥调度模块，点击知识管理，出现二级菜单\r\n        2、在不消失的情况下，切换右上角的模块\r\n[结果]知识管理的二级菜单还存在，消失不掉\r\n        \r\n\r\n[期望] 切换模块后，二级菜单消失","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[137,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【知识管理】点击知识管理，选择交通拥堵，进入专业知识页面，点历史案例，方向显示数字",null,2,"代码错误",null,null,"[步骤]1、点指挥调度-知识管理，选择交通拥堵，进入专业知识页面\r\n        2、选择历史案例页签，获取出来所有的历史数据\r\n[结果]方向显示数字\r\n         \r\n\r\n[期望] 获取的方向与填报的方向保持一致","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[138,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】在事件处置页面，点击某条记录的完整处置按钮，进入处置页面，选择事故类型，事件标题随之改变，但是编号没有改变",null,2,"代码错误",null,null,"[步骤]1、在事件处置页面，点击某条记录的完整处置按钮，进入处置页面\r\n         2、在事件类型的下拉列表中选择事件类型\r\n[结果]事件标题随事故类型的选择而变化，事件类型编号不变\r\n        \r\n\r\n      \r\n\r\n[期望]事件类型改变，事件标题中的事件类型及相应编号也随之改变","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[139,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】在事件处置页面，点某条记录的完整处置按钮，进入处置页面，点查看事件进度按钮，页面左下角出现网页错误",null,3,"代码错误",null,null,"[步骤]1、进入代办事项，在事件处置页面，点某条记录的完整处置按钮，进入处置页面\r\n         2、点 查看事件进度按钮\r\n[结果]页面左下角出现网页错误\r\n       \r\n\r\n[期望]正常进入事件进度页面，网页无错误","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[140,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整处置】进入完整处置页面的调试执行，在调度信息通知区域，输入拥堵情况为字符，如a，点提交按钮后，一直loading...",null,1,"代码错误",null,null,"[步骤]1、进入完整处置页面的调试执行，在调度信息通知区域，输入拥堵情况为字符，如a\r\n         2、点提交按钮\r\n[结果]按钮一直是loading...\r\n[期望]明确给出用户输入的错误提示信息","激活","已确认","秦洁","2014-08-20","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-20",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[141,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【代办事项】在代办事项页面，点某条记录的补填按钮，进入补填页面，事件编辑中的拥堵情况单位与调试执行中的拥堵情况单位书写不统一",null,1,"代码错误",null,null,"[步骤]1、在代办事项页面，点某条记录的补填按钮，进入补填页面\r\n         2、查看事件编辑中的拥堵情况单位、调试执行中的拥堵情况单位\r\n[结果]事件编辑中的拥堵情况单位是Km，K是大写\r\n         \r\n\r\n  调试执行中的拥堵情况单位是km，k是小写\r\n       \r\n\r\n[期望]拥堵情况单位保持一致","激活","已确认","秦洁","2014-08-22","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-23",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[142,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【完整处置】进入代办事项，点完整处置按钮进入处置页面，上方的任务展示有问题",null,2,"代码错误",null,null,"[步骤]进入代办事项，点击某条记录的完整处置按钮，进入处置页面\r\n[结果]上方的任务展示有问题\r\n          \r\n[期望]正常展示\r\n          ","激活","已确认","秦洁","2014-08-22","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-28",null,"0000-00-00",0,null,0,"秦洁","2014-08-14"]
[143,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【消息】在消息上报页面，选择接收部门，输入消息内容，上报成功后，在首页右下角的消息中查看，接收部门展示的是时间",null,2,"代码错误",null,null,"[步骤]1、选择【辅助管理】-【收费站】，进入消息上报页面\r\n         2、选择接收部门，输入消息内容，点上报按钮\r\n         3、上报成功后，在系统首页右下角查看消息\r\n[结果]消息列表页面的接收部门展示时间\r\n        \r\n\r\n[期望]接收部门展示消息上报页面选择的接收部门，而不是时间\r\n        ","激活","已确认","秦洁","2014-08-22","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-25",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[144,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【代办事项】代办事项页签的数据翻到第二页，切换到待评估/待归档页面，数据为空，点刷新按钮，刷新出代办事项中的数据",null,2,"代码错误",null,null,"[步骤]代办事项页签的数据翻到第二页，切换到待评估/待归档页面\r\n[结果]待评估/待归档页面的数据为空，点刷新按钮，刷新出代办事项中的数据\r\n[期望]准确展示数据","激活","已确认","秦洁","2014-08-22","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-25",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[145,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",0,0,"【完整填报】在调度信息通知区域，点出动设备的选择按钮，网页报错后，车辆选择页面就在最下面展示",null,3,"代码错误",null,null,"[步骤]在调度信息通知区域，点出动设备的选择按钮\r\n[结果]网页报错后，车辆选择页面就在最下面展示\r\n        \r\n\r\n[期望]网页无错误，车辆选择页面弹出框展示","激活","已确认","秦洁","2014-08-22","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-23",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[146,"gxjc营运管理项目(#1)","待办事项","GJXC",0,0,"【代办事项】快速填报完事件，进入到代办事项，还要去找刚填报完的事件，事件没有排序",null,2,"代码错误",null,null,"[步骤]快速填报完事件，进入到代办事项，刚填报完的事件没有在最前面展示\r\n[结果]事件没有排序\r\n        \r\n\r\n[期望]事件按倒序排列","激活","已确认","秦洁","2014-08-22","825版本(#3)","朱玲","曹碧蓉","已解决","825版本(#3)","2014-08-25",null,"0000-00-00",0,null,0,null,"0000-00-00"]
[147,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"焦点落在“统计预测”模块上，二级功能模块有时能展示，有时不能展示，或者展示过后1秒钟后即被隐藏\n【二级功能模块：道路、服务区、收费站】",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[148,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"焦点落在“互通”模块上后切换到“统计预测”模块时，“运行监测”模块的二级功能仍然展示，没有隐藏",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[149,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【道路】点击“最小化”按钮没反应，不能最小化",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[150,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【设备管理】\n1、点击“桩号”后展示的提示语为英语，是否应该改成中文\n2、另外输入框能够编辑，虽然不能编辑成功，如果不需要编辑是否能把输入框置灰",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[151,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【设备管理】\n无设备编号【设备编号是不是必填项？】",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[152,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】\n点击“董事会”出现的提示语看不懂",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[153,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】\n新增组织机构后，右侧内容界面展示不全，见图",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[154,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】\n新增角色后，界面看不到新增的角色名",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[155,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】\n编辑组织机构，“备注”没有调用原备注内容",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[156,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【组织机构】\n右侧有数据，界面未展示",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[157,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【清排障处理】\n界面数据展示不全",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[158,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【大队清障】输入框不能编辑",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[159,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【大队清障】【大队清障调度】中的“出动设备”和“出动人员”的选择项，车辆选择中的数据被覆盖",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[160,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【大队清障】上报成功提示语界面展示比较乱",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[161,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【配色管理】界面无数据",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[162,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】界面左侧无组织机构树",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[163,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",null,null,"界面展示看不到底部三个按钮，然而从系统首页底部的“快速填报”进入界面，界面则展示的是全的",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[164,"gxjc营运管理项目(#1)","指挥调度","GJXC",null,null,"【预案模型】点击界面右侧的编辑按钮，预案明细界面无内容",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[165,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【配色管理】新增操作无法成功",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[166,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【配色管理】编辑操作无法成功",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[167,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【设备管理】备注输入框提示语不是中文",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[168,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",null,null,"【预案模型】【新增预案】中无必填项，没有输入相关数据仍然能够新增成功",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[169,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",null,null,"【预案模型】【新增预案】【新增任务】不能添加任务",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[170,"gxjc营运管理项目(#1)","指挥调度(#2)","GJXC",null,null,"【平时交通营运管理】的详细页面中，“品名”、“是否泄漏”、“知识点”、“备注”等输入框是数据展示，不支持手动输入，需要把文本框中的输入符给隐藏",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[171,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"功能菜单看不全，需要按F11才能看全",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[172,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】中新增角色界面出现2个角色名称",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[173,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】中新增角色界面，在新增的界面有时角色名称会默认之前存在的值，例如之前有个角色名称为“5”，在新增角色时会自动默认这个角色名称",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[174,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】中右击左侧树形新增组织机构，新增成功，但界面未展示",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[175,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】新增组织机构界面的“备注”是必填项吗？（但在【组织机构】能新增成功）",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[176,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】无法删除组织机构",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[177,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【组织机构管理】中的查询功能不能查询",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[178,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】中的【新增组织机构】和【编辑组织机构】中没有“班种”输入框，然而【组织机构管理】中的【新增组织机构】和【编辑组织机构】却是有“班种”输入框的",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[179,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【角色管理】中的【新增组织机构】和【编辑组织机构】中没有“班种”输入框，然而【组织机构管理】中的【新增组织机构】和【编辑组织机构】却是有“班种”输入框的",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[180,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【权限管理】打不开",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[181,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【系统常量管理】新增系统常量界面：\n1.“有效标志”为必填项，但无“*”标记；\n2.“有效标志”、“代码标识”、“标识名称”展示了2个冒号\n3.页面中的“：”有2种展示，能否统一下",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[182,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【系统常量管理】新增系统常量界面：\n1.页面中的提示语，是不是有点问题",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[183,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【系统常量管理】新增系统常量界面：\n1.代码编号，能支持负数展示？？",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[184,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【修改密码】页面不美观",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[185,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【人员值班】日期时间，正序和倒序展示顺序一样",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[186,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【人员值班】\"导出\"功能不能使用",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[187,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【人员值班】按照月份查询:\n1.当查询7月份时,虽然能查询到7月份相应的数据,但是此时点击排序时,数据却变成了8月份的数据",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[188,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【排班】\"导出\"功能不能使用",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[189,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"1.【人员值班】中查询条件有日历供快速选择，但【排班】中查询条件无日历快速选择\n2.但点击【排班】中的查询条件后，再点击【人员值班】中查询条件时，发现【人员值班】中查询条件展示的日历快速选择没有了",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[190,"gxjc营运管理项目(#1)","辅助管理(#4)","GJXC",null,null,"【排班】按照月份查询:\n1.当查询7月份时,虽然能查询到7月份相应的数据,但是此时点击排序时,数据却变成了8月份的数据",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[191,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"1.查询的是7月份的数据，但展示的是8月份的数据。\n2.若7月份无数据，界面能不能展示为空。",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[192,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"横排的导航栏有“首页”，【运行监测】里也有个“首页”，这两个需要都保留吗？【此问题属于视觉体验】",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[193,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"焦点已经不落在【事件事故统计】上面了，但仍然展示下级分类",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[194,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【事件事故统计】【分类型事故数统计】：\n点击“详情”操作，界面打开后，无内容",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[195,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【事件事故统计】【分类型事故数统计】：\n界面内容与【知识管理】界面内容一致",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[196,"gxjc营运管理项目(#1)","运行监测(#1)","GJXC",null,null,"【事件事故统计】【分车型事故数统计】：\n“事故数量40，所占比例为56.34%”的车型为NULL",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[197,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",null,null,"【信息发布】，进入页面后，窗口无法退出，页面样式需要调整",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]
[198,"gxjc营运管理项目(#1)","信息发布(#3)","GJXC",null,null,"【模板管理】：不能新增",null,3,"代码错误",{"$nulls":3},"已确认","已确认","秦洁","2014-08-25","825版本(#3)","朱玲","陈继伟","已解决",null,"2014-08-30"]