{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["变更记录","产品问题管理表"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"变更记录","index":0,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[]}
{"$rows_empty":9}
[null,"变更记录",{"$nulls":5},"配置项状态记录"]
[null,"版本号","更新内容","作者","审批人","审批时间",null,"状态"]
[null,"V0.1","初稿编写完成","孙强、殷萍",null,null,null,"已入基线"]
[null,"V1.0","审核通过","孙强、殷萍","高才驰","2014-08-15"]

{"sheet":"产品问题管理表","index":1,"n_rows":113,"n_cols":18,"rows_kept":113,"cut":false,"hidden":false,"merged":[[0,0,0,17]]}
["产品缺陷管理表"]
["发现阶段","发现途径","问题编号","问题类型","严重级别","优先级","问题状态","所属模块","概要描述","缺陷说明","报告人","报告日期","关闭日期","责任人","问题来源","原因分析","解决结果说明","备注"]
["测试","测试",1,"缺陷","严重","中","已关闭","通用支撑",null,"在通用支撑中，进行添加或者是修改部门信息，在备注栏中，输入500个字母或者是数字（备注上限字符为500），页面将会撑开不正常(中文不会)\n另，其他子模块中的备注也存在同样问题","殷萍","2014-06-11","2014-06-13","马英虎","代码","代码","解决方案：编辑、明细页面表格样式统一设置为自动换行。"]
["测试","测试",2,"缺陷","一般","中","已关闭","通用支撑",null,"通用支撑删除后列表的总记录数没有及时更新。\n\n如部门列表中有公司记录22条，删除其中一条或者几条，总记录数显示的仍为22条。 \n\n且部门中存在20条后翻页，这时页面也显示为两页，及时删除后的记录数<20条","殷萍","2014-06-11","2014-06-13","马英虎","代码","代码","已解决"]
["测试","测试",3,"缺陷","轻微","高","已关闭","通用支撑",null,"通用支撑添加，点添加后，转到添加页面，发现页面上方显示的“通用支撑→修改”，正确应为“通用支撑→添加” ","殷萍","2014-06-11","2014-06-17","马英虎","代码","代码","原因：页面权限方案调整后没有更改脚本。\n\n解决方案：修改InitModulePage初始化脚本。 "]
["测试","测试",4,"缺陷","严重","高","已关闭","通用支撑",null,"选中部门，进行子部门的添加，部门编码默认部份显示的是公司编码而不是选择的部门编码","殷萍","2014-06-11","2014-06-17","马英虎","代码","代码","原因：需求变更\n\n已解决。"]
["测试","测试",5,"缺陷","严重","高","已关闭","通用支撑",null,"删除的部门，在数据库中active_yn值为0，但在部门树切换后还是显示在部门树上。","殷萍","2014-06-11","2014-06-17","马英虎","代码","代码","原因：查询逻辑不完善\n\n已解决。"]
["测试","测试",6,"缺陷","轻微","中","已关闭","通用支撑",null,"添加部门时，部门编码的必填标记不应换行显示","殷萍","2014-06-11","2014-06-17","马英虎","代码","设计","原因：指定的文本框宽度过宽。\n\n解决方案：调整文本框宽度。"]
["测试","测试",7,"缺陷","严重","高","已关闭","通用支撑",null,"通用支撑，修改部门部门编码。\n\n操作，选择左边公司，右边通用支撑出现公司下的部门列表。选择其中一个部门进行修改，修改部门的编码。确定后退出，发现部门列表上的部门编码全部变成了刚才修改的部门的编码。也就是说在列表中的所有的部门编码都一样了。","殷萍","2014-06-12","2014-06-17","马英虎","代码","代码","原因：部门编码修改方法逻辑有问题\n\n解决方案：改正修改部门编码的方法"]
["测试","测试",8,"缺陷","轻微","低","已关闭","通用支撑",null,"通用支撑删除后列表的总记录数没有及时更新。\n如角色列表中有公司记录35条，删除其中一条或者几条，总记录数显示的仍为35条。 ","殷萍","2014-06-12","2014-06-18","马英虎","代码","代码","已解决，请获取最新版本 "]
["测试","测试",9,"缺陷","轻微","中","已关闭","通用支撑",null,"通用支撑添加，点添加后，转到添加页面，发现页面上方显示的“通用支撑→修改”，正确应为“通用支撑→添加” ","殷萍","2014-06-13","2014-06-18","马英虎","代码","代码","已解决，请更新脚本"]
["测试","测试",10,"缺陷","一般","中","已关闭","通用支撑",null,"角色添加页面有两个“重填”按钮 ","殷萍","2014-06-13","2014-06-18","马英虎","代码","代码","已解决，请更新脚本"]
["测试","测试",11,"缺陷","轻微","中","已关闭","通用支撑",null,"通用支撑添加，点添加后，转到添加页面，发现页面上方显示为“通用支撑→修改”，正确应为“通用支撑→添加”！ ","殷萍","2014-06-17","2014-06-18","马英虎","代码","代码","已解决，请更新脚本"]
["测试","测试",12,"缺陷","一般","中","已关闭","通用支撑",null,"用户明细页面，公司部门字段都没有显示 ","殷萍","2014-06-17","2014-06-18","马英虎","代码","代码","已解决，请获取最新版本 "]
["测试","测试",13,"缺陷","严重","中","已关闭","通用支撑",null,"在不同的部门添加员工，刚添加时，列表中显示的不是本部门的员工，而是所有部门的员工，但切换部门后显示正常 ","殷萍","2014-06-17","2014-06-18","马英虎","代码","代码","已解决，请获取最新版本 "]
["测试","测试",14,"缺陷","严重","高","已关闭","通用支撑",null,"通用支撑，添加后，返回。发现用户列表中仍旧为空，没出现新添加用户信息。点查询后，才出来。查询出来后的用户信息列表内容，点哪个公司，都存在。 ","殷萍","2014-06-17","2014-06-18","马英虎","代码","代码","已解决，请获取最新版本 "]
["测试","测试",15,"缺陷","一般","高","已关闭","数据维护",null,"添加设备，设备属性可以为空，与需求、详细设计不符。","孙强","2014-06-17","2014-06-19","王晓勇","代码","设计","设备属性给默认值。设置不能选空。 "]
["测试","测试",16,"缺陷","严重","高","已关闭","数据维护",null,"删除设备后，设备列表未马上更新，仍跟原来相同。但左边的树状上已经更新。 ","孙强","2014-06-17","2014-06-19","王晓勇","代码","代码","删除后没有绑定一下。\n请获取最新代码 "]
["测试","测试",17,"缺陷","轻微","高","已关闭","数据维护",null,"数据维护模块查询条件中的文本框不可编辑 ","孙强","2014-06-17","2014-06-19","马英虎","代码","设计","控件在修改过程当中，获取最新"]
["测试","测试",18,"缺陷","严重","高","已关闭","数据维护",null,"添加设备时，对作业线选择没有进行相应公司的过滤，如公司A下的作业线，可以在公司B下添加设备时引用 ","孙强","2014-06-17","2014-06-23","王晓勇","代码","代码","添加了公司过滤条件\n请获取最新代码 "]
["测试","测试",19,"缺陷","轻微","低","已关闭","数据维护",null,"数据维护选择执行岗位码后，岗位成功被引用，但岗位选择界面没有被关闭 ","孙强","2014-06-17","2014-06-23","王晓勇","代码","代码","原因：脚本错误；\n处理方法：修改了【确定】按钮脚本。"]
["测试","测试",20,"缺陷","轻微","中","已关闭","数据维护",null,"添加仪抄量，信号类型为温度时，发射率应该要有一个默认值0.95 ","孙强","2014-06-17","2014-06-23","马英虎","代码","代码","增加了默认值 "]
["测试","测试",21,"缺陷","一般","中","已关闭","数据维护",null,"手抄量选择温度时，不应该必须填写发射率，只有在仪抄量时才需要 ","孙强","2014-06-17","2014-06-23","王晓勇","代码","代码","已解决，获取最新代码 "]
["测试","测试",22,"缺陷","轻微","低","已关闭","数据维护",null,"提交审核的标准在数据维护模块和数据维护审核模块中明细信息不一致：提交审核的标准（变更类型为新增）在标准管理模块的明细信息中有变更历史和审核历史记录，在数据维护审核模块则没有 ","孙强","2014-06-17","2014-06-24","王晓勇","代码","代码","已解决。审核明细隐藏变更、审核等历史记录。 "]
["测试","测试",23,"缺陷","一般","中","已关闭","数据维护",null,"数据维护审核通过后，标准仍然是未审核状态 ","孙强","2014-06-19","2014-06-24","王晓勇","代码","代码","更新bzglpackage.sql "]
["测试","测试",24,"缺陷","严重","高","已关闭","数据维护",null,"在第一个组织结构下添加结果选项分组时，有部分分组不能显示，查询数据库，发现组织结构的ID变成了-1 ","孙强","2014-06-19","2014-06-24","王晓勇","代码","代码","已解决，请获取最新代码 "]
["测试","测试",25,"缺陷","严重","高","已关闭","数据维护",null,"结果选项分组和条目数的添加都没有限制，以往结果选项分组最多允许99，每个分组下条目最多允许50个","孙强","2014-06-19","2014-06-24","王晓勇","代码","代码","已控制 一个公司不超过99个 每个分组条目不超过50 获取全部代码 "]
["测试","测试",26,"缺陷","轻微","低","已关闭","数据维护",null,"数据维护在添加结果选项分组时不能删除结果选项条目\n在对结果选项分组内容进行修改时，可以删除结果选项条目，但在添加过程中不行。 ","孙强","2014-06-19","2014-06-24","马英虎","代码","设计","脚本错误 获取 \\MEMSWebApp\\AppLX\\AppBaseInfo\\DataCodeGroupManager\\DataCodeGroupEdit.aspx "]
["测试","测试",27,"缺陷","严重","高","已关闭","通用支撑",null,"添加id位置时，编码在确定后能自动转换成大写，但查询时，ID编码却区分大小写 ","孙强","2014-06-19","2014-06-24","马英虎","代码","代码","在条件输入完成后转换成大写 \\AppLX\\AppBaseInfo\\IDPosManager\\IDPosList.aspx 和 \\AppLX\\AppBaseInfo\\IDPosManager\\IDPosEdit.aspx "]
["测试","测试",28,"缺陷","轻微","中","已关闭","通用支撑",null,"通用支撑，查询功能，查询条件中的“厂内编码”不知道是什么逻辑。查询出不正确结果出现。","孙强","2014-06-20","2014-06-27","马英虎","代码","代码","条件设置错误 获取\\AppLX\\AppBaseInfo\\IDPosManager\\IDPosList.aspx "]
["测试","测试",29,"缺陷","轻微","中","已关闭","通用支撑",null,"加ID位置时，ID编码只输入如8位，点击重填，系统提示“须为长度为16的十六进制数 ”，并ID类型的选择不可见 ","孙强","2014-06-20","2014-06-27","马英虎","代码","代码","已控制，获取全部代码 "]
["测试","测试",30,"缺陷","一般","中","已关闭","通用支撑",null,"ID位置删除时，没有进行任何提示就直接删除了 ","殷萍","2014-06-20","2014-06-27","马英虎","代码","代码","基类BaseForm统一处理。\n获取 \\MEMSWebApp\\Framework\\BaseForm.cs "]
["测试","测试",31,"缺陷","轻微","中","已关闭","数据维护",null,"路线下没有计划，删除路线时提示路线下存在计划，不允许删除，新增的路线也如此 ","孙强","2014-06-20","2014-06-27","高才驰","代码","代码","获取\\Service\\Service\\Dal\\DJGLDal\\DJLineDal.cs "]
["测试","测试",32,"缺陷","一般","中","已关闭","数据维护",null,"路线被删除后，路线的ACTIVE_YN值被置为0，此时系统中同一部门下应允许建立与被删除路线同名的路线，而系统中不允许\n能否重现：每次都能重现\n重现步骤：\n1.进入路线管理模块，添加一条名称为1的路线\n2.删除路线1\n3.在同一部门下重新建立一条名称为1的路线 ","孙强","2014-06-23","2014-06-27","高才驰","代码","代码","获取 \\Service\\Service\\Dal\\DJGLDal\\DJLineDal.cs"]
["测试","测试",33,"缺陷","严重","高","已关闭","数据维护",null,"部门下所有路线被删除后，引用部门时仍提示该部门下存在路线不能再次引用 ","殷萍","2014-06-23","2014-06-27","孙强","代码","代码","删除路线在SQL中的未剔除 获取\\Service\\Service\\Dal\\DJGLDal\\DJLineDal.cs "]
["测试","测试",34,"缺陷","严重","中","已关闭","数据维护",null,"路线明细界面添加人、添加日期字段命名与其他模块不统一，其他模块命名为：添加人、添加日期，路线明细界面命名为：创建人、创建时间 ","殷萍","2014-06-23","2014-06-27","孙强","代码","代码","执行\\Model\\Model\\Script\\Oracle\\11.CreatePro.sql "]
["测试","测试",35,"缺陷","轻微","中","已关闭","数据维护",null,"首次在添加周期时，通过右键粘贴汉字到周期名称对应的文档框，未限制字符长度，保存后会报错提示字符超长（注：只是右键粘贴，Ctrl+V或手动输入有正常控制） ","孙强","2014-06-23","2014-07-04","马英虎","代码","设计","控制不住系统右键粘贴，现在改为禁止了右键系统Menu\n请获取最新代码 "]
["测试","测试",36,"缺陷","严重","高","已关闭","数据维护",null,"修改了路线中的点检仪标识符，结果把标准化信息给删除了 ","殷萍","2014-06-23","2014-07-04","马英虎","代码","代码","获取代码"]
["测试","测试",37,"缺陷","轻微","中","已关闭","数据维护",null,"路线管理和计划管理模块数据范围为部门或公司时，如果不指定部门或公司，默认应当看到本部门或本公司的数据，系统中看不到数据 ","孙强","2014-06-23","2014-07-04","马英虎","代码","代码","获取 \\Model\\Model\\Script\\Oracle\\16.DJGLPackage.sql "]
["测试","测试",38,"缺陷","轻微","中","已关闭","数据维护",null,"路线管理模块没有进行复制时也可以进行粘贴，粘贴后原有翻班规则被清空 ","孙强","2014-06-23","2014-07-04","马英虎","代码","代码","获取 \\MEMSWebApp\\AppLX\\AppDJGL\\DJLineManager\\DJLineCopyList.aspx.cs "]
["测试","测试",39,"缺陷","一般","中","已关闭","数据维护",null,"1.系统中所有二代点检仪与三代点检仪的标识符应该都不允许相同，系统中不同路线下二代、三代点检仪的标识符可以相同，与设计不符\n2.点检仪为三代，添加点检仪时，系统中有判断最多只允许10条路线引用同一个标识符，修改点检仪时系统中没有判断 ","殷萍","2014-06-23","2014-07-04","马英虎","代码","代码","获取 \\Service\\Service\\Dal\\DJGLDal\\DJLineDal.cs和\\Service\\Service\\DJGLService\\DJLineService.cs "]
["测试","测试",40,"缺陷","轻微","中","已关闭","数据维护",null,"修改计划周期的功能未实现\n能否重现：每次都能重现\n重现步骤：\n1.进入点检计划模块，选中一条计划，点击修改\n2.在修改界面点开周期下拉框，下拉框里没有任何选项，无法重新设置周期 ","殷萍","2014-06-23","2014-07-04","孙强","代码","代码","页面下拉框未绑定成功，下拉框单独绑定\n已修改完成，请获取DJPlanEdit.aspx代码 "]
["测试","测试",41,"缺陷","一般","中","已关闭","数据维护",null,"ID类型为D的路线，引用R型钮扣下的标准时，系统中应该有提示信息提示R型钮扣下的标准不能被D型路线引用。系统中ID类型为D的路线引用R型钮扣下的标准时，标准虽未被成功引用，但没有提示信息，且钮扣仍被挂到了路线下","殷萍","2014-06-23","2014-07-04","孙强","代码","代码","增加路线ID类型为默认查询条件，根据路线ID类型来查询标准"]
["测试","测试",42,"缺陷","严重","高","已关闭","数据维护",null,"路线添加计划引用新的钮扣后，路线树状图未及时刷新，重新进入点检计划模块树状图中才刷出新引用的钮扣","孙强","2014-06-24","2014-07-04","马英虎","代码","代码","增加树刷新脚本，添加计划后刷新树上ID钮扣节点 "]
["测试","测试",43,"缺陷","严重","高","已关闭","数据维护",null,"进入计划管理模块选中钮扣后，列表中应该默认显示出钮扣下所有计划，列表中并未显示出钮扣下的计划，必须点击查询按钮后列表中才显示出计划信息 ","孙强","2014-06-24","2014-07-04","马英虎","代码","代码","已经通过修改控件解决该问题 "]
["测试","测试",44,"缺陷","轻微","中","已关闭","数据维护",null,"列表设置页面，在所有的模块中都显示为‘基础信息-公司管理’ ","孙强","2014-06-24","2014-07-04","高才驰","代码","设计","以前是取数据库，现在改为固定名称\n请获取最新代码 "]
["测试","测试",45,"缺陷","严重","高","已关闭","数据维护",null,"计划导入时，路线的标准化标识没有进行相应的刷新 ","孙强","2014-06-24","2014-07-04","高才驰","代码","代码","获取最新代码，已经加入控制 "]
["测试","测试",46,"缺陷","轻微","中","已关闭","数据维护",null,"周期复制到第二个组织机构下的路线，一天多次的周期修改时报错：[IndexOutOfRangeException: 索引超出了数组界限。]","孙强","2014-06-24","2014-07-04","高才驰","代码","代码","处理了周期粘贴的时候班次问题。\n粘贴的周期需要重新修改班次。\n请获取最新代码 "]
["测试","测试",47,"缺陷","轻微","中","已关闭","数据维护",null,"添加计划界面查询条件中按“设备名称”字段查询的功能未实现 ","孙强","2014-06-24","2014-07-04","高才驰","代码","代码","查询条件未绑定，已修改，获取代码 "]
["测试","测试",48,"缺陷","一般","中","已关闭","数据维护",null,"添加计划引用标准时，点检计划新增界面主控列表中显示的是启停点信息 ","孙强","2014-06-24","2014-07-04","高才驰","代码","代码","请获取Common.Framework.BindUIData和Model.AppConst "]
["测试","测试",49,"缺陷","严重","高","已关闭","数据维护",null,"步骤：\n1、选择路线\n2、在查询条件中选择ID位置，点击查询\n3、在列表中勾选某一id位置\n4、点击明细，报错\nORA-00904: \"位置2\": 标识符无效\nORA-06512: 在 \"XSTECMS.DJGLPACKAGE\", line 2668\nORA-06512: 在 line 1","殷萍","2014-06-24","2014-07-04","高才驰","代码","代码","执行16.DJGLPackage.sql "]
["测试","测试",50,"缺陷","轻微","中","已关闭","数据展示",null,"数据展示中录入方式字段显示不合理，“M”是数据库中的值，在列表中显示时应转换成客户易懂的字符串，例如“点检仪上传”","孙强","2014-06-25","2014-07-04","高才驰","代码","设计","执行视图V_DJGL_DJResult 并把其它几个V_DJGL_DJResult开头的视图都重建一下 "]
["测试","测试",51,"缺陷","严重","高","已关闭","数据展示",null,"数据展示模块查询条件中没有对开始时间和结束时间的先后关系进行限制 ","孙强","2014-06-25","2014-07-04","高才驰","代码","代码","获取 \\MEMSWebApp\\AppLX\\AppDJGL\\ResultSearch\\ResultSearchList.aspx "]
["测试","测试",52,"缺陷","轻微","中","已关闭","数据展示",null,"数据展示模块查询条件中“岗位编码”写成了“岗位编号” ","殷萍","2014-06-25","2014-07-04","马英虎","代码","代码","获取并执行：脚本10.InitDBStructDesc.sql "]
["测试","测试",53,"缺陷","轻微","中","已关闭","数据展示",null,"数据展示页面查询后进入明细后返回未保留查询条件和结果 ","殷萍","2014-06-25","2014-07-04","孙强","代码","代码","获取代码 "]
["测试","测试",54,"缺陷","一般","中","已关闭","数据展示",null,"点检结果上传后进入数据展示，报错提示“从数据类型 varchar 转换为 float 时出错。” ","殷萍","2014-06-25","2014-07-04","马英虎","代码","代码","执行视图V_DJGL_DJResult "]
["测试","测试",55,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护明细页面有勾选框，但没有任何可操作的按钮 ","殷萍","2014-06-25","2014-07-04","马英虎","代码","代码","获取代码 "]
["测试","测试",56,"缺陷","一般","中","已关闭","数据维护",null,"数据维护统计页面的“设置”按钮没有任何用处，应该去掉 ","孙强","2014-06-27","2014-07-04","马英虎","代码","代码","重新执行权限 "]
["测试","测试",57,"缺陷","严重","高","已关闭","数据维护",null,"周期为一周一次时，部分日期查询数据维护时待检数量和必检数量统计不正确\n周期：一周一次（周一到周六有效）\n计划条目：4条\n11月1日，周一做了一条数据进行了上传，数据维护统计正确\n11月6日，查询数据维护统计，待检和必检应该为3条，系统中显示4条 ","孙强","2014-06-27","2014-07-04","高才驰","代码","代码","执行脚本DJGLPACKAGE "]
["测试","测试",58,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护中点击必检项后报错：\n列名 'LINE_ID' 无效。 ","孙强","2014-06-27","2014-07-04","高才驰","代码","代码","修改了DJGLPACKAGE脚本，请获取执行 "]
["测试","测试",59,"缺陷","一般","中","已关闭","数据维护",null,"点检排程的数据维护在数据维护中查询不到（如点检排程中12号有5条任务，当前日期为12号，但是在当前排程路线下，数据维护的统计数据为空） ","孙强","2014-06-30","2014-07-11","高才驰","代码","代码","删除原来的数据，执行16.BGProcess.sql脚本后新的数据，点检排成也可以看到数据维护 "]
["测试","测试",60,"缺陷","严重","高","已关闭","数据维护",null,"周期一天十二次，计划A、B两条，生成任务24条，（当前10:48，漏检数量为10条），导出漏检10条任务，在模板中修改前5条按默认为运行，后5条修改设备状态为停止（与标准定义的设备状态不同）后输入点检结果和点检时间后在实绩里面导入，导入进入数据维护统计页面查询，页面漏检为0，已检为0，必检24不变，进入明细页面后，按任务状态进行查询，当前统计数为：未检数量2条，不需检数量为17条，已检5条，实际统计数应为：未检数量应为14条，不需检应为5条，已检为5条，漏检为0条 ","殷萍","2014-06-30","2014-07-11","高才驰","代码","代码","获取执行脚本10 "]
["测试","测试",61,"缺陷","轻微","中","已关闭","数据展示",null,"数据展示和漏检查询页面在输入结果值后，报警等级仍可手动修改 ","孙强","2014-06-30","2014-07-11","高才驰","代码","设计","已解决，请获取代码 "]
["测试","测试",62,"缺陷","严重","高","已关闭","数据展示",null,"数据展示明细页面没有滚动条，导致后面的漏检没法看到 ","孙强","2014-06-30","2014-07-11","马英虎","代码","代码","获取最新代码 "]
["测试","测试",63,"缺陷","轻微","中","已关闭","数据展示",null,"数据展示明细一旦根据条件查询后，菜单项就不可见了 ","孙强","2014-06-30","2014-07-11","马英虎","代码","代码","获取最新代码 "]
["测试","测试",64,"缺陷","轻微","中","已关闭","数据展示",null,"数据展示中，从2010-12-1到2011-1-5日期查询报错：获取点检数据展示数据失败！\n\n执行方法:GetDJUnCheckCount([startDt = 2010-12-1 0:00:00, endDt = 2011-1-5 0:00:00, groupType = DayShift, orgID = 0, deptID = 0, lineID = 1, postID = 4])\n详细信息:ORA-01790: 表达式必须具有与对应表达式相同的数据类型\nORA-06512: 在 \"XSTECMS.DJGLPACKAGE\", line 1531","孙强","2014-06-30","2014-07-11","高才驰","代码","代码","漏检表中MobjectStatus_TX字段和分区表字段类型不一致 "]
["测试","测试",65,"缺陷","一般","中","已关闭","数据维护",null,"5条报警记录的报警等级都为警告，但查询条件中选择警告，却查不到一条记录 ","殷萍","2014-06-30","2014-07-11","高才驰","代码","代码","参数传错了，已修改\n请获取最新代码"]
["测试","测试",66,"缺陷","轻微","中","已关闭","数据维护",null,"如果缺陷管理流程没有配置，报警处理中转入缺陷，虽有提示配置缺陷管理流程，但此报警信息已经转入到了缺陷，由此造成了此条报警信息在缺陷中变成了垃圾数据 ","殷萍","2014-06-30","2014-07-11","高才驰","代码","代码","添加了验证，如果没有此流程则不能点转入缺陷\n请获取最新代码 "]
["测试","测试",67,"缺陷","一般","中","已关闭","数据维护",null,"报警记录处理时，应控制一条数据只能处理为对应一条缺陷，当前系统里面一条报警信息能被重复为多条缺陷 ","殷萍","2014-06-30","2014-07-11","高才驰","代码","代码","验证了重复提交的问题 "]
["测试","测试",68,"缺陷","严重","高","已关闭","数据维护",null,"报警处理为转入缺陷后，在缺陷录入环节查询不到当前数据 ","殷萍","2014-06-30","2014-07-11","高才驰","代码","代码","修改了tacheID取值\n请获取最新代码 "]
["测试","测试",69,"缺陷","严重","高","已关闭","数据维护",null,"建议在报警统计数据列表的最后一行增加合计行","殷萍","2014-06-30","2014-07-11","高才驰","代码","代码","添加了合计\n请获取最新代码 "]
["测试","测试",70,"缺陷","轻微","中","已关闭","数据维护",null,"通过报警处理转入缺陷的缺陷来源显示为空 ","殷萍","2014-07-01","2014-07-11","高才驰","代码","设计","ok，修改了该字段\n请获取最新代码 "]
["测试","测试",71,"缺陷","严重","高","已关闭","数据维护",null,"当前登陆用户的“报警处理”的数据范围公司，设置了三个公司，但是用户在报警处理加载页面的查询条件中，公司加载了所有的公司到下拉框中 ","殷萍","2014-07-01","2014-07-11","高才驰","代码","代码","修改了下拉框的绑定\n请获取最新代码 "]
["测试","测试",72,"缺陷","轻微","中","已关闭","数据维护",null,"点检异常后生成的报警，其编码目前系统都是一样，未按编号规则递增 ","殷萍","2014-07-01","2014-07-11","高才驰","代码","代码","执行\\Model\\ModelLX\\Script\\SqlServer\\02.ECMSCommonPackage.sql "]
["测试","测试",73,"缺陷","轻微","中","已关闭","数据维护",null,"1，处理措施修改为延期后，报错提示“修改失败”；\n2， tab页中的备件、材料、工器具、人工删除不规范，部分有提示，部分无提示，请统一规范\n3，根据设备带入的点检分工显示为名称（点检员），手动清除后选择的点检方分工显示为编码（MOONSDEP21）","殷萍","2014-07-01","2014-07-11","马英虎","代码","代码","获取代码 执行脚本02 、04 、 08 、25 "]
["测试","测试",74,"缺陷","一般","中","已关闭","数据维护",null,"数据维护被提交或纳入计划或删除后，数据维护的统计数未及时更新，并分页也未及时更新\n如，原本21条待修数据，按20条分页，当前显示为2页，在提交一条数据，纳入计划一条数据，删除一条数据后，系统应显示还有18条数据，并显示为1页，实际不然 ","孙强","2014-07-02","2014-07-11","马英虎","代码","代码","获取\\MEMSWebApp\\AppLX\\AppJXGL\\WorkTask\\WorkTaskList.aspx "]
["测试","测试",75,"缺陷","严重","高","已关闭","数据维护",null,"在工单的历史记录信息中当新增或修改数据维护时勾选默认提交按钮时，未记录提交历史记录信息 ","孙强","2014-07-02","2014-07-11","马英虎","代码","代码","获取代码 "]
["测试","测试",76,"缺陷","轻微","中","已关闭","数据维护",null,"被处理为延期的数据维护需要控制不可被纳入数据维护 ","孙强","2014-07-02","2014-07-11","马英虎","代码","设计","获取代码 "]
["测试","测试",77,"缺陷","严重","高","已关闭","数据维护",null,"数据维护立项管理编辑的检修定额的弹出框页面中的翻页功能无效\n注：作业指导书、检修记录卡、安全挂牌、危险源可能也会存在这种情况 ","孙强","2014-07-02","2014-07-11","马英虎","代码","代码","获取代码"]
["测试","测试",78,"缺陷","轻微","中","已关闭","数据维护",null,"1，检修分类为空时报错\n2，流程中的正在变更中的检修定额标准应不可被数据维护检修定额引用\n3，检修记录卡、危险源、安全挂牌等弹出框显示不规范，且部分无确定按钮\n4，添加完成后的实施方式显示为“WT”，实际为“委托” ","孙强","2014-07-02","2014-07-11","马英虎","代码","代码","获取 代码 并 执行脚本 08 和 25 \n\n执行视图脚本 "]
["测试","测试",79,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护立项管理界面查询条件中按岗位编码查询的功能未实现，选择任何岗位，都可以查询出所有数据。\n“延期分类”查询条件功能也未实现 ","孙强","2014-07-02","2014-07-11","马英虎","代码","代码","执行脚本25 "]
["测试","测试",80,"缺陷","一般","中","已关闭","数据维护",null,"在默认编号规则下，手动添加数据维护完成，显示的数据维护编号为“编号自动生成”，","孙强","2014-07-02","2014-07-11","马英虎","代码","代码","获取\\Model\\Model\\TableUtils\\JX_JXPlanUtils.cs "]
["测试","测试",81,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护审核时，点击审核或批量审核时无反应 ","孙强","2014-07-03","2014-07-11","马英虎","代码","代码","审核的是项目 请选择项目 "]
["测试","测试",82,"缺陷","一般","中","已关闭","数据维护",null,"在数据维护被提交后，当前数据维护下的检修项目仍显示在页面上，实际检修项目与数据维护应一起被刷新显示 ","孙强","2014-07-03","2014-07-11","马英虎","代码","代码","获取 \\MEMSWebApp\\AppLX\\AppJXGL\\JXJHGL\\JXJHBZ\\JXJHBZList.aspx "]
["测试","测试",83,"缺陷","严重","高","已关闭","数据维护",null,"数据维护审核出错， 具体报错如下\n注：此条计划在提交之前设置了数据维护与工单链接的流程环节为工单策划，然后提交->DJZ审核通过->SBZR审核通过，确定后报错","孙强","2014-07-03","2014-07-11","马英虎","代码","代码","获取 \\Service\\Service\\Dal\\JXGLDal\\WorkOrderDal.cs 并执行脚本25 "]
["测试","测试",84,"缺陷","严重","高","已关闭","数据维护",null,"系统日志中数据维护的批量审核的操作日志记录到审核中去了， ","孙强","2014-07-08","2014-07-18","高才驰","代码","代码","获取代码 "]
["测试","测试",85,"缺陷","轻微","中","已关闭","数据维护",null,"目前系统里面数据维护模块的操作记录信息只记录了数据维护审核的信息，无计划编制和提交的操作记录信息\n建议增加编制提交的操作记录信息OR如果不记录编制和提交，就也不记录数据维护审核的环节 ","孙强","2014-07-08","2014-07-18","高才驰","代码","设计","计划的操作历史不需要增加到工单里面来，只增加关联的历史记录 获取代码，执行25脚本 "]
["测试","测试",86,"缺陷","严重","高","已关闭","数据维护",null,"在数据维护关联数据维护页面，未选中数据维护项进行删除，页面提示删除成功\n1，关联删除时是否增加弹出确认删除提示框？\n2，未选择项目删除后，提示用户选择需要的数据维护后再进行删除 ","孙强","2014-07-08","2014-07-18","高才驰","代码","代码","获取代码 "]
["测试","测试",87,"缺陷","轻微","中","已关闭","数据维护",null,"在数据维护查询页面，选择一条数据进行查看明细，在明细页面，数据维护项中的实施方式显示为\"WH\"\"WT\" ","孙强","2014-07-08","2014-07-18","高才驰","代码","代码","执行 脚本 08 "]
["测试","测试",88,"缺陷","轻微","中","已关闭","数据维护",null,"在工单查询页面，存在三条待实绩审核的数据的，工单状态为审核，在查询条件根据工单状态“编制”（非审核）时进行查询，仍可查询的出当前三条数据 ","孙强","2014-07-08","2014-07-18","高才驰","代码","代码","获取\\MEMSWebApp\\AppLX\\AppJXGL\\GDGL\\GDCX\\GDCXList.aspx "]
["测试","测试",89,"缺陷","一般","中","已关闭","数据维护",null,"建议实绩录入时带入工单策划时输入的备件、材料、工器具、人工等信息 ","孙强","2014-07-08","2014-07-18","高才驰","代码","代码","采纳， 获取 \\MEMSWebApp\\AppLX\\AppJXGL\\WorkTask\\WorkTaskEdit.aspx "]
["测试","测试",90,"缺陷","严重","高","已关闭","数据维护",null,"工单激活、工单实施、实绩录入等操作未记录到系统日志中\n但：有记录到历史操作记录中 ","孙强","2014-07-08","2014-07-18","高才驰","代码","代码","工单实施是没有，获取 \\Model\\Model\\AppConst\\AppActionConst.cs。"]
["测试","测试",91,"缺陷","轻微","中","已关闭","数据维护",null,"工单实施中的上传报告对应的控件在非工单实施环节时应控制为不可编辑状态，当前在进行实绩录入操作时，七上传报告对应的控件仍可操作并可用 ","孙强","2014-07-09","2014-07-18","高才驰","代码","设计","获取代码 "]
["测试","测试",92,"缺陷","严重","高","已关闭","数据维护",null,"当前系统中工单统计图表中的统计数据统计为未完成的工单，实绩应统计所有的数据，包括所有完成未完成的","孙强","2014-07-09","2014-07-18","马英虎","代码","代码","获取 \\MEMSWebApp\\AppLX\\AppJXGL\\GDGL\\GDTJ\\GDTJList.aspx "]
["测试","测试",93,"缺陷","轻微","中","已关闭","数据维护",null,"在工单查询页面，选择两条数据进行查看明细，查看第一条完成后，翻页查看第二条，在操作历史tab页下，操作历史记录信息会并行重复显示，有几条数据就会重复显示几条重复的操作历史信息 ","孙强","2014-07-09","2014-07-18","马英虎","代码","代码","获取代码 "]
["测试","测试",94,"缺陷","轻微","中","已关闭","数据维护",null,"操作如下：工单统计页面，树节点选中集团，集团下有两个公司，统计类别为日期，2011-1-18号下有数据，但是选中后点击进入明细查看，数据均为空\n工单统计问题同上 ","孙强","2014-07-09","2014-07-18","马英虎","代码","代码","获取代码 "]
["测试","测试",95,"缺陷","一般","中","已关闭","数据维护",null,"工单查询页面的查询条件中的“工单环节”查询无效 ","孙强","2014-07-09","2014-07-18","马英虎","代码","代码","获取\\MEMSWebApp\\AppLX\\AppJXGL\\GDGL\\GDCX\\GDCXList.aspx "]
["测试","测试",96,"缺陷","轻微","中","已关闭","数据维护",null,"缺陷申请检修走工单流程，在操作历史中，工单添加和提交在操作环节和操作属性中都出现了未知 ","殷萍","2014-07-11","2014-07-18","马英虎","代码","代码","获取E:\\2641\\代码\\Service\\Service\\BaseInfoService\\BSWorkFlowService.cs "]
["测试","测试",97,"缺陷","一般","中","已关闭","数据维护",null,"工单查询条件中，先选择了一公司，然后再选择《不限》，部门和作业线下拉框中还是可以选择被选择过的公司对应信息 ","殷萍","2014-07-11","2014-07-18","马英虎","代码","代码","获取代码"]
["测试","测试",98,"缺陷","严重","高","已关闭","数据维护",null,"在实绩审核模块对工单进行审核后，不管审核是否通过，操作历史中都记录“验收工单,工单编码：XXXX。验收结果：通过”","殷萍","2014-07-11","2014-07-18","马英虎","代码","代码","获取代码 "]
["测试","测试",99,"缺陷","严重","高","已关闭","数据维护",null,"工单查询中存在修改删除功能（修改可用，删除用了无效） ","殷萍","2014-07-11","2014-07-18","马英虎","代码","代码","暂时不需要的两个功能 已去掉 执行权限脚本"]
["测试","测试",100,"缺陷","轻微","中","已关闭","数据维护",null,"工单实施，工单验收可上传报告，上传后，看明细，内容为空，历史记录中的附件亦为空！ ","殷萍","2014-07-11","2014-07-18","马英虎","代码","设计","获取代码 "]
["测试","测试",101,"缺陷","严重","高","已关闭","数据维护",null,"在工单查询页面，选中一条或多条数据后，点击按钮“修改”，无反应 ","殷萍","2014-07-15","2014-07-18","马英虎","代码","代码","去掉删除 修改功能 "]
["测试","测试",102,"缺陷","轻微","中","已关闭","数据维护",null,"工单验收工单所上传的附件并不存储在字段“yanshoufile_bl”\n验收环节上传附件，查看数据库jx_workoder,字段“yanshoufilename_bl;yanshoufile_bl”无附件内容 ","殷萍","2014-07-15","2014-07-18","高才驰","代码","代码","存历史表里"]
["测试","测试",103,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护->COVI管理->添加/修改/明细，字段名有问题\n东线18点，co前面多了个“r”\n见附图 ","殷萍","2014-07-15","2014-07-18","高才驰","代码","代码","请重新获取代码 "]
["测试","测试",104,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护->COVI管理，当前登录人数据范围为“公司”，列表页面显示所有公司的数据 ","殷萍","2014-07-15","2014-07-25","高才驰","代码","代码","请重新获取脚本并运行，运行后重启IIS "]
["测试","测试",105,"缺陷","一般","中","已关闭","数据维护",null,"数据维护->COVI管理，月报表，年选择“不限”时，报错","殷萍","2014-07-15","2014-07-25","高才驰","代码","代码","请重新获取代码 "]
["测试","测试",106,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护->COVI管理，月报表有问题：\n数据范围是公司，月报表弹出框的下拉列表却显示所有的公司 ","殷萍","2014-07-18","2014-07-25","高才驰","代码","代码","请重新获取代码 "]
["测试","测试",107,"缺陷","一般","中","已关闭","数据维护",null,"牵引原因，抛锚车行驶方向，抛锚车车型，作业方式字段显示为必填项，但是不选择也可以保存成功 ","殷萍","2014-07-18","2014-07-25","高才驰","代码","代码","保存时进行数据验证 "]
["测试","测试",108,"缺陷","严重","高","已关闭","数据维护",null,"查询页面，“是否收取”字段选择“未收时查询不到数据（未收只对费用补收里面添加为未收的数据能查出来，对直接添加的数据不能查询） ","殷萍","2014-07-21","2014-07-25","高才驰","代码","代码","是否收取字段值为空时，存储值不对，已修改 "]
["测试","测试",109,"缺陷","严重","高","已关闭","数据维护",null,"数据维护->牵引管理\n1.list页面数据未按照倒叙顺序排列\n2.相同数据可以多次添加，建议限制\n3.当作业方式为“牵引”时，是否收取和发票号码是否为必填？","孙强","2014-07-21","2014-07-25","马英虎","代码","代码","1 已改为按时间倒序排序\n2 业务上并未做限制，目前也没有限制标准，操作时只要数据通过合法验证都能添加进去\n3 牵引时，是否收取和发票号码为非必填，因为存在费用补收操作，可在费用补收时去填写 "]
["验收","客户反馈",110,"缺陷","轻微","中","已关闭","数据维护",null,"修改堵塞时间报错，如下\n消息: Sys.WebForms.PageRequestManagerServerErrorException: 输入字符串的格式不正确。","孙强","2014-08-10","2014-08-11","马英虎","代码","设计","数据输入未做限制，导致类型转换报错，已处理 "]
["验收","客户反馈",111,"缺陷","轻微","中","已关闭","数据维护",null,"数据维护->牵引管理->费用补收\n费用补收里面的“设置”按钮，当操作顺序为收费金额->是否收取选择已收->发票号码，再点击“重置”时，重置就只对发票号码有效，对收费金额无效 ","孙强","2014-08-10","2014-08-11","高才驰","代码","设计","这里不需要重置按钮，已禁用 "]